|  | Ministry of Transport |  |  |
| --- | --- | --- | --- |
|  | Vietnam Expressway Corporation |  |  |
|  | Project Management Unit No. 85 |  |  |

IDA Credit	No.	:	3843-VN

Project ID	No.	:	P106235

Consulting Services

for

Detailed Design for Danang - Quang Ngai Expressway Development Project

Monthly Progress Report

September 2011

| The Joint Venture of |  |
| --- | --- |
|  | THAI ENGINEERING CONSULTANTS CO., LTD. |

Ref. No.	:	DQEDD-PMU-35-11

Date	:	21 October, 2011

Mr. Nguyen Tien Ha

Project Manager

Project Management Unit No. 85 (PMU85)

Fax. No. : +84-(38)3834705

Subject:		Submission of Monthly Progress Report – September 2011 (English/Vietnamese)

Dear Sir,

In accordance with Appendix B - Reporting Requirements in the Contract for Consultants’ Services, we would like to submit ten (10) copies of the Monthly Progress Report – September 2011 in English and Vietnamese versions, respectively.

Sincerely yours,

Ichizuru ISHIMOTO

Project Manager/Team Leader

c.c.	:	Office Copy

Encl.	:	Monthly Progress Report –September 2011 (English: 10 copies, Vietnamese: 10 copies)

TABLE OF CONTENTS

TRANSMITTAL LETTER

PROJECT LOCATION MAP

1.	MONTHLY ACTIVITIES	1

1.1.	Activities up to Previous Month	1

1.2.	Major Events in this month	1

1.3.	Consultant’s Organization	1

1.4.	Mobilization Status in this month	1

1.5.	Meetings in this month	1

1.6.	Documents Submission in this month	1

1.7.	Correspondence in this month	1

2.	PROGRESS OF THE WORKS	2

2.1.	Summary	2

2.2.	Technical Standards to be Applied to the Project	2

2.3.	Progress of Survey Works	2

2.4.	Progress of Basic Design Works	8

2.5.	Progress of Detailed Design Works	13

2.6.	Procurement Assistance	15

2.7.	Project Implementation Program	15

2.8.	Technology Transfer	15

2.9.	Outstanding Issues in this month	15

3.	EXPECTED WORKs IN COMING MONTH	15

3.1	Survey Works	15

3.2	Design Works	16

3.3	Procurement Documents	17

Appendix 1	: Summary of (Draft) Contract

Appendix 2	: Major Events

Appendix 3	: Consultant’s Organization

Appendix 4	: Mobilization Status

Appendix 5	: List of Meetings

Appendix 6	: List of Documents Submitted

Appendix 7	: List of Correspondence

Appendix 8    	: Technical Standards to be applied to the Project

Appendix 9	: List of Sub-Consultants

Appendix 10	: List of Contact Persons

Appendix 11	: List of Reports

Appendix 12	: List of Drawings

# MONTHLY ACTIVITIES

## Activities up to Previous Month

The topographic survey was commenced from 15 July 2011, with consent by the minutes of contract negotiation between VEC and the Joint Venture of Nippon Koei Co., Ltd., Nippon Engineering Consultants Co., Ltd., Chodai Co., Ltd., and Thai Engineering Consultants Company Limited. The highway design works of the basic design works was commenced in parallel with the topographic survey to determine design centerline for the topographic survey.

As of 30 September 2011, the Contract for consultants’ service between Vietnam Expressway Corporation (VEC) under Ministry of Transport (MOT) and Joint Venture of Nippon Koei Co., Ltd., Nippon Engineering Consultants Co., Ltd., Chodai Co., Ltd., and Thai Engineering Consultants Company Limited. has not been signed.

Draft contract for the consulting service is summarized in Appendix 1: Summary of (Draft) Contract.

Since the commencement of the Service, the topographic survey work including modification of the centerline has progressed well.

## Major Events in this month

See Appendix 2: Major Events

## Consultant’s Organization

See Appendix 3: Consultant’s Organization

## Mobilization Status in this month

See Appendix 4: Mobilization Status.

## Meetings in this month

See Appendix 5: List of Meetings.

## Documents Submission in this month

See Appendix 6: List of Documents Submitted.

## Correspondence in this month

See Appendix 7: List of Correspondence.

# PROGRESS OF THE WORKS

## Summary

Since the commencement of the Services on 15th July 2011, the Consultant has mobilized his international and national engineers promptly and properly. The works completed in September 2011 are mentioned below.

List of the reports and drawings has been established and draft list of the reports is shown in Appendix 11.

## Technical Standards to be Applied to the Project

See Appendix 8: Technical Standards to be applied to the Project.

## Progress of Survey Works

### Summary

The progress of surveys works as of the end of this reporting month is summarized in Table 2.3.1-1.

Table 2.3.1-1 Summary of Survey Works Progress

| No. | Item | Progress (%) |  |  |
| --- | --- | --- | --- | --- |
|  |  | This Report | Last Report | Progress This Time |
| SV01 | Topographic Survey | 15 | 30 | 45 |
| SV02 | Hydrological Survey and Analysis | 5 | 10 | 15 |
| SV03 | Geotechnical and Geological Investigation | 0 | 0 | 0 |
| SV04 | Material Source Survey | 0 | 0 | 0 |
| SV05 | Relevant Facility Survey | 0 | 0 | 0 |
| SV06 | Traffic Forecast Review and Baseline Survey | 0 | 0 | 0 |
| SV07 | Independent Land Valuation Survey | 0 | 0 | 0 |
| SV08 | Environmental and Social Survey | 0 | 0 | 0 |
|  | Work completed |  |  |  |

### List of Sub-consultants

See Appendix 9: List of Sub-Consultants.

### Topographic Survey

#### Progress of Works

After approval of the survey work plan for control networks (GPS and Secondary control points) by PMU 85 letter No. 828/PMU85-PP2 dated 25th June 2011, as well as receipt of no objection letter for sub-consultants for topographic and geotechnical survey work by VEC letter No. 1533/VEC dated 22nd August 2011, the control point survey was commenced on 15th July 2011 by a subcontractor.

The control point survey including the secondary control point survey on realignment section between km70 - km80 has completed on 22nd September 2011.

The topographic survey was commenced on 22nd August 2011 by subcontractors, with consent of VEC and PMU85 obtained during meeting on 9th August 2011. Handover of the GPS and secondary control points to the subcontractors was made simultaneous with the commencement.

The consultant has found some sections which are needed to modify its alignments to avoid design control points. Major modified sections are as follows:

- KM20+480 – KM30+790 : To shorten the length of tunnel, to avoid school and  monument

- KM33+640 – KM36+750 : To avoid rocky mountain

- KM42+410 – KM47+880: To avoid inappropriate river crossing

- KM47+880 – KM52+240:  To avoid temple

- KM71+430 – KM81+370 : Re-alignment on shooting area

- KM84+270 – KM89+500 : To avoid high voltage line

- KM89+500 – KM95+820 : To avoid irrigation water reservoir

- KM101+780 – KM106+540 : To avoid high voltage line (500kv)

Since rainy day has been increased in these days, site work of the topographic survey has not been progressed well. Profile and cross section topographic survey of thruway is scheduled to complete by 15 November 2011. Detail progress of topographic survey works is shown in Table 2.3.3-1 and Table 2.3.3-2.

Table 2.3.3-1 Works Progress of Topographic Survey

| No. | Item | Progress (%) |  |  |
| --- | --- | --- | --- | --- |
|  |  | This Report | Last Report | Progress This Time |
| SV01-01 | Class IV horizontal network of controls and Class IV leveling network (GPS) | --- | 100 | 100 |
| SV01-02 | Secondary control point: | 6 | 94 | 100 |
| SV01- 03 | Horizontal alignment plan for topographic survey | 6 | 94 | 100 |
| SV01-04 | 3-D point survey | --- | --- | --- |
| SV01-04-01 | Main Line-Priority | 41 | 59 | 100 |
| SV01-04-02 | Main Line-others | 82 | 0 | 82 |
| SV01-05 | Fixing of design horizontal alignment | 30 | 0 | 30 |
| SV01- 06 | Main Line (Expressway) (KM0+000 – KM139+522) | --- | --- | --- |
| SV01- 06-01 | Profile survey | 0 | 0 | 0 |
| SV01- 06-02 | Cross-section survey | 0 | 0 | 0 |
| SV01-06-03 | Planimetric survey | 0 | 0 | 0 |
| SV01- 07 | Tunnel (Expressway) | 0 | 0 | 0 |
| SV01- 08 | Bridge (Expressway) | 0 | 0 | 0 |
| SV01- 09 | Culvert Box (Expressway) | 0 | 0 | 0 |
| SV01- 10 | Culvert Pipe (Expressway) | 0 | 0 | 0 |
| SV01- 11 | Canal (Re-alignment) (Expressway) | 0 | 0 | 0 |
| SV01- 12 | Interchanges (Expressway) | 0 | 0 | 0 |
| SV01- 13 | Main Line (Linking Road) | 0 | 0 | 0 |
| SV01- 14 | Bridge (Linking Road) | 0 | 0 | 0 |
| SV01- 15 | Culvert Box (Linking Road) | 0 | 0 | 0 |
| SV01- 16 | Culvert Pipe (Linking Road) | 0 | 0 | 0 |
| SV01- 17 | Intersection (Linking Road) | 0 | 0 | 0 |
|  | Work completed |  |  |  |

#### Coordination with Concerned Agencies

The sub-consultants for the topographic survey noticed about execution of field topographic survey to concerned provincial PC and district PC through PMU 85 in prior to commencement of the survey.

Table 2.3.3-2 Progress and schedule of Survey Works

### Hydrological Survey and Analysis

The main work items for the hydrological survey and analysis are as follows:

- Hydrological survey (outsource to sub-consultant)

- Hydrological analysis (by senior hydrologist)

The main work items for inundation analysis are as follows:

- Inundation analysis (by senior hydrologist)

- Cost-benefit analysis (by senior hydrologist)

#### Progress of Works

The consultant has been prepared bidding documents for subletting the hydrological survey. The hydrological survey will be commenced from early October 2011.

Table 2.3.4-1 show work progress of the hydrological survey and analysis, and assumed survey period of the hydrological survey is from early October 2011 to early December 2011.

Table 2.3.4-1 Works Progress of Hydrological Survey and Analysis

| No. | Item | Progress (%) |  |  |
| --- | --- | --- | --- | --- |
|  |  | This Report | Last Report | Progress This Time |
| SV02-01 | Hydrological survey | --- | --- | --- |
| SV02-01-01 | Water level survey | 0 | 0 | 0 |
| SV02-01-02 | River velocity survey | 0 | 0 | 0 |
| SV02-01-03 | Flood level survey | 10 | 0 | 10 |
| SV02-01-04 | Data collection survey | 0 | 0 | 0 |
| SV02-02 | Hydrological analysis | 0 | 0 | 0 |
| SV02-03 | Inundation analysis | 0 | 0 | 0 |
| SV02-04 | Cost – Benefit analysis | 0 | 0 | 0 |
|  | Work completed |  |  |  |

Senior hydrologist conducted following works in September:

- Prepared draft of scope and specifications of hydrological survey works and held meeting with Thang Loi in Hanoi on 01 September 2011 to discuss on the scope and specifications of the survey.

- Visited the sites of Ky Lam, Chiem Son, Tam Ky, Tra Bong and Tra Khuc bridge locations on 03 September 2011, to prepare detailed specification for water level and velocity of flow survey in the rivers.

- Arranged meeting with President of ESS in Hue Province to get information on: (a) flood management model developed by JICA’s project in Quang Nam Province and model results for different scenarios; and (b) availability of hydrological and GIS data necessary for hydrological studies and model development. Meeting was arranged with:

- Mr. Yukishi Tomida

President

Earth System Science (ESS)

At present: working with JICA’s project in Hue, Vietnam

Date:  04 September 2011

- Evaluation of nominated sub-consultant for hydrological survey works has been completed.

- Prepared the detailed specifications of hydrological survey works and held meeting with Thang Loi in Hanoi on 12 September 2011 for finalization of scope and specifications and for requesting quotation and work plan of survey.

- Visited Department of Agriculture and Rural Development (DARD) in Quang Nam Province on 15 September 2011 to request DARD for providing permission to Division of Flood & Storm Control to support and provide necessary data and information for project. To get information on the planned irrigation projects and river improvement projects which affect the expressway.  Persons met were:

- Vice Director, DARD

- Head, Planning and Investment Division, DARD

- Head, Division of Flood and Storm Control, DARD

- Visited Department of Transport (DOT), Quang Nam on 15 September 2011 to get information on navigation clearance requirements of rivers and planned projects for inland waterway development. Persons met were:

- Vice Director, DOT

- Head, Division of Inland Waterway, DOT

#### The persons were contacted for the meeting :

See Appendix 10: List of Contact Persons.

### Geotechnical and Geological Investigation

#### Progress of Works

Sub-consultants for the geotechnical Investigation was approved by VEC letter No. 1533/VEC dated 22nd August 2011.

The consultant has been prepared bidding documents for subletting the geotechnical investigation.

The geotechnical investigation will be commenced after bridge/structure plan is approved.

### Material Source Survey

No activities during in September 2011.

### Relevant Facilities Survey

No activities during in September 2011.

### Traffic Forecast Review and Baseline Survey

No activities during in September 2011.

### Independent Land Valuation Survey

No activities during in September 2011.

### Environmental and Social Survey

No activities during in September 2011.

## Progress of Basic Design Works

### Summary

The progress of basic design works as of the end of this reporting month is shown in Table 2.4.1-1.

Table 2.4.1-1  Summary of Basic Design Works Progress

| No. | Item | Progress (%) |  |  |
| --- | --- | --- | --- | --- |
|  |  | This Report | Last Report | Progress This Time |
| BDS-01 | Previous Studies Review | 10 | 10 | 20 |
| BDS-02 | Detailed Engineering Design Framework | 20 | 0 | 20 |
| BDS-03 | Highway Design (thruway, linking road) | 10 | 10 | 20 |
| BDS-04 | Interchange Plan | 5 | 0 | 5 |
| BDS-05 | Tunnel Plan | 0 | 0 | 0 |
| BDS-06 | Bridge and Culvert Plan | 5 | 5 | 10 |
| BDS-06-01 | Standard Design (culvert, bridge, revetment and river protection) | 0 | 0 | 0 |
| BDS-06-02 | Comparative Study (major bridges) | 0 | 0 | 0 |
| BDS-07 | O&M building location plan | 0 | 0 | 0 |
| BDS-08 | Basic Design Report | 0 | 0 | 0 |
| BDS-09 | Safeguards | 0 | 0 | 0 |
| BDS-10 | Project Cost Estimate | 0 | 0 | 0 |
| BDS-11 | Procurement Documents | 0 | 0 | 0 |
| BDS-12 | Project Implementation Program | 0 | 0 | 0 |
|  | Work completed |  |  |  |

### Previous Studies Review

Previous study of TEDI F/S has been reviewed especially on design control setting and geometrical alignment design results.

Previous studies review report will be submitted after issuance of notice to proceed.

### Detailed Engineering Design Framework

Detailed engineering design framework has been considered parallel with the previous studies review.

Detailed engineering design framework report will be submitted after issuance of notice to proceed.

### Highway Design

#### Summary

Geometric design standards for thruway design were identified.

Horizontal alignment design has been conducted to provide survey center line for the topographic survey.

Alignment alternatives study has been conducted for several sections in the F/S.

The progress of highway design works as of the end of this reporting month is shown in Table 2.4.4-1.

Table 2.4.4-1   Summary of Works Progress of Highway Design

| No. | Item | Progress (%) |  |  |
| --- | --- | --- | --- | --- |
|  |  | This Report | Last Report | Progress This Time |
| DS-HW01 | Geometric Design Standards | 10 | 50 | 60 |
| DS-HW02 | Typical Cross Sections | 10 | 25 | 35 |
| DS-HW03 | Geometric Design | 0 | 0 | 0 |
| DS-HW03-01 | Alternative Alignment Study | 10 | 30 | 40 |
| DS-HW03-02 | Geometric Design (Horizontal) | 10 | 20 | 30 |
| DS-HW03-03 | Crossing Plan | 5 | 0 | 5 |
| DS-HW03-04 | Frontage Road Plan | 5 | 0 | 5 |
| DS-HW03-05 | Geometric Design (Vertical) | 0 | 0 | 0 |
| DS-HW04 | Cross Section Design | 0 | 0 | 0 |
| DS-HW05 | Drawings | 0 | 0 | 0 |
| DS-HW06 | Work Quantity | 0 | 0 | 0 |
|  | Work completed. |  |  |  |

#### Geometric Design Standards

Geometric design standards for thruway were established.

TCVN5729-97 shall be applied for the thruway design standard.

TCVN5729-97 and 22TCN 273-01 shall be applied for interchange ramp-ways design standards. However, AASHTO 2004 (5th Edition) shall also be referred for design elements which is not stipulated its standard in TCVN5729-97 and 22TCN 273-01.

#### Typical Cross Sections (1), Thruway

Thruway consists of embankment section, cut section and bridge/flyover section. Number of lanes on initial stage is four and six lanes is planned as ultimate stage. Additional typical cross sections to meet various site conditions will be prepared in early stage of the Basic Design.

##### Embankment Section (Thruway)

Figure 2.4.4-1 and Figure 2.4.4-2 shows typical cross section of the embankment section and cut section for the initial stage respectively.

Figure 2.4.4-1  Typical Cross Section of Embankment Section (Initial Stage)

##### Cut Section (Thruway)

Figure 2.4.4-2  Typical Cross Section of Cut Section (Initial Stage)

#### Geometric Design

##### Understanding of Site Conditions

Detailed site reconnaissance has been conducted to verify appropriateness of horizontal alignment design, and to identify design control points section by section.

##### Design Standards

Highway classification of “Type-A (design speed 120km/h)” in TCVN5729-97 is applied for the highway design.

##### Horizontal Alignment

The F/S horizontal alignment in being modified for the following sections:

- KM17+000 – KM20+600 : To set curve on bending point

- KM20+480 – KM30+790 : To shorten the length of tunnel, to avoid school and  monument

- KM33+640 – KM36+750 : To avoid rocky mountain

- KM42+410 – KM47+880: To avoid inappropriate river crossing

- KM47+880 – KM52+240:  To avoid temple

- KM71+430 – KM81+370 : Re-alignment on shooting area

- KM84+270 – KM89+500 : To avoid high voltage line

- KM89+500 – KM95+820 : To avoid irrigation water reservoir

- KM101+780 – KM106+540 : To avoid high voltage line (500kv)

##### Vertical Alignment

Vertical alignment design will be conducted based on design high water level, required vertical clearance for crossing roads, and result of profile survey.

##### Combination of Horizontal and Vertical Alignment

Appropriateness of combination of the horizontal and vertical alignment will be examined.

### Interchange Plan

Nine interchanges are planned in the F/S, and distances between the interchanges are 6km to 20km.

Additional interchange on provincial road 609 in Quang Nam province was proposed by Quang Nam Peoples Committee to provide good access to surrounding area where is rapid developing area.

Alternative study of the proposed interchange, as well as My Son interchange is being studied by the consultant.

### Tunnel Plan

Necessary clearance between tunnels (north and south bounds) and location of the topographic survey area are examined.

### Bridge Plan

#### Summary

The progress of bridge design works as of the end of this reporting month is shown in Table 2.4.7-1.

Table 2.4.7-1   Summary of Works Progress of Bridge  Design

| No. | Item | Progress (%) |  |  |
| --- | --- | --- | --- | --- |
|  |  | This Report | Last Report | Progress This Time |
| DS-BR01 | Previous Study Review | 20 | --- | 20 |
| DS-BR02 | D/D Framework (Technical Standard) | 0 | --- | 0 |
| DS-BR03 | Design Criteria and Conditions | 0 | --- | 0 |
| DS-BR04 | Typical Cross Sections | 0 | --- | 0 |
| DS-BR05 | Comparative Study (Major River Bridges) | 0 | --- | 0 |
| DS-BR06 | Bridge Plan | 0 | --- | 0 |
| DS-BR07 | Standard Design | 0 | --- | 0 |
| DS-BR08 | Structural Design | 0 | --- | 0 |
| DS-BR09 | Bridge Temporary Facilities Design | 0 | --- | 0 |
| DS-BR10 | Revetment/River Bed Protection Design | 0 | --- | 0 |
| DS-BR11 | Design Drawings | 0 | --- | 0 |
| DS-BR12 | Quantity Taking-off | 0 | --- | 0 |
|  | Work completed. |  |  |  |

#### DS-BR-01: Previous Studies Review

##### Conducted initial site survey at major river bridges

Initial site reconnaissance for major bridges has been conducted to collect site information for design such as river geographical condition, flood record, and measures on neighbor bridges.

##### Reviewed plan of thruway bridges in the F/S

- Necessity to conduct comparative study for major river bridge ,especially span arrangement was confirmed

- Necessity to update bridge plan in accordance with updated alignment ,current site conditions and 3D surveys was confirmed.

### Culvert Plan

No progress in this reporting month.

### O&M Building Location Plan

Site reconnaissance of Traffic Management Center (TMC) was carried out to confirm design control points. Layout plan and land use boundary of TMC are now being prepared for the approval by PMU85 and installation of right of ways on the site.

### Safeguards

No progress in this reporting month.

### Project Cost Estimate

No progress in this reporting month.

## Progress of Detailed Design Works

### Summary

The progress of detailed design works as of the end of this reporting month is shown in Table 2.5.1-1.

Table 2.5.1-1  Summary of Detailed Design Works Progress

| No. | Item | Progress (%) |  |  |
| --- | --- | --- | --- | --- |
|  |  | This Report | Last Report | Progress This Time |
| DDS-01 | Standard Design (road) | 0 | 0 | 0 |
| DDS-02 | Standard Design (bridge) | 0 | 0 | 0 |
| DDS-03 | Standard Design (cross structure) | 0 | 0 | 0 |
| DDS-04 | Standard Design (pavement) | 0 | 0 | 0 |
| DDS-05 | Standard Design (slope protection) | 0 | 0 | 0 |
| DDS-06 | Standard Design (soft ground treatment) | 0 | 0 | 0 |
| DDS-07 | Standard Design (drainage) | 0 | 0 | 0 |
| DDS-08 | Standard Design (bridge temporary facilities) | 0 | 0 | 0 |
| DDS-09 | Standard Design (building) | 0 | 0 | 0 |
| DDS-10 | Standard Design (electrical facilities) | 0 | 0 | 0 |
| DDS-11 | Road Safety Audit | 0 | 0 | 0 |
| DDS-12 | Design Reports | 0 | 0 | 0 |
| DDS-13 | Quantity Report | 0 | 0 | 0 |
|  | Work completed |  |  |  |

### Standard Design (Road)

No progress in this reporting month.

### Standard Design (Bridge)

No progress in this reporting month.

### Standard Design (Cross Structure)

No progress in this reporting month.

### Standard Design (Pavement)

No progress in this reporting month.

### Standard Design (Slope Protection)

No progress in this reporting month.

### Standard Design (Soft Ground Treatment)

No progress in this reporting month.

### Standard Design (Drainage)

No progress in this reporting month.

### Standard Design (Bridge Temporary Facilities)

No progress in this reporting month.

### Standard Design (Building)

No progress in this reporting month.

### Standard Design (Electrical Facilities)

No progress in this reporting month.

### Road Safety Audit

No progress in this reporting month.

### Design Reports

No progress in this reporting month.

### Quantity Report

No progress in this reporting month.

## Procurement Assistance

Vietnamese procurement specialist was mobilized and started to study relevant documents.

## Project Implementation Program

No progress in this reporting month.

## Technology Transfer

No progress in this reporting month.

## Outstanding Issues in this month

#### Re-alignment sections from F/S

In parallel with the progress of topographic survey, the centerline of the expressway is being updated as reported in Section 2.3.3. Official approval of this modification should be made timely.

#### Determination process of design high water level

Determination of design high water level is most critical factor on the detailed design. It was discussed with PMU85 for this issue on 30 September 2011.

# EXPECTED WORKs IN COMING MONTH

## 3.1	Survey Works

#### Topographic Survey

- Approx. 20% of 3-D point survey for the other sections (22km)

- Profile and cross section survey (km0 – km58)

#### Hydrological Survey and Analysis

- Procurement of sub-consultant

- Commencement of flood level survey

- Commencement of river velocity survey

#### Geotechnical and Geological Investigation

- Preparation of contract documents for sub-consultant

## 3.2	Design Works

### Highway Design

##### Summarization of Alignment Modification

- Summarize minor alignment modification from the F/S

##### Alignment Alternatives Study

- KM20+480 – KM30+790

- KM33+640 – KM36+750

- KM42+410 – KM47+880

- KM47+880 – KM52+240

- KM71+430 – KM81+370

- KM84+270 – KM89+500

- KM89+500 – KM95+820

- KM101+780 – KM106+540

##### Additional Interchange Study on Provincial Road 609

- To study requested additional interchange on provincial road 609 for discussion with Quang Nam PC

##### Horizontal Alignment Design for Topographic Survey

- To determine horizontal alignment for 3-D surveyed section to carry out profile and cross section topographic survey

##### Cross Structure Plan

- Cross structure plan for topographic survey

### Bridge/ Structural Design

##### DS-BR01: Previous Study Review

- To extract key issues/propose approaches to the D/D

##### DS-BR02: D/D Framework (Technical Standard)

- To review and update applicable technical standards.

##### DS-BR03 : Design Criteria and Conditions

- To establish design criteria and condition for bridge planning

##### DS-BR04: Typical Cross Sections

- To define typical Cross Sections

##### DS-BR05: Comparative Study (Major River Bridges)

- To conduct comparative study ,especially span arrangement

##### DS-BR06: Bridge Plan

- To update thruway bridge plan based on current condition.

- To start determination of the bridge locations to decide boring survey locations

### Road Structure Design

- Start standard road structure design to establish typical cross sections for various kinds of expressway sections.

### Building Design

- To get approval from PMU85 for the location and arrangement of the TMC.

- To install the right of ways for the TMC on the site as per the approved boundary land use drawing.

## 3.3	Procurement Documents

### 3.3.1	O&M Building Work

- To start preparation of Pre-Qualification documents for the ITS/O&M package

### 3.3.2	Priority packages

- To start selection of 1 priority package for first commencement.

- To start preparation of Pre-Qualification documents for the above package.

Appendix 1: Summary of (Draft) Contract

# Scope of works

## Terms of Reference (TOR)

Term of Reference is stipulated in the (Draft) Contract as Appendix A: Description of Services.

## Reporting Requirements

Reporting Requirements is stipulated in Appendix B of the (Draft) Contract as follows:

Table A-1-1: Reporting Schedule

| No. | Report Title | Submission Timing |
| --- | --- | --- |
| 1 | Inception Report | Within 1 month after commencement |
| 2 | Review of Previous Studies and Establishing the Detailed Design Framework | Within 2 months after commencement |
| 3 | Monthly Progress Report | Monthly |
| 4 | Environmental and Social Reports (EIS, EMP, EMDP (if required), RAP) |  |
| 5 | Design report, prequalification and bidding documents for the first 2 contract packages | Within 6 months after commencement |
| 6 | Full sets of design reports, prequalification and bidding documents for the whole project | Within 12 months after commencement |
| 7 | Road Safety Audit report |  |
| 8 | A brief report on the appropriateness of the proposed alignment, adequacy of socio-environmental impacts assessment and the corresponding mitigation measures | 2 months after signing the Contract |
| 9 | Updated draft EIA and EMP reports | 5 months after signing the Contract |
| 10 | Draft final updated EIA and EMP reports | 8 months after signing the Contract |
| 11 | Final updated EIA and EMP reports | Not less than 2 months in advance of completion of detailed engineering design |
| 12 | The replacement cost survey (Inception Report) | 1 month after beginning of the assignment |
| 13 | The replacement cost survey (Final Report) | 6 month after signing the Contract |
| 14 | Project Completion Report (PCR) | End of the Services |

# Personnel schedule

Personnel Schedule is stipulated in Appendix C of the (Draft) Contract as follows:

## International Staff

| No. | Position | Name | TOR | Agreed |
| --- | --- | --- | --- | --- |
| I1 | Project Manager/Team Leader | Ichizuru Ishimoto | 14.5 |  |
| I2 | Senior Highway Engineer | Akira Magario | 14 |  |
| I3 | Road Safety Audit Specialist | Takehiko Tsuji | 3 |  |
| I4 | Senior Bridge Engineer | Yoshinori Abe | 13 |  |
| I5 | Highway Engineer 1 | Koji Nakai | 12.5 |  |
| I6 | Bridge/Structural Engineer 1 | Tetsuya Maeda | 13 |  |
| I7 | Bridge/Structural Engineer 2 | Yoshiaki Nakakubo | 4 |  |
| I8 | Highway Engineer 2 | Decha Sa-ngaunprasith | 12 |  |
| I9 | Bridge/Structural Engineer 3 | Hiroo Jin | 12 |  |
| I10 | Bridge/Structural Engineer 4 | Yuichi Sano | 4 |  |
| I11 | Senior Interchange Specialist | Chanchai Techashongs | 7 |  |
| I12 | Bridge/Structural Engineer 5 | Hiroyuki Yokoyama | 11 |  |
| I13 | Tunnel Engineer | Wako Noto | 4 |  |
| I14 | Soil/Geotechnical Engineer 1 (Slope) | Manoon Arayasiri | 2 |  |
| I15 | Soft Ground Treatment Specialist | Suvichai Methpreechakul | 3 |  |
| I16 | Drainage Engineer | Suntichai Horpaopan | 7 |  |
| I17 | River Engineer | Arristeo B. Rabajante | 2 |  |
| I18 | Bridge/Structural Engineer 6 | Akira Yanagisawa | 7 |  |
| I19 | Pavement/Material Engineer | Bundit Kitsuwannarut | 4 |  |
| I20 | Survey Engineer | Kazuhiro Ishizuka | 6 |  |
| I21 | Soil/Geotechnical Engineer 2 | Jirarote Piyapornpong | 5 |  |
| I22 | Geological Engineer (Tunnel) | Seichiro Kanai | 2 |  |
| I23 | Senior Hydrologist | Khadananda Lamsal | 3 |  |
| I24 | Inundation Analyst | Silver Yance | 3 |  |
| I25 | Operating&Maintenance Specialist | Shigeki Takahashi | 4 |  |
| I26 | Expressway Management Unit Specialist | Yuichi Tsujimoto | 2 |  |
| I27 | Traffic Management Specialist | Hisanori Tomitaka | 2 |  |
| I28 | Asset Management Specialist | Kyoichi Takeuchi | 2 |  |
| I29 | Architect | Yoshinori Yamazaki | 3 |  |
| I30 | ITS Specialist | Koichi Nishimura | 5 |  |
| I31 | Communication System Engineer | Masahiro Sakagami | 3 |  |
| I32 | Senior Electrical Engineer | Eiji Matsuda | 7 |  |
| I33 | Toll Collection System Specialist | Masashi Iwamoto | 4 |  |
| I34 | Construction Planner/Cost Estimator | Masayuki Iwashita | 11 |  |
| I35 | Senior Procurement/Contract Specialist | Anothai Boonthikul | 12 |  |
| I36 | Social and Environmental Specialist | Yasuhira Minami | 4 |  |
| I37 | Resettlement Specialist | Vu Ngoc Long | 8 |  |
| I38 | Training Specialist | Noppong Unhabhokha | 4 |  |

## Vietnamese Staff

| No. | Position | Name | TOR | Agreed |
| --- | --- | --- | --- | --- |
| L1 | Co-Project Manager | Le Kim An | 14.5 |  |
| L2 | Highway Engineer 1 (Geometric) | Tran Dinh Van | 13 |  |
| L3 | Highway Engineer 2 (Road Structure) | Phan Dang Viet Anh | 13 |  |
| L4 | Road Safety Audit Specialist | Tran Quang Huy | 3 |  |
| L5 | Bridge/Structural Engineer 1 (Superstructure) | Le Toan Thang | 13 |  |
| L6 | Bridge/Structural Engineer 2 (Substructure/Foundation) | Dao Ngoc Vinh | 13 |  |
| L7 | Highway Engineer 3 (Geometric) | Le Thi Thanh Thuy | 12 |  |
| L8 | Highway Engineer 4 (Road Structure) | Vu Gia Hung | 12 |  |
| L9 | Bridge/Structural Engineer 3 | Do Hong Phuc | 4 |  |
| L10 | Bridge/Structural Engineer 4 | Pham Anh Kiet | 4 |  |
| L11 | Highway Engineer 5 (Geometric) | Nguyen Dinh Trung | 12 |  |
| L12 | Highway Engineer 6 (Road Structure) | Dao Manh Son | 12 |  |
| L13 | Bridge/Structural Engineer 5 | Le Kien Cuong | 4 |  |
| L14 | Bridge/Structural Engineer 6 | Tran Anh Tuan | 4 |  |
| L15 | Interchange Specialist | Le Thanh Hung | 2 |  |
| L16 | Bridge/Structural Engineer 7 | Pham Ngoc Tuan | 3 |  |
| L17 | Tunnel Engineer | Tran Phong Nha | 4 |  |
| L18 | Soil/Geotechnical Engineer 1 (Slope) | Quach Thi Thu | 2 |  |
| L19 | Soft Ground Treatment Specialist | Trinh Viet Linh | 3 |  |
| L20 | Drainage Engineer 1 | Nguyen Minh Ngoc | 7 |  |
| L21 | Drainage Engineer 2 | Nguyen Phuc Hoa | 6 |  |
| L22 | River Engineer | Nguyen Son | 2 |  |
| L23 | Pavement/Material Engineer 1 | Tran Trong Nghia | 4 |  |
| L24 | Pavement/Material Engineer 2 | Nguyen Viet Hai | 4 |  |
| L25 | Senior Surveyor 1 | Vo Thanh Binh | 7.5 |  |
| L26 | Senior Surveyor 2 | Le Van Thu | 6 |  |
| L27 | Senior Surveyor 3 | Nguyen Anh Tuan | 4 |  |
| L28 | Soil/Geotechnical Engineer 2 | Nguyen Doan Tinh | 5 |  |
| L29 | Soil/Geotechnical Engineer 3 | Nguyen Manh Tuan | 4 |  |
| L30 | Soil/Geotechnical Engineer 4 | Trinh Minh Khiem | 4 |  |
| L31 | Geological Engineer (Tunnel) | Tran Ngoc Nhan | 2 |  |
| L32 | Hydraulic Engineer 1 | Ngo The Hung | 3 |  |
| L33 | Hydraulic Engineer 2 | Pham Huu Nhu | 3 |  |
| L34 | Inundation Analyst | Nguyen Huy Phuong | 3 |  |
| L35 | Transport Economist | Vo Hoang Anh | 3 |  |
| L36 | Operating & Maintenance Specialist | Ha Quoc Hieu | 4 |  |
| L37 | Expressway Management Unit Specialist | Le Tung Lam | 2 |  |
| L38 | Traffic Management Specialist | Phan Minh Tuan | 3 |  |
| L39 | Asset Management Specialist | Trinh Ngoc Hai Thang | 2 |  |
| L40 | Architect 1 | Pham Quang Minh | 3 |  |
| L41 | Architect 2 | Ngo Vu Quang Khoa | 3 |  |
| L42 | ITS Specialist | Nguyen Huu Tinh | 5 |  |
| L43 | Communication System Engineer | To Minh Tri | 3 |  |
| L44 | Electrical Engineer 1 | Trinh Dinh Khiem | 7 |  |
| L45 | Electrical Engineer 2 | Vo Hong | 5 |  |
| L46 | Toll Collection System Specialist | Bui Phu Huy | 4 |  |
| L47 | Cost Estimator 1 (Civil Work Packages) | Nguyen Thi Bich Thuy | 11 |  |
| L48 | Cost Estimator 2 (Civil Work Packages) | Phan Thi Thuy Trinh | 7 |  |
| L49 | Cost Estimator 3 (Other Packages) | Nguyen Thi Sinh | 3 |  |
| L50 | Procurement/Contract Specialist 1 | Nguyen The Truong | 12 |  |
| L51 | Procurement/Contract Specialist 2 | Ha Ngoc Anh Minh | 6 |  |
| L52 | Senior Environmental Specialist | Pham Van Xuan | 8 |  |
| L53 | Environmental Specialist | Pham The Giang | 8 |  |
| L54 | Senior Resettlement Specialist | To be named | 14 |  |
| L55 | Social and Resettlement Specialist | Ho Thi Thu Thuy | 14 |  |
| L56 | Cultural and Archaeological Specialist | Le Duy Son | 14 |  |
| L57 | Training Specialist | To be named | 4 |  |

# contract amount

Cost Estimates is stipulated in Appendix D of the (Draft) Contract as follows:

# Tearm of Payment

Payment shall be made with the following schedule:

#### Twenty (20) percent of the Contract Price shall be paid on the commencement date against the submission of a bank guarantee for the same.

#### Ten (10) percent of the lump-sum amount (including equivalent VAT and CIT) shall be paid upon submission of Inception Report (ICR)

#### Twenty (25) percent of the lump-sum amount (including equivalent VAT and CIT) shall be paid upon submission of Interim Report, Basic Design Report (BDR) and Prequalification Documents;

#### Twenty (20) percent of the lump-sum amount (including equivalent VAT and CIT) shall be paid upon submission of Monthly Progress Report No.9, Detailed Design Reports and Bidding Documents of the first 3 packages.

#### Fifteen (15) percent of the lump-sum amount (including equivalent VAT and CIT) shall be paid upon submission of Detailed Design Reports and Bidding Documents of the remaining packages, Draft Final Project Completion Report and satisfactory completion of the following works:

- Review and update EIA, EMP, EMDP, RAP

- Construction method and schedule;

- Preparation of implementation program;

- Study and design of ITS and toll collection system;

- Cost Estimate;

- Expressway operation and maintenance

#### Ten (10) percent of the lump-sum amount (including equivalent VAT and CIT) shall be paid upon approval of Final Project Completion Report.

The amount for stake land acquisition item shall be paid in accordance with the unit price approved by the Client.

Payment shall be made according to the following schedule:

- The amount shall be paid up to Seventy (70) percent of the approved total amount upon hand-over of all land acquisition stakes of main route to the local authorities by the Consultant.

- The remaining amount shall be paid upon completion of assignments.

- Payments for provisional sum amount shall be made at the same time with some payments for lump-sum amount mentioned above.

The bank guarantee shall be released when the total payments reach fifty (50) percent of the lump-sum amount.

Appendix 2: Major Events

During the reporting period, from July to September 2011, there are several events that have impacted onto the consulting services as follows:

Table A-2-1: Major Events in September 2011

| No. | Event | Date/ Period | Impact to Services |
| --- | --- | --- | --- |
| 1 2 3 | PMU85 requested to study and select the priority package for commencement in the third quarter 2012. Notice of Quang Nam People’s Committee for conclusion of meeting hold at 7 September 2011. VEC requested to have explanation /response against comments from World Bank on the Draft Contract | 22/09/2011 13/09/2011 01/09/2011 | Consultants have studied for proper selection. Alignment Alternative No.4 was selected. Consultants prepared and had feedback for the matters. |

Table A-2-2: Major Events in August 2011

| No. | Event | Date/ Period | Impact to Services |
| --- | --- | --- | --- |
| 1 2 3 4 | VEC had comments on the Survey plan content and survey plan quantity Amendments to the Development Credit Agreements VEC requested to work with local authorites for alternative alignment between km 70-80. VEC approved for sub-consultants | 03/08/2011 09/08/2011 10/08/2011 22/08/2011 | Consultants have revised and updated as per comments PMU85 will be responsible for implementation of technical design. Consultants made Technical Study Report regarding to Alternative Alignment. Consultants prepared for contract signing with sub-consultants |

Table A-2-3: Major Events in July 2011

| No. | Event | Date/ Period | Impact to Services |
| --- | --- | --- | --- |
| 1 2 | Kick-off meeting MOT approved the additional procurement plan of Danang-Quang Ngai Expressway project-packages funded by JICA | 15/07/2011 28/07/2011 | Consultant mobilized 10 staffs to commence the survey work plan for control networks and consulting services. Consultants have re-confirmed the contract packaging. |

Appendix 3: Consultant’s Organization

Appendix 4: Mobilization Status

Table A-4-1: Mobilization Status of International Staff

Table A-4-1: Mobilization Status of Vietnamese Staff

Appendix 5: List of Meetings

Up to the end of September 2011, the consultant attended the following meetings with VEC, PMU85 and other relevant Authorities.

Meeting with VEC-PMU85

| No. | Minutes Ref | Location |  | Date & Time |
| --- | --- | --- | --- | --- |
| 1 | Conclusion of meeting from PMU85 | PMU85 –Danang Office |  | 15/07/2011 (09:00 - 10:30) |
| 2 | DQEDD-MR-01-11 | PMU85 –Danang Office |  | 18/07/2011 (09:00 – 10:30) |
| 3 |  | VEC office |  | 09/08/2011 (14:00 – 15:30) |
| 4 |  | PMU 85 Danang office |  | 08/09/2011 (09:00 – 10:30) |
| 5 | Second Minutes of Contract Negotiation | VEC office |  | 20/09/2011 (09:00 – 11:30) |
| 6 |  |  | PMU 85 Danang office | 30/09/2011 (09:00 – 10:00) |

Meeting with Quang Nam Province

| No. | Meeting | Minutes Ref | Location | Date & Time |
| --- | --- | --- | --- | --- |
| 1 | Meeting with Provincial Adviser - National Target Program to Response to Climate Change of Department of Natural Resources and Environment (DNRE) |  | DNRE Office | 26/08/2011 (8:30 - 10:00) |
| 2 | Meeting with Division of Flood &Storm control |  | Office of Division of Flood & Storm Control | 29/08/2011 (14:00-15:30) |
| 3 | Meeting with Natural Resources and Environment Technology Center |  | DNRE Office | 30/08/2011 (10:00-11:00) |
| 4 | Meeting with Quang Nam People’s Committee | Notice No. 346/TB-UBND dated 19 September 2011 issued by Quang Nam PC | Quang Nam People’s Committee Office | 07/09/2011 (14:00 - 16:00) |
| 5 | Meeting with Department of Agriculture and Rural Development – Quang Nam Province (DARD) |  | DARD office | 15/09/2011 (14:00-14:40) |
| 6 | Meeting with Department of Transportation – Quang Nam Province (DOT) |  | DOT office | 15/09/2011 (15:30-17:00) |

Meeting with TEDI

| No. | Meeting | Minutes Ref | Location | Date & Time |
| --- | --- | --- | --- | --- |
| 1 | TEDI meeting | DQEDD-TEDI-AG-02-11 | TEDI Office | 24/08/2011 (8:30 - 10:00) |

Meeting with Quang Ngai Province

| No. | Meeting | Minutes Ref | Location | Date & Time |
| --- | --- | --- | --- | --- |
| 1 | Meeting with Center for Mitigation and Management of Natural Disasters |  | Office of Center for Mitigation and Management of Natural Disasters | 30/08/2011 (13:30 - 15:00) |

Other Meeting

| No. | Meeting | Minutes Ref | Location | Date & Time |
| --- | --- | --- | --- | --- |
| 1 | Meeting with Mr Fukishi Tomida -President of Earth System Science |  |  | 04/09/2011 |

Appendix 6: List of Documents Submitted

| No. | Ref. No. | Submission Date | Title of Documents |
| --- | --- | --- | --- |
| 1 | DQEDD-VEC-04-11 | 07/06/2011 | Revised Work Plan for Control Point Survey |
| 1a | DQEDD-PMU85-01-11 | 21/06/2011 | Survey Work Plan for Control Network |
| 1b | DQEDD-VEC-05-11 | 20/07/2011 | Revised Work Plan for Control Point Survey |
| 2 | DQEDD-VEC-06-11 | 28/07/2011 | Evaluation report on Sub-consultants for Topographic and Geotechnical Surveys |
| 2a | DQEDD-VEC-14-11 | 10/08/2011 | Evaluation report for Companies Competency for Natural Condition Survey |
| 2b | DQEDD-VEC-15-11 | 16/08/2011 | Company Profile of Sub-consultants. |
| 3 | DQEDD-PMU85-12-11 | 30/08/2011 | Technical Report ”Alignment Alternative Study for Section between KM70-Km80” |
| 3a | DQEDD-PMU85-13-11 | 06/09/2011 | Technical Report (Revision-1) “Alignment Alternative Study for Section between Km70-Km80” |
| 2c | DQEDD-PMU85-15-11 | 08/09/2011 | Company profile of Sub-Consultants |
| 4 | DQEDD-PMU85-20-11 | 26/09/2011 | Monthly Progress Report – July/August 2011 |
| 5 | DQEDD-PMU85-21-11 | 26/09/2011 | Work Plan for Topographic Survey |
| 6 | DQEDD-PMU85-22-11 | 30/09/2011 | Evaluation Report on Sub-consultants for Hydrological Survey |

Appendix 7: List of Correspondence

Correspondence received from PMU 85

| No. |  | Ref. No. |  | Date Received |  | Subject |  | Status |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 867/PMU85-PP2 | 01/07/2011 | Addendum of existing issues of survey work plan for control networks | Closed |
| 2 | 870/BQL-DNQN | 04/07/2011 | Acceptance for Kick-off meeting. | Closed |
| 3 | 39/BDHDA_DNQN | 19/07/2011 | Acceptance for Site hand-over control point monuments | Closed |
| 4 | 980/TB-BQL | 25/07/2011 | Conclusion of kick-off meeting | Closed |
| 5 | 41/BQL-DNQN | 29/07/2011 | Mobilization plan before issuance of Notice to Proceed. | Closed |
| 6 | 42/BQL-DNQN | 02/08/2011 | Provision of digital file of FS drawings. | Closed |
| 7 | 42/BQL-DNQN | 31/08/2011 | Comments on study results for alignment alternative between km70 to km80 | Closed |
| 8 | 43/BQL-DNQN | 01/09/2011 | Request for preparation of meeting with Quang Nam People’s Committee | Closed |
| 9 | 1316/PMU85-PP2 | 22/09/2011 | Progress of Detailed Design |  |

Correspondence sent to PMU85

| No. |  | Ref. No. |  | Date Sent |  | Subject |  | Status |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | DQEDD-PMU85-01-11 | 21/06/2011 | Submission of Survey Work Plan for control network | Closed |
| 2 | DQEDD-PMU85-02-11 | 22/06/2011 | Request of Implementation Organization of PMU85 | Closed |
| 3 | DQEDD-PMU85-03-11 | 26/06/2011 | Appointment of Acting Team Leader | Closed |
| 4 | DQEDD-PMU85-04-11 | 28/06/2011 | Request for Provision of CP survey data | Closed |
| 5 | DQEDD-PMU85-05-11 | 28/06/2011 | Request for Kick-off meeting on 15 July 2011. | Closed |
| 6 | DQEDD-PMU85-06-11 | 12/07/2011 | Request for Approval of sub-consultants for Natural Condition Survey | Closed |
| 7 | DQEDD-PMU85-07-11 | 13/07/2011 | Technical Specifications for Topo-Survey | Closed |
| 8 | DQEDD-PMU85-08-11 | 18/07/2011 | Request of Site Hand-over of control point monuments | Closed |
| 9 | DQEDD-PMU85-09-11 | 28/07/2011 | Mobilization Plan before issuance of Notice to Proceed | Closed |
| 10 | DQEDD-PMU85-10-11 | 01/08/2011 | Request of provision of Digital files of F/S drawings | Closed |
| 11 | DQEDD-PMU85-11-11 | 27/08/2011 | Request of meeting arrangement with Quang Nam People’s Committee. | Closed |
| 12 | DQEDD-PMU85-12-11 | 30/08/2011 | Study results on the Alignment between Km70 and km 80 | Closed |
| 13 | DQEDD-PMU85-13-11 | 05/09/2011 | Request of Design Changes |  |
| 14 | DQEDD-PMU85-13a-11 | 06/09/2011 | Clarification of Study Results on the Alignment between KM70 and KM80 | Closed |
| 15 | DQEDD-PMU85-14-11 | 06/09/2011 | Request of Meeting on 8 September 2011 | Closed |
| 16 | DQEDD-PMU85-15-11 | 08/09/2011 | Submission of Company Profile of Sub-Consultants | Closed |
| 17 | DQEDD-PMU85-16-11 | 08/09/2011 | Request for Issuing letters to Department of Natural Resources and Environment (DNRE) and Department of Agriculture and Rural Development (DARD) of Quang Nam Province. |  |
| 18 | DQEDD-PMU85-17-11 | 08/09/2011 | Request for Issuing letters to People Committee, Department of Natural Resources and Environment (DNRE) and Department of Agriculture and Rural Development (DARD) of Quang Ngai Province. |  |
| 19 | DQEDD-PMU85-18-11 | 10/09/2011 | Appointment of Acting Team Leader | Closed |
| 20 | DQEDD-PMU85-19-11 | 10/09/2011 | Request of Provision of AutoCAD files of Tuy Loan Intersection. |  |
| 21 | DQEDD-PMU85-20-11 | 26/09/2011 | Submission of Monthly Progress Report-July/August 2011 (English/Vietnamese) | Closed |
| 22 | DQEDD-PMU85-21-11 | 26/09/2011 | Submission of Work Plan for Topographic Survey | Closed |
| 23 | DQEDD-PMU85-22-11 | 30/09/2011 | Submission of Evaluation Report on Sub-consultants for Hydrological Survey |  |

Correspondence received from VEC

| No. |  | Ref. No. |  | Date Received ent |  | Subject |  | Status |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 953/VEC-KTCNMT | 02/06/2011 | Comments on Survey Work Plan for control Network-Detailed design Stage. | Closed |
| 2 | 1053/VEC-KTCNMT | 20/06/2011 | To execute specific tasks related to investigation and design | Closed |
| 3 | 1391/VEC-KTCNMT | 03/08/2011 | Comments on Revised work plan for control point survey | Closed |
| 4 | 1449/VEC-KTCNMT | 10/08/2011 | Study of realignment between km 70-km80 | Closed |
| 5 | 1533/VEC-KTCNMT | 22/08/2011 | Approval for sub-consultant for Topographic and Geotechnical Survey works | Closed |
| 6 | 1606/VEC-KHDT | 31/08/2011 | Draft contract for detailed design consulting services. | Closed |
| 7 | 1723/VEC-DA | 15/09/2011 | Invitation to Negotiation Meeting. | Closed |

Correspondence sent to VEC :

| No. |  | Ref. No. |  | Date Sent |  | Subject |  | Status |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | DQEDD-VEC-01-11 | 20/05/2011 | Submission of Survey Work Plan for Control Network | Closed |
| 2 | DQEDD-VEC-02-11 | 24/05/2011 | Clarification of Capability of Senior Hydrologist | Closed |
| 3 | DQEDD-VEC-03-11 | 26/05/2011 | Submission of Discussion Materials Used in Contract Negotiation | Closed |
| 4 | DQEDD-VEC-04-11 | 07/06/2011 | Submission of Revised Work Plan for Control Point Survey | Closed |
| 5 | DQEDD-VEC-05-11 | 20/07/2011 | Submission of Revised Work Plan for Control Point Survey | Closed |
| 6 | DQEDD-VEC-06-11 | 20/07/2011 | Notice of New Contact Address of the Project Office | Closed |
| 7 | DQEDD-VEC-07-11 | 27/07/2011 | Request for VISA Application Arrangement | Closed |
| 8 | DQEDD-VEC-08-11 | 28/07/2011 | Request for Timely Approval of Sub-consultants for Topographic Survey. | Closed |
| 9 | DQEDD-VEC-09-11 | 03/08/2011 | Mobilization Plan before Issuance of Notice to Proceed | Closed |
| 10 | DQEDD-VEC-10-11 | 03/08/2011 | Reconfirmation of Necessity of Early Commencement in Q1 of 2012 | Closed |
| 11 | DQEDD-VEC-11-11 | 03/08/2011 | Confirmation of Contract Packaging |  |
| 12 | DQEDD-VEC-12-11 | 05/08/2011 | Request for Timely Approval of Sub-consultants for Topographic Survey.(Revision 1) | Closed |
| 13 | DQEDD-VEC-13-11 | 05/08/2011 | Request of Meeting on 9 August 2011 | Closed |
| 14 | DQEDD-VEC-14-11 | 10/08/2011 | Re-submission of Evaluation Report for Companies Competency for Natural Condition Survey. | Closed |
| 15 | DQEDD-VEC-15-11 | 16/08/2011 | Submission of Company Profile of Sub-consultants | Closed |

Appendix 8: Technical Standards to be Applied to the Project

According to the Decision No. 362/QD-BGTVT dated on 20 February 2009, the following technical standards are to be applied to the Project. Those are being updated with recent updates of Vietnamese technical standards.

| No. | Standards to be applied | Code |  |
| --- | --- | --- | --- |
| I | TO BE APPLIED FOR SURVEY |  |  |
| 1 | Specification for measuring and drawing topography |  | 96TCN43-1990 |
| 2 | Specification for drawing topographical maps with scale 1:500 1:1000 1:2000 1:5000 1:10000 1:25000 |  | 96TCN42-1990 |
| 3 | Geodesy works in engineering - general requirements |  | TCXDVN309-2004 |
| 4 | Specification for measuring and analyzing GPS data |  | TCXDVN364-2006 |
| 5 | Specification for boring survey |  | 22TCN259-2000 |
| 6 | Specification for geotechnical investigation of marine works |  | 22TCN260-2000 |
| 7 | Specification for surveying and designing the highway embankment on the soft ground |  | 22TCN262-2000 |
| 8 | Specification for surveying highway |  | 22TCN263-2000 |
| 9 | Specification for geotechnical investigation and design solution for roads in land sliding areas |  | 22TCN171-1987 |
| 10 | Specification for Static Penetration Test (CPT and CPTU) |  | 22TCN317-2004 |
| 11 | Specification for site shearing test |  | 22TCN355-2000 |
| 12 | Construction soil site testing method SPT |  | TCXD226-1999 |
| 13 | Construction soil-physic-mechanical test |  | TCVN4195-4202-1995 |
| 14 | Surveying works for design and construction of pile foundation |  | 20TCN160-1987 |
| 15 | Construction soil exploiting packing transporting and maintaining samples |  | TCXD2683-1991 |
| 16 | Specification for checking bridge on highway technical requirements |  | 22TCN243-1998 |
| 17 | Specification for testing elastic modulus of the pavement by deflection measurement Benkelman beam |  | 22TCN251-1998 |
| 18 | Specification for testing and evaluating pavement strength and flexible pavement of highway by FWD |  | 22TCN335-2006 |
| 19 | Specification for analyzing water used in transport constructions |  | 22TCN61-1984 |
| 20 | Specification for geotechnical investigation for constructions in Karst area |  | TCXDVN366-2006 |
| II | TO BE APPLIED FOR DESIGN |  |  |
| 1 | Expressway highway design requirements |  | TCVN5729-1997 |
| 2 | Highway Design requirements |  | TCVN4054:2005 |
| 3 | Standard for designing highway (junctions) |  | 22 TCN273-2001 |
| 4 |  |  | 22TCN244-1998 |
| 5 | Geotextile applying for embankment of soft soil ground |  | 22TCN248-1998* |
| 6 | Specification for designing of flexible pavement |  | 22TCN211-2006 |
| 7 | Specification for rigid pavement design |  | 22TCN223-1995 |
| 8 | Standard of bridge design |  | 22TCN272-2005 |
| 9 | Standard for design culverts with limit state (applying for culvert design and auxiliaries) |  | 22TCN18-1979 |
| 10 | Pile foundation design standard |  | TCXDVN205-1998 |
| 11 | PC concrete nail T13 T15 & D13 D15 |  | 22TCN267-2000 |
| 12 | Rubber bearings |  | AASHTO M251-06-UL, ASTM D4014-03(2007) |
| 13 | Standard for expansion joints |  | AASHTO M297-96, AASHTO M183-96 |
| 14 | Specification for design of bridges and auxiliaries for bridges |  | 22TCN200-1989 |
| 15 | Calculation of flood flow features |  | 22TCN220-1995 |
| 16 | Transport works in earthquake zone design standard |  | 22TCN221-1995 |
| 17 | Regulations of traffic signals on highway |  | 22TCN237-2001* |
| 18 | Guiding board on expressway |  | 22TCN331-2005* |
| 19 | Drainage design standard |  | 22TCN51-1984 |
| 20 | Standard for design lighting of roads and squares in urban |  | TCXDVN259-2001 |
| 21 | Lighting outdoor of public works and infrastructure in urban construction design standards |  | TCXDVN333-2005 |
| 22 | Specification for environment impact assessment in preparing FS and design for transport works |  | 22TCN242-1998 |
| 23 | Design earthquake bearing facilities |  | TCXDVN375-2006 |
| 24 | Concrete and reinforced concrete |  | TCXDVN356-2005 |

Following laws, regulations and technical standards are also to be applied in the Detailed Design.

| No. | Laws/Standards to be applied |  | Code |
| --- | --- | --- | --- |
| 1 | Bidding law |  | Law No.61/2005/QH11 |
| 2 | Amended law on capital construction |  | Law No.38/2009/QH12 |
| 3 | Instruction on applying bidding law and selection of contractors according to construction law |  | Decree No.85/2009/ND-CP |
| 4 | Highway Design Requirements |  | TCVN4054-2005 |
| 5 | National Technical Regulation on Establishment of Leveling Network |  | QCVN11-2008/BTNMT |
| 6 | Expressway highway design requirements |  | TCVN5729-2007 |
| 7 | Decision on promulgating regulations on recognition and management of laboratory specializing in construction industry |  | Decision No.11/2008/QĐ-BXD |
| 8 | Rules for technical classification of inland waterways |  | TCVN5664-2009 |
| 9 | Drainage & swerage external networks and facilities - design standard |  | TCVN7957-2008 |

Appendix 9: List of Sub-Consultants

| No. | Company Name | Abbreviation | Head Office Address / Contact | Person in Charge |
| --- | --- | --- | --- | --- |
| 1 | Thang Loi Engineering Consultants | Thang Loi | 16A/93 Trung Kinh Str, Cau Giay Dist, Hanoi / TEL: 04-3378-44627 | ### Cao Tuan Dung |
| 2 | Transport Engineering Design Joint Stock Incorporated South | TEDI South | 92 Nam Ky Khoi Nghia, Dist 1, HCMC / TEL: 08-3829-9988 | Nguyen Anh Tuan |
| 3 | Technology Development & Investment Consultant Joint Stock Company | TDIC | 116 Dong Da, Danang / TEL: 0511-3889732 | Le Thi Thanh Thuy |
| 4 | E&R Engineering Consultants Joint Stock Company | ENR | Room 425, CT5 Building, Song Da My Dinh New City, Me Tri Commune, Tu Liem Dist, Hanoi / TEL: 04-6652-4636 | Vu Duc Long |
| 5 | Thien Khai Joint Stock Company | Thien Khai | Room 703, Block A, Ha Thanh Building, 102 Thai Thinh Str, Dong Da Dist, Hanoi / TEL: 04-3538-0680 | To be named |
| 6 | EGS (Vietnam) Company Limited | EGS | R403A, C4 Building, Thang Long International Village, Dich Vong Ward, Cau Giay Dist, Hanoi / TEL: 04-3754-5208 | Nguyen Khanh Thanh |
| 7 | InPEL International Consultants & Investment Corp. | InPEL | 34T Tower, Hoang Dao Thuy Rd., Cau Giay Dist, Hanoi / TEL: 04-2242-0879 | To be named |
| 8 | Thanh Cong Consultancy & Construction Joint Stock Company | Thanh Cong | 1505, Vanh Dai Dong Str, An Phu Ward, Dist 2, HCMC/ TEL: 08-6281-8158 | To be named |
| 9 | Tan Phat Joint Stock Company | Tan Phat | Building A3, Group 84, Hoang Cau Str, O Cho Dua Ward, Dong Da Dist, Hanoi / TEL: 04-3513-2274 | To be named |
| 10 | North Central Region Consulting Investment Construction Joint Stock Company | BMT | 64 Phan Chu Trinh Str, Vinh, Nghe An/ TEL: 038-3846845 | To be named |
| 11 | Construction Investment Consultant ATH., Joint Stock Company | ATH | 15/129 Xa Dan 2, Xa Dan Str (Kim Lien – O Cho Dua new), Nam Dong Ward, Dong Da Dist, Hanoi / TEL: 04-3572-6864 | To be named |
| 12 | Independent Intellectual Consultancy Company., Ltd. | ICTC | 83 Path 107 Lang Trung, Lang Ha Ward, Dong Da Dist, Hanoi / TEL: 04-2246-2356 | To be named |

Appendix 10: List of Contact Person

| No. | Date of Contact | Contact Person | Title | Organization |
| --- | --- | --- | --- | --- |
| 1 | 26 /08/2011 | Mr Ian Wood | Provincial Adviser | National target Program to Response to Climate Change |
| 2 | 29/08/2011 | Mr Nguyen Minh Tuan | Director | Division of Flood and Storm Control- Department of Agriculture and Rural Development, Quang Nam Province. |
| 3 | 30/08/2011 | Mr Dao Xuan Nguyen | Diretor | Natural Resources and Environment Technology Center-Department of Natural Resources and Environment, Quang Nam Province. |
| 4 | 30/08/2011 | Mr Phan Van On Mr Bui Duc Thai | Director Model Operator | Center for Mitigation and Management of Natural Disasters- Department of Agriculture and Rural Development |
| 5 | 04/09/2011 | Mr Yukishi Tomida | President | Earth System Science Co., Ltd. , Japan |
| 6 | 07/09/2011 | Mr. Dinh Van Thu | Vice Chairman | Quang Nam People’c Committee |
| 7 | 07/09/2011 | Mr. Huynh Khanh Toan | Vice Chairman, Manager of Chu Lai Open Economy Zone | Quang Nam People’c Committee |
| 8 | 07/09/2011 | Mr. Tran Thanh An | Vice Director of DOT | DOT – Quang Nam Province |
| 9 | 15/09/2011 | Mr. Nguyen Van Tien | Vice Director | DARD –Quang Nam Province |
| 10 | 15/09/2011 | Mr. Le Van Sinh | Project Manager | DOT – Quang Nam Province |

Appendix 11: List of Reports (Version 1-111011)

Reports/Documents

| Code | Report Title | Responsible Staff | TOC Date | Progress (%) |  |  |  |  | Submission Date |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | July | Aug | Sep | Oct | Nov | SCH | ACT |
| GN | General Reports | --- |  |  |  |  |  |  |  |  |
| GN1000 | Inception Report | Ishimoto |  |  |  |  |  |  | --- |  |
| GN2000 | Monthly Progress Report | Ishimoto |  |  |  |  |  |  |  |  |
| GN2010 | Monthly Progress Report (July-August) (English) | Ishimoto |  | 100 | 100 |  |  |  | --- | 26/9/11 |
| GN2011 | Monthly Progress Report (July-August) (Vietnamese) | Ishimoto |  | 100 | 100 |  |  |  | --- | 26/9/11 |
| GN2020 | Monthly Progress Report (September) (English) | Ishimoto |  |  |  | 100 |  |  | --- | 15/10/11 |
| GN2021 | Monthly Progress Report (September) (Vietnamese) | Ishimoto |  |  |  | 100 |  |  | --- | 15/10/11 |
| GN3000 | The Services Completion Report | Ishimoto |  |  |  |  |  |  | --- |  |

| DS | Design Reports | --- |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DS1000 | Previous Studies Review Report |  |  |  |  |  |  |  |  |  |
| DS2000 | Detailed Engineering Design Framework |  |  |  |  |  |  |  |  |  |
| DS3000 | Brief Report on Appropriateness of the F/S Alignment |  |  |  |  |  |  |  |  |  |
| DS4000 | Basic Design Report (Civil, Draft Design Report) |  |  |  |  |  |  |  |  |  |
| DS5000 | Design Report |  |  |  |  |  |  |  |  |  |
| RA | Road Safety Audit | --- |  |  |  |  |  |  |  |  |
| RA1000 | Road Safety Audit Report |  |  |  |  |  |  |  |  |  |
| PA | Procurement Plan Reports | --- |  |  |  |  |  |  |  |  |
| PA1000 | Pre-qualification Document |  |  |  |  |  |  |  |  |  |
| PA2000 | Bidding Documents |  |  |  |  |  |  |  |  |  |
| ER | Environmental and Social Reports | --- |  |  |  |  |  |  |  |  |
| ER1000 | Updated draft EIA and EMP |  |  |  |  |  |  |  |  |  |
| ER2000 | Draft Final Updated EIA and EMP |  |  |  |  |  |  |  |  |  |
| ER3000 | Comprehensive Plan on Compensation, Support and Resettlement |  |  |  |  |  |  |  |  |  |

Technical Reports

| Code | Report Title | Responsible Staff | TOC Date | Progress (%) |  |  |  |  | Submission Date |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | July | Aug | Sep | Oct | Nov | SCH | ACT |
| SV | Survey Reports | --- |  |  |  |  |  |  |  |  |
| DS | Design Reports | --- |  |  |  |  |  |  |  |  |
| RA | Road Safety Audit | --- |  |  |  |  |  |  |  |  |
| PM | Perspectives & 3D Models | --- |  |  |  |  |  |  |  |  |
| QT | Quantity Reports | --- |  |  |  |  |  |  |  |  |
| OM | Operation and Maintenance Reports | --- |  |  |  |  |  |  |  |  |
| CE | Cost Estimate Reports | --- |  |  |  |  |  |  |  |  |
| PA | Procurement Plan Reports | --- |  |  |  |  |  |  |  |  |
| ER | Environmental and Social Reports | --- |  |  |  |  |  |  |  |  |

Appendix 12: List of Drawings

Under preparation