## NY paid
Joint Venture of NK - NEC - Chodai - TEC
BREAKDOWN FOR SUB-CONTRACTOR PAYMENT
[20 empty] | 0 | [31 empty] | #REF! | [22 empty] | Updated 151203 |  | #REF! |  |  | Updated:130726
STT |  | Code | Sub-contract | Address | Tax code | Date of signing | Time of commencemant and completion | Detail | price | [12 empty] | Exchange rate | Payment status | [48 empty] | Total of paid amount | Remaining Amount in USD (Not yet paid) | Adjust 140602 | Detailed of remaining amount | Dealine of payment | Remaining Amount in USD ( HO) | Remaining Amount in JPY (HO) | Contact person | Remark
[9 empty] | Contract price | Add No.1/adjusted |  | Add No.2 |  | Add No.3 |  | Add No.4 |  | Add No.5 |  | Total of Contract & Add | equivalent in JPY |  | The first payment | [6 empty] | The second payment | [6 empty] | The third payment | [6 empty] | The fourth payment | [6 empty] | The fifth payment | [6 empty] | The sixth payment | [6 empty] | The final payment
[10 empty] | Dif | Total | Dif | Total | Dif | Total | Dif | Total | Dif | Total |  |  |  | in USD (Inc VAT) | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site
A. Survey
I. Topo survey | [78 empty] | #REF! | #REF!
II. Hydro survey | [78 empty] | #REF! | #REF!
III. Geo survey | [8 empty] | 460983 | 183320 | 644303 | 225231 | 869534 | 0 | 869534 | 0 | 0 | 0 | 0 | 869534 | 57168410.9 | 426.367 | 166914.5345 | 13468213 | 0 | 404.1326 | 16691.4535 | 347649596.6422 | 0 | 133716.3618 | 11795912 | 0 | 444.2369 | 13371.6362 | 278504438.3949 | 0 | 119429.46 | 12167468 | 0 | 509.8586 | 11942.946 | 251231812.056 | 0 | 28144 | 2882508 | 0 | 102.42 | 2814.4 | 59203718.4 | 0 | 96700 | 9830522 | 0 | 101.66 | 9670 | 205448820 | 0 | 48349.6364 | 5286550 | 0 | 109.34 | 4834.9636 | 102723637.4182 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 652579.392 | 216954.608 |  |  |  | 103169.6436 | -335849 | 0 | 0
1 | JA1200309 | E&R | E&R engineering consultants joint stock company |  |  | 18/06/2012 | 15/08/2012 | Engineering Geological Survey works ( Package 1, Hoa Vang section, Km0+000-km8+000) | 186528 |  |  | 206392 | 392920 | [6 empty] | 392920 | 34364455 | 96.2051 | 67113.08 | 5299484 | 19/07/2012 | 78.9635 | 6711.308 | 139783123.024 | 06/09/2012 | 33914.18 | 2701604 | 22/11/2012 | 79.66 | 3391.418 | 70636454.104 | 19/12/2012 | 34629.46 | 3503809 | 11/07/2013 | 101.18 | 3462.946 | 72846532.056 | 15/08/2013 | 28144 | 2882508 | 26/12/2013 | 102.42 | 2814.4 | 59203718.4 | 15/01/2014 | 96700 | 9830522 | 19/06/2014 | 101.66 | 9670 | 205448820 | 21/07/2014 | 48349.6364 | 5286550 | 11/12/2014 | 109.34 | 4834.9636 | 102723637.4182 | 31/12/2014 | [7 empty] | 339735.392 | 53184.608 | TT lần cuối: USD 106369,2 | 25% of additional work | stop (Acceptance Minutes: 24 July 2013) => 23/01/2014 | -73972.72 | 4859978 |  | Paid 80% of the original , NY made the 4th & 5th paymnent
5 | JA1200559 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 31/08/2012 |  | Engineering Geological Survey works ( Package 2, Bridge section, Km8+000-Km16+880) | 93500 | 101200 | 194700 | [8 empty] | 194700 | 7349100 | 78.6 | 34000 | 2708440 | 13/12/2012 | 79.66 | 3400 | 70815200 | 21/01/2013 | 34000 | 3329280 | 06/06/2013 | 97.92 | 3400 | 70815200 | 18/07/2013 | 18000 | 1834920 | 03/04/2014 | 101.94 | 1800 | 37864800 | 09/05/2014 | [28 empty] | 94600 | 100100 | ok | 100% of additional work (USD 100,100.00) | Stop | 108700 | -1191640 |  | Paid 80% of the original. NY pay for supplymental works, additional works
6 | JA1200139 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 15/02/2012 | 01/03-31/05 | Engineering Geological Survey works (Package 3A, Ky Lam Bridge section ) | 80196 | 11191 | 91387 | 3771 | 95158 | [6 empty] | 95158 | 7510528.3 | 93.6522 | 29161.8182 | 2604413 | 31/05/2012 | 89.309 | 2916.1818 | 60738239 | 15/06/2012 | 29162.1818 | 2262971 | 08/11/2012 | 77.5995 | 2916.2182 | 60738992.2909 | 19/12/2012 | 12968.18 | 1321958 | 03/04/2014 | 101.9386 | 1296.818 | 27279863.448 | 09/05/2014 | [28 empty] | 78421.398 | 16736.602 | TT lan 4:8368 TT lan cuoi:8368.60 | 100% of additional work (USD 16,736.) | Stop | 23865.82 | 638411 |  | Paid 80% of the original.
18 | JA1200565 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 27/08/2012 |  | Engineering Geological Survey works ( Package A3, Km99+500-Km110+100) | 66000 | 61600 | 127600 | [8 empty] | 127600 | 5187600 | 78.6 | 24000 | 1862400 | 25/10/2012 | 77.6 | 2400 | 49987200 | 29/11/2012 | 24000 | 2350080 | 06/06/2013 | 97.92 | 2400 | 49987200 | 18/07/2013 | 33000 | 3364020 | 03/04/2014 | 101.94 | 3300 | 69418800 | 09/05/2014 | [28 empty] | 89100 | 38500 | ok | 100% of additional work (USD 38,500) | Stop | 46600 | -2860500 |  | Paid 80% of the original , NY made the 3rd, 4th & 5th paymnent
19 | JA1200475 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 2012-01-08 |  | Engineering Geological Survey works (Package A3, Tra bong Bridge section, Km 108+775.25-km109+230.25 ) | 34759 | 9329 | 44088 | 15068 | 59156 | [6 empty] | 59156 | 2756727.6 | 79.3097 | 12639.6364 | 993476 | 27/09/2012 | 78.6 | 1263.9636 | 26325834.6182 | 29/11/2012 | 12640 | 1151977 | 14/03/2013 | 91.1374 | 1264 | 26326592 | 22/04/2013 | 20831.82 | 2142761 | 06/03/2013 | 102.86 | 2083.182 | 43821816.552 | 17/04/2014 | [28 empty] | 50722.602 | 8433.398 | TT lan 4:4217 TT lan cuoi:4216.4 | 100% of additional work (USD 8,434) | Stop | -2023.4564 | -1782098 |  | Paid 80% of the original.
VI.Other works | [8 empty] | 95260 | 31020 | 126280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126280 | 7517919 | 78.92 | 34640 | 2688064 | 41132 | 77.6 | 3464 | 72148192 | 0 | 34640 | 3638932 | 0 | 105.05 | 3464 | 72868704 | 0 | 21920 | 2228387 | 0 | 101.66 | 2192 | 46571232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 100320 | 25960 |  | 0 |  | 35080 | -1720911.1818 | 0 | 0
2 | JA1200311 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 2012-01-06 | 10/6-31/7/2012 | Land acquisition & Row staking works | 95260 | 31020 | 126280 | [8 empty] | 126280 | 7517919 | 78.92 | 34640 | 2688064 | 2012-08-11 | 77.6 | 3464 | 72148192 | 19/12/2012 | 34640 | 3638932 | 23/01/2014 | 105.05 | 3464 | 72868704 | 18/03/2013 | 21920 | 2228387 | 10/07/2014 | 101.66 | 2192 | 46571232 | 05/08/2014 | [28 empty] | 100320 | 25960 |  | 100% off additional works | Stop | 35080 | -1720911.1818 |  | Paid 40% of the original contract
Total Amount in USD | [8 empty] | 556243 | 214340 | 770583 | 225231 | 869534 | 0 | 869534 | 0 | 0 | 0 | 0 | 995814 | 64686329.9 | 505.287 | 201554.5345 | 16156277 | 41132 | 481.7326 | 20155.4535 | 419797788.6422 | 0 | 168356.3618 | 15434844 | 0 | 549.2869 | 16835.6362 | 351373142.3949 | 0 | 141349.46 | 14395855 | 0 | 611.5186 | 14134.946 | 297803044.056 | 0 | 28144 | 2882508 | 0 | 102.42 | 2814.4 | 59203718.4 | 0 | 96700 | 9830522 | 0 | 101.66 | 9670 | 205448820 | 0 | 48349.6364 | 5286550 | 0 | 109.34 | 4834.9636 | 102723637.4182 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 752899.392 | 242914.608 |  |  |  | 134478.6436 | -2056760.1818 | #REF! | #REF!
|  |  | Check |  |  |  |  | Total | [10 empty] | 995814 | [49 empty] | Check |  |  | 242914.608 | 242914.608
Note on M11: Huong: NY signed Add No.1 b/c Ishimoto
Note on V11: Huong: Email: 3/7/2012
Note on X11: Huong: email dated 20120710
Note on K12: Huong: NY signed Add
Note on Y13: Huong: 05/24/2012
Note on AB13: Huong: DN-QN paid 15/06/2012
Note on K14: Huong: NY signed Add
Note on M15: Huong: NY signed Add
Note on Y15: Huong: Email from Tokyo: 18/09/2012
Note on J17: Huong: Including 10%VAT
Note on V17: Huong: Email: 3/7/2012

## All sub-Consultant
Joint Venture of NK - NEC - Chodai - TEC
BREAKDOWN FOR SUB-CONTRACTOR PAYMENT
[20 empty] | 152126.09 | [31 empty] | #DIV/0! | [22 empty] | Updated 151203 |  | 2715.5436 |  |  | Updated:130726
STT |  | Code | Sub-contract | Address | Tax code | Date of signing | Time of commencemant and completion | Detail | price | [12 empty] | Exchange rate | Payment status | [48 empty] | Total of paid amount | Remaining Amount in USD (Not yet paid) | Adjust 140602 | Detailed of remaining amount | Dealine of payment | Remaining Amount in USD ( HO) | Remaining Amount in JPY (HO) | Contact person | Remark
[9 empty] | Contract price | Add No.1/adjusted |  | Add No.2 |  | Add No.3 |  | Add No.4 |  | Add No.5 |  | Total of Contract & Add | equivalent in JPY |  | The first payment | [6 empty] | The second payment | [6 empty] | The third payment | [6 empty] | The fourth payment | [6 empty] | The fifth payment | [6 empty] | The sixth payment | [6 empty] | The final payment
[10 empty] | Dif | Total | Dif | Total | Dif | Total | Dif | Total | Dif | Total |  |  |  | in USD (Inc VAT) | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site
A. Survey
I. Topo survey | [8 empty] | 1102185 | 6147.9 | 1108332.9 | 101706 | 1210038.9 | 34065 | 1244103.9 | 5938.9 | 1250042.8 | 4268.29 | 1254311.09 | 1254311.09 | 92317167.7 | 764.0124 | 500785.7582 | 38978373.4545 | 41223 | 803.776 | 6932.7758 | 144704995.7811 | 0 | 417506.8409 | 33307935.6145 | 0 | 765.7373 | 34974.6641 | 771728623.0364 | 0 | 195115.0909 | 19218309.6073 | 0 | 492.64 | 19511.5091 | 410444099.5273 | 0 | 7967.2727 | 778774 | 0 | 97.7466 | 796.7273 | 16759954.9091 | 0 | 23661.8182 | 2423444 | 0 | 102.42 | 2366.1818 | 49775000.7273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40629.5364 | 4143208 | 0 |  | 4062.9536 | 85965128.9673 | 0 | 1254311.129 | -0.039 |  |  |  | 68344.7727 | -7500989.6764 | 0 | 0
1 | JA1100597 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 15/07/2011 | 15/07-31/10/2011 | Control point survey works | 97544 | [10 empty] | 97544 | 6903504 | 70.7732 | 39017.6 | 2990699 | 02/11/2011 | 76.65 |  |  |  | 35470.55 | 2799335 | 26/06/2012 | 78.92 | 3547.055 | 73878062 | 20/07/2012 | 17735.2727 | 1748520 | 08/08/2013 | 98.59 | 1773.5273 | 37307914 | 04/10/2013 | [28 empty] | 97544.005 | -0.005 |  | Closed |  | 5320.5773 | -635050 | Van: 0435579345; 0913300509 | Paid: 100% of original contract, no addendum
2 | JA1100595 | TEDIS | Transport engineering design joint stock inc.South |  |  | 22/08/2011 | 22/08-31/12/2011 | Topographic survey works | 110000 |  |  | 2750 | 112750 | 2750 | 115500 |  |  |  |  | 115500 | 8798995.7 | 79.9909 | 44000 | 3372600 | 20/10/2011 | 76.65 |  |  |  | 44000 | 3616360 | 26/04/2012 | 82.19 |  |  |  | 25000 | 2459000 | 26/09/2013 | 98.36 | 2500 | 52590000 | 07/11/2013 | [28 empty] | 115500 | 0 |  | Closed |  | 2500 | -1448873 | Binh: 083299988;0903307968 | Paid: 80% of original contract, not yet paid for Add 2&3
3 | JA1100598 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 22/08/2011 | 22/08-31/12/2011 | Topographic survey works | 602701 |  |  | 60820 | 663521 | [6 empty] | 663521 | 48651036 | 80.7217 | 241080.4 | 18478813 | 02/11/2011 | 76.65 |  |  |  | 219164 | 17296423 | 28/06/2012 | 78.92 | 21916.4 | 456474779.2 | 20/07/2012 | 109582 | 10803689 | 08/08/2013 | 98.59 | 10958.2 | 230516695.2 | 04/10/2013 | 7967.2727 | 778774 | 14/11/2013 | 97.7466 | 796.7273 | 16759954.9091 | 15/01/2014 | 23661.8182 | 2423444 | 16/01/2014 | 102.42 | 2366.1818 | 49775000.7273 | 18/03/2014 | [7 empty] | 23661.8182 | 2405377 | 10/07/2014 | 101.6565 | 2366.1818 | 50271903 | 05/08/2014 | 663521 | 0 | ok | Closed | (Acceptance Minutes: 31 May 2013) => 30/11/2013 | 38403.6909 | -3535484 | Van: 0435579345; 0913300509; Fax: 0435579344 | Paid: 100% of original contract, not yet paid for Add 2
4 | JA1100594 | E&R | E&R engineering consultants joint stock company |  |  | 22/08/2011 | 22/08-31/12/2011 | Topographic survey works | 126500 | [10 empty] | 126500 | 11189540 | 88.4549 | 50600 | 3878490 | 20/10/2011 | 76.65 |  |  |  | 46000 | 3630320 | 27/06/2012 | 78.92 | 4600 | 95808800 | 20/07/2012 | 23000 | 2255840 | 12/09/2013 |  | 2300 | 48382800 | 29/11/2013 | [28 empty] | 126500 | 0 |  | Closed |  | 6900 | 1424890 | Trang: 0466524636 | Paid: 80% of original contract
|  | E&R | E&R engineering consultants joint stock company |  |  | 18/06/2012 |  | Addendum No.2 for populous resident areas |  | 2847.9 | 129347.9 | [8 empty] | 2847.9 |  | 0 | [7 empty] | 2071.2 |  | 20/07/2012 | DN Office paid directly | 207.1 | 47452391 | 20/07/2012 | 517.8182 | 50787.6073 | 12/09/2013 |  | 51.7818 | 1089282.3273 | 29/11/2013 | [28 empty] | 2847.9 | 0 |  | Closed |  | 258.8818 | -50787.6073 | DN-QN project site office paid 100% | Paid: 80% of Addendum No.2 (Project Office make a payment)
|  | E&R | E&R engineering consultants joint stock company |  |  |  |  | Addendum No.3 for Topographic survey works |  |  |  | 20436 | 149783.9 | [6 empty] | 20436 |  |  | 14862.55 | 1465245 | 18/07/2011 | 98.5864 | 1486.255 | 31264860.18 | 15/08/2013 | 3715.6364 | 364429.6145 | 12/09/2013 |  | 371.5636 | 7816212.6545 | 29/11/2013 | [35 empty] | 20436.005 | -0.005 |  | Closed |  | 1857.8136 | -1829674.6145 |  | Paid: 80% of Addendum No.3
5 | JA1100596 | TDIC | Technology development & investment consultant JSC |  |  | 22/08/2011 | 22/08-31/12/2011 | Topographic survey works | 82500 | [10 empty] | 82500 | 8077939 | 97.9144 | 33000 | 2529450 | 20/10/2011 | 76.65 |  |  |  | 30000 | 2435700 | 31/05/2012 | 81.19 | 3000 | 62445000 | 15/06/2012 | 15000 | 1478850 | 08/08/2013 | 98.59 | 1500 | 31554000 | 12/09/2013 | [28 empty] | 82500 | 0 |  | Closed |  | 4500 | 1633939 | Phuong: 05113889732-6253103 | Paid: 100% of original contract
|  | TDIC | Technology development & investment consultant JSC |  |  | 2011-01-04 | 22/08-31/12/2011 | Addendum No.2 for Topographic survey works |  |  |  | 17700 | 100200 | [6 empty] | 17700 |  | 0 | 12872.7273 | 1339793.4545 | 31/01/2013 |  | 1287.2727 | 26811316.3636 | 19/03/2013 | 3218.1818 | 316522 | 26/09/2013 | 98.3543 | 321.8182 | 6769767.2727 | 07/11/2013 | [35 empty] | 17700 | 0 |  | Closed |  | 1609.0909 | -1656315.4545 |  | Paid: 80% of Addendum No.2 (Project Office make a payment)
|  | TDIC | Technology development & investment consultant JSC |  |  |  | 22/08-31/12/2012 | Addendum No.3 for Topographic survey works | [5 empty] | 8512 | 108712 |  |  |  |  | 8512 |  |  | 6190.91 | 644539 | 27/06/2013 |  | 619.091 | 12894427.348 | 18/07/2013 | 1547.2727 | 152189 | 26/09/2013 | 98.3595 | 154.7273 | 3254842.9091 | 07/11/2013 | [35 empty] | 8512.001 | -0.001 |  | Closed |  | 773.8173 | -796728 |  | Paid: 80% of Addendum No.3
6 | JA1100593 | EGS | EGS(Vietnam) company limited |  |  | 22/08/2011 | 22/08-31/12/2011 | Topographic survey works | 59400 | [10 empty] | 59400 | 4437450 | 74.7045 | 23760 | 1955531 | 20/10/2011 | 82.3035 |  |  |  | 23760 | 1955532 | 27/12/2011 | 82.3035 | [31 empty] | 10800 | 1106460 | 02/01//2014 | 102.45 | 1080 | 22718880 | 15/01/2014 | 59400 | 0 |  | Closed |  | 1080 | -580073 | Chi Hang: 0912 908 529; 0437545208 | Paid: 80% of original contract
|  | EGS | EGS(Vietnam) company limited |  |  | 10/01/2012 |  | Addendum No.1 for Topographic survey works |  | 3300 | 62700 | [8 empty] | 3300 |  | 0 | 3000 |  | 02/02/2012 | 0 | 300 | 6248400 | 30/07/2012 | [42 empty] | 3300 | 0 |  | Closed |  | 0 | 0 |  | Paid: 100% of Addendum No.1
|  | EGS | EGS(Vietnam) company limited |  |  | 12/06/2012 |  | Addendum No.3 for Topographic survey works | [5 empty] | 22803 | 85503 |  |  |  |  | 22803 | 1781598.39 | 78.13 | 16418.16 | 1295721 | 06/07/2012 | 78.92 | 1641.816 | 34195743.648 | 30/07/2012 | [35 empty] | 4311.8636 | 441750.4295 | 02/01//2014 | 102.45 | 431.1864 | 9070379.3455 | 15/01/2014 | 22803.026 | -0.026 |  | Closed |  | 2072.9764 | 44126.9605 | Difference amount of 165.84 will be paid together with the next payment (6,584-16,4178.16) | Paid:80% of Addendum No.3
|  | EGS | EGS(Vietnam) company limited |  |  | 29/11/2012 |  | Addendum No.4 for Topographic survey works | [7 empty] | 5938.9 | 91441.9 |  |  | 5938.9 | 487702.468 | 82.12 | 4319.2 | 354676 | 25/12/2012 | 82.1161 | 431.92 | 8996029.76 | 01/02/2013 | [35 empty] | 1079.8 | 110625.51 | 02/01//2014 | 102.45 | 107.98 | 2271467.28 | 15/01/2014 | 5938.9 | 0 |  | Closed |  | 539.9 | 22400.958 |  | Paid:80% of Addendum No.4
|  | EGS | EGS(Vietnam) company limited |  |  | 11/12/2012 |  | Addendum No.5 for Topographic survey works | [9 empty] | 4268.29 | 95710.19 | 4268.29 | 139158.142 | 32.6028 | 3104.2109 |  | 18/01/2013 |  | 310.4211 | 6465450.4815 | 01/03/2013 | [35 empty] | 776.0545 | 78995.0605 | 02/01//2014 | 102.45 | 77.6055 | 1632499.3418 | 15/01/2014 | 4268.292 | -0.002 |  | Closed |  | 388.0245 | 60163.0815 |  | Paid:80% of Addendum No.5
| JA1200577 | E&R | E&R engineering consultants joint stock company |  |  | 10/09/2012 |  | Public Utility Survey Works | 23540 | [10 empty] | 23540 | 1850244 | 78.6 | 8560 | 672816 | 2012-11-10 | 78.6 | 856 | 17828768 | 30/10/2012 | 8560 | 741125 | 31/01/2013 | 86.58 | 856 | 17828768 | 20/02/2013 | 4280 | 421623 | 14/11/2013 | 98.51 | 428 | 9003408 | 29/11/2013 | [28 empty] | 23540 | 0 |  | Closed |  | 2140 | -153524 |  | Paid: 80% of original contract
II. Hydro survey | [8 empty] | 74810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74810 | 7523413 | 70.7726 | 29924 | 3155881 | 41154 | 78.13 | 0 | 0 | 0 | 28113.6364 | 3028739 | 0 | 78.92 | 1810.3636 | 37706261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14056.82 | 1089115 | 0 |  | 905.18 | 19423395 | 0 | 74810 | 0 |  |  |  | 2715.5436 | 249678 | 0 | 0
1 | JA1100754 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 2011-05-10 | 05/09-31/12/2011 | Hydrological survey works | 49785 | [10 empty] | 49785 | 3523413 | 70.7726 | 19914 | 1555881 | 22/12/2011 | 78.13 |  |  |  | 18103.6364 | 1428739 | 28/06/2012 | 78.92 | 1810.3636 | 37706261 | 20/07/2012 | [28 empty] | 9051.82 | 1089115 | 12/02/2015 | 120.32 | 905.18 | 19423395 | 2/4/2015 | 49785 | 0 | ok | Closed | Stop | 2715.5436 | -550322 |  | Paid: 80% of original contract
2 |  | DHI | DHI VietNam Company Limited | Unit 303, 30 Nguyen Du Building, Nguyen Du Steet, Hanoi, VN |  | 29/11/2011 | 29/11/2011-20/01/2012 | Inundation analysis of Quang Ngai Section | 25025 | [10 empty] | 25025 |  | 0 | 10010 |  | 2012-09-02 | 0 |  |  |  | 10010 |  | 27/04/2012 | 0 | [31 empty] | 5005 |  | 16/08/2012 |  |  |  |  | 25025 | 0 |  | Closed |  | 0 | 0 | ms.Phương kt: 0912 573 068 | DN-QN project site office paid 100% final payment in VND => untilnow, finished
3 |  | ESS | Earth system science Co., LTD |  |  | 20/11/2011 | 20/11/2011-31/01/2012 | Inundation analysis of DN - Quang Nam Section | [11 empty] | 0 | 4000000 |  |  | 1600000 | [6 empty] | 1600000 | [40 empty] | 0 | 0 |  | HO follow |  | 0 | 800000 | Contract 100% in JPY, paid 80% contract price
III. Geo survey | [8 empty] | 1582751 | 279881.89 | 1862632.89 | 231831 | 2094463.89 | 20790 | 2115253.89 | 0 | 0 | 0 | 0 | 2115253.89 | 168923425.4 | 2058.5051 | 581229.2618 | 46650710 | 82446 | 1941.8996 | 58122.9262 | 1210926487.3149 | 0 | 519598.9009 | 43332273 | 0 | 2133.4287 | 47479.7541 | 989998310.8418 | 0 | 287463.0845 | 28454059 | 0 | 1784.2936 | 28746.3085 | 603648140.6338 | 0 | 95000.14 | 9474495 | 0 | 597.2283 | 9500.014 | 199048698.792 | 0 | 144256.1364 | 14725951 | 0 | 309.1301 | 14425.6136 | 305487908.4545 | 0 | 48349.6364 | 5286550 | 0 | 109.34 | 4834.9636 | 102723637.4182 | 0 | 53901.82 | 5676402 | 42128 |  | 5390.185 | 106255317 | 0 | 1898298.745 | 216954.645 |  |  |  | 89254.5464 | 4164288.5455 | 10681856 | 0
1 | JA1200309 | E&R | E&R engineering consultants joint stock company |  |  | 18/06/2012 | 15/08/2012 | Engineering Geological Survey works ( Package 1, Hoa Vang section, Km0+000-km8+000) | 186528 |  |  | 206392 | 392920 | [6 empty] | 392920 | 34364455 | 96.2051 | 67113.08 | 5299484 | 19/07/2012 | 78.9635 | 6711.308 | 139783123.024 | 06/09/2012 | 33914.18 | 2701604 | 22/11/2012 | 79.66 | 3391.418 | 70636454.104 | 19/12/2012 | 34629.46 | 3503809 | 11/07/2013 | 101.18 | 3462.946 | 72846532.056 | 15/08/2013 | 28144 | 2882508 | 26/12/2013 | 102.42 | 2814.4 | 59203718.4 | 15/01/2014 | 96700 | 9830522 | 19/06/2014 | 101.66 | 9670 | 205448820 | 21/07/2014 | 48349.6364 | 5286550 | 11/12/2014 | 109.34 | 4834.9636 | 102723637.4182 | 31/12/2014 | [7 empty] | 339735.392 | 53184.608 | TT lần cuối: USD 106369,2 | 25% of additional work | stop (Acceptance Minutes: 24 July 2013) => 23/01/2014 | -73972.72 | 4859978 |  | Paid 80% of the original , NY made the 4th & 5th paymnent
2 | JA1201065 | PHUHA | Phuha Building and Investment Consultancy JSC |  |  | 20/02/2013 |  | Engineering Geological Survey works (Pakage 1, Alignment Shifted Section, Km0+500-km2+680) | 53460 | 13200 | 66660 | [8 empty] | 66660 | 6375949.8 | 119.2658 | 19440 | 1798394 | 21/03/2012 | 92.51 | 1944 | 40489632 | 22/04/2013 | 19440 | 1966939 | 11/07/2013 | 101.18 | 1944 | 40893984 | 07/08/2013 | 4320 | 422280 | 14/11/2013 | 97.75 | 432 | 9087552 | 24/12/2013 | 8700 | 850425 | 14/11/2013 | 97.75 | 870 | 18301320 | 24/12/2013 | [14 empty] | 8700 | 913935 | 23/01/2014 | 105.05 | 870 | 18301320 | 24/02/2014 | 66660 | 0 |  | Closed |  | -7140 | -155655 |  | Paid 80% of the original , NY made the 3rd, 4th & 5th paymnent
3 | JA1201071 | VRC | Vietroads design consultant and verification quality construction JSC |  |  | 05/02/2013 |  | Engineering Geological Survey works ( Package 1, Tuy Loan Interchange) | 56650 | -12080 | 44570 | [8 empty] | 44570 | 5240691.5 | 92.51 | 20600 | 1905706 | 21/03/2013 | 92.51 | 2060 | 42905680 | 25/03/2013 | 11815 | 1164841 | 08/08/2013 | 98.59 | 1181 | 24853078 | 09/09/2013 | 8103.6364 | 871344 | 31/10/2013 | 107.5251 | 810.3636 | 17046809.4545 | 29/11/2013 | [28 empty] | 44570 | 0 |  | Closed |  | 4051.3636 | 822374 |  | Paid 80% of the actual quantity
4 | JA1200432 | E&R | E&R engineering consultants joint stock company |  |  | 16/07/2012 | 16/07-30/09/2012 | Engineering Geological Survey works ( Package 2, Earthwork Section Km8+000-Km16+880) | 87998 | 100794 | 188792 | [8 empty] | 188792 | 18912947.9 | 100.1788 | 31999.2727 | 2501383 | 17/08/2012 | 78.17 | 3199.9273 | 66648085.2364 | 06/09/2012 | 31999.2727 | 2549062 | 13/12/2012 | 79.66 | 3199.9273 | 66648085.2364 | 17/01/2013 | 31323.27 | 3067175 | 23/05/2013 | 97.92 | 3132.327 | 65240106.756 | 14/06/2013 | 38153.64 | 3735942 | 06/06/2013 | 97.9184 | 3815.364 | 79466401.392 | 14/06/2013 | 38153.6364 | 3907696 | 26/12/2013 | 102.42 | 3815.3636 | 80259989.4545 | 15/01/2014 | [14 empty] | 188792.001 | -0.001 |  | Closed | (Acceptance Minutes: 24 February 2013) => 23/07/2013 | 17162.9082 | 1432331 |  | Paid 100% of original scope, NY paid for final payment of additional scope
5 | JA1200559 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 31/08/2012 |  | Engineering Geological Survey works ( Package 2, Bridge section, Km8+000-Km16+880) | 93500 | 101200 | 194700 | [8 empty] | 194700 | 7349100 | 78.6 | 34000 | 2708440 | 13/12/2012 | 79.66 | 3400 | 70815200 | 21/01/2013 | 34000 | 3329280 | 06/06/2013 | 97.92 | 3400 | 70815200 | 18/07/2013 | 18000 | 1834920 | 03/04/2014 | 101.94 | 1800 | 37864800 | 09/05/2014 | [28 empty] | 94600 | 100100 | ok | 100% of additional work (USD 100,100.00) | Stop | 108700 | -1191640 |  | Paid 80% of the original. NY pay for supplymental works, additional works
6 | JA1200139 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 15/02/2012 | 01/03-31/05 | Engineering Geological Survey works (Package 3A, Ky Lam Bridge section ) | 80196 | 11191 | 91387 | 3771 | 95158 | [6 empty] | 95158 | 7510528.3 | 93.6522 | 29161.8182 | 2604413 | 31/05/2012 | 89.309 | 2916.1818 | 60738239 | 15/06/2012 | 29162.1818 | 2262971 | 08/11/2012 | 77.5995 | 2916.2182 | 60738992.2909 | 19/12/2012 | 12968.18 | 1321958 | 03/04/2014 | 101.9386 | 1296.818 | 27279863.448 | 09/05/2014 | [28 empty] | 78421.398 | 16736.602 | TT lan 4:8368 TT lan cuoi:8368.60 | 100% of additional work (USD 16,736.) | Stop | 23865.82 | 638411 |  | Paid 80% of the original.
7 | JA1200558 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 31/08/2012 |  | Engineering Geological Survey works ( Package 3B, Km18+100-Km21+500) | 71500 | 0 | 71500 | [8 empty] | 71500 | 5619900 | 78.6 | 26000 | 2135120 | 27/12/2012 | 82.12 | 2600 | 54152800 | 20/02/2013 | 26000 | 2445300 | 02/05/2013 | 94.05 | 2600 | 54152800 | 25/06/2013 | [28 empty] | 13000 | 1564160 | 12/02/2015 | 120.32 | 1300 | 27895400 | 2/4/2015 | 71500 | 0 | ok | Closed | Stop | 6500 | -1035580 |  | Paid 80% of the original.
8 | JA1200476 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 2012-01-08 |  | Engineering Geological Survey works ( Package 3B, Chiem Sơn Bridge section, Km19+975.2 -Km20+430.1 ) | 31011 | -3669 | 27342 | [8 empty] | 27342 | 2459497.7 | 79.3105 | 11276.7273 | 886351 | 27/09/2012 | 78.6 | 1127.6727 | 23487167.5636 | 29/11/2012 | 11276.36 | 1027761 | 14/03/2013 | 91.143 | 1127.636 | 23486402.608 | 22/04/2013 | [28 empty] | 2303.27 | 277129 | 12/02/2015 | 120.3198 | 230.33 | 4942357 | 2/4/2015 | 27341.996 | 0.004 | ok | final payment of original scope | Stop | 2485.6427 | 44666 |  | Paid 80% of the original.
9 | JA1200629 | ATH | Construction Investment Consultant ATH.,JSC |  |  | 17/09/2012 |  | Engineering Geological Survey works ( Package 4, Section 1, Km21+500-Km26+800) | 33314 | -4067 | 29247 | [8 empty] | 29247 | 2618526.9 | 78.6014 | 12114.1818 | 952175 | 18/10/2012 | 78.6 | 1211.4182 | 25231417.8909 | 19/12/2012 | 12114.18 | 1186211 | 06/06/2013 | 97.9192 | 1211.418 | 25231414.104 | 10/07/2013 | 2359.8182 | 230672 | 14/11/2013 | 97.7499 | 235.9818 | 4964113.5273 | 05/12/2013 | [28 empty] | 29246.998 | 0.002 |  | Closed |  | 2658.82 | 11421 |  | Paid 80% of the original.
10 | JA1200430 | FMC | Fukken & Minami Consultant Co., LTD |  |  | 16/07/2012 |  | Engineering Geological Survey works ( Tunnel Section, Km22+485-km23+037) | 92950 | -550 | 92400 | [8 empty] | 92400 | 7371864 | 79.31 | 33800 | 2642146 | 30/08/2012 | 78.17 | 3380 | 70398640 | 05/10/2012 | 33800 | 2926404 | 18/02/2013 | 86.58 | 3380 | 70398640 | 12/03/2013 | 16400 | 1613104 | 03/10/2013 | 98.36 | 1640 | 34499040 | 07/11/2013 | [28 empty] | 92400 | 0 |  | Closed |  | 8400 | -479959.4545 | Ms.Trúc, KTT, 0854.045343 | Paid 80% of the original.
11 | JA1200630 | ATH | Construction Investment Consultant ATH.,JSC |  |  | 17/09/2012 |  | Engineering Geological Survey works ( Package 4, Section 2, Km26+800-Km32+600) | 24691 | 18712.8 | 43403.8 | [8 empty] | 43403.8 | 3968417.2 | 160.7232 | 8978.5455 | 705671 | 18/10/2012 | 78.5952 | 897.8545 | 18700514.4727 | 19/12/2012 | 8978.55 | 908450 | 27/06/2013 | 101.18 | 897.855 | 18700523.94 | 10/07/2013 | 2695.9091 | 263525 | 14/11/2013 | 97.75 | 269.5909 | 5671114.3636 | 05/12/2013 | 9402.5 | 963004 | 19/12/2013 | 102.42 | 940.25 | 19779099 | 15/01/2014 | 9402.5 | 987733 | 23/01/2014 | 105.05 | 940.25 | 19779099 | 24/02/2014 | [14 empty] | 43403.805 | -0.005 |  | Closed |  | 3945.7955 | -220731 |  | Paid 80% of the original.
12 | JA1200518 | TC | Thanh Cong Construction Consultant JSC |  |  | 23/08/2012 |  | Engineering Geological Survey works ( Package 5, Km032+600-Km042+000) | 66217 | -7916.76 | 58300.24 | [8 empty] | 58300.24 | 5251646.4 | 79.3096 | 24078.9091 | 1868523 | 25/10/2012 | 77.6 | 2407.8909 | 50151551.8545 | 08/11/2012 | 24078.91 | 2227540 | 11/04/2013 | 92.51 | 2407.891 | 50151553.748 | 24/05/2013 | 4842.4 | 495959 | 19/12/2013 | 102.4201 | 484.24 | 10186472.64 | 15/01/2014 | [28 empty] | 58300.241 | -0.001 |  | Closed |  | 5300.0209 | 182202 |  | Paid 80% of the original.
13 | JA1200493 | TEDIS | Transport engineering design joint stock inc.South |  |  | 13/08/2012 |  | Engineering Geological Survey works ( Package 6, Km 42+000-km52+000) | 52429 | -1444.22 | 50984.78 | [8 empty] | 50984.78 | 4158167.2 | 79.3104 | 19064.5455 | 1498509 | 2012-11-10 | 78.6019 | 1906.4545 | 39708582 | 30/10/2012 | 19064.5455 | 1763662 | 21/03/2013 | 92.51 | 1906.4545 | 39707635 | 25/04/2013 | 8220.7091 | 808589 | 26/09/2013 | 98.36 | 822.0709 | 17293083.6436 | 07/11/2013 | [28 empty] | 50984.78 | 0 |  | Closed |  | 4634.98 | -290608 |  | Paid 80% of the original.
14 | JA1200517 | TC | Thanh Cong Construction Consultant JSC |  |  | 23/08/2012 |  | Engineering Geological Survey works ( Package 7, Km052+000-Km065+000) | 58702 | 5098.4 | 63800.4 | [8 empty] | 63800.4 | 4655615.8 | 79.3093 | 21346.1818 | 1656464 | 25/10/2012 | 77.6 | 2134.6182 | 44459827.4909 | 08/11/2012 | 21346.1818 | 1974735 | 11/04/2013 | 92.51 | 2134.6182 | 44459827.4909 | 25/04/2013 | 15308 | 1567845 | 19/12/2013 | 102.42 | 1530.8 | 32201908.8 | 15/01/2014 | [28 empty] | 63800.4 | 0 |  | Closed |  | 5800.0364 | -966666 |  | Paid 80% of the original.
15 | JA1200556 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 27/08/2012 |  | Engineering Geological Survey works ( Package A1, Km65+000-Km081+150) | 99000 | -3300 | 95700 | [8 empty] | 95700 | 7781400 | 78.6 | 36000 | 2793600 | 25/10/2012 | 77.6 | 3600 | 74980800 | 29/11/2012 | 36000 | 3642480 | 4/07/2013 | 101.18 | 3600 | 74980800 | 18/07/2013 | [28 empty] | 15000 | 1804800 | 12/02/2015 | 120.32 | 1500 | 32187000 | 02/04/2015 | 95700 | 0 | ok | final payment of original scope | Stop | 8700 | -1166880 |  | Paid 80% of the original.
16 | JA1200491 | TEDIS | Transport engineering design joint stock inc.South |  |  | 13/08/2012 |  | Engineering Geological Survey works ( Package A2, Section 1) | 37706 | 8583.87 | 46289.87 | [8 empty] | 46289.87 | 2990446.8 | 79.3096 | 13710.9091 | 1077685 | 2012-11-10 | 78.6006 | 1371.0909 | 28557271 | 30/10/2012 | 13710.9091 | 1351787 | 08/08/2013 | 98.5921 | 1371.0909 | 28842268.3636 | 22/08/2013 | 14659.8818 | 1441946 | 26/09/2013 | 98.36 | 1465.9882 | 30838527.3927 | 07/11/2013 | [28 empty] | 46289.87 | 0 |  | Closed |  | 4208.17 | -1152830 |  | Paid 80% of the original.
17 | JA1200492 | PHUHA | Phuha Building and Investment Consultancy JSC |  |  | 15/08/2012 |  | Engineering Geological Survey works ( Package A2, Section 2) | 77000 |  |  | 25300 | 102300 | [6 empty] | 102300 | 11813305 | 115.4771 | 28000 | 2188760 | 06/09/2012 | 78.17 | 2800 | 58318400 | 05/10/2012 | 28000 | 2590280 | 28/3/2013 | 92.51 | 2800 | 58318400 | 22/04/2013 | 21000 | 2059680 | 12/08/2013 | 98.08 | 2100 | 44175600 | 12/09/2013 | 8000 | 786880 | 03/10/2013 | 98.36 | 800 | 16828800 | 29/11/2013 | [14 empty] | 8000 | 819360 | 19/12/2013 | 102.42 | 800 | 16828800 | 15/01/2014 | 102300 | 0 |  | Closed |  | 9300 | 3368345 | 7625600 | paid 100% of the original scopy, NY paid for additional scope
| JA1200492 | PHUHA | Phuha Building and Investment Consultancy JSC |  |  | 25/10/2012 |  | Addendum1 for Engineering Geological Survey works (the location of O&M building Area) |  | 17600 | 17600 |  |  | 20790 | 38390 |  |  |  |  | 38390 |  | 0 | 6400 | 525568 | 24/01/2013 | 82.12 | 640 | 13329920 | 01/02/2013 | 6400 | 647552 | 27/06/2013 | 101.18 | 640 | 13329920 | 10/07/2013 | 19200 | 1883136 | 12/09/2013 | 98.08 | 1920 | 40389120 | 08/10/2013 | [21 empty] | 2900 | 297018 | 02/01/2014 | 102.42 | 290 | 6100440 | 24/02/2014 | 38390 | 0 |  | Closed |  | -17300 | -3353274 | 3056256 | Paid 80% of the Add no.1 , NY made the 3rd, final paymnent
18 | JA1200565 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 27/08/2012 |  | Engineering Geological Survey works ( Package A3, Km99+500-Km110+100) | 66000 | 61600 | 127600 | [8 empty] | 127600 | 5187600 | 78.6 | 24000 | 1862400 | 25/10/2012 | 77.6 | 2400 | 49987200 | 29/11/2012 | 24000 | 2350080 | 06/06/2013 | 97.92 | 2400 | 49987200 | 18/07/2013 | 33000 | 3364020 | 03/04/2014 | 101.94 | 3300 | 69418800 | 09/05/2014 | [28 empty] | 89100 | 38500 | ok | 100% of additional work (USD 38,500) | Stop | 46600 | -2860500 |  | Paid 80% of the original , NY made the 3rd, 4th & 5th paymnent
19 | JA1200475 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 2012-01-08 |  | Engineering Geological Survey works (Package A3, Tra bong Bridge section, Km 108+775.25-km109+230.25 ) | 34759 | 9329 | 44088 | 15068 | 59156 | [6 empty] | 59156 | 2756727.6 | 79.3097 | 12639.6364 | 993476 | 27/09/2012 | 78.6 | 1263.9636 | 26325834.6182 | 29/11/2012 | 12640 | 1151977 | 14/03/2013 | 91.1374 | 1264 | 26326592 | 22/04/2013 | 20831.82 | 2142761 | 06/03/2013 | 102.86 | 2083.182 | 43821816.552 | 17/04/2014 | [28 empty] | 50722.602 | 8433.398 | TT lan 4:4217 TT lan cuoi:4216.4 | 100% of additional work (USD 8,434) | Stop | -2023.4564 | -1782098 |  | Paid 80% of the original.
20 | JA1200221 | TDIC | Technology development & investment consultant JSC |  |  | 24/05/2012 | 31/07/2012 | Engineering Geological Survey works (Package A4, Binh Son-Son Tinh, Km110+100-km124+700) | 107800 |  |  | -18700 | 89100 | [6 empty] | 89100 | 8752282 | 81.19 | 39200 | 3093664 | 14/06/2012 | 78.92 | 3920 | 81986800 | 20/07/2012 | 19600 | 1532132 | 23/08/2012 | 78.17 | 1960 | 40856200 | 05/10/2012 | 19600 | 1561336 | 13/12/2012 | 79.66 | 1960 | 40822880 | 17/01/2013 | 2600 | 255736 | 26/09/2013 | 98.36 | 260 | 5469360 | 07/11/2013 | [21 empty] | 89100 | 0 |  | Closed |  | -81000 | 1513752 |  | Paid: 80% of original contract
21 | JA1200431 | TK | Thien Khai Joint Stock Company |  |  | 16/07/2012 | 20/7-15/09/2012 | Engineering Geological Survey works ( Package A5, Km124+700-Km139+204 excluding Tra Khuc bridge section) | 123191 | -29118.2 | 94072.8 | [8 empty] | 94072.8 | 9770277 | 79.31 | 44796.7273 | 3501731 | 24/08/2012 | 78.1693 | 4479.6727 | 93302624 | 05/10/2012 | 44796.36 |  | 31/01/2013 |  |  |  | Can not pay b/c over payment | [35 empty] | 94072.76 | 0.04 |  | Closed |  | 4479.7127 | 5380339 | Mr.Viet Anh, tel: 0435380681 . Email: nvatkc@gmail.com | Paid: 80% of original contract, but over pyment, So revised contract amount should be same as 80% of the original.
22 | JA1200477 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 2012-01-08 |  | Engineering Geological Survey works (Package A5, Tra Khuc Bridge section, Km124+979.4-km125+728.2 ) | 33349 | -2271 | 31078 | [8 empty] | 31078 | 2644885.1 | 79.3093 | 12126.9091 | 953175 | 27/09/2012 | 78.6 | 1212.6909 | 25257926.2545 | 29/11/2012 | 12127.27 | 1105247 | 14/03/2013 | 91.1373 | 1212.727 | 25258677.956 | 22/04/2013 | [28 empty] | 3998.55 |  | 42128 |  | 399.855 |  | Maybe in Dec 2015 | 31078.002 | -0.002 | OK | final payment of original scope | Stop | 2825.2709 | 346019 |  | Paid: 80% of original contract
23 | JA1201064 | VRC | Vietroads design consultant and verification quality construction JSC |  |  | 01/03/2013 |  | Engineering Geological Survey works (other Interchange) | 14800 | -3011 | 11789 | [8 empty] | 11789 | 1369194.2 | 92.5131 | 5381.8182 | 497872 | 11/04/2013 | 92.51 | 538.1818 | 11209250.9091 | 22/04/2013 | 5335 | 525978 | 08/08/2013 | 98.5901 | 533.5 | 11223662 | 09/09/2013 | [35 empty] | 11788.5 | 1.819e-12 |  | Closed |  | 1072.1818 | 220872 |  | Paid 100% of the original.
[72 empty] | 0 | 0 |  |  |  | 0 | 0
VI.Other works | [8 empty] | 876612 | 32780 | 568040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 909392 | 32473279.8 | 408.6359 | 253333.3636 | 13784872 | 41132 | 423.5287 | 16533.3364 | 203597068.1636 | 0 | 206957.1773 | 12620290 | 0 | 509.1648 | 20695.7177 | 267560964.5856 | 0 | 189229.4545 | 9274467 | 0 | 410.0302 | 18922.9455 | 188316906.9091 | 0 | 60000 | 2057000 | 0 | 102.85 | 6000 | 42492000 | 0 | 60000 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41600 | 4229056 | 0 |  | 4160 | 88383360 | 0 | 883431.995 | 25960.005 |  | 0 |  | 25409.0945 | -6544170.0909 | 0 | 0
1 | JA1101012 | RCS | Joint venture of independent valuaion consultance Co of DN-Qnam-Qngai |  |  | 30/01/2012 | 30/01-31/07/2012 | Independent replacement cost survey (RCS) | 220000 | [10 empty] | 220000 | 16136000 | 73.3455 | 88000 | 7144720 | 17/05/2012 | 81.19 |  |  |  | 40000 | 3943600 | '08/08/2013 | 98.59 | 4000 | 84144000 | 09/09/2013 | 60000 | 6303000 | 23/01/2014 | 105.05 | 6000 | 126216000 | 24/02/2014 | 20000 | 2057000 | 14/08/2014 | 102.85 | 2000 | 42492000 | 28/08/2014 | [21 empty] | 220000 | 0 | ok | Closed |  | 12000 | -3312320 | Ms.lang: 0905121416 | Paid 60% of the original contract
2 | JA1200311 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 2012-01-06 | 10/6-31/7/2012 | Land acquisition & Row staking works | 95260 | 31020 | 126280 | [8 empty] | 126280 | 7517919 | 78.92 | 34640 | 2688064 | 2012-08-11 | 77.6 | 3464 | 72148192 | 19/12/2012 | 34640 | 3638932 | 23/01/2014 | 105.05 | 3464 | 72868704 | 18/03/2013 | 21920 | 2228387 | 10/07/2014 | 101.66 | 2192 | 46571232 | 05/08/2014 | [28 empty] | 100320 | 25960 |  | 100% off additional works |  | 35080 | -1720911.1818 |  | Paid 40% of the original contract
3 |  | VRC | Vietroads design consultant and verification quality construction JSC |  |  | 15/05/2012 | 30/06/2012 | Baseline traffic survey Works | 5758 | [10 empty] | 5758 |  | 0 | 2093.8182 |  |  | 0 | 209.3818 | 4361004.5091 | 20/07/2012 | 3140.7273 |  |  | 0 | 314.0727 | 6541506.7636 | 01/02/2013 | [35 empty] | 5758 | 0 |  | Closed |  | -5234.5455 | 0 | DN-QN project site office paid 100% | Finish
4 | JA1200513 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 15/08/2012 |  | Material Survey Works | 17204 | [10 empty] | 17204 | 1364448.8 | 79.31 | 6256 | 548220 | 15/11/2012 | 87.6311 | 625.6 | 13029996.8 | 19/12/2012 | 6256.36 | 570172 | 14/03/2013 | 91.1348 | 625.636 | 13030746.608 | 22/04/2013 | 3127.6364 | 317956 | 03/07/2014 | 101.6602 | 312.7636 | 6644984 | 05/08/2014 | [28 empty] | 17203.996 | 0.004 | ok | Closed |  | -15639.9964 | -195940
5 |  | TV | Hydrographic - Geology Construction Investigation Consultancy JSC |  |  | 24/06/2013 |  | Material Survey Works for ATB | 3176 | [10 empty] | 3176 |  | 0 | 1154.9091 |  |  | 0 | 115.4909 | 26724134.4 | 05/07/2013 | 1732.3636 |  |  |  | 173.2364 | 3644200.1455 | 07/11/2013 | [35 empty] | 3176 | 0 |  | Closed |  | -2887.2727 | 0 | DN-QN project site office paid 100%. Pay in VNĐ. TT đợt cuối, Cty Thủy văn phải xuất Hóa Đơn trước | Paid 40% of the original contract
| JA1200478 | TEDI | Transport Engineering Design Inc. ( TEDI) |  |  | 2012-01-06 |  | Purchase Contract for land acquisition and ROW stakes | 72214 | [10 empty] | 72214 | 5206662 | 79.3105 | 32825 | 2579966 | 11/10/2012 | 78.5976 | 3282.5 | 69739995 | 30/09/2014 | 32824.09 | 3588986 | 04/12/2014 | 109.34 | 3282.409 | 69738061.614 | 31/12/2014 | [35 empty] | 72213.999 | 0.001 |  | Closed |  |  | -1435622.9091
| JA1200922 | TL | Thang Loi Engineering Consultant Co.,Ltd |  |  | 2012-01-08 |  | Detailed Engineering Design | 440000 | 1760 | 441760 | [8 empty] | 441760 |  |  | 80000 |  |  |  | 8000 |  |  | 80000 |  |  |  | 8000 |  |  | 100000 |  |  |  | 10000 |  |  | 40000 |  |  |  | 4000 |  |  | 60000 |  |  |  | 6000 | [9 empty] | 41600 | 4229056 | 10/07/2014 | 101.66 | 4160 | 88383360 | 05/08/2014 | 441760 | 0 | ok | Closed
6 | JA1400350 | VRC | Vietroads design consultant and verification quality construction JSC |  |  | 24/10/2013 |  | Land acquisition & Row staking works (for ROW reports No.16&No.17) | 23000 | [10 empty] | 23000 | 2248250 | 97.75 | 8363.6364 | 823902 | 14/11/2013 | 98.51 | 836.3636 | 17593745.4545 | 30/12/2013 | 8363.6364 | 878600 | 23/01/2014 | 105.05 | 836.3636 | 17593745.4545 | 24/02/2014 | 4181.8182 | 425124 | 19/06/2014 | 101.6601 | 418.1818 | 8884690.9091 | 21/07/2014 | [28 empty] | 23000 | 0 | ok | Closed |  | 2090.9091 | 120624
[72 empty] | 0 | 0 |  |  |  | 0 | 0
Total Amount in USD | [8 empty] | 3636358 | 318809.79 | 3539005.79 | 333537 | 3304502.79 | 54855 | 3359357.79 | 5938.9 | 1250042.8 | 4268.29 | 1254311.09 | 4353766.98 | 301237285.9 | 3301.926 | 1365272.3836 | 102569836.4545 | 205955 | 3247.3343 | 81589.0384 | 1559228551.2596 | 0 | 1172176.5555 | 92289237.6145 | 0 | 3487.2508 | 104960.4995 | 2066994159.4638 | 0 | 671807.63 | 56946835.6073 | 0 | 2686.9638 | 67180.763 | 1202409147.0702 | 0 | 162967.4127 | 12310269 | 0 | 797.825 | 16296.7413 | 258300653.7011 | 0 | 227917.9545 | 17149395 | 0 | 411.5501 | 22791.7955 | 355262909.1818 | 0 | 48349.6364 | 5286550 | 0 | 109.34 | 4834.9636 | 102723637.4182 | 0 | 150188.1764 | 15137781 | 42128 |  | 14518.3186 | 300027200.9673 | 0 | 4110851.869 | 242914.611 |  |  |  | -211324.3227 | -9631193.2218 | 10681856 | 0
|  |  | Check |  |  |  |  | Total | [10 empty] | 4353766.98 | [49 empty] | Check |  |  | 242915.111 | 242915.111
II. Summary for Sub-Contract by Sub-Consultant
STT |  | Code | Sub-contract | Address | Tax code | Date of signing | Time of commencemant and completion | Detail | price | [12 empty] | Exchange rate | Payment status | [48 empty] | Total of payment | Remaining Amount in USD (Not yet paid) |  | Detailed of remaining amount | Dealine of payment | Remaining Amount in USD ( HO) | Remaining Amount in JPY (HO) | Contact person | Remark
[9 empty] | Contract price | Add No.1/adjusted |  | Add No.2 |  | Add No.3 |  | Add No.4 |  | Add No.5 |  | Total of Contract & Add | equivalent in JPY |  | The first payment (40%) | [6 empty] | The second payment | [6 empty] | The third payment | [6 empty] | The fourth payment | [6 empty] | The fifth payment | [13 empty] | The final payment (20%)
[10 empty] | Dif | Total | Dif | Total | Dif | Total | Dif | Total | Dif | Total |  |  |  | in USD (Inc VAT) | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | [7 empty] | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site
1 |  | TL | Thang Loi engineering consultants Co., Ltd | [5 empty] | 1811809 | 206860 | 1251435 | 79659 | 817835 | 0 | 0 | 0 | 0 | 0 | 0 | 2098328 | 109269959.5 | 1026.4791 | 606113.0909 | 41198652 |  | 1038.7502 | 30610.1091 | 470923356.2364 |  | 578840.3582 | 43048697 |  | 1175.032 | 57884.0358 | 1039705217.6629 |  | 337164.9091 | 23762211 |  | 809.1787 | 33716.4909 | 499426105.2 |  | 47967.2727 | 778774 |  | 97.7466 | 4796.7273 | 16759954.9091 |  | 83661.8182 | 2423444 |  | 102.42 | 8366.1818 | 49775000.7273 | [8 empty] | 108615.4582 | 11369637 |  | 684.5963 | 10861.5468 | 223103415 |  | 1908597.999 | 189730.001 |  |  | stop all payment to Thang Loi until this additional work will be settled.
2 |  | E&R | E&R engineering consultants joint stock company | [5 empty] | 424566 | 103641.9 | 318139.9 | 226828 | 542703.9 | 0 | 0 | 0 | 0 | 0 | 0 | 755035.9 | 66317186.9 | 363.4387 | 173134.9027 | 13817418 |  | 410.9699 | 12253.4903 | 255524836.4404 |  | 126260.2891 | 9986540.6145 |  | #VALUE! | 12626.0089 | 306190710.9949 |  | 93750.5482 | 9299234.6073 |  | 297.6101 | 9375.0548 | 196562129.1393 |  | 66297.64 | 6618450 |  | 200.3383 | 6629.764 | 138670119.792 |  | 134853.6364 | 13738218 |  | 204.08 | 13485.3636 | 285708809.4545 | [8 empty] | 0 | 0 |  | 0 | 0 | 0 |  | 701851.298 | 53184.602 |  |  | stop all payment to E&R until this additional work will be settled.
3 |  | ATH | [6 empty] | 58005 | 14645.8 | 72650.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72650.8 | 6586944.1 | 239.3246 | 21092.7273 | 1657846 |  | 157.1953 | 2109.2727 | 43931932.3636 |  | 21092.73 | 2094661 |  | 199.0992 | 2109.273 | 43931938.044 |  | 5055.7273 | 494197 |  | 195.4999 | 505.5727 | 10635227.8909 |  | 9402.5 | 963004 |  | 102.42 | 940.25 | 19779099 |  | 9402.5 | 987733 |  | 105.05 | 940.25 | 19779099 | [8 empty] | 0 | 0 |  | 0 | 0 | 0 |  | 72650.803 | -0.003 |  | Closed
4 |  | DHI | [6 empty] | 25025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25025 | 0 | 0 | 10010 | 0 |  | 0 | 0 | 0 |  | 10010 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | [8 empty] | 5005 | 0 |  | 0 | 0 | 0 |  | 25025 | 0 |  | Closed
5 |  | EGS | [6 empty] | 59400 | 3300 | 62700 | 0 | 0 | 22803 | 85503 | 5938.9 | 91441.9 | 4268.29 | 95710.19 | 95710.19 | 6845909 | 267.5573 | 50601.5709 | 3605928 |  | 243.3396 | 2684.1571 | 55905623.8895 |  | 23760 | 1955532 |  | 82.3035 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | [8 empty] | 16967.7182 | 1737831 |  | 409.8 | 1696.7718 | 35693225.9673 |  | 95710.218 | -0.028 |  | Closed
6 |  | FMC | [6 empty] | 92950 | -550 | 92400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92400 | 7371864 | 79.31 | 33800 | 2642146 |  | 78.17 | 3380 | 70398640 |  | 33800 | 2926404 |  | 86.58 | 3380 | 70398640 |  | 16400 | 1613104 |  | 98.36 | 1640 | 34499040 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | [8 empty] | 0 | 0 |  | 0 | 0 | 0 |  | 92400 | 0 |  | Closed
7 |  | RCS | Joint venture of independent valuation consultance Co of DN-Qnam-Qngai | [5 empty] | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000 | 16136000 | 73.3455 | 88000 | 7144720 |  | 81.19 | 0 | 0 |  | 40000 | 3943600 |  | 98.59 | 4000 | 84144000 |  | 60000 | 6303000 |  | 105.05 | 6000 | 126216000 |  | 20000 | 2057000 |  | 102.85 | 2000 | 42492000 |  | 0 | 0 |  | 0 | 0 | 0 | [8 empty] | 0 | 0 |  | 0 | 0 | 0 |  | 220000 | 0 |  | Closed | NY completed
8 |  | PHUHA | [6 empty] | 130460 | 30800 | 84260 | 25300 | 102300 | 20790 | 38390 | 0 | 0 | 0 | 0 | 207350 | 18189254.8 | 234.7429 | 53840 | 4512722 |  | 252.8 | 5384 | 112137952 |  | 53840 | 5204771 |  | 294.87 | 5384 | 112542304 |  | 44520 | 4365096 |  | 293.91 | 4452 | 93652272 |  | 16700 | 1637305 |  | 196.11 | 1670 | 35130120 |  | 0 | 0 |  | 0 | 0 | 0 | [8 empty] | 19600 | 2030313 |  | 309.89 | 1960 | 41230560 |  | 207350 | 0 |  | Closed
9 |  | TC | [6 empty] | 124919 | -2818.36 | 122100.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122100.64 | 9907262.2 | 158.619 | 45425.0909 | 3524987 |  | 155.2 | 4542.5091 | 94611379.3455 |  | 45425.0918 | 4202275 |  | 185.02 | 4542.5092 | 94611381.2389 |  | 20150.4 | 2063804 |  | 204.8401 | 2015.04 | 42388381.44 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | [8 empty] | 0 | 0 |  | 0 | 0 | 0 |  | 122100.641 | -0.001 |  | Closed
10 |  | TDIC | [6 empty] | 190300 | 0 | 0 | -1000 | 189300 | 8512 | 108712 | 0 | 0 | 0 | 0 | 197812 | 16830221 | 179.1044 | 91263.6373 | 7607446.4545 |  | 155.57 | 5826.3637 | 121692543.7116 |  | 54365.4545 | 4436543 |  | 356.0738 | 5436.5455 | 113325810.1818 |  | 34600 | 3040186 |  | 178.25 | 3460 | 72376880 |  | 2600 | 255736 |  | 98.36 | 260 | 5469360 |  | 0 | 0 |  | 0 | 0 | 0 | [8 empty] | 0 | 0 |  | 0 | 0 | 0 |  | 197812.001 | -0.001 |  | Closed
11 |  | TEDI | Transport Engineering Design Inc. ( TEDI) | [5 empty] | 72214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72214 | 5206662 | 79.3105 | 32825 | 2579966 |  | 78.5976 | 3282.5 | 69739995 |  | 32824.09 | 3588986 |  | 109.34 | 3282.409 | 69738061.614 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | [8 empty] | 0 | 0 |  | 0 | 0 | 0 |  | 72213.999 | 0.001 |  | Closed | NY completed
12 |  | TEDIS | [6 empty] | 200135 | 7139.65 | 97274.65 | 2750 | 112750 | 2750 | 115500 | 0 | 0 | 0 | 0 | 212774.65 | 15947609.7 | 238.6109 | 76775.4545 | 5948794 |  | 233.8524 | 3277.5455 | 68265853 |  | 76775.4545 | 6731809 |  | 273.2921 | 3277.5455 | 68549903.3636 |  | 47880.5909 | 4709535 |  | 295.08 | 4788.0591 | 100721611.0364 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | [8 empty] | 0 | 0 |  | 0 | 0 | 0 |  | 212774.65 | 0 |  | Closed
13 |  | TK | [6 empty] | 123191 | -29118.2 | 94072.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94072.8 | 9770277 | 79.31 | 44796.7273 | 3501731 |  | 78.1693 | 4479.6727 | 93302624 |  | 44796.36 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | [8 empty] | 0 | 0 |  | 0 | 0 | 0 |  | 94072.76 | 0.04 |  | Closed
14 |  | TV | [6 empty] | 3176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3176 | 0 | 0 | 1154.9091 | 0 |  | 0 | 115.4909 | 26724134.4 |  | 1732.3636 | 0 |  | 0 | 173.2364 | 3644200.1455 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | [8 empty] | 0 | 0 |  | 0 | 0 | 0 |  | 3176 | 0 |  | Closed
15 |  | VRC | Vietroads design consultant and verification quality construction JSC | [5 empty] | 100208 | -15091 | 56359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85117 | 8858135.7 | 282.7731 | 36439.2727 | 3227480 |  | 283.53 | 3643.9273 | 76069680.8727 |  | 28654.3636 | 2569419 |  | 302.2301 | 2864.9364 | 60211992.2182 |  | 12285.4545 | 1296468 |  | 209.1851 | 1228.5455 | 25931500.3636 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | [8 empty] | 0 | 0 |  | 0 | 0 | 0 |  | 85116.5 | 1.819e-12 |  | Closed | NY completed
|  | Total | [6 empty] | 3636358 | 318809.79 | 2251392.79 | 333537 | 1764888.9 | 54855 | 348105 | 5938.9 | 91441.9 | 4268.29 | 95710.19 | 4353766.98 | 297237285.9 | 3301.926 | 1365272.3836 | 100969836.4545 | 0 | 3247.3343 | 81589.0384 | 1559228551.2596 | 0 | 1172176.5555 | 90689237.6145 | 0 | #VALUE! | 104960.4995 | 2066994159.4638 | 0 | 671807.63 | 56946835.6073 | 0 | 2686.9638 | 67180.763 | 1202409147.0702 | 0 | 162967.4127 | 12310269 | 0 | 797.825 | 16296.7413 | 258300653.7011 | 0 | 227917.9545 | 17149395 | 0 | 411.5501 | 22791.7955 | 355262909.1818 | 0 | [7 empty] | 150188.1764 | 15137781 | 0 | 1404.2863 | 14518.3186 | 300027200.9673 | 0 | 4110851.869 | 242914.611
169051.101
237419
14300.002
223118.998
III. Breakdown for payment
STT |  | Code | Sub-contract | Address | Tax code | Date of signing | Time of commencemant and completion | Detail | price | [12 empty] | Exchange rate | Payment status | [48 empty] | Total of payment | Remaining Amount in USD |  | Detailed of remaining amount | Dealine of payment | Remaining Amount in USD ( HO) | Remaining Amount in JPY (HO) | Contact person | Remark
[9 empty] | Contract price | Add No.1/adjusted |  | Add No.2 |  | Add No.3 |  | Add No.4 |  | Add No.5 |  | Total of Contract & Add | equivalent in JPY |  | The first payment (40%) | [6 empty] | The second payment | [6 empty] | The third payment | [6 empty] | The fourth payment | [6 empty] | The fifth payment | [13 empty] | The final payment (20%)
[10 empty] | Dif | Total | Dif | Total | Dif | Total | Dif | Total | Dif | Total |  |  |  | in USD (Inc VAT) | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site | [7 empty] | in USD | equivalent in JPY | Date payment from HO | Exchange rate | VAT in USD | Equivalent in VND | Date payment from Project site
A. Claimed by invoice and HO processed
B. Claimed by invoice, but not yet processed by HO
B. not yet Claimed by invoice by Sub-Consultant | [8 empty] | 913102 | 225778.9 | 830353.9 | 225231 | 547234 | 0 | 0 | 0 | 0 | 0 | 0 | 1364111.9 | 72278421.7 | 953.9047 | 339697.1709 | 27060370 | 41132 | 955.3802 | 31978.3171 | 667416477.4604 | 0 | 304687.7182 | 28673357 | 0 | 1115.0572 | 30468.7718 | 566958083.9589 | 0 | 141349.46 | 12167468 | 0 | 509.8586 | 14134.946 | 251231812.056 | 0 | 28144 | 2882508 | 0 | 102.42 | 2814.4 | 59203718.4 | 0 | 96700 | 9830522 | 0 | 101.66 | 9670 | 205448820 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1052829.384 | 311282.516 | 0 | 0
1 | JA08O1057 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 2011-05-10 | 05/09-31/12/2011 | Hydrological survey works | 49785 | [10 empty] | 49785 | 3523413 | 70.7726 | 19914 | 1555881 | 22/12/2011 | 78.13 |  |  |  | 18103.6364 | 1428739 | 28/06/2012 | 78.92 | 1810.3636 | 37706261 | 20/07/2012 | [35 empty] | 39828 | 9957 | ok | Final payment : 20% of original contract | Stop | 11767.3636 | 538793 |  | Paid: 80% of original contract
5 | JA1200559 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 31/08/2012 |  | Engineering Geological Survey works ( Package 2, Bridge section, Km8+000-Km16+880) | 93500 | 101200 | 194700 | [8 empty] | 194700 | 7349100 | 78.6 | 34000 | 2708440 | 13/12/2012 | 79.66 | 3400 | 70815200 | 21/01/2013 | 34000 | 3329280 | 06/06/2013 | 97.92 | 3400 | 70815200 | 18/07/2013 | 18000 | 1834920 | 03/04/2014 | 101.94 | 1800 | 37864800 | 09/05/2014 | [28 empty] | 94600 | 100100 | ok | 100% of additional work (USD 100,100.00) | Stop | 108700 | -1191640 |  | Paid 80% of the original. NY pay for supplymental works, additional works
6 | JA1200139 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 15/02/2012 | 01/03-31/05 | Engineering Geological Survey works (Package 3A, Ky Lam Bridge section ) | 80196 | 11191 | 91387 | 3771 | 95158 | [6 empty] | 95158 | 7510528.3 | 93.6522 | 29161.8182 | 2604413 | 31/05/2012 | 89.309 | 2916.1818 | 60738239 | 15/06/2012 | 29162.1818 | 2262971 | 08/11/2012 | 77.5995 | 2916.2182 | 60738992.2909 | 19/12/2012 | 12968.18 | 1321958 | 03/04/2014 | 101.9386 | 1296.818 | 27279863.448 | 09/05/2014 | [28 empty] | 78421.398 | 16736.602 | TT lan 4:8368 TT lan cuoi:8368.60 | 100% of additional work (USD 16,736.) | Stop | 23865.82 | 638411 |  | Paid 80% of the original.
7 | JA1200558 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 31/08/2012 |  | Engineering Geological Survey works ( Package 3B, Km18+100-Km21+500) | 71500 | 20678.9 | 92178.9 | [8 empty] | 92178.9 | 5619900 | 78.6 | 26000 | 2135120 | 27/12/2012 | 82.12 | 2600 | 54152800 | 20/02/2013 | 26000 | 2445300 | 02/05/2013 | 94.05 | 2600 | 54152800 | 25/06/2013 | [35 empty] | 57200 | 34978.9 | ok | final payment of original scope | Stop | 40178.9 | 528580 |  | Paid 80% of the original.
8 | JA1200476 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 2012-01-08 |  | Engineering Geological Survey works ( Package 3B, Chiem Sơn Bridge section, Km19+975.2 -Km20+430.1 ) | 31011 | -3669 | 27342 | [8 empty] | 27342 | 2459497.7 | 79.3105 | 11276.7273 | 886351 | 27/09/2012 | 78.6 | 1127.6727 | 23487167.5636 | 29/11/2012 | 11276.36 | 1027761 | 14/03/2013 | 91.143 | 1127.636 | 23486402.608 | 22/04/2013 | [35 empty] | 24808.396 | 2533.604 | ok | final payment of original scope | Stop | 4788.9127 | 321795 |  | Paid 80% of the original.
15 | JA1200556 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 27/08/2012 |  | Engineering Geological Survey works ( Package A1, Km65+000-Km081+150) | 99000 | -3300 | 95700 | [8 empty] | 95700 | 7781400 | 78.6 | 36000 | 2793600 | 25/10/2012 | 77.6 | 3600 | 74980800 | 29/11/2012 | 36000 | 3642480 | 4/07/2013 | 101.18 | 3600 | 74980800 | 18/07/2013 | [35 empty] | 79200 | 16500 | ok | final payment of original scope | Stop | 23700 | 637920 |  | Paid 80% of the original.
18 | JA1200565 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 27/08/2012 |  | Engineering Geological Survey works ( Package A3, Km99+500-Km110+100) | 66000 | 61600 | 127600 | [8 empty] | 127600 | 5187600 | 78.6 | 24000 | 1862400 | 25/10/2012 | 77.6 | 2400 | 49987200 | 29/11/2012 | 24000 | 2350080 | 06/06/2013 | 97.92 | 2400 | 49987200 | 18/07/2013 | 33000 | 3364020 | 03/04/2014 | 101.94 | 3300 | 69418800 | 09/05/2014 | [28 empty] | 89100 | 38500 | ok | 100% of additional work (USD 38,500) | Stop | 46600 | -2860500 |  | Paid 80% of the original , NY made the 3rd, 4th & 5th paymnent
19 | JA1200475 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 2012-01-08 |  | Engineering Geological Survey works (Package A3, Tra bong Bridge section, Km 108+775.25-km109+230.25 ) | 34759 | 9329 | 44088 | 15068 | 59156 | [6 empty] | 59156 | 2756727.6 | 79.3097 | 12639.6364 | 993476 | 27/09/2012 | 78.6 | 1263.9636 | 26325834.6182 | 29/11/2012 | 12640 | 1151977 | 14/03/2013 | 91.1374 | 1264 | 26326592 | 22/04/2013 | 20831.82 | 2142761 | 06/03/2013 | 102.86 | 2083.182 | 43821816.552 | 17/04/2014 | [28 empty] | 50722.602 | 8433.398 | TT lan 4:4217 TT lan cuoi:4216.4 | 100% of additional work (USD 8,434) | Stop | -2023.4564 | -1782098 |  | Paid 80% of the original.
22 | JA1200477 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 2012-01-08 |  | Engineering Geological Survey works (Package A5, Tra Khuc Bridge section, Km124+979.4-km125+728.2 ) | 33349 | -2271 | 31078 | [8 empty] | 31078 | 2644885.1 | 79.3093 | 12126.9091 | 953175 | 27/09/2012 | 78.6 | 1212.6909 | 25257926.2545 | 29/11/2012 | 12127.27 | 1105247 | 14/03/2013 | 91.1373 | 1212.727 | 25258677.956 | 22/04/2013 | [35 empty] | 26679.597 | 4398.403 | OK | final payment of original scope | Stop | 6823.8209 | 346019 |  | Paid: 80% of original contract
2 | JA1200311 | TL | Thang Loi engineering consultants Co., Ltd |  |  | 2012-01-06 | 10/6-31/7/2012 | Land acquisition & Row staking works | 95260 | 31020 | 126280 | [8 empty] | 126280 | 7517919 | 78.92 | 34640 | 2688064 | 2012-08-11 | 77.6 | 3464 | 72148192 | 19/12/2012 | 34640 | 3638932 | 23/01/2014 | 105.05 | 3464 | 72868704 | 18/03/2013 | 21920 |  |  |  | 2192 | [30 empty] | 100320 | 25960 |  | 20% of original contract | Stop | 35080 | 507475.8182 |  | Paid 40% of the original contract
1 | JA12000309 | E&R | E&R engineering consultants joint stock company |  |  | 18/06/2012 | 15/08/2012 | Engineering Geological Survey works ( Package 1, Hoa Vang section, Km0+000-km8+000) | 186528 |  |  | 206392 | 392920 | [6 empty] | 392920 | 14720789 | 78.92 | 67113.08 | 5299484 | 19/07/2012 | 78.9635 | 6711.308 | 139783123.024 | 06/09/2012 | 33914.18 | 2701604 | 22/11/2012 | 79.66 | 3391.418 | 70636454.104 | 19/12/2012 | 34629.46 | 3503809 | 11/07/2013 | 101.18 | 3462.946 | 72846532.056 | 15/08/2013 | 28144 | 2882508 | 26/12/2013 | 102.42 | 2814.4 | 59203718.4 | 15/01/2014 | 96700 | 9830522 | 19/06/2014 | 101.66 | 9670 | 205448820 | 21/07/2014 | 48349.6364 |  |  |  | 4834.9636 | [9 empty] | 339735.392 | 53184.608 | TT lần cuối: USD 106369,2 | 50% of additional work (USD 212,740) | stop (Acceptance Minutes: 24 July 2013) => 23/01/2014 | -73972.72 | -10835391.5455 |  | Paid 80% of the original , NY made the 4th & 5th paymnent
| JA1200478 | TEDI | Transport Engineering Design Inc. ( TEDI) |  |  | 2012-01-06 |  | Purchase Contract for land acquisition and ROW stakes | 72214 | [10 empty] | 72214 | 5206662 | 79.3105 | 32825 | 2579966 | 11/10/2012 | 78.5976 | 3282.5 | 69739995 | 30/09/2014 | 32824.09 | 3588986 | 04/12/2014 | 109.34 | 3282.409 | [37 empty] | 72213.999 | 0.001 |  | Closed |  |  | -1435622.9091
|  | Total | [6 empty] | 913102 | 225778.9 | 830353.9 | 225231 | 547234 | 0 | 0 | 0 | 0 | 0 | 0 | 1364111.9 | 72278421.7 | 953.9047 | 339697.1709 | 27060370 | 41132 | 955.3802 | 31978.3171 | 667416477.4604 | 0 | 304687.7182 | 28673357 | 0 | 1115.0572 | 30468.7718 | 566958083.9589 | 0 | 141349.46 | 12167468 | 0 | 509.8586 | 14134.946 | 251231812.056 | 0 | 28144 | 2882508 | 0 | 102.42 | 2814.4 | 59203718.4 | 0 | 96700 | 9830522 | 0 | 101.66 | 9670 | 205448820 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1052829.384 | 311282.516 | 0 | 0
68367.905
[27 empty] | 73824.388 |  |  | 37305.598 | [6 empty] | 38092.406
Note on X9: DSIV: TT02/11
Note on AF9: Huong: HO Email: 120618
Note on AI9: Huong: DN-QN site project paid 20120720
Note on X11: DSIV: 02/11
Note on AF11: Huong: HO Email: 120618
Note on AJ11: Huong: paid 20120720 ( invoice No.14)
Note on X12: DSIV: 20/10
Note on AE12: Huong: Mr.ishimoto approved interim payment 120611, but HO has not paid yet
Note on AJ12: Huong: paid 20120720 ( invoice 48)
Note on J13: Huong: including 10%VAT
Note on V13: Huong: email: 3/7/2012
Note on X15: DSIV: 20/10
Note on V16: Huong: Tokyo: 7.800.570 d, email: 6 Aug 2012
Note on V18: Huong: including Addendum1
Note on X18: DSIV: 20/10
Note on AE18: Huong: 27/4
Note on AC19: PAID :
Note on J20: Huong: Inc VAT
Note on X20: Huong: Send email to tokyo dated 25 June 2012
Note on AC20: Huong: Paid
Note on J21: Huong: Inc VAT
Note on X21: Huong: Send email to tokyo dated 25 June 2012
Note on AC21: Huong: Paid
Note on X23: Huong: Mr.Ishi agreed for 1st payment dated 122709
Note on X25: Huong: paid: 22/12/2011
Note on AF25: Huong: HO Email: 120618
Note on AJ25: Huong: DN_QN project site office paid VAT in VND ( Inv.16)
Note on M29: Huong: NY signed Add No.1 b/c Ishimoto
Note on V29: Huong: Email: 3/7/2012
Note on X29: Huong: email dated 20120710
Note on K30: Huong: NY signed Add No.1
Note on J32: Huong: Da bao gom 10%Vat
Note on Y32: Email: 09 Aug 2012
Note on K33: Huong: NY signed Add
Note on Y34: Huong: 05/24/2012
Note on AB34: Huong: DN-QN paid 15/06/2012
Note on Y36: Huong: Email from Tokyo: 18/09/2012
Note on Y38: Huong: Dated 26 August 2012.
Note on K39: Huong: NY signed Add
Note on K47: Huong: NY signed Add
Note on M48: Huong: NY signed Add
Note on Y48: Huong: Email from Tokyo: 18/09/2012
Note on V49: Huong: contract price including 10%VAT: 8.752.282đ. Email dated 06 Jun 2012
Note on Y49: Huong: Email: June 7, 2012
Note on AB49: Huong: paid 20120720 ( inv.62)
Note on AE49: Huong: Mr.Ishimoto agreed on 09 Aug 2012
Note on AF49: Huong: Tokyo : 13 Aug 2012
Note on J50: Huong: including 10%VAT
Note on K50: Huong: NY signed add
Note on V50: Huong: Price contract before VAT: 8.882.086d
Note on Y50: Huong: Tokyo 15 Aug 2012
Note on Y51: Huong: Email from Tokyo: 18/09/2012
Note on X55: Huong: paid: 11/05
Note on J56: Huong: Including 10%VAT
Note on V56: Huong: Email: 3/7/2012
Note on J57: Huong: inluding 10%VAT
Note on X60: Mr.Ishimoto agree for 1st payment dated 120927
Note on X99: Huong: paid: 22/12/2011
Note on AF99: Huong: HO Email: 120618
Note on AJ99: Huong: DN_QN project site office paid VAT in VND ( Inv.16)
Note on K100: Huong: NY signed Add
Note on Y101: Huong: 05/24/2012
Note on AB101: Huong: DN-QN paid 15/06/2012
Note on Y103: Huong: Email from Tokyo: 18/09/2012
Note on K105: Huong: NY signed Add
Note on M106: Huong: NY signed Add
Note on Y106: Huong: Email from Tokyo: 18/09/2012
Note on Y107: Huong: Email from Tokyo: 18/09/2012
Note on J108: Huong: Including 10%VAT
Note on V108: Huong: Email: 3/7/2012
Note on M109: Huong: NY signed Add No.1 b/c Ishimoto
Note on V109: Huong: Email: 3/7/2012
Note on X109: Huong: email dated 20120710
Note on X110: Mr.Ishimoto agree for 1st payment dated 120927