## Cover
Topographic Survey Plan
| 1 | Project Facility Plan |  |  | Page 2
| 2 | Survey Packages and Demarcation among Sub-contractors |  |  | Page 3
| 3 | Survey Cost
|  | 3.1 | Survey Cost by Sub-contractors |  | Page 4
|  | 3.2 | Survey Cost by Survey Packages |  | Page 5
| 4 | Survey Plan
|  | 4.1 | Survey Plan |  | Page 8
|  | 4.2 | Detailed Survey Plan
|  |  | 4.2.1 | Detailed Survey Plan (Main Line, Road Section) | Page 20
|  |  | 4.2.2 | Detailed Survey Plan (Tunnel) | Page 23
|  |  | 4.2.3 | Detailed Survey Plan (Bridge) | Page 24
|  |  | 4.2.4 | Detailed Survey Plan (Culvert Box) | Page 28
|  |  | 4.2.5 | Detailed Survey Plan (Culvert Pipe) | Page 32
|  |  | 4.2.6 | Detailed Survey Plan (Interchange) | Page 36
|  |  | 4.2.7 | Detailed Survey Plan (Building) | Page 37
|  |  | 4.2.8 | Detailed Survey Plan (Intersection) | Page 38
|  |  | 4.2.9 | Detailed Survey Plan (Canal (Re-alignment)) | Page 39

## 1.Facility Plan
1A
Danang
Hanoi/
HCMC
Dung Quat
East-West Corridor
Tuy Loan IC
My Son IC
Ha Lam IC
Tam Ky IC
Chu Lai IC
Dung Quat IC
Binh Son IC
Quang Ngai North IC
Quang Ngai IC
KM000+000
KM020+805
KM040+776
KM064+200
KM083+800
KM102+255
KM112+615
KM123+915
KM130+750
KM000+000
KM007+800
KM099+500
KM131+500
Quang Ngai
Quang Nam
Danang
North-South Expressway
Project Road
Quang Tri-Danang (Plan)
Quang Ngai-Quy Nhon (Plan)
Other Classified Road
Danang Bypass
National Highway
Provincial/District/City Roads
Provincial/District/City Road (Plan)
Railway
North-South Railway
LEGEND
Project Facilities
Thruway
Linking Road (New Construction)
Interchange (IC)
Traffic Management Center (TMC)
Expressway Operation Office (EOO)
Service Area (SA)
Parking Area (PA)
Toll Barrier (TB)
Toll Gate (TG)
Toll Plaza Office (TPO)
14B
PA, KM029+130
SA, KM069+600
TMC, KM000+950
Tuy Loan TPO
My Son
Ha Lam TPO
Tam Ky TPO
Chu Lai TPO
Dung Quat TPO
TB, KM129+800
14E
TPO
Quang Ngai TPO
BP
EP
Jurisdiction
TB, KM004+750
District
District
Chu Lai
Road
Road
Industrial
Dung Quat
Industrial
Tra Bong-
Road
Provincial
Road
Provincial
Quang Ngai
City Ring Road
610
616
Road
623
Road
625
Quang Ngai
City
Road
Binh Long
EOO, KM064+750
PA, KM098+800
Binh Son
Thruway (Embankment Section, Initial Stage&Ultimate Stage)
Thruway (Cutting Section, Initial Stage&Ultimate Stage)
Thruway (Bridge Section, Initial Stage&Ultimate Stage)
Thruway (Tunnel Section, Initial Stage&Ultimate Stage)
Linking Road (Embankment Section, Initial Stage)
Linking Road (Bridge Section, Initial Stage)
Culvert
Frontage Road
TPO
North TPO
Quang Ngai

## 2.PKG
A. Control Point and Leveling Network Survey
Jurisdiction |  | Road |  | Construction Contract Package (Civil Works) |  |  |  |  | Survey Package | [6 empty] | Demarcation among Sub-contractors
|  | Classification |  | No. | Section |  |  | Length | No. |  | Section |  |  | Equation | Length | TEDI | TEDIS | TECCO533 | VECC | EGS | Tien Khai | INPEL | BMT
| Quang Nam/ |  | Expressway | [5 empty] | 1 | CP | 16000 | - | 60000 |  |  | 100%
| Quang Ngai | [9 empty] | 73000 | - | 109000
[11 empty] | 109000 | - | 131500
|  |  | Linking Road | [7 empty] | 131500 | - | 139500
Total | [15 empty] | 100%
B. Expressway, C. Linking Road
Jurisdiction |  | Road |  | Construction Contract Package (Civil Works) |  |  |  |  | Survey Package | [6 empty] | Demarcation among Sub-contractors
|  | Classification |  | No. | Section |  |  | Length | No. |  | Section |  |  | Equation | Length | TEDI | TEDIS | TECCO533 | VECC | EGS | Tien Khai | INPEL | BMT
| Danang |  | Expressway | PKG01 | 0 | - | 8000 | 8000 | 1 | ML01-1 | -800 | - | 4050 |  | 4850 |  |  |  | 4850
[9 empty] | 2 | ML01-2 | 3950 | - | 8050 |  | 4100 |  |  |  | 4100
| Quang Nam |  |  | PKG02 | 8000 | - | 17000 | 9000 | 3 | ML02-1 | 7950 | - | 13050 |  | 5100 |  |  |  | 5100
[9 empty] | 4 | ML02-2 | 12950 | - | 17050 |  | 4100 |  |  |  | 4100
|  |  |  | PKG03 | 17000 | - | 22000 | 5059.78 | 5 | ML03-1 | 16950 | - | 22050 | -59.78 | 5159.78 | 5159.78
|  |  |  | PKG04 | 22000 | - | 32000 | 10000 | 6 | ML04-1 | 21950 | - | 26850 |  | 4900 |  |  |  |  | 4900
[9 empty] | 7 | ML04-2 | 26750 | - | 32050 |  | 5300 |  |  |  |  | 5300
|  |  |  | PKG05 | 32000 | - | 42000 | 10000 | 8 | ML05-1 | 31950 | - | 35050 |  | 3100 | 3100
[9 empty] | 9 | ML05-2 | 34950 | - | 42050 |  | 7100 |  | 7100
|  |  |  | PKG06 | 42000 | - | 52000 | 10000 | 10 | ML06-1 | 41950 | - | 46650 |  | 4700 |  | 4700
[9 empty] | 11 | ML06-2 | 46550 | - | 52050 |  | 5500 |  | 5500
|  |  |  | PKG07 | 52000 | - | 65000 | 13000 | 12 | ML07-1 | 51950 | - | 56050 |  | 4100 |  |  | 4100
[9 empty] | 13 | ML07-2 | 55950 | - | 60050 |  | 4100 |  |  | 4100
[9 empty] | 14 | ML07-3 | 59950 | - | 65050 |  | 5100 |  |  | 5100
|  |  |  | PKGA1 | 65000 | - | 81500 | 16557.32 | 15 | MLA1-1 | 64950 | - | 71050 |  | 6100 | 6100
[9 empty] | 16 | MLA1-2 | 70950 | - | 76050 | -57.32 | 5157.32 | 5157.32
[9 empty] | 17 | MLA1-3 | 75950 | - | 81550 |  | 5600 | 5600
|  |  |  | PKGA2 | 81500 | - | 100000 | 18200 | 18 | MLA2-1 | 81450 | - | 87050 |  | 5600 | 5600
[9 empty] | 19 | MLA2-2 | 86950 | - | 93050 |  | 6100 | 6100
[9 empty] | 20 | MLA2-3 | 92950 | - | 100050 | 300 | 6800 | 6800
|  |  |  | PKGA3 | 100000 | - | 110000 | 10173.22 | 21 | MLA3-1 | 99950 | - | 105050 | -173.22 | 5273.22 | 5273.22
[9 empty] | 22 | MLA3-2 | 104950 | - | 110050 |  | 5100 | 5100
| Quang Ngai |  |  | PKGA4 | 110000 | - | 125000 | 15000 | 23 | MLA4-1 | 109950 | - | 115050 |  | 5100 | 5100
[9 empty] | 24 | MLA4-2 | 114950 | - | 120050 |  | 5100 | 5100
[9 empty] | 25 | MLA4-3 | 119950 | - | 125050 |  | 5100 | 5100
|  |  |  | PKGA5 | 125000 | - | 139522 | 14522 | 26 | MLA5-1 | 124950 | - | 131550 |  | 6600 | 6600
|  |  | Linking Road | [5 empty] | 27 | MLA5-2 | 131450 | - | 136050 |  | 4600 | 4600
[9 empty] | 28 | MLA5-3 | 135950 | - | 139572 |  | 3622 | 3622
Total | [7 empty] | 139512.32 | [6 empty] | 143062.32 | 84112.32 | 17300 | 13300 | 18150 | 10200 | 0 | 0 | 0
[15 empty] | 100% | 58.79% | 12.09% | 9.297% | 12.69% | 7.13% | 0% | 0% | 0%
Topographic Survey for PKG15 (O&M Buildings) is included in each Survey Package above
Each Survey Section overlaps 100 m with neighboring Survey Sections

## 3.1Cost by Sub-contractors
No. | Item | [5 empty] | Specifications |  | Unit | Total |  |  |  | By Sub-contractors
[14 empty] | TEDI |  | TEDIS |  |  | TECCO533 |  | VECC |  | EGS |  | Tien Khai |  | INPEL |  | BMT
[10 empty] | Unit Price | Qty | Amount |  | Qty | Amount | Qty |  | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount
[10 empty] | (USD) |  | (USD) |  |  | (USD) |  |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD)
A |  | Control Point and Leveling Network | [9 empty] | 159149.91 |  |  | 159149.91
1 |  | Primary Control Point (GPS) | [9 empty] | 72395.61 |  |  | 72395.61
1.1 |  | Primary Control Point (GPS) |  |  |  |  | Class IV, VN2000 |  | (nos.) | 918.09 | 49 | 44986.41 |  | 49 | 44986.41
1.2 |  | Primary Leveling Network (GPS Network) | [6 empty] | (km) | 130.52 | 210 | 27409.2 |  | 210 | 27409.2
2 |  | Secondary Control Point | [9 empty] | 86754.3 |  |  | 86754.3
2.1 |  | Secondary Control Point |  |  |  |  | Class II |  | (nos.) | 150.63 | 500 | 75315 |  | 500 | 75315
2.2 |  | Secondary Leveling Network | [6 empty] | (km) | 67.29 | 170 | 11439.3 |  | 170 | 11439.3
B |  | Expressway | [8 empty] | 0 | 1080114.422 | 0 | 0 | 591196.0362 | 0 |  | 135058.3317 | 0 | 110145.2251 | 0 | 174841.399 | 0 | 68873.43
3 |  | Main Line (ML, Road Section) | [8 empty] | 0 | 607431.5851 |  | 0 | 348387.2022 | 0 |  | 77327.5355 | 0 | 64671.5166 | 0 | 70637.51 | 0 | 46407.8209
3.1 |  | Planimetric |  |  |  |  | 1/1,000 |  | (ha) | 61.29 | 1556.481 | 95396.7211 |  | 890.1594 | 54557.8702 | 199.549 | 0 | 12230.3582 | 165.613 | 10150.4208 | 181.8537 | 11145.8133 | 119.3059 | 7312.2586
3.2 |  | Profile |  |  |  |  | 1/1,000; 1/100 |  | (km) | 438.31 | 111.1772 | 48730.0851 |  | 63.5828 | 27868.9836 | 14.2535 |  | 6247.4516 | 11.8295 | 5184.9881 | 12.9896 | 5693.4497 | 8.5219 | 3735.2121
3.3 |  | Cross-section |  |  |  |  | 1/200 |  | (km) | 572.73 | 808.941 | 463304.7789 |  | 464.373 | 265960.3483 | 102.753 |  | 58849.7257 | 86.142 | 49336.1077 | 93.933 | 53798.2471 | 61.74 | 35360.3502
4 |  | Tunnel (TN) | [8 empty] | 0 | 178.8672 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 178.8672
4.1 |  | Planimetric |  |  |  |  | 1/500 |  | (ha) | 175.36 | 1.02 | 178.8672 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1.02 | 178.8672
5 |  | Bridge (BR) | [8 empty] | 0 | 239908.8655 |  | 0 | 135144.1979 | 0 |  | 28721.1639 | 0 | 14144.2265 | 0 | 52223.7382 | 0 | 9675.539
5.1 |  | Secondary Control Point |  |  |  |  | Class II |  | (nos.) | 150.63 | 314 | 47297.82 |  | 158 | 23799.54 | 48 |  | 7230.24 | 24 | 3615.12 | 64 | 9640.32 | 20 | 3012.6
5.2 |  | Planimetric (On Shore) |  |  |  |  | 1/500 |  | (ha) | 175.36 | 320.0843 | 56129.9916 |  | 199.7561 | 35029.2385 | 29.799 |  | 5225.5526 | 14.021 | 2458.7226 | 64.1238 | 11244.7496 | 12.3844 | 2171.7284
5.3 |  | Planimetric (Off Shore) |  |  |  |  | 1/500 |  | (ha) | 226.18 | 101.3222 | 22917.0552 |  | 55.132 | 12469.7558 | 12.852 |  | 2906.8654 | 6.566 | 1485.0979 | 23.2225 | 5252.465 | 3.5497 | 802.8711
5.4 |  | Profile (On Shore) |  |  |  |  | 1/500 |  | (km) | 438.31 | 25.678 | 11254.9351 |  | 16.6517 | 7298.6176 | 2.1285 |  | 932.9428 | 1.0015 | 438.9675 | 5.0117 | 2196.6782 | 0.8846 | 387.729
5.5 |  | Profile (Off Shore) |  |  |  |  | 1/500 |  | (km) | 474.97 | 7.2373 | 3437.5004 |  | 3.938 | 1870.4319 | 0.918 |  | 436.0225 | 0.469 | 222.7609 | 1.6587 | 787.8565 | 0.25355 | 120.4286
5.6 |  | Cross-section (Approach Road) |  |  |  |  | 1/200 |  | (km) | 572.73 | 112.875 | 64646.8987 |  | 62.496 | 35793.3341 | 14.259 |  | 8166.5571 | 6.762 | 3872.8003 | 24.066 | 13783.3202 | 5.292 | 3030.8872
5.7 |  | River Profile |  |  |  |  | 1/1,000; 1/100 |  | (km) | 474.97 | 39.2 | 18618.824 |  | 21.7 | 10306.849 | 4.4 |  | 2089.868 | 2.3 | 1092.431 | 10.7 | 5082.179 | 0.1 | 47.497
5.8 |  | River Cross-section |  |  |  |  | 1/200 |  | (km) | 655.49 | 23.8079 | 15605.8404 |  | 13.084 | 8576.4312 | 2.644 |  | 1733.1156 | 1.462 | 958.3264 | 6.4626 | 4236.1697 | 0.1553 | 101.7976
6 |  | Culvert Box (CB) | [8 empty] | 0 | 94665.074 |  | 0 | 31169.302 | 0 |  | 13141.208 | 0 | 15772.839 | 0 | 22373.832 | 0 | 12207.893
6.1 |  | Profile |  |  |  |  | 1/500 |  | (km) | 438.31 | 42.4 | 18584.344 |  | 13.6 | 5961.016 | 6 |  | 2629.86 | 7.2 | 3155.832 | 10 | 4383.1 | 5.6 | 2454.536
6.2 |  | Profile |  |  |  |  | 1/200 |  | (km) | 438.31 | 5.8 | 2542.198 |  | 4.2 | 1840.902 | 0.2 |  | 87.662 | 0.3 | 131.493 | 0.8 | 350.648 | 0.3 | 131.493
6.3 |  | Cross-section |  |  |  |  | 1/200 |  | (km) | 572.73 | 128.4 | 73538.532 |  | 40.8 | 23367.384 | 18.2 |  | 10423.686 | 21.8 | 12485.514 | 30.8 | 17640.084 | 16.8 | 9621.864
7 |  | Culvert Pipe (CP) | [8 empty] | 0 | 788.958 |  | 0 | 262.986 | 0 |  | 43.831 | 0 | 131.493 | 0 | 262.986 | 0 | 87.662
7.1 |  | Profile |  |  |  |  | 1/200 |  | (km) | 438.31 | 1.8 | 788.958 |  | 0.6 | 262.986 | 0.1 |  | 43.831 | 0.3 | 131.493 | 0.6 | 262.986 | 0.2 | 87.662
8 |  | Canal (Re-alignment) | [8 empty] | 0 | 6201.3654 |  | 0 | 2181.6578 | 0 |  | 223.0427 | 0 | 601.8326 | 0 | 3194.8323 | 0 | 0
8.1 |  | Profile |  |  |  |  | 1/500 |  | (km) | 438.31 | 3.904 | 1711.1622 |  | 1.371 | 600.923 | 0.143 |  | 62.6783 | 0.38 | 166.5578 | 2.01 | 881.0031 | 0 | 0
8.2 |  | Cross-section |  |  |  |  | 1/200 |  | (km) | 572.73 | 7.84 | 4490.2032 |  | 2.76 | 1580.7348 | 0.28 |  | 160.3644 | 0.76 | 435.2748 | 4.04 | 2313.8292 | 0 | 0
9 |  | Interchange (IC) | [8 empty] | 0 | 127351.8412 |  | 0 | 71939.3559 | 0 |  | 15601.5505 | 0 | 14651.4646 | 0 | 25159.4701 | 0 | 0
9.1 |  | Secondary Control Point |  |  |  |  | Class II |  | (nos.) | 150.63 | 72 | 10845.36 |  | 48 | 7230.24 | 8 |  | 1205.04 | 8 | 1205.04 | 8 | 1205.04 | 0 | 0
9.2 |  | Secondary Leveling Network | [6 empty] | (km) | 67.29 | 18 | 1211.22 |  | 12 | 807.48 | 2 |  | 134.58 | 2 | 134.58 | 2 | 134.58 | 0 | 0
9.3 |  | Planimetric |  |  |  |  | 1/500 |  | (ha) | 175.36 | 276 | 48399.36 |  | 155 | 27180.8 | 33 |  | 5786.88 | 28 | 4910.08 | 60 | 10521.6 | 0 | 0
9.4 |  | Profile (Rampway) |  |  |  |  | 1/1,000; 1/100 |  | (km) | 438.31 | 19.4 | 8503.214 |  | 10.65 | 4668.0015 | 2.46 |  | 1078.2426 | 2.43 | 1065.0933 | 3.86 | 1691.8766 | 0 | 0
9.5 |  | Cross-section (Rampway) |  |  |  |  | 1/200 |  | (km) | 572.73 | 101.955 | 58392.6872 |  | 55.965 | 32052.8345 | 12.915 |  | 7396.808 | 12.81 | 7336.6713 | 20.265 | 11606.3735 | 0 | 0
10 |  | Building (BL) | [8 empty] | 0 | 3587.8656 |  | 0 | 2111.3344 | 0 |  | 0 | 0 | 171.8528 | 0 | 989.0304 | 0 | 315.648
10.1 |  | Planimetric |  |  |  |  | 1/500 |  | (ha) | 175.36 | 20.46 | 3587.8656 |  | 12.04 | 2111.3344 | 0 |  | 0 | 0.98 | 171.8528 | 5.64 | 989.0304 | 1.8 | 315.648
C |  | Linking Road | [8 empty] | 0 | 42222.8665 |  | 0 | 37530.7465 | 0 |  | 1564.04 | 0 | 1564.04 | 0 | 1564.04 | 0 | 0
11 |  | Main Line (ML, Road Section) | [8 empty] | 0 | 22547.1433 |  | 0 | 22547.1433 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.1 |  | Planimetric |  |  |  |  | 1/1,000 |  | (ha) | 61.29 | 79.25 | 4857.2325 |  | 79.25 | 4857.2325 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.2 |  | Profile |  |  |  |  | 1/1,000; 1/100 |  | (km) | 438.31 | 7.925 | 3473.6067 |  | 7.925 | 3473.6067 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.3 |  | Cross-section |  |  |  |  | 1/200 |  | (km) | 572.73 | 24.822 | 14216.3041 |  | 24.822 | 14216.3041 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 |  | Bridge (BR) | [8 empty] | 0 | 2113.6972 |  | 0 | 2113.6972 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.1 |  | Secondary Control Point |  |  |  |  | Class II |  | (nos.) | 150.63 | 6 | 903.78 |  | 6 | 903.78 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.2 |  | Planimetric (On Shore) |  |  |  |  | 1/500 |  | (ha) | 175.36 | 2.22 | 389.2992 |  | 2.22 | 389.2992 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.3 |  | Planimetric (Off Shore) |  |  |  |  | 1/500 |  | (ha) | 226.18 | 0.75 | 169.635 |  | 0.75 | 169.635 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.4 |  | Profile (On Shore) |  |  |  |  | 1/500 |  | (km) | 438.31 | 0.222 | 97.3048 |  | 0.222 | 97.3048 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.5 |  | Profile (Off Shore) |  |  |  |  | 1/500 |  | (km) | 474.97 | 0.075 | 35.6228 |  | 0.075 | 35.6228 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.6 |  | Cross-section (Approach Road) |  |  |  |  | 1/200 |  | (km) | 572.73 | 0.567 | 324.7379 |  | 0.567 | 324.7379 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.7 |  | River Profile |  |  |  |  | 1/1,000; 1/100 |  | (km) | 474.97 | 0.2 | 94.994 |  | 0.2 | 94.994 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.8 |  | River Cross-section |  |  |  |  | 1/200 |  | (km) | 655.49 | 0.15 | 98.3235 |  | 0.15 | 98.3235 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | Culvert Box (CB) | [8 empty] | 0 | 1051.944 |  | 0 | 1051.944 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.1 |  | Profile |  |  |  |  | 1/500 |  | (km) | 438.31 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.2 |  | Profile |  |  |  |  | 1/200 |  | (km) | 438.31 | 2.4 | 1051.944 |  | 2.4 | 1051.944 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.3 |  | Cross-section |  |  |  |  | 1/200 |  | (km) | 572.73 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Culvert Pipe (CP) | [8 empty] | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
14.1 |  | Profile |  |  |  |  | 1/200 |  | (km) | 438.31 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 |  | Intersection (IS, NH1A) | [8 empty] | 0 | 16510.082 |  | 0 | 11817.962 | 0 |  | 1564.04 | 0 | 1564.04 | 0 | 1564.04 | 0 | 0
15.1 |  | Planimetric |  |  |  |  | 1/500 |  | (ha) | 175.36 | 42 | 7365.12 |  | 30 | 5260.8 | 4 |  | 701.44 | 4 | 701.44 | 4 | 701.44 | 0 | 0
15.2 |  | Profile |  |  |  |  | 1/1,000; 1/100 |  | (km) | 438.31 | 4.4 | 1928.564 |  | 3.2 | 1402.592 | 0.4 |  | 175.324 | 0.4 | 175.324 | 0.4 | 175.324 | 0 | 0
15.3 |  | Cross-section |  |  |  |  | 1/200 |  | (km) | 572.73 | 12.6 | 7216.398 |  | 9 | 5154.57 | 1.2 |  | 687.276 | 1.2 | 687.276 | 1.2 | 687.276 | 0 | 0
D |  | Mobilization and Temporary Camp Yard |  |  |  |  | 2% | of A+B+C |  |  |  | 25629.744 |  |  | 15757.5339 |  |  | 2732.4474 |  | 2234.1853 |  | 3528.1088 |  | 1377.4686
E |  | Reporting |  |  |  |  | 2% | of A+B+C |  |  |  | 25629.744 |  |  | 15757.5339 |  |  | 2732.4474 |  | 2234.1853 |  | 3528.1088 |  | 1377.4686
Total | [11 empty] | 1332746.6864 |  |  | 819391.7604 |  |  | 142087.2666 |  | 116177.6357 |  | 183461.6565 |  | 71628.3672
[12 empty] | 100% |  |  | 61.48% |  |  | 10.66% |  | 8.717% |  | 13.77% |  | 5.374%
Exchange Rate |  |  | 1 USD | = | 20800 | (exchange selling rate, 20 May 2011, Vietcombank) | [12 empty] | 0 | 0
Unit Price |  |  | 10% | Discount from Standard Unit Price (Quang Nam Province, 2011) | [14 empty] | 0 | 0
106619734.9128
1321673.05
-11073.6364
-885890.9128

## 3.2Cost by Packages
No. | Item | [5 empty] | Specifications |  | Unit | Unit Price | By Survey Packages | [23 empty] | By Survey Packages | [17 empty] | By Survey Packages
[10 empty] | (USD) |  |  | PKG01 |  |  |  | PKG02 |  |  |  | PKG03 |  | PKG04 |  |  |  | PKG05 |  |  |  | PKG06 |  |  |  | PKG07 | [5 empty] | PKGA1 | [5 empty] | PKGA2 | [5 empty] | PKGA3 |  |  |  | PKGA4 | [5 empty] | PKGA5
[11 empty] | CP |  | ML01-1 |  | ML01-2 |  | ML02-1 |  | ML02-2 |  | ML03-1 |  | ML04-1 |  | ML04-2 |  | ML05-1 |  | ML05-2 |  | ML06-1 |  | ML06-2 |  | ML07-1 |  | ML07-2 |  | ML07-3 |  | MLA1-1 |  | MLA1-2 |  | MLA1-3 |  | MLA2-1 |  | MLA2-2 |  | MLA2-3 |  | MLA3-1 |  | MLA3-2 |  | MLA4-1 |  | MLA4-2 |  | MLA4-3 |  | MLA5-1 |  | MLA5-2 |  | MLA5-3
TEDI
[11 empty] | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount
[12 empty] | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD) |  | (USD)
A |  | Control Point and Leveling Network |  |  |  |  | 0 |  | 0 | 0 |  | 159149.91
1 |  | Primary Control Point (GPS) |  |  |  |  | 0 |  | 0 | 0 |  | 72395.61
1.1 |  | Primary Control Point (GPS) |  |  |  |  | Class IV, VN2000 |  | (nos.) | 918.09 | 49 | 44986.41
1.2 |  | Primary Leveling Network (GPS Network) |  |  |  |  | 0 |  | (km) | 130.52 | 210 | 27409.2
2 |  | Secondary Control Point |  |  |  |  | 0 |  | 0 | 0 |  | 86754.3
2.1 |  | Secondary Control Point |  |  |  |  | Class II |  | (nos.) | 150.63 | 500 | 75315
2.2 |  | Secondary Leveling Network |  |  |  |  | 0 |  | (km) | 67.29 | 170 | 11439.3
B |  | Expressway |  |  |  |  | 0 |  | 0 | 0 |  |  |  | 65766.3524 |  | 32480.6529 |  | 42897.7192 |  | 33696.6744 |  | 59810.4515 |  | 31890.2456 |  | 36983.1844 |  | 17662.6603 |  | 63792.7118 |  | 32582.6697 |  | 38682.9502 |  | 30744.4436 |  | 29128.7053 |  | 50272.0761 |  | 50296.7378 |  | 34852.9544 |  | 36254.8139 |  | 47391.4319 |  | 40452.9132 |  | 43367.213 |  | 42983.1288 |  | 35001.9878 |  | 45800.7699 |  | 39523.4201 |  | 45846.531 |  | 51951.0227 |  | 0 |  | 0
3 |  | Main Line (ML, Road Section) |  |  |  |  | 0 |  | 0 | 0 |  |  |  | 17556.1276 |  | 20190.9391 |  | 19915.8084 |  | 12974.635 |  | 11212.768 |  | 20439.243 |  | 25968.5779 |  | 15557.5269 |  | 31324.3448 |  | 19173.0438 |  | 26830.1469 |  | 19450.8969 |  | 18122.3424 |  | 27098.2773 |  | 28115.9212 |  | 25915.9064 |  | 30207.5285 |  | 28581.6753 |  | 29333.0607 |  | 36349.5453 |  | 27460.0315 |  | 22164.9736 |  | 22162.3809 |  | 26898.7817 |  | 23575.7749 |  | 20851.3273 |  | 0 |  | 0
3.1 |  | Planimetric |  |  |  |  | 1/1,000 |  | (ha) | 61.29 |  |  | 45.0303 | 2759.9071 | 51.6635 | 3166.4559 | 51.4199 | 3151.5257 | 33.74 | 2067.9246 | 29.2604 | 1793.3669 | 52.5266 | 3219.3553 | 66.7793 | 4092.9033 | 39.8125 | 2440.1081 | 80.976 | 4963.019 | 49.763 | 3049.9743 | 68.81 | 4217.3649 | 50.036 | 3066.7064 | 46.599 | 2856.0527 | 68.978 | 4227.6616 | 71.785 | 4399.7027 | 66.2105 | 4058.0403 | 77.098 | 4725.3364 | 73.178 | 4485.0796 | 74.928 | 4592.3371 | 92.512 | 5670.0605 | 70.1571 | 4299.9274 | 56.616 | 3469.9946 | 56.588 | 3468.2785 | 68.642 | 4207.0682 | 60.032 | 3679.3613 | 53.34 | 3269.2086
3.2 |  | Profile |  |  |  |  | 1/1,000; 1/100 |  | (km) | 438.31 |  |  | 3.2165 | 1409.8022 | 3.6902 | 1617.4735 | 3.6728 | 1609.8469 | 2.41 | 1056.3271 | 2.09 | 916.0789 | 3.7519 | 1644.4953 | 4.77 | 2090.7168 | 2.8438 | 1246.4441 | 5.784 | 2535.185 | 3.5545 | 1557.9729 | 4.915 | 2154.2937 | 3.574 | 1566.5199 | 3.3285 | 1458.9148 | 4.927 | 2159.5534 | 5.1275 | 2247.4345 | 4.7293 | 2072.9082 | 5.507 | 2413.7732 | 5.227 | 2291.0464 | 5.352 | 2345.8351 | 6.608 | 2896.3525 | 5.0112 | 2196.4678 | 4.044 | 1772.5256 | 4.042 | 1771.649 | 4.903 | 2149.0339 | 4.288 | 1879.4733 | 3.81 | 1669.9611
3.3 |  | Cross-section |  |  |  |  | 1/200 |  | (km) | 572.73 |  |  | 23.373 | 13386.4183 | 26.901 | 15407.0097 | 26.46 | 15154.4358 | 17.199 | 9850.3833 | 14.847 | 8503.3223 | 27.195 | 15575.3923 | 34.545 | 19784.9578 | 20.727 | 11870.9747 | 41.601 | 23826.1407 | 25.431 | 14565.0966 | 35.721 | 20458.4883 | 25.872 | 14817.6706 | 24.108 | 13807.3748 | 36.162 | 20711.0623 | 37.485 | 21468.7841 | 34.545 | 19784.9579 | 40.278 | 23068.4189 | 38.073 | 21805.5493 | 39.102 | 22394.8885 | 48.51 | 27783.1323 | 36.603 | 20963.6362 | 29.547 | 16922.4533 | 29.547 | 16922.4533 | 35.868 | 20542.6796 | 31.458 | 18016.9403 | 27.783 | 15912.1576
4 |  | Tunnel (TN) |  |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 178.8672 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4.1 |  | Planimetric |  |  |  |  | 1/500 |  | (ha) | 175.36 | [12 empty] | 1.02 | 178.8672
5 |  | Bridge (BR) |  |  |  |  | 0 |  | 0 | 0 |  |  |  | 19752.7918 |  | 4162.3572 |  | 14092.9248 |  | 14215.6644 |  | 26103.2562 |  | 5146.2734 |  | 4529.2655 |  | 2017.4714 |  | 12509.9854 |  | 10440.4061 |  | 5770.7723 |  | 5167.6847 |  | 7555.963 |  | 1420.5789 |  | 11040.4851 |  | 4214.8406 |  | 5915.7923 |  | 5638.566 |  | 8488.2215 |  | 3719.7407 |  | 2061.0412 |  | 11930.5832 |  | 10534.1717 |  | 11718.2074 |  | 9550.5009 |  | 22211.3196 |  | 0 |  | 0
5.1 |  | Secondary Control Point |  |  |  |  | Class II |  | (nos.) | 150.63 |  |  | 16 | 2410.08 | 8 | 1205.04 | 18 | 2711.34 | 22 | 3313.86 | 20 | 3012.6 | 10 | 1506.3 | 10 | 1506.3 | 4 | 602.52 | 20 | 3012.6 | 18 | 2711.34 | 10 | 1506.3 | 8 | 1205.04 | 14 | 2108.82 | 2 | 301.26 | 12 | 1807.56 | 6 | 903.78 | 10 | 1506.3 | 10 | 1506.3 | 12 | 1807.56 | 6 | 903.78 | 4 | 602.52 | 14 | 2108.82 | 12 | 1807.56 | 20 | 3012.6 | 12 | 1807.56 | 16 | 2410.08
5.2 |  | Planimetric (On Shore) |  |  |  |  | 1/500 |  | (ha) | 175.36 |  |  | 20.5774 | 3608.4529 | 4.1517 | 728.0421 | 19.0163 | 3334.6984 | 20.3784 | 3573.5562 | 22.9316 | 4021.2941 | 6.0508 | 1061.0683 | 6.3336 | 1110.6601 | 3.5875 | 629.104 | 12.488 | 2189.8957 | 11.459 | 2009.4502 | 5.852 | 1026.2067 | 4.746 | 832.2586 | 7.875 | 1380.96 | 1.4 | 245.504 | 13.795 | 2419.0912 | 3.64 | 638.3104 | 11.88 | 2083.2768 | 8.25 | 1446.72 | 10.91 | 1913.1776 | 6.15 | 1078.464 | 3.164 | 554.839 | 13.122 | 2301.0739 | 24.472 | 4291.4099 | 23.06 | 4043.8016 | 21.708 | 3806.7149 | 33.086 | 5801.961
5.3 |  | Planimetric (Off Shore) |  |  |  |  | 1/500 |  | (ha) | 226.18 |  |  | 12.9423 | 2927.2894 | 1.5848 | 358.4501 | 5.4138 | 1224.4933 | 3.2816 | 742.2323 | 19.208 | 4344.4654 | 2.4626 | 556.9909 | 1.0871 | 245.8803 | 0 | 0 | 5.936 | 1342.6045 | 4.578 | 1035.452 | 2.338 | 528.8088 | 2.618 | 592.1392 | 2.926 | 661.8027 | 1.022 | 231.156 | 5.67 | 1282.4406 | 2.352 | 531.9754 | 0.462 | 104.4952 | 2.142 | 484.4776 | 4.032 | 911.9578 | 1.008 | 227.9894 | 0.504 | 113.9947 | 6.832 | 1545.2618 | 0 | 0 | 1.078 | 243.822 | 0 | 0 | 11.844 | 2678.8759
5.4 |  | Profile (On Shore) |  |  |  |  | 1/500 |  | (km) | 438.31 |  |  | 1.7741 | 777.6058 | 0.29655 | 129.9808 | 1.4855 | 651.0876 | 1.4556 | 638.004 | 1.638 | 717.9408 | 0.4322 | 189.4376 | 0.4524 | 198.2914 | 0.25625 | 112.3169 | 0.892 | 390.9725 | 0.8185 | 358.7567 | 0.418 | 183.2136 | 0.339 | 148.5871 | 0.5625 | 246.5494 | 0.1 | 43.831 | 1.1525 | 505.1523 | 0.26 | 113.9606 | 1.164 | 510.1928 | 0.737 | 323.0345 | 0.907 | 397.5472 | 0.567 | 248.5218 | 0.226 | 99.0581 | 1.085 | 475.5664 | 2.024 | 887.1394 | 2.258 | 989.704 | 1.846 | 809.1203 | 2.531 | 1109.3626
5.5 |  | Profile (Off Shore) |  |  |  |  | 1/500 |  | (km) | 474.97 |  |  | 0.92445 | 439.086 | 0.1132 | 53.7666 | 0.3867 | 183.6709 | 0.2344 | 111.333 | 1.372 | 651.6588 | 0.1759 | 83.5472 | 0.07765 | 36.8814 | 0 | 0 | 0.424 | 201.3873 | 0.327 | 155.3152 | 0.167 | 79.32 | 0.187 | 88.8194 | 0.209 | 99.2687 | 0.073 | 34.6728 | 0.405 | 192.3629 | 0.168 | 79.795 | 0.033 | 15.674 | 0.153 | 72.6704 | 0.288 | 136.7914 | 0.072 | 34.1978 | 0.036 | 17.0989 | 0.488 | 231.7854 | 0 | 0 | 0.077 | 36.5727 | 0 | 0 | 0.846 | 401.8246
5.6 |  | Cross-section (Approach Road) |  |  |  |  | 1/200 |  | (km) | 572.73 |  |  | 7.371 | 4221.5928 | 1.764 | 1010.2957 | 7.14 | 4089.2922 | 7.791 | 4462.1394 | 9.408 | 5388.2438 | 2.793 | 1599.6349 | 2.499 | 1431.2523 | 1.176 | 673.5305 | 5.88 | 3367.6524 | 5.586 | 3199.2698 | 2.793 | 1599.6349 | 2.352 | 1347.061 | 3.675 | 2104.7827 | 0.735 | 420.9565 | 5.376 | 3078.9965 | 1.911 | 1094.487 | 2.961 | 1695.8535 | 2.877 | 1647.7442 | 4.641 | 2658.0399 | 2.142 | 1226.7877 | 1.176 | 673.5305 | 4.641 | 2658.0399 | 6.195 | 3548.0624 | 5.922 | 3391.7071 | 5.46 | 3127.1058 | 8.61 | 4931.2053
5.7 |  | River Profile |  |  |  |  | 1/1,000; 1/100 |  | (km) | 474.97 |  |  | 6.2 | 2944.814 | 0.8 | 379.976 | 2.1 | 997.437 | 1.6 | 759.952 | 9.2 | 4369.724 | 0.1 | 47.497 | 0 | 0 | 0 | 0 | 2.3 | 1092.431 | 1.1 | 522.467 | 1 | 474.97 | 1.1 | 522.467 | 1.1 | 522.467 | 0.1 | 47.497 | 2 | 949.94 | 1 | 474.97 |  |  | 0.1 | 47.497 | 0.8 | 379.976 | 0 | 0 | 0 | 0 | 3 | 1424.91 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6 | 2659.832
5.8 |  | River Cross-section |  |  |  |  | 1/200 |  | (km) | 655.49 |  |  | 3.6978 | 2423.8709 | 0.4528 | 296.8059 | 1.3744 | 900.9055 | 0.9376 | 614.5874 | 5.488 | 3597.3291 | 0.1553 | 101.7976 | 0 | 0 | 0 | 0 | 1.392 | 912.4421 | 0.684 | 448.3552 | 0.568 | 372.3183 | 0.658 | 431.3124 | 0.658 | 431.3124 | 0.146 | 95.7015 | 1.228 | 804.9417 | 0.576 | 377.5622 |  |  | 0.168 | 110.1223 | 0.432 | 283.1717 | 0 | 0 | 0 | 0 | 1.808 | 1185.1259 | 0 | 0 | 0 | 0 | 0 | 0 | 3.384 | 2218.1782
6 |  | Culvert Box (CB) |  |  |  |  | 0 |  | 0 | 0 |  |  |  | 2675.462 |  | 6900.8 |  | 7217.554 |  | 5580.016 |  | 7807.231 |  | 6125.862 |  | 6082.031 |  | 43.831 |  | 4356.831 |  | 2746.177 |  | 6038.2 |  | 6038.2 |  | 3450.4 |  | 6284.239 |  | 7807.231 |  | 4488.324 |  | 87.662 |  | 219.155 |  | 2631.631 |  | 2982.279 |  | 1769.031 |  | 906.431 |  | 175.324 |  | 906.431 |  | 131.493 |  | 1213.248 |  | 0 |  | 0
6.1 |  | Profile |  |  |  |  | 1/500 |  | (km) | 438.31 |  |  | 1.2 | 525.972 | 3.2 | 1402.592 | 3.2 | 1402.592 | 2.4 | 1051.944 | 3.6 | 1577.916 | 2.8 | 1227.268 | 2.8 | 1227.268 | 0 | 0 | 2 | 876.62 | 1.2 | 525.972 | 2.8 | 1227.268 | 2.8 | 1227.268 | 1.6 | 701.296 | 2.8 | 1227.268 | 3.6 | 1577.916 | 2 | 876.62 | 0 | 0 | 0 | 0 | 1.2 | 525.972 | 1.2 | 525.972 | 0.8 | 350.648 | 0.4 | 175.324 | 0 | 0 | 0.4 | 175.324 | 0 | 0 | 0.4 | 175.324
6.2 |  | Profile |  |  |  |  | 1/200 |  | (km) | 438.31 |  |  | 0.2 | 87.662 | 0 | 0 | 0.2 | 87.662 | 0.4 | 175.324 | 0.1 | 43.831 | 0.2 | 87.662 | 0.1 | 43.831 | 0.1 | 43.831 | 0.1 | 43.831 | 0.1 | 43.831 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 131.493 | 0.1 | 43.831 | 0.4 | 175.324 | 0.2 | 87.662 | 0.5 | 219.155 | 0.1 | 43.831 | 0.9 | 394.479 | 0.1 | 43.831 | 0.1 | 43.831 | 0.4 | 175.324 | 0.1 | 43.831 | 0.3 | 131.493 | 0.8 | 350.648
6.3 |  | Cross-section |  |  |  |  | 1/200 |  | (km) | 572.73 |  |  | 3.6 | 2061.828 | 9.6 | 5498.208 | 10 | 5727.3 | 7.6 | 4352.748 | 10.8 | 6185.484 | 8.4 | 4810.932 | 8.4 | 4810.932 | 0 | 0 | 6 | 3436.38 | 3.8 | 2176.374 | 8.4 | 4810.932 | 8.4 | 4810.932 | 4.8 | 2749.104 | 8.6 | 4925.478 | 10.8 | 6185.484 | 6 | 3436.38 |  |  | 0 | 0 | 3.6 | 2061.828 | 3.6 | 2061.828 | 2.4 | 1374.552 | 1.2 | 687.276 | 0 | 0 | 1.2 | 687.276 | 0 | 0 | 1.2 | 687.276
7 |  | Culvert Pipe (CP) |  |  |  |  | 0 |  | 0 | 0 |  |  |  | 131.493 |  | 0 |  | 87.662 |  | 43.831 |  | 0 |  | 0 |  | 87.662 |  | 43.831 |  | 0 |  | 0 |  | 43.831 |  | 87.662 |  | 0 |  | 43.831 |  | 43.831 |  | 43.831 |  | 43.831 |  | 87.662 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7.1 |  | Profile |  |  |  |  | 1/200 |  | (km) | 438.31 |  |  | 0.3 | 131.493 | 0 | 0 | 0.2 | 87.662 | 0.1 | 43.831 | 0 | 0 | 0 | 0 | 0.2 | 87.662 | 0.1 | 43.831 | 0 | 0 | 0 | 0 | 0.1 | 43.831 | 0.2 | 87.662 | 0 | 0 | 0.1 | 43.831 | 0.1 | 43.831 | 0.1 | 43.831 | 0.1 | 43.831 | 0.2 | 87.662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Canal (Re-alignment) | [11 empty] | 0 |  | 728.5342 |  | 1583.77 |  | 882.5281 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 223.0427 |  | 0 |  | 0 |  | 0 |  | 601.8326 |  | 1991.6054 |  | 190.0524 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8.1 |  | Profile |  |  |  |  | 1/500 |  | (km) | 438.31 |  |  |  |  | 0.46 | 201.6226 | 1 | 438.31 | 0.55 | 241.0705 | [10 empty] | 0.143 | 62.6783 | [6 empty] | 0.38 | 166.5578 | 1.251 | 548.3258 | 0.12 | 52.5972
8.2 |  | Cross-section |  |  |  |  | 1/200 |  | (km) | 572.73 |  |  |  |  | 0.92 | 526.9116 | 2 | 1145.46 | 1.12 | 641.4576 | [10 empty] | 0.28 | 160.3644 | [6 empty] | 0.76 | 435.2748 | 2.52 | 1443.2796 | 0.24 | 137.4552
9 |  | Interchange (IC) |  |  |  |  | 0 |  | 0 | 0 |  |  |  | 25159.4701 |  | 0 |  | 0 |  | 0 |  | 14687.1963 |  | 0 |  | 0 |  | 0 |  | 15601.5505 |  | 0 |  | 0 |  | 0 |  | 0 |  | 14651.4646 |  | 0 |  | 0 |  | 0 |  | 12864.3736 |  | 0 |  | 0 |  | 11693.0252 |  | 0 |  | 12928.8934 |  | 0 |  | 12588.7622 |  | 7177.1054 |  | 0 |  | 0
9.1 |  | Secondary Control Point |  |  |  |  | Class II |  | (nos.) | 150.63 |  |  | 8 | 1205.04 | [6 empty] | 8 | 1205.04 | [6 empty] | 8 | 1205.04 | [8 empty] | 8 | 1205.04 | [6 empty] | 8 | 1205.04 |  |  |  |  | 8 | 1205.04 |  |  | 8 | 1205.04 |  |  | 8 | 1205.04 | 8 | 1205.04
9.2 |  | Secondary Leveling Network |  |  |  |  | 0 |  | (km) | 67.29 |  |  | 2 | 134.58 | [6 empty] | 2 | 134.58 | [6 empty] | 2 | 134.58 | [8 empty] | 2 | 134.58 | [6 empty] | 2 | 134.58 |  |  |  |  | 2 | 134.58 |  |  | 2 | 134.58 |  |  | 2 | 134.58 | 2 | 134.58
9.3 |  | Planimetric |  |  |  |  | 1/500 |  | (ha) | 175.36 |  |  | 60 | 10521.6 | [6 empty] | 27 | 4734.72 | [6 empty] | 33 | 5786.88 | [8 empty] | 28 | 4910.08 | [6 empty] | 28 | 4910.08 |  |  |  |  | 28 | 4910.08 |  |  | 28 | 4910.08 |  |  | 28 | 4910.08 | 16 | 2805.76
9.4 |  | Profile (Rampway) |  |  |  |  | 1/1,000; 1/100 |  | (km) | 438.31 |  |  | 3.86 | 1691.8766 | [6 empty] | 2.5 | 1095.775 | [6 empty] | 2.46 | 1078.2426 | [8 empty] | 2.43 | 1065.0933 | [6 empty] | 1.92 | 841.5552 |  |  |  |  | 1.58 | 692.5298 |  |  | 1.93 | 845.9383 |  |  | 1.84 | 806.4904 | 0.88 | 385.7128
9.5 |  | Cross-section (Rampway) |  |  |  |  | 1/200 |  | (km) | 572.73 |  |  | 20.265 | 11606.3735 | [6 empty] | 13.125 | 7517.0813 | [6 empty] | 12.915 | 7396.808 | [8 empty] | 12.81 | 7336.6713 | [6 empty] | 10.08 | 5773.1184 |  |  |  |  | 8.295 | 4750.7954 |  |  | 10.185 | 5833.2551 |  |  | 9.66 | 5532.5718 | 4.62 | 2646.0126
10 |  | Building (BL) |  |  |  |  | 0 |  | 0 | 0 |  |  |  | 491.008 |  | 498.0224 |  | 0 |  | 0 |  | 0 |  | 0 |  | 315.648 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 171.8528 |  | 1297.664 |  | 0 |  | 0 |  | 0 |  | 0 |  | 315.648 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 498.0224 |  | 0 |  | 0
10.1 |  | Planimetric |  |  |  |  | 1/500 |  | (ha) | 175.36 |  |  | 2.8 | 491.008 | 2.84 | 498.0224 | [8 empty] | 1.8 | 315.648 | [12 empty] | 0.98 | 171.8528 | 7.4 | 1297.664 | [8 empty] | 1.8 | 315.648 | [10 empty] | 2.84 | 498.0224
C |  | Linking Road |  |  |  |  | 0 |  | 0 | 0 |  |  |  | 1564.04 |  | 0 |  | 0 |  | 0 |  | 1564.04 |  | 0 |  | 0 |  | 0 |  | 1564.04 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1564.04 |  | 0 |  | 0 |  | 0 |  | 1564.04 |  | 0 |  | 0 |  | 1564.04 |  | 0 |  | 1564.04 |  | 0 |  | 1564.04 |  | 1564.04 |  | 15056.8303 |  | 13089.6761
11 |  | Main Line (ML, Road Section) |  |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 12486.993 |  | 10060.1503
11.1 |  | Planimetric |  |  |  |  | 1/1,000 |  | (ha) | 61.29 | [54 empty] | 43.96 | 2694.3084 | 35.29 | 2162.9241
11.2 |  | Profile |  |  |  |  | 1/1,000; 1/100 |  | (km) | 438.31 | [54 empty] | 4.396 | 1926.8108 | 3.529 | 1546.796
11.3 |  | Cross-section |  |  |  |  | 1/200 |  | (km) | 572.73 | [54 empty] | 13.734 | 7865.8738 | 11.088 | 6350.4302
12 |  | Bridge (BR) |  |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1391.6039 |  | 722.0933
12.1 |  | Secondary Control Point |  |  |  |  | Class II |  | (nos.) | 150.63 | [54 empty] | 4 | 602.52 | 2 | 301.26
12.2 |  | Planimetric (On Shore) |  |  |  |  | 1/500 |  | (ha) | 175.36 | [54 empty] | 1.62 | 284.0832 | 0.6 | 105.216
12.3 |  | Planimetric (Off Shore) |  |  |  |  | 1/500 |  | (ha) | 226.18 | [54 empty] | 0.42 | 94.9956 | 0.33 | 74.6394
12.4 |  | Profile (On Shore) |  |  |  |  | 1/500 |  | (km) | 438.31 | [54 empty] | 0.162 | 71.0062 | 0.06 | 26.2986
12.5 |  | Profile (Off Shore) |  |  |  |  | 1/500 |  | (km) | 474.97 | [54 empty] | 0.042 | 19.9487 | 0.033 | 15.674
12.6 |  | Cross-section (Approach Road) |  |  |  |  | 1/200 |  | (km) | 572.73 | [54 empty] | 0.378 | 216.4919 | 0.189 | 108.246
12.7 |  | River Profile |  |  |  |  | 1/1,000; 1/100 |  | (km) | 474.97 | [54 empty] | 0.1 | 47.497 | 0.1 | 47.497
12.8 |  | River Cross-section |  |  |  |  | 1/200 |  | (km) | 655.49 | [54 empty] | 0.084 | 55.0612 | 0.066 | 43.2623
13 |  | Culvert Box (CB) |  |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 525.972 |  | 525.972
13.1 |  | Profile |  |  |  |  | 1/500 |  | (km) | 438.31 | [54 empty] | 0 | 0 | 0 | 0
13.2 |  | Profile |  |  |  |  | 1/200 |  | (km) | 438.31 | [54 empty] | 1.2 | 525.972 | 1.2 | 525.972
13.3 |  | Cross-section |  |  |  |  | 1/200 |  | (km) | 572.73 | [54 empty] | 0 | 0 | 0 | 0
14 |  | Culvert Pipe (CP) |  |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14.1 |  | Profile |  |  |  |  | 1/200 |  | (km) | 438.31 | [54 empty] | 0 | 0 | 0 | 0
15 |  | Intersection (IS, NH1A) |  |  |  |  | 0 |  | 0 | 0 |  |  |  | 1564.04 |  | 0 |  | 0 |  | 0 |  | 1564.04 |  | 0 |  | 0 |  | 0 |  | 1564.04 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1564.04 |  | 0 |  | 0 |  | 0 |  | 1564.04 |  | 0 |  | 0 |  | 1564.04 |  | 0 |  | 1564.04 |  | 0 |  | 1564.04 |  | 1564.04 |  | 652.2615 |  | 1781.4605
15.1 |  | Planimetric |  |  |  |  | 1/500 |  | (ha) | 175.36 |  |  | 4 | 701.44 | [6 empty] | 4 | 701.44 | [6 empty] | 4 | 701.44 | [8 empty] | 4 | 701.44 | [6 empty] | 4 | 701.44 |  |  |  |  | 4 | 701.44 |  |  | 4 | 701.44 |  |  | 4 | 701.44 | 4 | 701.44 | 1.5 | 263.04 | 4.5 | 789.12
15.2 |  | Profile |  |  |  |  | 1/1,000; 1/100 |  | (km) | 438.31 |  |  | 0.4 | 175.324 | [6 empty] | 0.4 | 175.324 | [6 empty] | 0.4 | 175.324 | [8 empty] | 0.4 | 175.324 | [6 empty] | 0.4 | 175.324 |  |  |  |  | 0.4 | 175.324 |  |  | 0.4 | 175.324 |  |  | 0.4 | 175.324 | 0.4 | 175.324 | 0.3 | 131.493 | 0.5 | 219.155
15.3 |  | Cross-section |  |  |  |  | 1/200 |  | (km) | 572.73 |  |  | 1.2 | 687.276 | [6 empty] | 1.2 | 687.276 | [6 empty] | 1.2 | 687.276 | [8 empty] | 1.2 | 687.276 | [6 empty] | 1.2 | 687.276 |  |  |  |  | 1.2 | 687.276 |  |  | 1.2 | 687.276 |  |  | 1.2 | 687.276 | 1.2 | 687.276 | 0.45 | 257.7285 | 1.35 | 773.1855
D |  | Mobilization and Temporary Camp Yard |  |  |  |  | 2% | of A+B+C | 0 |  |  | 3182.9982 |  | 1346.6078 |  | 649.6131 |  | 857.9544 |  | 673.9335 |  | 1227.4898 |  | 637.8049 |  | 739.6637 |  | 353.2532 |  | 1307.135 |  | 651.6534 |  | 773.659 |  | 614.8889 |  | 582.5741 |  | 1036.7223 |  | 1005.9348 |  | 697.0591 |  | 725.0963 |  | 979.1094 |  | 809.0583 |  | 867.3443 |  | 890.9434 |  | 700.0398 |  | 947.2962 |  | 790.4684 |  | 948.2114 |  | 1070.3013 |  | 301.1366 |  | 261.7935
E |  | Reporting |  |  |  |  | 2% | of A+B+C | 0 |  |  | 3182.9982 |  | 1346.6078 |  | 649.6131 |  | 857.9544 |  | 673.9335 |  | 1227.4898 |  | 637.8049 |  | 739.6637 |  | 353.2532 |  | 1307.135 |  | 651.6534 |  | 773.659 |  | 614.8889 |  | 582.5741 |  | 1036.7223 |  | 1005.9348 |  | 697.0591 |  | 725.0963 |  | 979.1094 |  | 809.0583 |  | 867.3443 |  | 890.9434 |  | 700.0398 |  | 947.2962 |  | 790.4684 |  | 948.2114 |  | 1070.3013 |  | 301.1366 |  | 261.7935
Total | [11 empty] | 165515.9064 |  | 70023.6081 |  | 33779.879 |  | 44613.6279 |  | 35044.5414 |  | 63829.4711 |  | 33165.8554 |  | 38462.5118 |  | 18369.1667 |  | 67971.0219 |  | 33885.9765 |  | 40230.2682 |  | 31974.2213 |  | 30293.8536 |  | 53909.5608 |  | 52308.6073 |  | 36247.0726 |  | 37705.0064 |  | 50913.6907 |  | 42071.0297 |  | 45101.9015 |  | 46329.0556 |  | 36402.0673 |  | 49259.4023 |  | 41104.3569 |  | 49306.9939 |  | 55655.6652 |  | 15659.1036 |  | 13613.2632
[12 empty] | 12.42% |  | 5.254% |  | 2.535% |  | 3.347% |  | 2.629% |  | 4.789% |  | 2.489% |  | 2.886% |  | 1.378% |  | 5.1% |  | 2.543% |  | 3.019% |  | 2.399% |  | 2.273% |  | 4.045% |  | 3.925% |  | 2.72% |  | 2.829% |  | 3.82% |  | 3.157% |  | 3.384% |  | 3.476% |  | 2.731% |  | 3.696% |  | 3.084% |  | 3.7% |  | 4.176% |  | 1.175% |  | 1.021%
Exchange Rate |  |  | 1 USD | = | 20800 | (exchange selling rate, 20 May 2011, Vietcombank)
Unit Price |  |  | 10% | Discount from Standard Unit Price (Quang Nam Province, 2011)
1332746.6864
1332746.6864

## 4.1Plan
Jurisdiction |  | Construction | List of Facilities | [23 empty] | Survey Section |  |  | Equation | Section | Remarks
|  | Contract No. | Expressway | [17 empty] | Linking Road | [5 empty] | BP - EP |  |  |  | Length
|  |  | Main Line | [10 empty] | Canal | Flyover | Interchange |  |  |  | Building | Main Line |  |  |  |  | Intersection
|  |  | ML | TN | BR | [5 empty] | CB |  | CP | CN | BR | IC | BR | CB | CP | BL | ML | BR |  | CB | CP | IS
[5 empty] | LRB | ORB | SB | CB | VD | OP | WT | RD |  |  | FO |  | IRB | WT |  |  |  | ORB | VD | WT
| Danang | PKG01 | ML01-1 | [23 empty] | -800 | - | 4050 |  | 4850
|  |  | ML001 | [23 empty] | -800 | - | -174.55 |  | 625.45
[5 empty] | VD: VD01 | [14 empty] | -174.55 | - | -65.45 |  | 109.1 |  | Widening (Existing BR on Danang Bypass)
|  |  | ML002 | [23 empty] | -65.45 | - | 1047.425 |  | 1112.875
[5 empty] | LRB: LRB01 | [14 empty] | 1047.425 | - | 2190.575 |  | 1143.15
|  |  | ML003 | [23 empty] | 2190.575 | - | 2319.35 |  | 128.775
[5 empty] | LRB: LRB02 | [14 empty] | 2319.35 | - | 2700.65 |  | 381.3
|  |  | ML004 | [23 empty] | 2700.65 | - | 4050 |  | 1349.35 |  |  | 4850
[5 empty] | WT: WT001 | [14 empty] | -155 | [5 empty] | Widening (Existing CB(WT) on Danang Bypass)
[16 empty] | IC01 | [10 empty] | 0 | [5 empty] | Tuy Loan IC
[17 empty] | IRB01 | [9 empty] | 0 | [5 empty] | IR (Tuy Loan IC)
[17 empty] | IRB02 | [9 empty] | 0 | [5 empty] | IR (Tuy Loan IC)
[19 empty] | CP159 | [7 empty] | 0 | [5 empty] | IR (Tuy Loan IC)
[26 empty] | IS01 | 0 | [5 empty] | NH14B (Tuy Loan IC)
[15 empty] | FO01 | [11 empty] | 0 | [5 empty] | NH14B
[13 empty] | CP001 | [13 empty] | 62
[13 empty] | CP002 | [13 empty] | 431
[15 empty] | FO02 | [11 empty] | 590
[13 empty] | CP003 | [13 empty] | 885
[20 empty] | BL01 | [6 empty] | 950 | [5 empty] | TMC
[5 empty] | WT: WT002 | [14 empty] | 1160
[5 empty] | RD: RD001 | [14 empty] | 1162
[5 empty] | RD: RD002 | [14 empty] | 3049
[13 empty] | CP004 | [13 empty] | 3211 | [5 empty] | Connect to/from CN01
[14 empty] | CN01 | [12 empty] | 3211 | [5 empty] | Connect to/from CP004
[13 empty] | CP005 | [13 empty] | 3512
[5 empty] | RD: RD003 | [14 empty] | 3692
|  |  | ML01-2 | [23 empty] | 3950 | - | 8050 |  | 4100
|  |  | ML005 | [23 empty] | 3950 | - | 5466.4 |  | 1516.4
[5 empty] | LRB: LRB03 | [14 empty] | 5466.4 | - | 5708.275 |  | 241.875 |  | Continuous BR Survey Section
[5 empty] | OP: OP01 | [14 empty] | 5708.275 | - | 5793.05 |  | 84.775
|  |  | ML006 | [23 empty] | 5793.05 | - | 7884.45 |  | 2091.4
[5 empty] | OP: OP02 | [14 empty] | 7884.45 | - | 7967.55 |  | 83.1
|  |  | ML007 | [23 empty] | 7967.55 | - | 8050 |  | 82.45 |  |  | 4100
[5 empty] | RD: RD004 | [14 empty] | 4281
[5 empty] | RD: RD005 | [14 empty] | 4528
[20 empty] | BL02 | [6 empty] | 4750 | [5 empty] | TB including TP and TPO
[13 empty] | CP006 | [13 empty] | 4926
[5 empty] | RD: RD006 | [14 empty] | 4929
[5 empty] | RD: RD007 | [14 empty] | 5239
[5 empty] | RD: RD008 | [14 empty] | 5517
[13 empty] | CP007 | [13 empty] | 5520
[5 empty] | RD: RD009 | [14 empty] | 5678
[13 empty] | CP008 | [13 empty] | 5681
[13 empty] | CP009 | [13 empty] | 5761
[5 empty] | RD: RD010 | [14 empty] | 6031
[5 empty] | RD: RD011 | [14 empty] | 7364
| Quang Nam | PKG02 | ML02-1 | [23 empty] | 7950 | - | 13050 |  | 5100
|  |  | ML008 | [23 empty] | 7950 | - | 9678.35 |  | 1728.35
[5 empty] | LRB: LRB04 | [14 empty] | 9678.35 | - | 10061.65 |  | 383.3
|  |  | ML009 | [23 empty] | 10061.65 | - | 10175.9 |  | 114.25
[5 empty] | VD: VD02 | [14 empty] | 10175.9 | - | 10366.1 |  | 190.2
|  |  | ML010 | [23 empty] | 10366.1 | - | 10723.4 |  | 357.3
[5 empty] | LRB: LRB05 | [14 empty] | 10723.4 | - | 11040.6 |  | 317.2
|  |  | ML011 | [23 empty] | 11040.6 | - | 11728.875 |  | 688.275
[5 empty] | VD: VD03 | [14 empty] | 11728.875 | - | 12079.125 |  | 350.25
|  |  | ML012 | [23 empty] | 12079.125 | - | 12545.9 |  | 466.775
[5 empty] | ORB: ORB01 | [14 empty] | 12545.9 | - | 12732.1 |  | 186.2
|  |  | ML013 | [23 empty] | 12732.1 | - | 13050 |  | 317.9 |  |  | 5100
[13 empty] | CP010 | [13 empty] | 8220 | [5 empty] | Connect to/from CN02
[14 empty] | CN02 | [12 empty] | 8220 | [5 empty] | Connect to/from CP010
[13 empty] | CP011 | [13 empty] | 8738
[5 empty] | RD: RD012 | [14 empty] | 9028
[5 empty] | RD: RD013 | [14 empty] | 9300
[5 empty] | WT: WT003 | [14 empty] | 9391 | [5 empty] | Connect to/from CN03
[14 empty] | CN03 | [12 empty] | 9391 | [5 empty] | Connect to/from WT003
[5 empty] | RD: RD014 | [14 empty] | 9434
[15 empty] | FO03 | [11 empty] | 9585
[5 empty] | RD: RD015 | [14 empty] | 9772
[13 empty] | CP012 | [13 empty] | 9774
[13 empty] | CP013 | [13 empty] | 10763
[5 empty] | RD: RD016 | [14 empty] | 10766
[5 empty] | WT: WT004 | [14 empty] | 11088 | [5 empty] | Connect to/from CN04
[14 empty] | CN04 | [12 empty] | 11088 | [5 empty] | Connect to/from WT004
[5 empty] | RD: RD017 | [14 empty] | 11270
[13 empty] | CP014 | [13 empty] | 11272
[5 empty] | RD: RD018 | [14 empty] | 11519
[13 empty] | CP015 | [13 empty] | 12012
[5 empty] | RD: RD019 | [14 empty] | 12256
[13 empty] | CP016 | [13 empty] | 12256
[13 empty] | CP017 | [13 empty] | 12427
[13 empty] | CP018 | [13 empty] | 12753 | [5 empty] | Connect to/from CN05
[14 empty] | CN05 | [12 empty] | 12753 | [5 empty] | Connect to/from CP018
|  |  | ML02-2 | [23 empty] | 12950 | - | 17050 |  | 4100
|  |  | ML014 | [23 empty] | 12950 | - | 13040.85 |  | 90.85
[5 empty] | VD: VD04 | [14 empty] | 13040.85 | - | 13379.15 |  | 338.3
|  |  | ML015 | [23 empty] | 13379.15 | - | 13574.95 |  | 195.8
[5 empty] | OP: OP03 | [14 empty] | 13574.95 | - | 13677.05 |  | 102.1
|  |  | ML016 | [23 empty] | 13677.05 | - | 13868.4 |  | 191.35
[5 empty] | LRB: LRB06 | [14 empty] | 13868.4 | - | 14185.6 |  | 317.2
|  |  | ML017 | [23 empty] | 14185.6 | - | 14714.4 |  | 528.8
[5 empty] | VD: VD05 | [14 empty] | 14714.4 | - | 15022 |  | 307.6 |  | Continuous BR Survey Section
[5 empty] | VD: VD06 | [14 empty] | 15022 | - | 15329.6 |  | 307.6
|  |  | ML018 | [23 empty] | 15329.6 | - | 16338.4 |  | 1008.8
[5 empty] | LRB: LRB07 | [14 empty] | 16338.4 | - | 16655.6 |  | 317.2
|  |  | ML019 | [23 empty] | 16655.6 | - | 17050 |  | 394.4 |  |  | 4100
[5 empty] | WT: WT005 | [14 empty] | 13028 | [5 empty] | Connect to/from CN06
[14 empty] | CN06 | [12 empty] | 13028 | [5 empty] | Connect to/from WT005
[13 empty] | CP019 | [13 empty] | 13162
[13 empty] | CP020 | [13 empty] | 13460
[5 empty] | RD: RD020 | [14 empty] | 14122
[5 empty] | WT: WT006 | [14 empty] | 14269
[5 empty] | RD: RD021 | [14 empty] | 14376
[5 empty] | RD: RD022 | [14 empty] | 14468
[5 empty] | WT: WT007 | [14 empty] | 14700 | [5 empty] | Connect to/from CN07
[14 empty] | CN07 | [12 empty] | 14700 | [5 empty] | Connect to/from WT007
[5 empty] | WT: WT008 | [14 empty] | 14946
[13 empty] | CP021 | [13 empty] | 15409
[13 empty] | CP022 | [13 empty] | 15593
[13 empty] | CP023 | [13 empty] | 15848 | [5 empty] | Connect to/from CN08
[14 empty] | CN08 | [12 empty] | 15848 | [5 empty] | Connect to/from CP023
[5 empty] | RD: RD023 | [14 empty] | 16193
[5 empty] | RD: RD024 | [14 empty] | 16775
[5 empty] | RD: RD025 | [14 empty] | 16943
| Quang Nam | PKG03 | ML03-1 | [23 empty] | 16950 | - | 22050 | -59.78 | 5159.78 |  | Back: KM019+259.78, Ahead: KM019+200
[5 empty] | LRB: LRB08 | [14 empty] | 16950 | - | 18209.45 |  | 1259.45 |  | Approach Road (BP Side) < 50 m
[5 empty] | VD: VD07 | [14 empty] | 18209.45 | - | 18412.1 |  | 202.65 |  | Continuous BR Survey Section
|  |  | ML020 | [23 empty] | 18412.1 | - | 18530.925 |  | 118.825
[5 empty] | VD: VD08 | [14 empty] | 18530.925 | - | 18715.4875 |  | 184.5625 |  | Continuous BR Survey Section
[5 empty] | VD: VD09 | [14 empty] | 18715.4875 | - | 18924.1 |  | 208.6125
|  |  | ML021 | [23 empty] | 18924.1 | - | 19165.95 |  | 241.85
[5 empty] | OP: OP04 | [14 empty] | 19165.95 | - | 19214.47 | -59.78 | 108.3 |  | Continuous BR Survey Section
[5 empty] | VD: VD10 | [14 empty] | 19214.47 | - | 19403.55 |  | 129.3
|  |  | ML022 | [23 empty] | 19403.55 | - | 19780 |  | 376.45
[5 empty] | LRB: LRB09 | [14 empty] | 19780 | - | 20590 |  | 810
|  |  | ML023 | [23 empty] | 20590 | - | 21846.45 |  | 1256.45
[5 empty] | VD: VD11 | [14 empty] | 21846.45 | - | 21953.55 |  | 107.1
|  |  | ML024 | [23 empty] | 21953.55 | - | 22050 |  | 96.45 |  |  | 5100
[5 empty] | RD: RD026 | [14 empty] | 18062
[5 empty] | RD: RD027 | [14 empty] | 18221
[5 empty] | WT: WT009 | [14 empty] | 19060
[5 empty] | RD: RD028 | [14 empty] | 19095
[5 empty] | RD: RD029 | [14 empty] | 19380
[5 empty] | RD: RD030 | [14 empty] | 19570
[5 empty] | RD: RD031 | [14 empty] | 19680
[16 empty] | IC02 | [10 empty] | 20805 | [5 empty] | My Son IC (Including TG, TP and TPO)
[17 empty] | IRB03 | [9 empty] | 20805 | [5 empty] | IR (My Son IC)
[19 empty] | CP160 | [7 empty] | 20805 | [5 empty] | IR (My Son IC)
[19 empty] | CP161 | [7 empty] | 20805 | [5 empty] | IR (My Son IC)
[26 empty] | IS02 | 20805 | [5 empty] | DR610 (My Son IC)
[5 empty] | RD: RD032 | [14 empty] | 21000
[5 empty] | RD: RD033 | [14 empty] | 21150
[5 empty] | RD: RD034 | [14 empty] | 21500
| Quang Nam | PKG04 | ML04-1 | [23 empty] | 21950 | - | 26850 |  | 4900
|  |  | ML025 | [23 empty] | 21950 | - | 22630 |  | 680
|  |  |  | TN01 | [22 empty] | 22630 | - | 23170 |  | 540 |  | At Portals: 0.60 ha (BP Side), 0.42 ha (EP Side)
|  |  | ML026 | [23 empty] | 23170 | - | 23268.925 |  | 98.925
[5 empty] | SB: SB01 | [14 empty] | 23268.925 | - | 23431.075 |  | 162.15
|  |  | ML027 | [23 empty] | 23431.075 | - | 24386.95 |  | 955.875
[5 empty] | OP: OP05 | [14 empty] | 24386.95 | - | 24473.05 |  | 86.1
|  |  | ML028 | [23 empty] | 24473.05 | - | 24559.175 |  | 86.125
[5 empty] | ORB: ORB02 | [14 empty] | 24559.175 | - | 24736.825 |  | 177.65
|  |  | ML029 | [23 empty] | 24736.825 | - | 25018.95 |  | 282.125
[5 empty] | OP: OP06 | [14 empty] | 25018.95 | - | 25105.05 |  | 86.1
|  |  | ML030 | [23 empty] | 25105.05 | - | 25671.95 |  | 566.9
[5 empty] | SB: SB02 | [14 empty] | 25671.95 | - | 25768.05 |  | 96.1
|  |  | ML031 | [23 empty] | 25768.05 | - | 26850 |  | 1081.95 |  |  | 4900
[5 empty] | RD: RD035 | [14 empty] | 22200
[5 empty] | RD: RD036 | [14 empty] | 23310
[5 empty] | RD: RD037 | [14 empty] | 24100
[13 empty] | CP024 | [13 empty] | 24200
[5 empty] | RD: RD038 | [14 empty] | 24600
[5 empty] | RD: RD039 | [14 empty] | 24760
[5 empty] | RD: RD040 | [14 empty] | 25200
[5 empty] | RD: RD041 | [14 empty] | 26000
[5 empty] | WT: WT010 | [14 empty] | 26100
[5 empty] | WT: WT011 | [14 empty] | 26480
|  |  | ML04-2 | [23 empty] | 26750 | - | 32050 |  | 5300
|  |  | ML032 | [23 empty] | 26750 | - | 26952.95 |  | 202.95
[5 empty] | VD: VD12 | [14 empty] | 26952.95 | - | 27047.05 |  | 94.1
|  |  | ML033 | [23 empty] | 27047.05 | - | 27856.95 |  | 809.9
[5 empty] | VD: VD13 | [14 empty] | 27856.95 | - | 27943.05 |  | 86.1
|  |  | ML034 | [23 empty] | 27943.05 | - | 28734.95 |  | 791.9
[5 empty] | OP: OP07 | [14 empty] | 28734.95 | - | 28821.05 |  | 86.1
|  |  | ML035 | [23 empty] | 28821.05 | - | 29411.175 |  | 590.125
[5 empty] | SB: SB03 | [14 empty] | 29411.175 | - | 29588.825 |  | 177.65
|  |  | ML036 | [23 empty] | 29588.825 | - | 31906.95 |  | 2318.125
[5 empty] | OP: OP08 | [14 empty] | 31906.95 | - | 31993.05 |  | 86.1
|  |  | ML037 | [23 empty] | 31993.05 | - | 32050 |  | 56.95 |  |  | 5300
[5 empty] | WT: WT012 | [14 empty] | 27200
[13 empty] | CP025 | [13 empty] | 27550
[13 empty] | CP026 | [13 empty] | 27950
[13 empty] | CP027 | [13 empty] | 28200
[13 empty] | CP028 | [13 empty] | 28850
[13 empty] | CP029 | [13 empty] | 29000
[20 empty] | BL03 | [6 empty] | 29130 | [5 empty] | PA
[13 empty] | CP030 | [13 empty] | 29650
[5 empty] | RD: RD042 | [14 empty] | 29260
[5 empty] | RD: RD043 | [14 empty] | 30020
[13 empty] | CP031 | [13 empty] | 30200
[5 empty] | RD: RD044 | [14 empty] | 30210
[5 empty] | RD: RD045 | [14 empty] | 30300
[13 empty] | CP032 | [13 empty] | 30400
[5 empty] | RD: RD046 | [14 empty] | 30700
[13 empty] | CP033 | [13 empty] | 31200
[5 empty] | RD: RD047 | [14 empty] | 31300
[5 empty] | RD: RD048 | [14 empty] | 32000
| Quang Nam | PKG05 | ML05-1 | [23 empty] | 31950 | - | 35050 |  | 3100
|  |  | ML038 | [23 empty] | 31950 | - | 32396.95 |  | 446.95
[5 empty] | VD: VD14 | [14 empty] | 32396.95 | - | 32483.05 |  | 86.1
|  |  | ML039 | [23 empty] | 32483.05 | - | 34034.925 |  | 1551.875
[5 empty] | VD: VD15 | [14 empty] | 34034.925 | - | 34205.075 |  | 170.15
|  |  | ML040 | [23 empty] | 34205.075 | - | 35050 |  | 844.925 |  |  | 3100
[13 empty] | CP034 | [13 empty] | 32600
[13 empty] | CP035 | [13 empty] | 32750
[13 empty] | CP036 | [13 empty] | 33100
[13 empty] | CP037 | [13 empty] | 33400
[13 empty] | CP038 | [13 empty] | 33850
[5 empty] | WT: WT013 | [14 empty] | 34200
[13 empty] | CP039 | [13 empty] | 34300
|  |  | ML05-2 | [23 empty] | 34950 | - | 42050 |  | 7100
|  |  | ML041 | [23 empty] | 34950 | - | 35305.5 |  | 355.5
[5 empty] | OP: OP09 | [14 empty] | 35305.5 | - | 35400.5 |  | 95
|  |  | ML042 | [23 empty] | 35400.5 | - | 36120 |  | 719.5
[5 empty] | ORB: ORB03 | [14 empty] | 36120 | - | 36280 |  | 160
|  |  | ML043 | [23 empty] | 36280 | - | 36738 |  | 458
[5 empty] | SB: SB04 | [14 empty] | 36738 | - | 36822 |  | 84
|  |  | ML044 | [23 empty] | 36822 | - | 38116 |  | 1294
[5 empty] | LRB: LRB10 | [14 empty] | 38116 | - | 38458 |  | 342
|  |  | ML045 | [23 empty] | 38458 | - | 38747.5 |  | 289.5
[5 empty] | OP: OP10 | [14 empty] | 38747.5 | - | 38826.5 |  | 79
|  |  | ML046 | [23 empty] | 38826.5 | - | 39362 |  | 535.5
[5 empty] | LRB: LRB11 | [14 empty] | 39362 | - | 39738 |  | 376
|  |  | ML047 | [23 empty] | 39738 | - | 39954 |  | 216
[5 empty] | CB: CB01 | [14 empty] | 39954 | - | 40036 |  | 82
|  |  | ML048 | [23 empty] | 40036 | - | 41072 |  | 1036
[5 empty] | OP: OP11 | [14 empty] | 41072 | - | 41170 |  | 98
|  |  | ML049 | [23 empty] | 41170 | - | 42050 |  | 880 |  |  | 7100
[13 empty] | CP040 | [13 empty] | 35050
[13 empty] | CP041 | [13 empty] | 35480
[5 empty] | WT: WT014 | [14 empty] | 35860
[5 empty] | RD: RD049 | [14 empty] | 36580
[13 empty] | CP042 | [13 empty] | 36600
[5 empty] | RD: RD050 | [14 empty] | 37560
[13 empty] | CP043 | [13 empty] | 37600
[13 empty] | CP044 | [13 empty] | 37900
[5 empty] | RD: RD051 | [14 empty] | 38880
[13 empty] | CP045 | [13 empty] | 39950
[5 empty] | RD: RD052 | [14 empty] | 40360
[13 empty] | CP046 | [13 empty] | 40550
[16 empty] | IC03 | [10 empty] | 40776 | [5 empty] | Ha Lam IC (Including TG, TP and TPO)
[17 empty] | IRB04 | [9 empty] | 40776 | [5 empty] | IR (Ha Lam IC)
[26 empty] | IS03 | 40776 | [5 empty] | NH14E (Ha Lam IC)
[13 empty] | CP047 | [13 empty] | 40800
[5 empty] | RD: RD053 | [14 empty] | 41560
[13 empty] | CP048 | [13 empty] | 41750
| Quang Nam | PKG06 | ML06-1 | [23 empty] | 41950 | - | 46650 |  | 4700
[5 empty] | CB: CB02 | [14 empty] | 41950 | - | 42137 |  | 187 |  | Approach Road (BP Side) < 50 m
|  |  | ML050 | [23 empty] | 42137 | - | 42549 |  | 412
[5 empty] | OP: OP12 | [14 empty] | 42549 | - | 42643 |  | 94
|  |  | ML051 | [23 empty] | 42643 | - | 43478.5 |  | 835.5
[5 empty] | CB: CB03 | [14 empty] | 43478.5 | - | 43561.5 |  | 83
|  |  | ML052 | [23 empty] | 43561.5 | - | 44221 |  | 659.5
[5 empty] | ORB: ORB04 | [14 empty] | 44221 | - | 44379 |  | 158
|  |  | ML053 | [23 empty] | 44379 | - | 45265.5 |  | 886.5
[5 empty] | SB: SB05 | [14 empty] | 45265.5 | - | 45346.5 |  | 81
|  |  | ML054 | [23 empty] | 45346.5 | - | 45482.5 |  | 136
[5 empty] | CB: CB04 | [14 empty] | 45482.5 | - | 45620.75 |  | 138.25 |  | Continuous BR Survey Section
[5 empty] | LRB: LRB12 | [14 empty] | 45620.75 | - | 45946 |  | 325.25
|  |  | ML055 | [23 empty] | 45946 | - | 46081.5 |  | 135.5
[5 empty] | OP: OP13 | [14 empty] | 46081.5 | - | 46160.5 |  | 79
|  |  | ML056 | [23 empty] | 46160.5 | - | 46650 |  | 489.5 |  |  | 4700
[5 empty] | RD: RD054 | [14 empty] | 42330
[13 empty] | CP049 | [13 empty] | 42700
[13 empty] | CP050 | [13 empty] | 42880
[13 empty] | CP051 | [13 empty] | 43680
[13 empty] | CP052 | [13 empty] | 43900
[5 empty] | WT: WT015 | [14 empty] | 44700 | [5 empty] | Connect to/from CN09
[14 empty] | CN09 | [12 empty] | 44700 | [5 empty] | Connect to/from WT015
[5 empty] | RD: RD055 | [14 empty] | 45060
[13 empty] | CP053 | [13 empty] | 46300
[5 empty] | RD: RD056 | [14 empty] | 46440
[13 empty] | CP054 | [13 empty] | 46550
|  |  | ML06-2 | [23 empty] | 46550 | - | 52050 |  | 5500
|  |  | ML057 | [23 empty] | 46550 | - | 46707.5 |  | 157.5
[5 empty] | SB: SB06 | [14 empty] | 46707.5 | - | 46792.5 |  | 85
|  |  | ML058 | [23 empty] | 46792.5 | - | 46972.5 |  | 180
[5 empty] | OP: OP14 | [14 empty] | 46972.5 | - | 47051.5 |  | 79
|  |  | ML059 | [23 empty] | 47051.5 | - | 47679 |  | 627.5
[5 empty] | LRB: LRB13 | [14 empty] | 47679 | - | 48021 |  | 342
|  |  | ML060 | [23 empty] | 48021 | - | 51080.5 |  | 3059.5
[5 empty] | OP: OP15 | [14 empty] | 51080.5 | - | 51159.5 |  | 79
|  |  | ML061 | [23 empty] | 51159.5 | - | 52050 |  | 890.5 |  |  | 5500
[13 empty] | CP055 | [13 empty] | 46900
[13 empty] | CP056 | [13 empty] | 47130
[5 empty] | RD: RD057 | [14 empty] | 47440
[13 empty] | CP057 | [13 empty] | 48100
[13 empty] | CP058 | [13 empty] | 48420
[5 empty] | RD: RD058 | [14 empty] | 48500
[13 empty] | CP059 | [13 empty] | 48890
[5 empty] | RD: RD059 | [14 empty] | 48920
[13 empty] | CP060 | [13 empty] | 49400
[5 empty] | RD: RD060 | [14 empty] | 49420
[13 empty] | CP061 | [13 empty] | 49640
[13 empty] | CP062 | [13 empty] | 50160
[5 empty] | RD: RD061 | [14 empty] | 50300
[13 empty] | CP063 | [13 empty] | 50340
[13 empty] | CP064 | [13 empty] | 50600
[5 empty] | RD: RD062 | [14 empty] | 50700
[13 empty] | CP065 | [13 empty] | 51000
[13 empty] | CP066 | [13 empty] | 51500
[13 empty] | CP067 | [13 empty] | 51850
[5 empty] | RD: RD063 | [14 empty] | 51900
| Quang Nam | PKG07 | ML07-1 | [23 empty] | 51950 | - | 56050 |  | 4100
|  |  | ML062 | [23 empty] | 51950 | - | 54182.5 |  | 2232.5
[5 empty] | OP: OP16 | [14 empty] | 54182.5 | - | 54261.5 |  | 79
|  |  | ML063 | [23 empty] | 54261.5 | - | 54730.5 |  | 469
[5 empty] | ORB: ORB05 | [14 empty] | 54730.5 | - | 54835.5 |  | 105
|  |  | ML064 | [23 empty] | 54835.5 | - | 55329 |  | 493.5
[5 empty] | LRB: LRB14 | [14 empty] | 55329 | - | 55671 |  | 342
|  |  | ML065 | [23 empty] | 55671 | - | 56050 |  | 379 |  |  | 4100
[13 empty] | CP068 | [13 empty] | 52490
[5 empty] | RD: RD064 | [14 empty] | 52500
[13 empty] | CP069 | [13 empty] | 52900
[5 empty] | RD: RD065 | [14 empty] | 52950
[5 empty] | RD: RD066 | [14 empty] | 53300
[13 empty] | CP070 | [13 empty] | 53400
[5 empty] | RD: RD067 | [14 empty] | 53700
[13 empty] | CP071 | [13 empty] | 53800
[13 empty] | CP072 | [13 empty] | 54300
[5 empty] | RD: RD068 | [14 empty] | 54700
[13 empty] | CP073 | [13 empty] | 55200
[5 empty] | RD: RD069 | [14 empty] | 55260
[13 empty] | CP074 | [13 empty] | 55900
[5 empty] | RD: RD070 | [14 empty] | 55940
|  |  | ML07-2 | [23 empty] | 55950 | - | 60050 |  | 4100
|  |  | ML066 | [23 empty] | 55950 | - | 56259 |  | 309
[5 empty] | CB: CB05 | [14 empty] | 56259 | - | 56335.75 |  | 76.75 |  | Continuous BR Survey Section
[5 empty] | OP: OP17 | [14 empty] | 56335.75 | - | 56409.5 |  | 73.75
|  |  | ML067 | [23 empty] | 56409.5 | - | 56897.5 |  | 488
[5 empty] | ORB: ORB06 | [14 empty] | 56897.5 | - | 57002.5 |  | 105
|  |  | ML068 | [23 empty] | 57002.5 | - | 57332 |  | 329.5
[5 empty] | OP: OP18 | [14 empty] | 57332 | - | 57424 |  | 92
|  |  | ML069 | [23 empty] | 57424 | - | 57949 |  | 525
[5 empty] | LRB: LRB15 | [14 empty] | 57949 | - | 58291 |  | 342
|  |  | ML070 | [23 empty] | 58291 | - | 59126 |  | 835
[5 empty] | OP: OP19 | [14 empty] | 59126 | - | 59208 |  | 82
|  |  | ML071 | [23 empty] | 59208 | - | 60050 |  | 842 |  |  | 4100
[13 empty] | CP075 | [13 empty] | 56500
[13 empty] | CP076 | [13 empty] | 56800
[5 empty] | RD: RD071 | [14 empty] | 56890
[13 empty] | CP077 | [13 empty] | 57300
[13 empty] | CP078 | [13 empty] | 57500
[5 empty] | RD: RD072 | [14 empty] | 57960
[5 empty] | RD: RD073 | [14 empty] | 58700
[13 empty] | CP079 | [13 empty] | 59100
[13 empty] | CP080 | [13 empty] | 59500
[13 empty] | CP081 | [13 empty] | 59800
[5 empty] | RD: RD074 | [14 empty] | 59913
|  |  | ML07-3 | [23 empty] | 59950 | - | 65050 |  | 5100
|  |  | ML072 | [23 empty] | 59950 | - | 62250.5 |  | 2300.5
[5 empty] | ORB: ORB07 | [14 empty] | 62250.5 | - | 62423.5 |  | 173
|  |  | ML073 | [23 empty] | 62423.5 | - | 65050 |  | 2626.5 |  |  | 5100
[5 empty] | RD: RD075 | [14 empty] | 60480
[5 empty] | RD: RD076 | [14 empty] | 61645
[13 empty] | CP082 | [13 empty] | 62216 | [5 empty] | Connect to/from CN10
[14 empty] | CN10 | [12 empty] | 62216 | [5 empty] | Connect to/from CP082
[13 empty] | CP083 | [13 empty] | 62400
[5 empty] | WT: WT016 | [14 empty] | 62720 | [5 empty] | Connect to/from CN11
[14 empty] | CN11 | [12 empty] | 62720 | [5 empty] | Connect to/from WT016
[5 empty] | RD: RD077 | [14 empty] | 62829
[5 empty] | RD: RD078 | [14 empty] | 63656
[5 empty] | RD: RD079 | [14 empty] | 64090
[16 empty] | IC04 | [10 empty] | 64200 | [5 empty] | Tam Ky IC (Including TG, TP and TPO)
[17 empty] | IRB05 | [9 empty] | 64200 | [5 empty] | IR (Tam Ky IC)
[26 empty] | IS04 | 64200 | [5 empty] | DR616 (Tam Ky IC)
[5 empty] | RD: RD080 | [14 empty] | 64240
[5 empty] | WT: WT017 | [14 empty] | 64252
[5 empty] | RD: RD081 | [14 empty] | 64492
[20 empty] | BL04 | [6 empty] | 64750 | [5 empty] | EOO
[5 empty] | WT: WT018 | [14 empty] | 64982
| Quang Nam | PKGA1 | MLA1-1 | [23 empty] | 64950 | - | 71050 |  | 6100
|  |  | ML074 | [23 empty] | 64950 | - | 66113.5 |  | 1163.5
[5 empty] | SB: SB07 | [14 empty] | 66113.5 | - | 66286.5 |  | 173
|  |  | ML075 | [23 empty] | 66286.5 | - | 67954.5 |  | 1668
[5 empty] | LRB: LRB16 | [14 empty] | 67954.5 | - | 68661.5 |  | 707
|  |  | ML076 | [23 empty] | 68661.5 | - | 70957.5 |  | 2296
[5 empty] | CB: CB06 | [14 empty] | 70957.5 | - | 71050 |  | 92.5 |  |  | 6100
[5 empty] | RD: RD082 | [14 empty] | 65339
[13 empty] | CP084 | [13 empty] | 65487
[5 empty] | RD: RD083 | [14 empty] | 65680
[14 empty] | CN12 | [12 empty] | 66200 | [5 empty] | Connect to/from SB07
[15 empty] | FO04 | [11 empty] | 66334
[5 empty] | RD: RD084 | [14 empty] | 66678
[14 empty] | CN13 | [12 empty] | 66815 | [5 empty] | Roadside, KM066+750 - KM066+880
[14 empty] | CN14 | [12 empty] | 67178 | [5 empty] | Roadside, KM066+980 - KM067+375
[13 empty] | CP085 | [13 empty] | 67188
[5 empty] | RD: RD085 | [14 empty] | 67468
[5 empty] | RD: RD086 | [14 empty] | 68100
[5 empty] | RD: RD087 | [14 empty] | 68470
[13 empty] | CP086 | [13 empty] | 68640
[5 empty] | RD: RD088 | [14 empty] | 69179
[13 empty] | CP087 | [13 empty] | 69237
[20 empty] | BL05 | [6 empty] | 69600 | [5 empty] | SA
[5 empty] | WT: WT019 | [14 empty] | 70245
[5 empty] | RD: RD089 | [14 empty] | 70275
[5 empty] | RD: RD090 | [14 empty] | 70700
[14 empty] | CN15 | [12 empty] | 71000 | [5 empty] | Connect to/from CB06
|  |  | MLA1-2 | [23 empty] | 70950 | - | 76050 | -57.32 | 5157.32 |  | Back: KM073+057.32, Ahead: KM073+000
|  |  | ML077 | [23 empty] | 70950 | - | 74140 | -57.32 | 3247.32
[5 empty] | LRB: LRB17 | [14 empty] | 74140 | - | 74484 |  | 344
|  |  | ML078 | [23 empty] | 74484 | - | 74837 |  | 353
[5 empty] | CB: CB07 | [14 empty] | 74837 | - | 74921 |  | 84
|  |  | ML079 | [23 empty] | 74921 | - | 76050 |  | 1129 |  |  | 5157.32
[13 empty] | CP088 | [13 empty] | 71360
[13 empty] | CP089 | [13 empty] | 71650 | [5 empty] | Connect to/from CN16
[14 empty] | CN16 | [12 empty] | 71650 | [5 empty] | Connect to/from CP089
[5 empty] | RD: RD091 | [14 empty] | 71900
[13 empty] | CP090 | [13 empty] | 71938
[13 empty] | CP091 | [13 empty] | 72316
[13 empty] | CP092 | [13 empty] | 72528
[5 empty] | RD: RD092 | [14 empty] | 72705
[13 empty] | CP093 | [13 empty] | 72707
[13 empty] | CP094 | [13 empty] | 72831
[13 empty] | CP095 | [13 empty] | 72955
[5 empty] | WT: WT020 | [14 empty] | 73200
[5 empty] | RD: RD093 | [14 empty] | 73628
[5 empty] | WT: WT021 | [14 empty] | 73800
[5 empty] | WT: WT022 | [14 empty] | 74080
[5 empty] | WT: WT023 | [14 empty] | 74500
[5 empty] | RD: RD094 | [14 empty] | 74840
[5 empty] | RD: RD095 | [14 empty] | 75454
[13 empty] | CP096 | [13 empty] | 75750
[13 empty] | CP097 | [13 empty] | 76000
|  |  | MLA1-3 | [23 empty] | 75950 | - | 81550 |  | 5600
|  |  | ML080 | [23 empty] | 75950 | - | 79165.5 |  | 3215.5
[5 empty] | CB: CB08 | [14 empty] | 79165.5 | - | 79258.5 |  | 93
|  |  | ML081 | [23 empty] | 79258.5 | - | 81550 |  | 2291.5 |  |  | 5600
[13 empty] | CP098 | [13 empty] | 76400
[13 empty] | CP099 | [13 empty] | 77000
[13 empty] | CP100 | [13 empty] | 77400
[13 empty] | CP101 | [13 empty] | 78200
[15 empty] | FO05 | [11 empty] | 78481
[13 empty] | CP102 | [13 empty] | 78800
[13 empty] | CP103 | [13 empty] | 79800
[15 empty] | FO06 | [11 empty] | 80071
[5 empty] | WT: WT024 | [14 empty] | 80600
[5 empty] | WT: WT025 | [14 empty] | 81100
| Quang Nam | PKGA2 | MLA2-1 | [23 empty] | 81450 | - | 87050 |  | 5600
|  |  | ML082 | [23 empty] | 81450 | - | 81503.5 |  | 53.5
[5 empty] | CB: CB09 | [14 empty] | 81503.5 | - | 81608.5 |  | 105
|  |  | ML083 | [23 empty] | 81608.5 | - | 82435 |  | 826.5
[5 empty] | ORB: ORB08 | [14 empty] | 82435 | - | 82619 |  | 184
|  |  | ML084 | [23 empty] | 82619 | - | 85274 |  | 2655
[5 empty] | CB: CB10 | [14 empty] | 85274 | - | 85358 |  | 84
|  |  | ML085 | [23 empty] | 85358 | - | 87050 |  | 1692 |  |  | 5600
[5 empty] | WT: WT026 | [14 empty] | 82341
[5 empty] | WT: WT027 | [14 empty] | 82679
[5 empty] | WT: WT028 | [14 empty] | 83400
[16 empty] | IC05 | [10 empty] | 83800 | [5 empty] | Chu Lai IC (Including TG, TP and TPO)
[17 empty] | IRB06 | [9 empty] | 83800 | [5 empty] | IR (Chu Lai IC)
[19 empty] | CP162 | [7 empty] | 83800 | [5 empty] | IR (Chu Lai IC)
[19 empty] | CP163 | [7 empty] | 83800 | [5 empty] | IR (Chu Lai IC)
[26 empty] | IS05 | 83800 | [5 empty] | Chu Lai Industrial Road (Chu Lai IC)
[5 empty] | WT: WT029 | [14 empty] | 84400
[5 empty] | WT: WT030 | [14 empty] | 84800
[13 empty] | CP104 | [13 empty] | 85941
[15 empty] | FO07 | [11 empty] | 85940
[13 empty] | CP105 | [13 empty] | 86300
[13 empty] | CP106 | [13 empty] | 86800
[13 empty] | CP107 | [13 empty] | 87000
|  |  | MLA2-2 | [23 empty] | 86950 | - | 93050 |  | 6100
|  |  | ML086 | [23 empty] | 86950 | - | 87844 |  | 894
[5 empty] | CB: CB11 | [14 empty] | 87844 | - | 87940 |  | 96
|  |  | ML087 | [23 empty] | 87940 | - | 88026 |  | 86
[5 empty] | LRB: LRB18 | [14 empty] | 88026 | - | 88334 |  | 308
|  |  | ML088 | [23 empty] | 88334 | - | 90580 |  | 2246
[5 empty] | CB: CB12 | [14 empty] | 90580 | - | 90740 |  | 160
|  |  | ML089 | [23 empty] | 90740 | - | 92566 |  | 1826
[5 empty] | CB: CB13 | [14 empty] | 92566 | - | 92750 |  | 184
|  |  | ML090 | [23 empty] | 92750 | - | 93050 |  | 300 |  |  | 6100
[13 empty] | CP108 | [13 empty] | 87500
[5 empty] | RD: RD096 | [14 empty] | 87795
[13 empty] | CP109 | [13 empty] | 88500
[13 empty] | CP110 | [13 empty] | 89000
[15 empty] | FO08 | [11 empty] | 89335
[13 empty] | CP111 | [13 empty] | 89674
[5 empty] | WT: WT031 | [14 empty] | 90400
[5 empty] | RD: RD097 | [14 empty] | 91159
[13 empty] | CP112 | [13 empty] | 91162
[13 empty] | CP113 | [13 empty] | 91500
[13 empty] | CP114 | [13 empty] | 92334
[5 empty] | RD: RD098 | [14 empty] | 92337
|  |  | MLA2-3 | [23 empty] | 92950 | - | 100050 | 300 | 6800 |  | Back: KM096+700, Ahead: KM097+000
|  |  | ML091 | [23 empty] | 92950 | - | 94270 |  | 1320
[5 empty] | CB: CB14 | [14 empty] | 94270 | - | 94366 |  | 96
|  |  | ML092 | [23 empty] | 94366 | - | 95670 |  | 1304
[5 empty] | CB: CB15 | [14 empty] | 95670 | - | 95766 |  | 96
|  |  | ML093 | [23 empty] | 95766 | - | 100050 | 300 | 3984 |  |  | 6800
[13 empty] | CP115 | [13 empty] | 93100
[5 empty] | RD: RD099 | [14 empty] | 93396
[5 empty] | WT: WT032 | [14 empty] | 93399
[5 empty] | WT: WT033 | [14 empty] | 93629
[5 empty] | WT: WT034 | [14 empty] | 94500
[5 empty] | WT: WT035 | [14 empty] | 95000
[13 empty] | CP116 | [13 empty] | 95200
[13 empty] | CP117 | [13 empty] | 95579
[5 empty] | WT: WT036 | [14 empty] | 96118
[5 empty] | RD: RD100 | [14 empty] | 96500
[5 empty] | WT: WT037 | [14 empty] | 96600
[5 empty] | WT: WT038 | [14 empty] | 97400
[5 empty] | WT: WT039 | [14 empty] | 98300
[20 empty] | BL06 | [6 empty] | 98800 | [5 empty] | PA
[5 empty] | RD: RD101 | [14 empty] | 98920
[5 empty] | WT: WT040 | [14 empty] | 99227
[13 empty] | CP118 | [13 empty] | 99400
[15 empty] | FO09 | [11 empty] | 99710
[13 empty] | CP119 | [13 empty] | 100000
| Quang Ngai | PKGA3 | MLA3-1 | [23 empty] | 99950 | - | 105050 | -173.22 | 5273.22 |  | Back: KM102+294.850, Ahead: KM102+121.630
|  |  | ML094 | [23 empty] | 99950 | - | 100252 |  | 302
[5 empty] | CB: CB16 | [14 empty] | 100252 | - | 100348 |  | 96
|  |  | ML095 | [23 empty] | 100348 | - | 103171 | -173.22 | 2996.22
[5 empty] | OP: OP20 | [14 empty] | 103171 | - | 103337 |  | 166
|  |  | ML096 | [23 empty] | 103337 | - | 105050 |  | 1713 |  |  | 5273.22
[13 empty] | CP120 | [13 empty] | 100600
[13 empty] | CP121 | [13 empty] | 101200
[13 empty] | CP122 | [13 empty] | 101846
[5 empty] | RD: RD102 | [14 empty] | 101849
[16 empty] | IC06 | [10 empty] | 102255 | [5 empty] | Dung Quat IC (Including TG, TP and TPO)
[17 empty] | IRB07 | [9 empty] | 102255 | [5 empty] | IR (Dung Quat IC)
[17 empty] | IRB08 | [9 empty] | 102255 | [5 empty] | IR (Dung Quat IC)
[17 empty] | IRB09 | [9 empty] | 102255 | [5 empty] | IR (Dung Quat IC)
[17 empty] | IRB10 | [9 empty] | 102255 | [5 empty] | IR (Dung Quat IC)
[19 empty] | CP164 | [7 empty] | 102255 | [5 empty] | IR (Dung Quat IC)
[19 empty] | CP165 | [7 empty] | 102255 | [5 empty] | IR (Dung Quat IC)
[26 empty] | IS06 | 102255 | [5 empty] | Dung Quant Industrial Road (Dung Quat IC)
[5 empty] | WT: WT041 | [14 empty] | 102500
[13 empty] | CP123 | [13 empty] | 103000
[13 empty] | CP124 | [13 empty] | 103400
[13 empty] | CP125 | [13 empty] | 104700
[5 empty] | RD: RD103 | [14 empty] | 104954
[13 empty] | CP126 | [13 empty] | 105000
|  |  | MLA3-2 | [23 empty] | 104950 | - | 110050 |  | 5100
|  |  | ML097 | [23 empty] | 104950 | - | 105280 |  | 330
[5 empty] | VD: VD16 | [14 empty] | 105280 | - | 105376 |  | 96
|  |  | ML098 | [23 empty] | 105376 | - | 106626 |  | 1250
[5 empty] | OP: OP21 | [14 empty] | 106626 | - | 106792 |  | 166
|  |  | ML099 | [23 empty] | 106792 | - | 108952 |  | 2160
[5 empty] | SB: SB08 | [14 empty] | 108952 | - | 109056 |  | 104 |  | Continuous BR Survey Section
[5 empty] | LRB: LRB19 | [14 empty] | 109056 | - | 109746 |  | 690
|  |  | ML100 | [23 empty] | 109746 | - | 110050 |  | 304 |  |  | 5100
[13 empty] | CP127 | [13 empty] | 105900
[5 empty] | RD: RD104 | [14 empty] | 106021
[13 empty] | CP128 | [13 empty] | 106300
[13 empty] | CP129 | [13 empty] | 107100
[13 empty] | CP130 | [13 empty] | 108000
[15 empty] | FO10 | [11 empty] | 108478
[5 empty] | WT: WT042 | [14 empty] | 109663
| Quang Ngai | PKGA4 | MLA4-1 | [23 empty] | 109950 | - | 115050 |  | 5100
|  |  | ML101 | [23 empty] | 109950 | - | 110045 |  | 95
[5 empty] | OP: OP22 | [14 empty] | 110045 | - | 110211 |  | 166
|  |  | ML102 | [23 empty] | 110211 | - | 110674 |  | 463
[5 empty] | VD: VD17 | [14 empty] | 110674 | - | 111566 |  | 892
|  |  | ML103 | [23 empty] | 111566 | - | 115050 |  | 3484 |  |  | 5100
[5 empty] | WT: WT043 | [14 empty] | 110200
[5 empty] | WT: WT044 | [14 empty] | 110400
[5 empty] | WT: WT045 | [14 empty] | 110567
[5 empty] | WT: WT046 | [14 empty] | 112311
[15 empty] | FO11 | [11 empty] | 112411
[13 empty] | CP131 | [13 empty] | 112411
[16 empty] | IC07 | [10 empty] | 112615 | [5 empty] | Binh Son IC (Including TG, TP and TPO)
[17 empty] | IRB11 | [9 empty] | 112615 | [5 empty] | IR (Binh Son IC)
[19 empty] | CP166 | [7 empty] | 112615 | [5 empty] | IR (Binh Son IC)
[19 empty] | CP167 | [7 empty] | 112615 | [5 empty] | IR (Binh Son IC)
[26 empty] | IS07 | 112615 | [5 empty] | Tra Bong - Binh Long Road (Binh Son IC)
[13 empty] | CP132 | [13 empty] | 113447
[13 empty] | CP133 | [13 empty] | 114180
[15 empty] | FO12 | [11 empty] | 114755
[13 empty] | CP134 | [13 empty] | 114975
|  |  | MLA4-2 | [23 empty] | 114950 | - | 120050 |  | 5100
|  |  | ML104 | [23 empty] | 114950 | - | 116280 |  | 1330
[5 empty] | CB: CB17 | [14 empty] | 116280 | - | 116372 |  | 92
|  |  | ML105 | [23 empty] | 116372 | - | 118320.5 |  | 1948.5
[5 empty] | CB: CB18 | [14 empty] | 118320.5 | - | 118425.5 |  | 105
|  |  | ML106 | [23 empty] | 118425.5 | - | 120050 |  | 1624.5 |  |  | 5100
[15 empty] | FO13 | [11 empty] | 115242
[5 empty] | RD: RD105 | [14 empty] | 116275
[13 empty] | CP135 | [13 empty] | 116441
[15 empty] | FO14 | [11 empty] | 116888
[13 empty] | CP136 | [13 empty] | 116892
[13 empty] | CP137 | [13 empty] | 117356
[15 empty] | FO15 | [11 empty] | 118065
[13 empty] | CP138 | [13 empty] | 118547
[13 empty] | CP139 | [13 empty] | 118958
[13 empty] | CP140 | [13 empty] | 119234
[5 empty] | WT: WT047 | [14 empty] | 119481
[15 empty] | FO16 | [11 empty] | 119508
[13 empty] | CP141 | [13 empty] | 119687
|  |  | MLA4-3 | [23 empty] | 119950 | - | 125050 |  | 5100
|  |  | ML107 | [23 empty] | 119950 | - | 123994 |  | 4044
[5 empty] | VD: VD18 | [14 empty] | 123994 | - | 124806 |  | 812
|  |  | ML108 | [23 empty] | 124806 | - | 125050 |  | 244 |  |  | 5100
[15 empty] | FO17 | [11 empty] | 120316
[13 empty] | CP142 | [13 empty] | 120687
[13 empty] | CP143 | [13 empty] | 120985
[13 empty] | CP144 | [13 empty] | 121144
[13 empty] | CP145 | [13 empty] | 121287
[13 empty] | CP146 | [13 empty] | 121555
[13 empty] | CP147 | [13 empty] | 121946
[13 empty] | CP148 | [13 empty] | 122029
[13 empty] | CP149 | [13 empty] | 122580
[5 empty] | WT: WT048 | [14 empty] | 123096
[13 empty] | CP150 | [13 empty] | 123131
[5 empty] | WT: WT049 | [14 empty] | 123281
[13 empty] | CP151 | [13 empty] | 123647
[16 empty] | IC08 | [10 empty] | 123915 | [5 empty] | Quang Ngai North IC (Including TG, TP and TPO)
[17 empty] | IRB12 | [9 empty] | 123915 | [5 empty] | IR (Quang Ngai North IC)
[18 empty] | WT057 | [8 empty] | 123915 | [5 empty] | IR (Quang Ngai North IC)
[19 empty] | CP168 | [7 empty] | 123915 | [5 empty] | IR (Quang Ngai North IC)
[26 empty] | IS08 | 123915 | [5 empty] | PR623 (Quang Ngai North IC)
[13 empty] | CP152 | [13 empty] | 123927
[13 empty] | CP153 | [13 empty] | 124073
| Quang Ngai | PKGA5 | MLA5-1 | [23 empty] | 124950 | - | 131550 |  | 6600
|  |  | ML109 | [23 empty] | 124950 | - | 125077 |  | 127
[5 empty] | LRB: LRB20 | [14 empty] | 125077 | - | 126323 |  | 1246
|  |  | ML110 | [23 empty] | 126323 | - | 126674 |  | 351
[5 empty] | VD: VD19 | [14 empty] | 126674 | - | 127726 |  | 1052
|  |  | ML111 | [23 empty] | 127726 | - | 127934 |  | 208
[5 empty] | VD: VD20 | [14 empty] | 127934 | - | 128426 |  | 492
|  |  | ML112 | [23 empty] | 128426 | - | 131550 |  | 3124 |  |  | 6600
[5 empty] | WT: WT050 | [14 empty] | 127847
[5 empty] | WT: WT051 | [14 empty] | 128402
[5 empty] | WT: WT052 | [14 empty] | 128743
[15 empty] | FO19 | [11 empty] | 128948
[13 empty] | CP154 | [13 empty] | 129246
[5 empty] | WT: WT053 | [14 empty] | 129339
[20 empty] | BL07 | [6 empty] | 129800 | [5 empty] | TB including TP and TPO
[13 empty] | CP155 | [13 empty] | 129905
[5 empty] | RD: RD106 | [14 empty] | 130000
[13 empty] | CP156 | [13 empty] | 130246
[13 empty] | CP157 | [13 empty] | 130394
[5 empty] | WT: WT054 | [14 empty] | 130482
[5 empty] | WT: WT055 | [14 empty] | 130630
[16 empty] | IC09 | [10 empty] | 130750 | [5 empty] | Quang Ngai IC
[18 empty] | WT058 | [8 empty] | 130750 | [5 empty] | IR (Quang Ngai IC)
[26 empty] | IS09 | 130750 | [5 empty] | PR625 (Quang Ngai IC)
[13 empty] | CP158 | [13 empty] | 131000
[5 empty] | WT: WT056 | [14 empty] | 131435
[21 empty] | MLA5-2 | [5 empty] | 131450 | - | 136050 |  | 4600
[21 empty] | ML113 | [5 empty] | 131450 | - | 132883 |  | 1433
[22 empty] | ORB09 |  |  |  |  | 132883 | - | 132985 |  | 102
[21 empty] | ML114 | [5 empty] | 132985 | - | 134675 |  | 1690
[23 empty] | VD21 |  |  |  | 134675 | - | 134777 |  | 102
[21 empty] | ML115 | [5 empty] | 134777 | - | 136050 |  | 1273 |  |  | 4600
[25 empty] | CP169 |  | 131605
[24 empty] | WT059 |  |  | 131868
[24 empty] | WT060 |  |  | 132440
[25 empty] | CP170 |  | 133265
[24 empty] | WT061 |  |  | 133343
[26 empty] | IS10 | 133371
[25 empty] | CP171 |  | 133394
[24 empty] | WT062 |  |  | 133600
[24 empty] | WT063 |  |  | 133696
[25 empty] | CP172 |  | 133893
[26 empty] | IS11 | 134222
[24 empty] | WT064 |  |  | 134226
[24 empty] | WT065 |  |  | 134391
[25 empty] | CP173 |  | 134686
[24 empty] | WT066 |  |  | 134828
[25 empty] | CP174 |  | 134880
[25 empty] | CP175 |  | 134969
[24 empty] | WT067 |  |  | 135142
[26 empty] | IS12 | 135415
[25 empty] | CP176 |  | 135456
[24 empty] | WT068 |  |  | 135646
[24 empty] | WT069 |  |  | 135699
[24 empty] | WT070 |  |  | 135969
[21 empty] | MLA5-3 | [5 empty] | 135950 | - | 139572 |  | 3622
[21 empty] | ML116 | [5 empty] | 135950 | - | 138552.5 |  | 2602.5
[22 empty] | ORB10 |  |  |  |  | 138552.5 | - | 138645.5 |  | 93
[21 empty] | ML117 | [5 empty] | 138645.5 | - | 139572 |  | 926.5 |  |  | 3622
[24 empty] | WT071 |  |  | 136077
[24 empty] | WT072 |  |  | 136218
[24 empty] | WT073 |  |  | 136356
[24 empty] | WT074 |  |  | 136469
[24 empty] | WT075 |  |  | 136738
[24 empty] | WT076 |  |  | 136975
[24 empty] | WT077 |  |  | 137095
[26 empty] | IS13 | 137215
[24 empty] | WT078 |  |  | 137224
[25 empty] | CP177 |  | 137361
[25 empty] | CP178 |  | 137461
[25 empty] | CP179 |  | 137724
[24 empty] | WT079 |  |  | 137825
[25 empty] | CP180 |  | 138265
[25 empty] | CP181 |  | 138353
[24 empty] | WT080 |  |  | 138422
[24 empty] | WT081 |  |  | 138672
[25 empty] | CP182 |  | 138803
[25 empty] | CP183 |  | 138903
[25 empty] | CP184 |  | 139006
[25 empty] | CP185 |  | 139108
[25 empty] | CP186 |  | 139212
[25 empty] | CP187 |  | 139316
[24 empty] | WT082 |  |  | 139465
[26 empty] | IS14 | 139522 | [5 empty] | Existing NH1A

## 4.2.1RD
Item |  | Expressway | Linking Road
| Planimetric (Width) | 140 | 100
| Cross-section (Width) | 140 | 60
| Cross-section (Pitch) | 20 | 20
| Cross-section (Transition) | 5% | 5% |  | ***.** (m) | : Including Equation
Jurisdiction |  | Construction | Survey | Survey Section |  |  |  |  | Survey | Qty and Price | [8 empty] | Remarks
|  | Contract No. | Package | [5 empty] | Length | 3.1 Planimetric |  |  | 3.2 Profile |  |  | 3.3 Cross-section
[10 empty] | Qty | Unit Price | Amount | Qty | Unit Price | Amount | Qty | Unit Price | Amount
[10 empty] | (ha) | (USD) | (USD) | (km) | (USD) | (USD) | (km) | (USD) | (USD)
B. Expressway, 3. Main Line (ML, Road Section)
| Danang | PKG01 | ML01-1 | ML001 | -800 |  | - | -174.55 | 625.45 | 8.7563 |  |  | 0.62545 |  |  | 4.557
|  |  |  | ML002 | -65.45 |  | - | 1047.425 | 1112.875 | 15.5802 |  |  | 1.1129 |  |  | 8.085
|  |  |  | ML003 | 2190.575 |  | - | 2319.35 | 128.775 | 1.8029 |  |  | 0.12878 |  |  | 0.882
|  |  |  | ML004 | 2700.65 |  | - | 4050 | 1349.35 | 18.8909 |  |  | 1.3493 |  |  | 9.849
|  |  |  | Sub-total |  |  |  |  | 3216.45 | 45.0303 | 61.29 | 2759.9071 | 3.2165 | 438.31 | 1409.8022 | 23.373 | 572.73 | 13386.4183
|  |  | ML01-2 | ML005 | 3950 |  | - | 5466.4 | 1516.4 | 21.2296 |  |  | 1.5164 |  |  | 11.025
|  |  |  | ML006 | 5793.05 |  | - | 7884.45 | 2091.4 | 29.2796 |  |  | 2.0914 |  |  | 15.288
|  |  |  | ML007 | 7967.55 |  | - | 8050 | 82.45 | 1.1543 |  |  | 0.08245 |  |  | 0.588
|  |  |  | Sub-total |  |  |  |  | 3690.25 | 51.6635 | 61.29 | 3166.4559 | 3.6902 | 438.31 | 1617.4735 | 26.901 | 572.73 | 15407.0097
| Quang Nam | PKG02 | ML02-1 | ML008 | 7950 |  | - | 9678.35 | 1728.35 | 24.1969 |  |  | 1.7284 |  |  | 12.642
|  |  |  | ML009 | 10061.65 |  | - | 10175.9 | 114.25 | 1.5995 |  |  | 0.11425 |  |  | 0.735
|  |  |  | ML010 | 10366.1 |  | - | 10723.4 | 357.3 | 5.0022 |  |  | 0.3573 |  |  | 2.499
|  |  |  | ML011 | 11040.6 |  | - | 11728.875 | 688.275 | 9.6358 |  |  | 0.68827 |  |  | 4.998
|  |  |  | ML012 | 12079.125 |  | - | 12545.9 | 466.775 | 6.5348 |  |  | 0.46677 |  |  | 3.381
|  |  |  | ML013 | 12732.1 |  | - | 13050 | 317.9 | 4.4506 |  |  | 0.3179 |  |  | 2.205
|  |  |  | Sub-total |  |  |  |  | 3672.85 | 51.4199 | 61.29 | 3151.5257 | 3.6728 | 438.31 | 1609.8469 | 26.46 | 572.73 | 15154.4358
|  |  | ML02-2 | ML014 | 12950 |  | - | 13040.85 | 90.85 | 1.2719 |  |  | 0.09085 |  |  | 0.588
|  |  |  | ML015 | 13379.15 |  | - | 13574.95 | 195.8 | 2.7412 |  |  | 0.1958 |  |  | 1.323
|  |  |  | ML016 | 13677.05 |  | - | 13868.4 | 191.35 | 2.6789 |  |  | 0.19135 |  |  | 1.323
|  |  |  | ML017 | 14185.6 |  | - | 14714.4 | 528.8 | 7.4032 |  |  | 0.5288 |  |  | 3.822
|  |  |  | ML018 | 15329.6 |  | - | 16338.4 | 1008.8 | 14.1232 |  |  | 1.0088 |  |  | 7.35
|  |  |  | ML019 | 16655.6 |  | - | 17050 | 394.4 | 5.5216 |  |  | 0.3944 |  |  | 2.793
|  |  |  | Sub-total |  |  |  |  | 2410 | 33.74 | 61.29 | 2067.9246 | 2.41 | 438.31 | 1056.3271 | 17.199 | 572.73 | 9850.3833
|  | PKG03 | ML03-1 | ML020 | 18412.1 |  | - | 18530.925 | 118.825 | 1.6636 |  |  | 0.11883 |  |  | 0.735
|  |  |  | ML021 | 18924.1 |  | - | 19165.95 | 241.85 | 3.3859 |  |  | 0.24185 |  |  | 1.764
|  |  |  | ML022 | 19403.55 |  | - | 19780 | 376.45 | 5.2703 |  |  | 0.37645 |  |  | 2.646
|  |  |  | ML023 | 20590 |  | - | 21846.45 | 1256.45 | 17.5903 |  |  | 1.2565 |  |  | 9.114
|  |  |  | ML024 | 21953.55 |  | - | 22050 | 96.45 | 1.3503 |  |  | 0.09645 |  |  | 0.588
|  |  |  | Sub-total |  |  |  |  | 2090.025 | 29.2604 | 61.29 | 1793.3669 | 2.09 | 438.31 | 916.0789 | 14.847 | 572.73 | 8503.3223
|  | PKG04 | ML04-1 | ML025 | 21950 |  | - | 22630 | 680 | 9.52 |  |  | 0.68 |  |  | 4.998
|  |  |  | ML026 | 23170 |  | - | 23268.925 | 98.925 | 1.3849 |  |  | 0.098925 |  |  | 0.588
|  |  |  | ML027 | 23431.075 |  | - | 24386.95 | 955.875 | 13.3823 |  |  | 0.95588 |  |  | 6.909
|  |  |  | ML028 | 24473.05 |  | - | 24559.175 | 86.125 | 1.2058 |  |  | 0.086125 |  |  | 0.588
|  |  |  | ML029 | 24736.825 |  | - | 25018.95 | 282.125 | 3.9497 |  |  | 0.28213 |  |  | 2.058
|  |  |  | ML030 | 25105.05 |  | - | 25671.95 | 566.9 | 7.9366 |  |  | 0.5669 |  |  | 4.116
|  |  |  | ML031 | 25768.05 |  | - | 26850 | 1081.95 | 15.1473 |  |  | 1.082 |  |  | 7.938
|  |  |  | Sub-total |  |  |  |  | 3751.9 | 52.5266 | 61.29 | 3219.3553 | 3.7519 | 438.31 | 1644.4953 | 27.195 | 572.73 | 15575.3923
|  |  | ML04-2 | ML032 | 26750 |  | - | 26952.95 | 202.95 | 2.8413 |  |  | 0.20295 |  |  | 1.47
|  |  |  | ML033 | 27047.05 |  | - | 27856.95 | 809.9 | 11.3386 |  |  | 0.8099 |  |  | 5.88
|  |  |  | ML034 | 27943.05 |  | - | 28734.95 | 791.9 | 11.0866 |  |  | 0.7919 |  |  | 5.733
|  |  |  | ML035 | 28821.05 |  | - | 29411.175 | 590.125 | 8.2617 |  |  | 0.59013 |  |  | 4.263
|  |  |  | ML036 | 29588.825 |  | - | 31906.95 | 2318.125 | 32.4537 |  |  | 2.3181 |  |  | 16.905
|  |  |  | ML037 | 31993.05 |  | - | 32050 | 56.95 | 0.7973 |  |  | 0.05695 |  |  | 0.294
|  |  |  | Sub-total |  |  |  |  | 4769.95 | 66.7793 | 61.29 | 4092.9033 | 4.77 | 438.31 | 2090.7168 | 34.545 | 572.73 | 19784.9578
|  | PKG05 | ML05-1 | ML038 | 31950 |  | - | 32396.95 | 446.95 | 6.2573 |  |  | 0.44695 |  |  | 3.234
|  |  |  | ML039 | 32483.05 |  | - | 34034.925 | 1551.875 | 21.7263 |  |  | 1.5519 |  |  | 11.319
|  |  |  | ML040 | 34205.075 |  | - | 35050 | 844.925 | 11.829 |  |  | 0.84493 |  |  | 6.174
|  |  |  | Sub-total |  |  |  |  | 2843.75 | 39.8125 | 61.29 | 2440.1081 | 2.8438 | 438.31 | 1246.4441 | 20.727 | 572.73 | 11870.9747
|  |  | ML05-2 | ML041 | 34950 |  | - | 35305.5 | 355.5 | 4.977 |  |  | 0.3555 |  |  | 2.499
|  |  |  | ML042 | 35400.5 |  | - | 36120 | 719.5 | 10.073 |  |  | 0.7195 |  |  | 5.145
|  |  |  | ML043 | 36280 |  | - | 36738 | 458 | 6.412 |  |  | 0.458 |  |  | 3.234
|  |  |  | ML044 | 36822 |  | - | 38116 | 1294 | 18.116 |  |  | 1.294 |  |  | 9.408
|  |  |  | ML045 | 38458 |  | - | 38747.5 | 289.5 | 4.053 |  |  | 0.2895 |  |  | 2.058
|  |  |  | ML046 | 38826.5 |  | - | 39362 | 535.5 | 7.497 |  |  | 0.5355 |  |  | 3.822
|  |  |  | ML047 | 39738 |  | - | 39954 | 216 | 3.024 |  |  | 0.216 |  |  | 1.47
|  |  |  | ML048 | 40036 |  | - | 41072 | 1036 | 14.504 |  |  | 1.036 |  |  | 7.497
|  |  |  | ML049 | 41170 |  | - | 42050 | 880 | 12.32 |  |  | 0.88 |  |  | 6.468
|  |  |  | Sub-total |  |  |  |  | 5784 | 80.976 | 61.29 | 4963.019 | 5.784 | 438.31 | 2535.185 | 41.601 | 572.73 | 23826.1407
| Quang Nam | PKG06 | ML06-1 | ML050 | 42137 |  | - | 42549 | 412 | 5.768 |  |  | 0.412 |  |  | 2.94
|  |  |  | ML051 | 42643 |  | - | 43478.5 | 835.5 | 11.697 |  |  | 0.8355 |  |  | 6.027
|  |  |  | ML052 | 43561.5 |  | - | 44221 | 659.5 | 9.233 |  |  | 0.6595 |  |  | 4.704
|  |  |  | ML053 | 44379 |  | - | 45265.5 | 886.5 | 12.411 |  |  | 0.8865 |  |  | 6.468
|  |  |  | ML054 | 45346.5 |  | - | 45482.5 | 136 | 1.904 |  |  | 0.136 |  |  | 0.882
|  |  |  | ML055 | 45946 |  | - | 46081.5 | 135.5 | 1.897 |  |  | 0.1355 |  |  | 0.882
|  |  |  | ML056 | 46160.5 |  | - | 46650 | 489.5 | 6.853 |  |  | 0.4895 |  |  | 3.528
|  |  |  | Sub-total |  |  |  |  | 3554.5 | 49.763 | 61.29 | 3049.9743 | 3.5545 | 438.31 | 1557.9729 | 25.431 | 572.73 | 14565.0966
|  |  | ML06-2 | ML057 | 46550 |  | - | 46707.5 | 157.5 | 2.205 |  |  | 0.1575 |  |  | 1.029
|  |  |  | ML058 | 46792.5 |  | - | 46972.5 | 180 | 2.52 |  |  | 0.18 |  |  | 1.323
|  |  |  | ML059 | 47051.5 |  | - | 47679 | 627.5 | 8.785 |  |  | 0.6275 |  |  | 4.557
|  |  |  | ML060 | 48021 |  | - | 51080.5 | 3059.5 | 42.833 |  |  | 3.0595 |  |  | 22.344
|  |  |  | ML061 | 51159.5 |  | - | 52050 | 890.5 | 12.467 |  |  | 0.8905 |  |  | 6.468
|  |  |  | Sub-total |  |  |  |  | 4915 | 68.81 | 61.29 | 4217.3649 | 4.915 | 438.31 | 2154.2937 | 35.721 | 572.73 | 20458.4883
| Quang Nam | PKG07 | ML07-1 | ML062 | 51950 |  | - | 54182.5 | 2232.5 | 31.255 |  |  | 2.2325 |  |  | 16.317
|  |  |  | ML063 | 54261.5 |  | - | 54730.5 | 469 | 6.566 |  |  | 0.469 |  |  | 3.381
|  |  |  | ML064 | 54835.5 |  | - | 55329 | 493.5 | 6.909 |  |  | 0.4935 |  |  | 3.528
|  |  |  | ML065 | 55671 |  | - | 56050 | 379 | 5.306 |  |  | 0.379 |  |  | 2.646
|  |  |  | Sub-total |  |  |  |  | 3195 | 50.036 | 61.29 | 3066.7064 | 3.574 | 438.31 | 1566.5199 | 25.872 | 572.73 | 14817.6706
|  |  | ML07-2 | ML066 | 55950 |  | - | 56259 | 309 | 4.326 |  |  | 0.309 |  |  | 2.205
|  |  |  | ML067 | 56409.5 |  | - | 56897.5 | 488 | 6.832 |  |  | 0.488 |  |  | 3.528
|  |  |  | ML068 | 57002.5 |  | - | 57332 | 329.5 | 4.613 |  |  | 0.3295 |  |  | 2.352
|  |  |  | ML069 | 57424 |  | - | 57949 | 525 | 7.35 |  |  | 0.525 |  |  | 3.822
|  |  |  | ML070 | 58291 |  | - | 59126 | 835 | 11.69 |  |  | 0.835 |  |  | 6.027
|  |  |  | ML071 | 59208 |  | - | 60050 | 842 | 11.788 |  |  | 0.842 |  |  | 6.174
|  |  |  | Sub-total |  |  |  |  | 3328.5 | 46.599 | 61.29 | 2856.0527 | 3.3285 | 438.31 | 1458.9148 | 24.108 | 572.73 | 13807.3748
|  |  | ML07-3 | ML072 | 59950 |  | - | 62250.5 | 2300.5 | 32.207 |  |  | 2.3005 |  |  | 16.905
|  |  |  | ML073 | 62423.5 |  | - | 65050 | 2626.5 | 36.771 |  |  | 2.6265 |  |  | 19.257
|  |  |  | Sub-total |  |  |  |  | 4927 | 68.978 | 61.29 | 4227.6616 | 4.927 | 438.31 | 2159.5534 | 36.162 | 572.73 | 20711.0623
| Quang Nam | PKGA1 | MLA1-1 | ML074 | 64950 |  | - | 66113.5 | 1163.5 | 16.289 |  |  | 1.1635 |  |  | 8.526
|  |  |  | ML075 | 66286.5 |  | - | 67954.5 | 1668 | 23.352 |  |  | 1.668 |  |  | 12.201
|  |  |  | ML076 | 68661.5 |  | - | 70957.5 | 2296 | 32.144 |  |  | 2.296 |  |  | 16.758
|  |  |  | Sub-total |  |  |  |  | 5127.5 | 71.785 | 61.29 | 4399.7027 | 5.1275 | 438.31 | 2247.4345 | 37.485 | 572.73 | 21468.7841
|  |  | MLA1-2 | ML077 | 70950 |  | - | 74140 | 3247.32 | 45.4625 |  |  | 3.2473 |  |  | 23.814
|  |  |  | ML078 | 74484 |  | - | 74837 | 353 | 4.942 |  |  | 0.353 |  |  | 2.499
|  |  |  | ML079 | 74921 |  | - | 76050 | 1129 | 15.806 |  |  | 1.129 |  |  | 8.232
|  |  |  | Sub-total |  |  |  |  | 4729.32 | 66.2105 | 61.29 | 4058.0403 | 4.7293 | 438.31 | 2072.9082 | 34.545 | 572.73 | 19784.9579
|  |  | MLA1-3 | ML080 | 75950 |  | - | 79165.5 | 3215.5 | 45.017 |  |  | 3.2155 |  |  | 23.52
|  |  |  | ML081 | 79258.5 |  | - | 81550 | 2291.5 | 32.081 |  |  | 2.2915 |  |  | 16.758
|  |  |  | Sub-total |  |  |  |  | 5507 | 77.098 | 61.29 | 4725.3364 | 5.507 | 438.31 | 2413.7732 | 40.278 | 572.73 | 23068.4189
|  | PKGA2 | MLA2-1 | ML082 | 81450 |  | - | 81503.5 | 53.5 | 0.749 |  |  | 0.0535 |  |  | 0.294
|  |  |  | ML083 | 81608.5 |  | - | 82435 | 826.5 | 11.571 |  |  | 0.8265 |  |  | 6.027
|  |  |  | ML084 | 82619 |  | - | 85274 | 2655 | 37.17 |  |  | 2.655 |  |  | 19.404
|  |  |  | ML085 | 85358 |  | - | 87050 | 1692 | 23.688 |  |  | 1.692 |  |  | 12.348
|  |  |  | Sub-total |  |  |  |  | 5227 | 73.178 | 61.29 | 4485.0796 | 5.227 | 438.31 | 2291.0464 | 38.073 | 572.73 | 21805.5493
|  |  | MLA2-2 | ML086 | 86950 |  | - | 87844 | 894 | 12.516 |  |  | 0.894 |  |  | 6.468
|  |  |  | ML087 | 87940 |  | - | 88026 | 86 | 1.204 |  |  | 0.086 |  |  | 0.588
|  |  |  | ML088 | 88334 |  | - | 90580 | 2246 | 31.444 |  |  | 2.246 |  |  | 16.464
|  |  |  | ML089 | 90740 |  | - | 92566 | 1826 | 25.564 |  |  | 1.826 |  |  | 13.377
|  |  |  | ML090 | 92750 |  | - | 93050 | 300 | 4.2 |  |  | 0.3 |  |  | 2.205
|  |  |  | Sub-total |  |  |  |  | 5352 | 74.928 | 61.29 | 4592.3371 | 5.352 | 438.31 | 2345.8351 | 39.102 | 572.73 | 22394.8885
|  |  | MLA2-3 | ML091 | 92950 |  | - | 94270 | 1320 | 18.48 |  |  | 1.32 |  |  | 9.702
|  |  |  | ML092 | 94366 |  | - | 95670 | 1304 | 18.256 |  |  | 1.304 |  |  | 9.555
|  |  |  | ML093 | 95766 |  | - | 100050 | 3984 | 55.776 |  |  | 3.984 |  |  | 29.253
|  |  |  | Sub-total |  |  |  |  | 6608 | 92.512 | 61.29 | 5670.0605 | 6.608 | 438.31 | 2896.3525 | 48.51 | 572.73 | 27783.1323
| Quang Ngai | PKGA3 | MLA3-1 | ML094 | 99950 |  | - | 100252 | 302 | 4.228 |  |  | 0.302 |  |  | 2.205
|  |  |  | ML095 | 100348 |  | - | 103171 | 2996.22 | 41.9471 |  |  | 2.9962 |  |  | 21.903
|  |  |  | ML096 | 103337 |  | - | 105050 | 1713 | 23.982 |  |  | 1.713 |  |  | 12.495
|  |  |  | Sub-total |  |  |  |  | 5011.22 | 70.1571 | 61.29 | 4299.9274 | 5.0112 | 438.31 | 2196.4678 | 36.603 | 572.73 | 20963.6362
|  |  | MLA3-2 | ML097 | 104950 |  | - | 105280 | 330 | 4.62 |  |  | 0.33 |  |  | 2.352
|  |  |  | ML098 | 105376 |  | - | 106626 | 1250 | 17.5 |  |  | 1.25 |  |  | 9.114
|  |  |  | ML099 | 106792 |  | - | 108952 | 2160 | 30.24 |  |  | 2.16 |  |  | 15.876
|  |  |  | ML100 | 109746 |  | - | 110050 | 304 | 4.256 |  |  | 0.304 |  |  | 2.205
|  |  |  | Sub-total |  |  |  |  | 4044 | 56.616 | 61.29 | 3469.9946 | 4.044 | 438.31 | 1772.5256 | 29.547 | 572.73 | 16922.4533
| Quang Ngai | PKGA4 | MLA4-1 | ML101 | 109950 |  | - | 110045 | 95 | 1.33 |  |  | 0.095 |  |  | 0.588
|  |  |  | ML102 | 110211 |  | - | 110674 | 463 | 6.482 |  |  | 0.463 |  |  | 3.381
|  |  |  | ML103 | 111566 |  | - | 115050 | 3484 | 48.776 |  |  | 3.484 |  |  | 25.578
|  |  |  | Sub-total |  |  |  |  | 558 | 56.588 | 61.29 | 3468.2785 | 4.042 | 438.31 | 1771.649 | 29.547 | 572.73 | 16922.4533
|  |  | MLA4-2 | ML104 | 114950 |  | - | 116280 | 1330 | 18.62 |  |  | 1.33 |  |  | 9.702
|  |  |  | ML105 | 116372 |  | - | 118320.5 | 1948.5 | 27.279 |  |  | 1.9485 |  |  | 14.259
|  |  |  | ML106 | 118425.5 |  | - | 120050 | 1624.5 | 22.743 |  |  | 1.6245 |  |  | 11.907
|  |  |  | Sub-total |  |  |  |  | 4903 | 68.642 | 61.29 | 4207.0682 | 4.903 | 438.31 | 2149.0339 | 35.868 | 572.73 | 20542.6796
|  |  | MLA4-3 | ML107 | 119950 |  | - | 123994 | 4044 | 56.616 |  |  | 4.044 |  |  | 29.694
|  |  |  | ML108 | 124806 |  | - | 125050 | 244 | 3.416 |  |  | 0.244 |  |  | 1.764
|  |  |  | Sub-total |  |  |  |  | 4288 | 60.032 | 61.29 | 3679.3613 | 4.288 | 438.31 | 1879.4733 | 31.458 | 572.73 | 18016.9403
| Quang Ngai | PKGA5 | MLA5-1 | ML109 | 124950 |  | - | 125077 | 127 | 1.778 |  |  | 0.127 |  |  | 0.882
|  |  |  | ML110 | 126323 |  | - | 126674 | 351 | 4.914 |  |  | 0.351 |  |  | 2.499
|  |  |  | ML111 | 127726 |  | - | 127934 | 208 | 2.912 |  |  | 0.208 |  |  | 1.47
|  |  |  | ML112 | 128426 |  | - | 131550 | 3124 | 43.736 |  |  | 3.124 |  |  | 22.932
|  |  |  | Sub-total |  |  |  |  | 3810 | 53.34 | 61.29 | 3269.2086 | 3.81 | 438.31 | 1669.9611 | 27.783 | 572.73 | 15912.1576
Jurisdiction |  | Construction | Survey | Survey Section |  |  |  |  | Section | Qty and Price | [8 empty] | Remarks
|  | Contract No. | Package | [5 empty] | Length | 11.1 Planimetric |  |  | 11.2 Profile |  |  | 11.3 Cross-section
[10 empty] | Qty | Unit Price | Amount | Qty | Unit Price | Amount | Qty | Unit Price | Amount
[10 empty] | (ha) | (USD) | (USD) | (km) | (USD) | (USD) | (km) | (USD) | (USD)
C. Linking Road, 11. Main Line (ML, Road Section)
Quang Ngai |  | PKGA5 | MLA5-2 | ML113 | 131450 |  | - | 132883 | 1433 | 14.33 |  |  | 1.433 |  |  | 4.473
|  |  |  | ML114 | 132985 |  | - | 134675 | 1690 | 16.9 |  |  | 1.69 |  |  | 5.292
|  |  |  | ML115 | 134777 |  | - | 136050 | 1273 | 12.73 |  |  | 1.273 |  |  | 3.969
|  |  |  | Sub-total |  |  |  |  | 4396 | 43.96 | 61.29 | 2694.3084 | 4.396 | 438.31 | 1926.8108 | 13.734 | 572.73 | 7865.8738
|  |  | MLA5-3 | ML116 | 135950 |  | - | 138552.5 | 2602.5 | 26.025 |  |  | 2.6025 |  |  | 8.19
|  |  |  | ML117 | 138645.5 |  | - | 139572 | 926.5 | 9.265 |  |  | 0.9265 |  |  | 2.898
|  |  |  | Sub-total |  |  |  |  | 3529 | 35.29 | 61.29 | 2162.9241 | 3.529 | 438.31 | 1546.796 | 11.088 | 572.73 | 6350.4302

## 4.2.2TN
Jurisdiction |  | Construction | Survey | Features of Tunnel |  |  |  | Survey Section |  |  |  |  | Qty and Price |  |  |  |  | Remarks
|  | Contract No. | Package | Section |  |  | Length | Section |  |  |  | Length | 4.1 Planimetric |  |  | Profile | Cross-section
[7 empty] | (m) |  |  |  |  | (m) | Qty | Unit Price | Amount
[13 empty] | (ha) | (USD) | (USD)
B. Expressway, 4. Tunnel (TN)
| Quang Nam | PKG04 | ML04-1 | 22630 | - | 23170 | 540 | TN01 | 22630 | - | 23170 | 540 | 1.02 |  |  | Included in Seismic Measurement Survey |  |  | At Portals: 0.60 ha (BP Side), 0.42 ha (EP Side)
|  |  |  | Sub-total |  |  | 540 |  |  |  |  | 540 | 1.02 | 175.36 | 178.8672

## 4.2.3BR
Item |  |  |  | BR (excl. IRB)
|  |  |  | L < 100 | L > 100 | Expressway | [12 empty] | Linking Road |  | VP, OP, FO |  |  | Other BR |  | LRB | ORB
[6 empty] | FO |  | Other BR | [10 empty] | ORB, VD
[8 empty] | L < 50 |  | 50 < L < 100 |  |  | 100 < L < 300 |  |  | L > 300 |  |  | L < 50
| Secondary Control Point |  |  | 2 | 4
| Approach Road Length |  |  |  |  | 2@ | 200 | 2@ | 30 | 2@ |  | 50 | 2@ | 100 |  | 2@ | 200 |  | 2@ | 30
| Planimetric |  | Width |  |  | 100 |  | 140 | [10 empty] | 100
| Cross-section |  | Pitch |  |  | 20
| (Approach Road) |  | Width |  |  | 60 |  | 140 | [10 empty] | 60
|  |  | Transition |  |  | 5%
| On Shore/Off Shore |  | On Shore | [17 empty] | Whole Section |  |  | Approach Section
|  |  | Off Shore | [20 empty] | Bridge Section
| River Profile |  | Pitch/Nos. | [22 empty] | 30 | 1
|  |  | Length | [22 empty] | 200 | 100 |  | KM***+*** |  | : Continuous BR Survey Section (Length between BR Survey Sections < 50 m)
| River Cross-section |  | Nos. | [22 empty] | 4 | 2 |  | ***.** (m) |  | : Including Equation
Jurisdiction |  | Construction | Survey | Features of Bridge | [8 empty] | Survey Section | [8 empty] | Qty and Price
|  | Contract No. | Package | Station | Length | Width |  | Section |  |  |  |  | Section | [6 empty] | Length |  | 5.1 Secondary Control Point |  |  | Planimetric | [6 empty] | Profile | [5 empty] | 5.6 Cross-section |  |  | 5.7 River Profile |  |  | 5.8 River Cross-section
[5 empty] | (m) | (m) | [6 empty] | (m) | [6 empty] | (m) |  |  |  |  | 5.2 On Shore |  |  | 5.3 Off Shore |  |  |  | 5.4 On Shore |  |  | 5.5 Off Shore |  |  | (Approach Road)
[22 empty] | Qty | Unit Price | Amount | Qty | Unit Price | Amount | Qty |  | Unit Price | Amount | Qty | Unit Price | Amount | Qty | Unit Price | Amount | Qty | Unit Price | Amount | Qty | Unit Price | Amount | Qty | Unit Price | Amount
[22 empty] | (nos.) | (USD) | (USD) | (ha) | (USD) | (USD) | (ha) |  | (USD) | (USD) | (km) | (USD) | (USD) | (km) | (USD) | (USD) | (km) | (USD) | (USD) | (km) | (USD) | (USD) | (km) | (USD) | (USD)
B. Expressway, 5. Bridge (BR, Main Line (ML))
| Danang | PKG01 | ML01-1 | -120 | 49.1 | 26 |  | -144.55 |  | - | -95.45 |  | VD01 |  | -174.55 |  | - | -65.45 |  | 109.1 |  | 2 |  |  | 1.5274 | [6 empty] | 0.1091 | [5 empty] | 0.441
|  |  |  | 1619 | 743.15 | 26 |  | 1247.425 |  | - | 1990.575 |  | LRB01 |  | 1047.425 |  | - | 2190.575 |  | 1143.15 |  | 4 |  |  | 5.6 |  |  | 10.4041 |  |  |  | 0.4 |  |  | 0.74315 |  |  | 2.94 |  |  | 5 |  |  | 2.9726
|  |  |  | 2510 | 181.3 | 26 |  | 2419.35 |  | - | 2600.65 |  | LRB02 |  | 2319.35 |  | - | 2700.65 |  | 381.3 |  | 4 |  |  | 2.8 |  |  | 2.5382 |  |  |  | 0.2 |  |  | 0.1813 |  |  | 1.47 |  |  | 1.2 |  |  | 0.7252
|  |  |  | Sub-total | 973.55 | [14 empty] | 1633.55 |  | 10 | 150.63 | 1506.3 | 9.9274 | 175.36 | 1740.8689 | 12.9423 |  | 226.18 | 2927.2894 | 0.7091 | 438.31 | 310.8056 | 0.92445 | 474.97 | 439.086 | 4.851 | 572.73 | 2778.3132 | 6.2 | 474.97 | 2944.814 | 3.6978 | 655.49 | 2423.8709
|  |  | ML01-2 | 5623 | 113.2 | 26 |  | 5566.4 |  | - | 5679.6 |  | LRB03 |  | 5466.4 |  | - | 5708.275 |  | 241.875 |  | 4 |  |  | 1.8014 |  |  | 1.5848 |  |  |  | 0.12868 |  |  | 0.1132 |  |  | 0.882 |  |  | 0.8 |  |  | 0.4528
|  |  |  | 5750 | 26.1 | 26 |  | 5736.95 |  | - | 5763.05 |  | OP01 |  | 5708.275 |  | - | 5793.05 |  | 84.775 |  | 2 |  |  | 1.1869 | [6 empty] | 0.084775 | [5 empty] | 0.441
|  |  |  | 7926 | 23.1 | 26 |  | 7914.45 |  | - | 7937.55 |  | OP02 |  | 7884.45 |  | - | 7967.55 |  | 83.1 |  | 2 |  |  | 1.1634 | [6 empty] | 0.0831 | [5 empty] | 0.441
|  |  |  | Sub-total | 162.4 | [14 empty] | 409.75 |  | 8 | 150.63 | 1205.04 | 4.1517 | 175.36 | 728.0421 | 1.5848 |  | 226.18 | 358.4501 | 0.29655 | 438.31 | 129.9808 | 0.1132 | 474.97 | 53.7666 | 1.764 | 572.73 | 1010.2957 | 0.8 | 474.97 | 379.976 | 0.4528 | 655.49 | 296.8059
| Quang Nam | PKG02 | ML02-1 | 9870 | 183.3 | 26 |  | 9778.35 |  | - | 9961.65 |  | LRB04 |  | 9678.35 |  | - | 10061.65 |  | 383.3 |  | 4 |  |  | 2.8 |  |  | 2.5662 |  |  |  | 0.2 |  |  | 0.1833 |  |  | 1.47 |  |  | 1.2 |  |  | 0.7332
|  |  |  | 10271 | 90.2 | 26 |  | 10225.9 |  | - | 10316.1 |  | VD02 |  | 10175.9 |  | - | 10366.1 |  | 190.2 |  | 2 |  |  | 2.6628 | [6 empty] | 0.1902 | [5 empty] | 0.735
|  |  |  | 10882 | 117.2 | 26 |  | 10823.4 |  | - | 10940.6 |  | LRB05 |  | 10723.4 |  | - | 11040.6 |  | 317.2 |  | 4 |  |  | 2.8 |  |  | 1.6408 |  |  |  | 0.2 |  |  | 0.1172 |  |  | 1.47 |  |  | 0.8 |  |  | 0.4688
|  |  |  | 11904 | 150.25 | 26 |  | 11828.875 |  | - | 11979.125 |  | VD03 |  | 11728.875 |  | - | 12079.125 |  | 350.25 |  | 4 |  |  | 4.9035 | [6 empty] | 0.35025 | [5 empty] | 1.47
|  |  |  | 12639 | 86.2 | 26 |  | 12595.9 |  | - | 12682.1 |  | ORB01 |  | 12545.9 |  | - | 12732.1 |  | 186.2 |  | 2 |  |  | 1.4 |  |  | 1.2068 |  |  |  | 0.1 |  |  | 0.0862 |  |  | 0.735 |  |  | 0.1 |  |  | 0.1724
|  |  |  | Sub-total | 627.15 | [14 empty] | 1427.15 |  | 16 | 150.63 | 2410.08 | 14.5663 | 175.36 | 2554.3464 | 5.4138 |  | 226.18 | 1224.4933 | 1.0405 | 438.31 | 456.0396 | 0.3867 | 474.97 | 183.6709 | 5.88 | 572.73 | 3367.6524 | 2.1 | 474.97 | 997.437 | 1.3744 | 655.49 | 900.9055
|  |  | ML02-2 | 13210 | 138.3 | 26 |  | 13140.85 |  | - | 13279.15 |  | VD04 |  | 13040.85 |  | - | 13379.15 |  | 338.3 |  | 4 |  |  | 4.7362 | [6 empty] | 0.3383 | [5 empty] | 1.47
|  |  |  | 13626 | 42.1 | 26 |  | 13604.95 |  | - | 13647.05 |  | OP03 |  | 13574.95 |  | - | 13677.05 |  | 102.1 |  | 2 |  |  | 1.4294 | [6 empty] | 0.1021 | [5 empty] | 0.441
|  |  |  | 14027 | 117.2 | 26 |  | 13968.4 |  | - | 14085.6 |  | LRB06 |  | 13868.4 |  | - | 14185.6 |  | 317.2 |  | 4 |  |  | 2.8 |  |  | 1.6408 |  |  |  | 0.2 |  |  | 0.1172 |  |  | 1.47 |  |  | 0.8 |  |  | 0.4688
|  |  |  | 14873 | 117.2 | 26 |  | 14814.4 |  | - | 14931.6 |  | VD05 |  | 14714.4 |  | - | 15022 |  | 307.6 |  | 4 |  |  | 4.3064 | [6 empty] | 0.3076 | [5 empty] | 1.47
|  |  |  | 15171 | 117.2 | 26 |  | 15112.4 |  | - | 15229.6 |  | VD06 |  | 15022 |  | - | 15329.6 |  | 307.6 |  | 4 |  |  | 4.3064 | [6 empty] | 0.3076 | [5 empty] | 1.47
|  |  |  | 16497 | 117.2 | 26 |  | 16438.4 |  | - | 16555.6 |  | LRB07 |  | 16338.4 |  | - | 16655.6 |  | 317.2 |  | 4 |  |  | 2.8 |  |  | 1.6408 |  |  |  | 0.2 |  |  | 0.1172 |  |  | 1.47 |  |  | 0.8 |  |  | 0.4688
|  |  |  | Sub-total | 649.2 | [14 empty] | 1690 |  | 22 | 150.63 | 3313.86 | 20.3784 | 175.36 | 3573.5562 | 3.2816 |  | 226.18 | 742.2323 | 1.4556 | 438.31 | 638.004 | 0.2344 | 474.97 | 111.333 | 7.791 | 572.73 | 4462.1394 | 1.6 | 474.97 | 759.952 | 0.9376 | 655.49 | 614.5874
|  | PKG03 | ML03-1 | 17662 | 962 | 26 |  | 17181 |  | - | 18143 |  | LRB08 |  | 16950 |  | - | 18209.45 |  | 1259.45 |  | 4 |  |  | 4.1643 |  |  | 13.468 |  |  |  | 0.29745 |  |  | 0.962 |  |  | 2.205 |  |  | 6.4 |  |  | 3.848
|  |  |  | 18319 | 86.2 | 26 |  | 18275.9 |  | - | 18362.1 |  | VD07 |  | 18209.45 |  | - | 18412.1 |  | 202.65 |  | 2 |  |  | 2.8371 | [6 empty] | 0.20265 | [5 empty] | 0.882
|  |  |  | 18612 | 62.15 | 26 |  | 18580.925 |  | - | 18643.075 |  | VD08 |  | 18530.925 |  | - | 18715.4875 |  | 184.5625 |  | 2 |  |  | 2.5839 | [6 empty] | 0.18456 | [5 empty] | 0.882
|  |  |  | 18831 | 86.2 | 26 |  | 18787.9 |  | - | 18874.1 |  | VD09 |  | 18715.4875 |  | - | 18924.1 |  | 208.6125 |  | 2 |  |  | 2.9206 | [6 empty] | 0.20861 | [5 empty] | 0.882
|  |  |  | 19209 | 26.1 | 26 |  | 19195.95 |  | - | 19222.05 |  | OP04 |  | 19165.95 |  | - | 19214.47 |  | 108.3 |  | 2 |  |  | 1.5162 | [6 empty] | 0.1083 | [5 empty] | 0.588
|  |  |  | 19350 | 47.1 | 26 |  | 19326.45 |  | - | 19373.55 |  | VD10 |  | 19214.47 |  | - | 19403.55 |  | 129.3 |  | 2 |  |  | 1.8102 | [6 empty] | 0.1293 | [5 empty] | 0.588
|  |  |  | 20185 | 410 | 26 |  | 19980 |  | - | 20390 |  | LRB09 |  | 19780 |  | - | 20590 |  | 810 |  | 4 |  |  | 5.6 |  |  | 5.74 |  |  |  | 0.4 |  |  | 0.41 |  |  | 2.94 |  |  | 2.8 |  |  | 1.64
|  |  |  | 21900 | 47.1 | 26 |  | 21876.45 |  | - | 21923.55 |  | VD11 |  | 21846.45 |  | - | 21953.55 |  | 107.1 |  | 2 |  |  | 1.4994 | [6 empty] | 0.1071 | [5 empty] | 0.441
|  |  |  | Sub-total | 1726.85 | [14 empty] | 3009.975 |  | 20 | 150.63 | 3012.6 | 22.9316 | 175.36 | 4021.2941 | 19.208 |  | 226.18 | 4344.4654 | 1.638 | 438.31 | 717.9408 | 1.372 | 474.97 | 651.6588 | 9.408 | 572.73 | 5388.2438 | 9.2 | 474.97 | 4369.724 | 5.488 | 655.49 | 3597.3291
|  | PKG04 | ML04-1 | 23350 | 62.15 | 26 |  | 23318.925 |  | - | 23381.075 |  | SB01 |  | 23268.925 |  | - | 23431.075 |  | 162.15 |  | 2 |  |  | 1.4 |  |  | 0.8701 |  |  |  | 0.1 |  |  | 0.06215 |  |  | 0.735
|  |  |  | 24430 | 26.1 | 26 |  | 24416.95 |  | - | 24443.05 |  | OP05 |  | 24386.95 |  | - | 24473.05 |  | 86.1 |  | 2 |  |  | 1.2054 | [6 empty] | 0.0861 | [5 empty] | 0.441
|  |  |  | 24648 | 77.65 | 26 |  | 24609.175 |  | - | 24686.825 |  | ORB02 |  | 24559.175 |  | - | 24736.825 |  | 177.65 |  | 2 |  |  | 1.4 |  |  | 1.0871 |  |  |  | 0.1 |  |  | 0.07765 |  |  | 0.735 |  |  | 0.1 |  |  | 0.1553
|  |  |  | 25062 | 26.1 | 26 |  | 25048.95 |  | - | 25075.05 |  | OP06 |  | 25018.95 |  | - | 25105.05 |  | 86.1 |  | 2 |  |  | 1.2054 | [6 empty] | 0.0861 | [5 empty] | 0.441
|  |  |  | 25720 | 36.1 | 26 |  | 25701.95 |  | - | 25738.05 |  | SB02 |  | 25671.95 |  | - | 25768.05 |  | 96.1 |  | 2 |  |  | 0.84 |  |  | 0.5054 |  |  |  | 0.06 |  |  | 0.0361 |  |  | 0.441
|  |  |  | Sub-total | 228.1 | [14 empty] | 608.1 |  | 10 | 150.63 | 1506.3 | 6.0508 | 175.36 | 1061.0683 | 2.4626 |  | 226.18 | 556.9909 | 0.4322 | 438.31 | 189.4376 | 0.1759 | 474.97 | 83.5472 | 2.793 | 572.73 | 1599.6349 | 0.1 | 474.97 | 47.497 | 0.1553 | 655.49 | 101.7976
|  |  | ML04-2 | 27000 | 34.1 | 26 |  | 26982.95 |  | - | 27017.05 |  | VD12 |  | 26952.95 |  | - | 27047.05 |  | 94.1 |  | 2 |  |  | 1.3174 | [6 empty] | 0.0941 | [5 empty] | 0.441
|  |  |  | 27900 | 26.1 | 26 |  | 27886.95 |  | - | 27913.05 |  | VD13 |  | 27856.95 |  | - | 27943.05 |  | 86.1 |  | 2 |  |  | 1.2054 | [6 empty] | 0.0861 | [5 empty] | 0.441
|  |  |  | 28778 | 26.1 | 26 |  | 28764.95 |  | - | 28791.05 |  | OP07 |  | 28734.95 |  | - | 28821.05 |  | 86.1 |  | 2 |  |  | 1.2054 | [6 empty] | 0.0861 | [5 empty] | 0.441
|  |  |  | 29500 | 77.65 | 26 |  | 29461.175 |  | - | 29538.825 |  | SB03 |  | 29411.175 |  | - | 29588.825 |  | 177.65 |  | 2 |  |  | 1.4 |  |  | 1.0871 |  |  |  | 0.1 |  |  | 0.07765 |  |  | 0.735
|  |  |  | 31950 | 26.1 | 26 |  | 31936.95 |  | - | 31963.05 |  | OP08 |  | 31906.95 |  | - | 31993.05 |  | 86.1 |  | 2 |  |  | 1.2054 | [6 empty] | 0.0861 | [5 empty] | 0.441
|  |  |  | Sub-total | 190.05 | [14 empty] | 530.05 |  | 10 | 150.63 | 1506.3 | 6.3336 | 175.36 | 1110.6601 | 1.0871 |  | 226.18 | 245.8803 | 0.4524 | 438.31 | 198.2914 | 0.07765 | 474.97 | 36.8814 | 2.499 | 572.73 | 1431.2523
|  | PKG05 | ML05-1 | 32440 | 26.1 | 26 |  | 32426.95 |  | - | 32453.05 |  | VD14 |  | 32396.95 |  | - | 32483.05 |  | 86.1 |  | 2 |  |  | 1.2054 | [6 empty] | 0.0861 | [5 empty] | 0.441
|  |  |  | 34120 | 70.15 | 26 |  | 34084.925 |  | - | 34155.075 |  | VD15 |  | 34034.925 |  | - | 34205.075 |  | 170.15 |  | 2 |  |  | 2.3821 | [6 empty] | 0.17015 | [5 empty] | 0.735
|  |  |  | Sub-total | 96.25 | [14 empty] | 256.25 |  | 4 | 150.63 | 602.52 | 3.5875 | 175.36 | 629.104 | 0 |  | 226.18 | 0 | 0.25625 | 438.31 | 112.3169 | 0 | 474.97 | 0 | 1.176 | 572.73 | 673.5305 | 0 | 474.97 | 0 | 0 | 655.49 | 0
|  |  | ML05-2 | 35353 | 35 | 26 |  | 35335.5 |  | - | 35370.5 |  | OP09 |  | 35305.5 |  | - | 35400.5 |  | 95 |  | 2 |  |  | 1.33 | [6 empty] | 0.095 | [5 empty] | 0.441
|  |  |  | 36200 | 60 | 26 |  | 36170 |  | - | 36230 |  | ORB03 |  | 36120 |  | - | 36280 |  | 160 |  | 2 |  |  | 1.4 |  |  | 0.84 |  |  |  | 0.1 |  |  | 0.06 |  |  | 0.735 |  |  | 0.1 |  |  | 0.12
|  |  |  | 36780 | 24 | 26 |  | 36768 |  | - | 36792 |  | SB04 |  | 36738 |  | - | 36822 |  | 84 |  | 2 |  |  | 0.84 |  |  | 0.336 |  |  |  | 0.06 |  |  | 0.024 |  |  | 0.441
|  |  |  | 38287 | 142 | 26 |  | 38216 |  | - | 38358 |  | LRB10 |  | 38116 |  | - | 38458 |  | 342 |  | 4 |  |  | 2.8 |  |  | 1.988 |  |  |  | 0.2 |  |  | 0.142 |  |  | 1.47 |  |  | 1 |  |  | 0.568
|  |  |  | 38787 | 19 | 26 |  | 38777.5 |  | - | 38796.5 |  | OP10 |  | 38747.5 |  | - | 38826.5 |  | 79 |  | 2 |  |  | 1.106 | [6 empty] | 0.079 | [5 empty] | 0.441
|  |  |  | 39550 | 176 | 26 |  | 39462 |  | - | 39638 |  | LRB11 |  | 39362 |  | - | 39738 |  | 376 |  | 4 |  |  | 2.8 |  |  | 2.464 |  |  |  | 0.2 |  |  | 0.176 |  |  | 1.47 |  |  | 1.2 |  |  | 0.704
|  |  |  | 39995 | 22 | 26 |  | 39984 |  | - | 40006 |  | CB01 |  | 39954 |  | - | 40036 |  | 82 |  | 2 |  |  | 0.84 |  |  | 0.308 |  |  |  | 0.06 |  |  | 0.022 |  |  | 0.441
|  |  |  | 41121 | 38 | 26 |  | 41102 |  | - | 41140 |  | OP11 |  | 41072 |  | - | 41170 |  | 98 |  | 2 |  |  | 1.372 | [6 empty] | 0.098 | [5 empty] | 0.441
|  |  |  | Sub-total | 516 | [14 empty] | 1316 |  | 20 | 150.63 | 3012.6 | 12.488 | 175.36 | 2189.8957 | 5.936 |  | 226.18 | 1342.6045 | 0.892 | 438.31 | 390.9725 | 0.424 | 474.97 | 201.3873 | 5.88 | 572.73 | 3367.6524 | 2.3 | 474.97 | 1092.431 | 1.392 | 655.49 | 912.4421
| Quang Nam | PKG06 | ML06-1 | 42058 | 58 | 26 |  | 42029 |  | - | 42087 |  | CB02 |  | 41950 |  | - | 42137 |  | 187 |  | 2 |  |  | 1.806 |  |  | 0.812 |  |  |  | 0.129 |  |  | 0.058 |  |  | 0.882
|  |  |  | 42596 | 34 | 26 |  | 42579 |  | - | 42613 |  | OP12 |  | 42549 |  | - | 42643 |  | 94 |  | 2 |  |  | 1.316 | [6 empty] | 0.094 | [5 empty] | 0.441
|  |  |  | 43520 | 23 | 26 |  | 43508.5 |  | - | 43531.5 |  | CB03 |  | 43478.5 |  | - | 43561.5 |  | 83 |  | 2 |  |  | 0.84 |  |  | 0.322 |  |  |  | 0.06 |  |  | 0.023 |  |  | 0.441
|  |  |  | 44300 | 58 | 26 |  | 44271 |  | - | 44329 |  | ORB04 |  | 44221 |  | - | 44379 |  | 158 |  | 2 |  |  | 1.4 |  |  | 0.812 |  |  |  | 0.1 |  |  | 0.058 |  |  | 0.735 |  |  | 0.1 |  |  | 0.116
|  |  |  | 45306 | 21 | 26 |  | 45295.5 |  | - | 45316.5 |  | SB05 |  | 45265.5 |  | - | 45346.5 |  | 81 |  | 2 |  |  | 0.84 |  |  | 0.294 |  |  |  | 0.06 |  |  | 0.021 |  |  | 0.441
|  |  |  | 45525 | 25 | 26 |  | 45512.5 |  | - | 45537.5 |  | CB04 |  | 45482.5 |  | - | 45620.75 |  | 138.25 |  | 2 |  |  | 1.5855 |  |  | 0.35 |  |  |  | 0.11325 |  |  | 0.025 |  |  | 0.882
|  |  |  | 45775 | 142 | 26 |  | 45704 |  | - | 45846 |  | LRB12 |  | 45620.75 |  | - | 45946 |  | 325.25 |  | 4 |  |  | 2.5655 |  |  | 1.988 |  |  |  | 0.18325 |  |  | 0.142 |  |  | 1.323 |  |  | 1 |  |  | 0.568
|  |  |  | 46121 | 19 | 26 |  | 46111.5 |  | - | 46130.5 |  | OP13 |  | 46081.5 |  | - | 46160.5 |  | 79 |  | 2 |  |  | 1.106 | [6 empty] | 0.079 | [5 empty] | 0.441
|  |  |  | Sub-total | 380 | [14 empty] | 1145.5 |  | 18 | 150.63 | 2711.34 | 11.459 | 175.36 | 2009.4502 | 4.578 |  | 226.18 | 1035.452 | 0.8185 | 438.31 | 358.7567 | 0.327 | 474.97 | 155.3152 | 5.586 | 572.73 | 3199.2698 | 1.1 | 474.97 | 522.467 | 0.684 | 655.49 | 448.3552
|  |  | ML06-2 | 46750 | 25 | 26 |  | 46737.5 |  | - | 46762.5 |  | SB06 |  | 46707.5 |  | - | 46792.5 |  | 85 |  | 2 |  |  | 0.84 |  |  | 0.35 |  |  |  | 0.06 |  |  | 0.025 |  |  | 0.441
|  |  |  | 47012 | 19 | 26 |  | 47002.5 |  | - | 47021.5 |  | OP14 |  | 46972.5 |  | - | 47051.5 |  | 79 |  | 2 |  |  | 1.106 | [6 empty] | 0.079 | [5 empty] | 0.441
|  |  |  | 47850 | 142 | 26 |  | 47779 |  | - | 47921 |  | LRB13 |  | 47679 |  | - | 48021 |  | 342 |  | 4 |  |  | 2.8 |  |  | 1.988 |  |  |  | 0.2 |  |  | 0.142 |  |  | 1.47 |  |  | 1 |  |  | 0.568
|  |  |  | 51120 | 19 | 26 |  | 51110.5 |  | - | 51129.5 |  | OP15 |  | 51080.5 |  | - | 51159.5 |  | 79 |  | 2 |  |  | 1.106 | [6 empty] | 0.079 | [5 empty] | 0.441
|  |  |  | Sub-total | 205 | [14 empty] | 585 |  | 10 | 150.63 | 1506.3 | 5.852 | 175.36 | 1026.2067 | 2.338 |  | 226.18 | 528.8088 | 0.418 | 438.31 | 183.2136 | 0.167 | 474.97 | 79.32 | 2.793 | 572.73 | 1599.6349 | 1 | 474.97 | 474.97 | 0.568 | 655.49 | 372.3183
|  | PKG07 | ML07-1 | 54222 | 19 | 26 |  | 54212.5 |  | - | 54231.5 |  | OP16 |  | 54182.5 |  | - | 54261.5 |  | 79 |  | 2 |  |  | 1.106 | [6 empty] | 0.079 | [5 empty] | 0.441
|  |  |  | 54783 | 45 | 26 |  | 54760.5 |  | - | 54805.5 |  | ORB05 |  | 54730.5 |  | - | 54835.5 |  | 105 |  | 2 |  |  | 0.84 |  |  | 0.63 |  |  |  | 0.06 |  |  | 0.045 |  |  | 0.441 |  |  | 0.1 |  |  | 0.09
|  |  |  | 55500 | 142 | 26 |  | 55429 |  | - | 55571 |  | LRB14 |  | 55329 |  | - | 55671 |  | 342 |  | 4 |  |  | 2.8 |  |  | 1.988 |  |  |  | 0.2 |  |  | 0.142 |  |  | 1.47 |  |  | 1 |  |  | 0.568
|  |  |  | Sub-total | 206 | [14 empty] | 526 |  | 8 | 150.63 | 1205.04 | 4.746 | 175.36 | 832.2586 | 2.618 |  | 226.18 | 592.1392 | 0.339 | 438.31 | 148.5871 | 0.187 | 474.97 | 88.8194 | 2.352 | 572.73 | 1347.061 | 1.1 | 474.97 | 522.467 | 0.658 | 655.49 | 431.3124
|  |  | ML07-2 | 56300 | 22 | 26 |  | 56289 |  | - | 56311 |  | CB05 |  | 56259 |  | - | 56335.75 |  | 76.75 |  | 2 |  |  | 0.7665 |  |  | 0.308 |  |  |  | 0.05475 |  |  | 0.022 |  |  | 0.441
|  |  |  | 56370 | 19 | 26 |  | 56360.5 |  | - | 56379.5 |  | OP17 |  | 56335.75 |  | - | 56409.5 |  | 73.75 |  | 2 |  |  | 1.0325 | [6 empty] | 0.07375 | [5 empty] | 0.441
|  |  |  | 56950 | 45 | 26 |  | 56927.5 |  | - | 56972.5 |  | ORB06 |  | 56897.5 |  | - | 57002.5 |  | 105 |  | 2 |  |  | 0.84 |  |  | 0.63 |  |  |  | 0.06 |  |  | 0.045 |  |  | 0.441 |  |  | 0.1 |  |  | 0.09
|  |  |  | 57378 | 32 | 26 |  | 57362 |  | - | 57394 |  | OP18 |  | 57332 |  | - | 57424 |  | 92 |  | 2 |  |  | 1.288 | [6 empty] | 0.092 | [5 empty] | 0.441
|  |  |  | 58120 | 142 | 26 |  | 58049 |  | - | 58191 |  | LRB15 |  | 57949 |  | - | 58291 |  | 342 |  | 4 |  |  | 2.8 |  |  | 1.988 |  |  |  | 0.2 |  |  | 0.142 |  |  | 1.47 |  |  | 1 |  |  | 0.568
|  |  |  | 59167 | 22 | 26 |  | 59156 |  | - | 59178 |  | OP19 |  | 59126 |  | - | 59208 |  | 82 |  | 2 |  |  | 1.148 | [6 empty] | 0.082 | [5 empty] | 0.441
|  |  |  | Sub-total | 282 | [14 empty] | 771.5 |  | 14 | 150.63 | 2108.82 | 7.875 | 175.36 | 1380.96 | 2.926 |  | 226.18 | 661.8027 | 0.5625 | 438.31 | 246.5494 | 0.209 | 474.97 | 99.2687 | 3.675 | 572.73 | 2104.7827 | 1.1 | 474.97 | 522.467 | 0.658 | 655.49 | 431.3124
|  |  | ML07-3 | 62337 | 73 | 26 |  | 62300.5 |  | - | 62373.5 |  | ORB07 |  | 62250.5 |  | - | 62423.5 |  | 173 |  | 2 |  |  | 1.4 |  |  | 1.022 |  |  |  | 0.1 |  |  | 0.073 |  |  | 0.735 |  |  | 0.1 |  |  | 0.146
|  |  |  | Sub-total | 73 | [14 empty] | 173 |  | 2 | 150.63 | 301.26 | 1.4 | 175.36 | 245.504 | 1.022 |  | 226.18 | 231.156 | 0.1 | 438.31 | 43.831 | 0.073 | 474.97 | 34.6728 | 0.735 | 572.73 | 420.9565 | 0.1 | 474.97 | 47.497 | 0.146 | 655.49 | 95.7015
|  | PKGA1 | MLA1-1 | 66200 | 73 | 26 |  | 66163.5 |  | - | 66236.5 |  | SB07 |  | 66113.5 |  | - | 66286.5 |  | 173 |  | 2 |  |  | 1.4 |  |  | 1.022 |  |  |  | 0.1 |  |  | 0.073 |  |  | 0.735
|  |  |  | 68308 | 307 | 26 |  | 68154.5 |  | - | 68461.5 |  | LRB16 |  | 67954.5 |  | - | 68661.5 |  | 707 |  | 4 |  |  | 5.6 |  |  | 4.298 |  |  |  | 0.4 |  |  | 0.307 |  |  | 2.94 |  |  | 2 |  |  | 1.228
|  |  |  | 71000 | 25 | 26 |  | 70987.5 |  | - | 71012.5 |  | CB06 |  | 70957.5 |  | - | 71050 |  | 92.5 |  | 2 |  |  | 0.945 |  |  | 0.35 |  |  |  | 0.0675 |  |  | 0.025 |  |  | 0.441
|  |  |  | Sub-total | 405 | [14 empty] | 972.5 |  | 8 | 150.63 | 1205.04 | 7.945 | 175.36 | 1393.2352 | 5.67 |  | 226.18 | 1282.4406 | 0.5675 | 438.31 | 248.7409 | 0.405 | 474.97 | 192.3629 | 4.116 | 572.73 | 2357.3567 | 2 | 474.97 | 949.94 | 1.228 | 655.49 | 804.9417
|  |  | MLA1-2 | 74312 | 144 | 26 |  | 74240 |  | - | 74384 |  | LRB17 |  | 74140 |  | - | 74484 |  | 344 |  | 4 |  |  | 2.8 |  |  | 2.016 |  |  |  | 0.2 |  |  | 0.144 |  |  | 1.47 |  |  | 1 |  |  | 0.576
|  |  |  | 74879 | 24 | 26 |  | 74867 |  | - | 74891 |  | CB07 |  | 74837 |  | - | 74921 |  | 84 |  | 2 |  |  | 0.84 |  |  | 0.336 |  |  |  | 0.06 |  |  | 0.024 |  |  | 0.441
|  |  |  | Sub-total | 168 | [14 empty] | 428 |  | 6 | 150.63 | 903.78 | 3.64 | 175.36 | 638.3104 | 2.352 |  | 226.18 | 531.9754 | 0.26 | 438.31 | 113.9606 | 0.168 | 474.97 | 79.795 | 1.911 | 572.73 | 1094.487 | 1 | 474.97 | 474.97 | 0.576 | 655.49 | 377.5622
|  |  | MLA1-3 | 79212 | 33 | 26 |  | 79195.5 |  | - | 79228.5 |  | CB08 |  | 79165.5 |  | - | 79258.5 |  | 93 |  | 2 |  |  | 0.84 |  |  | 0.462 |  |  |  | 0.06 |  |  | 0.033 |  |  | 0.441
|  |  |  | Sub-total | 33 | [14 empty] | 93 |  | 2 | 150.63 | 301.26 | 0.84 | 175.36 | 147.3024 | 0.462 |  | 226.18 | 104.4952 | 0.06 | 438.31 | 26.2986 | 0.033 | 474.97 | 15.674 | 0.441 | 572.73 | 252.5739
|  | PKGA2 | MLA2-1 | 81556 | 45 | 26 |  | 81533.5 |  | - | 81578.5 |  | CB09 |  | 81503.5 |  | - | 81608.5 |  | 105 |  | 2 |  |  | 0.84 |  |  | 0.63 |  |  |  | 0.06 |  |  | 0.045 |  |  | 0.441
|  |  |  | 82527 | 84 | 26 |  | 82485 |  | - | 82569 |  | ORB08 |  | 82435 |  | - | 82619 |  | 184 |  | 2 |  |  | 1.4 |  |  | 1.176 |  |  |  | 0.1 |  |  | 0.084 |  |  | 0.735 |  |  | 0.1 |  |  | 0.168
|  |  |  | 85316 | 24 | 26 |  | 85304 |  | - | 85328 |  | CB10 |  | 85274 |  | - | 85358 |  | 84 |  | 2 |  |  | 0.84 |  |  | 0.336 |  |  |  | 0.06 |  |  | 0.024 |  |  | 0.441
|  |  |  | Sub-total | 153 | [14 empty] | 373 |  | 6 | 150.63 | 903.78 | 3.08 | 175.36 | 540.1088 | 2.142 |  | 226.18 | 484.4776 | 0.22 | 438.31 | 96.4282 | 0.153 | 474.97 | 72.6704 | 1.617 | 572.73 | 926.1044 | 0.1 | 474.97 | 47.497 | 0.168 | 655.49 | 110.1223
|  |  | MLA2-2 | 87892 | 36 | 26 |  | 87874 |  | - | 87910 |  | CB11 |  | 87844 |  | - | 87940 |  | 96 |  | 2 |  |  | 0.84 |  |  | 0.504 |  |  |  | 0.06 |  |  | 0.036 |  |  | 0.441
|  |  |  | 88180 | 108 | 26 |  | 88126 |  | - | 88234 |  | LRB18 |  | 88026 |  | - | 88334 |  | 308 |  | 4 |  |  | 2.8 |  |  | 1.512 |  |  |  | 0.2 |  |  | 0.108 |  |  | 1.47 |  |  | 0.8 |  |  | 0.432
|  |  |  | 90660 | 60 | 26 |  | 90630 |  | - | 90690 |  | CB12 |  | 90580 |  | - | 90740 |  | 160 |  | 2 |  |  | 1.4 |  |  | 0.84 |  |  |  | 0.1 |  |  | 0.06 |  |  | 0.735
|  |  |  | 92658 | 84 | 26 |  | 92616 |  | - | 92700 |  | CB13 |  | 92566 |  | - | 92750 |  | 184 |  | 2 |  |  | 1.4 |  |  | 1.176 |  |  |  | 0.1 |  |  | 0.084 |  |  | 0.735
|  |  |  | Sub-total | 288 | [14 empty] | 748 |  | 10 | 150.63 | 1506.3 | 6.44 | 175.36 | 1129.3184 | 4.032 |  | 226.18 | 911.9578 | 0.46 | 438.31 | 201.6226 | 0.288 | 474.97 | 136.7914 | 3.381 | 572.73 | 1936.4001 | 0.8 | 474.97 | 379.976 | 0.432 | 655.49 | 283.1717
|  |  | MLA2-3 | 94318 | 36 | 26 |  | 94300 |  | - | 94336 |  | CB14 |  | 94270 |  | - | 94366 |  | 96 |  | 2 |  |  | 0.84 |  |  | 0.504 |  |  |  | 0.06 |  |  | 0.036 |  |  | 0.441
|  |  |  | 95718 | 36 | 26 |  | 95700 |  | - | 95736 |  | CB15 |  | 95670 |  | - | 95766 |  | 96 |  | 2 |  |  | 0.84 |  |  | 0.504 |  |  |  | 0.06 |  |  | 0.036 |  |  | 0.441
|  |  |  | Sub-total | 72 | [14 empty] | 192 |  | 4 | 150.63 | 602.52 | 1.68 | 175.36 | 294.6048 | 1.008 |  | 226.18 | 227.9894 | 0.12 | 438.31 | 52.5972 | 0.072 | 474.97 | 34.1978 | 0.882 | 572.73 | 505.1479
| Quang Ngai | PKGA3 | MLA3-1 | 100300 | 36 | 26 |  | 100282 |  | - | 100318 |  | CB16 |  | 100252 |  | - | 100348 |  | 96 |  | 2 |  |  | 0.84 |  |  | 0.504 |  |  |  | 0.06 |  |  | 0.036 |  |  | 0.441
|  |  |  | 103254 | 66 | 26 |  | 103221 |  | - | 103287 |  | OP20 |  | 103171 |  | - | 103337 |  | 166 |  | 2 |  |  | 2.324 | [6 empty] | 0.166 | [5 empty] | 0.735
|  |  |  | Sub-total | 102 | [14 empty] | 262 |  | 4 | 150.63 | 602.52 | 3.164 | 175.36 | 554.839 | 0.504 |  | 226.18 | 113.9947 | 0.226 | 438.31 | 99.0581 | 0.036 | 474.97 | 17.0989 | 1.176 | 572.73 | 673.5305
|  |  | MLA3-2 | 105328 | 36 | 26 |  | 105310 |  | - | 105346 |  | VD16 |  | 105280 |  | - | 105376 |  | 96 |  | 2 |  |  | 1.344 | [6 empty] | 0.096 | [5 empty] | 0.441
|  |  |  | 106709 | 66 | 26 |  | 106676 |  | - | 106742 |  | OP21 |  | 106626 |  | - | 106792 |  | 166 |  | 2 |  |  | 2.324 | [6 empty] | 0.166 | [5 empty] | 0.735
|  |  |  | 109000 | 36 | 26 |  | 108982 |  | - | 109018 |  | SB08 |  | 108952 |  | - | 109056 |  | 104 |  | 2 |  |  | 0.952 |  |  | 0.504 |  |  |  | 0.068 |  |  | 0.036 |  |  | 0.441
|  |  |  | 109320 | 452 | 26 |  | 109094 |  | - | 109546 |  | LRB19 |  | 109056 |  | - | 109746 |  | 690 |  | 4 |  |  | 3.332 |  |  | 6.328 |  |  |  | 0.238 |  |  | 0.452 |  |  | 1.764 |  |  | 3 |  |  | 1.808
|  |  |  | Sub-total | 590 | [14 empty] | 1056 |  | 10 | 150.63 | 1506.3 | 7.952 | 175.36 | 1394.4627 | 6.832 |  | 226.18 | 1545.2618 | 0.568 | 438.31 | 248.9601 | 0.488 | 474.97 | 231.7854 | 3.381 | 572.73 | 1936.4001 | 3 | 474.97 | 1424.91 | 1.808 | 655.49 | 1185.1259
|  | PKGA4 | MLA4-1 | 110128 | 66 | 26 |  | 110095 |  | - | 110161 |  | OP22 |  | 110045 |  | - | 110211 |  | 166 |  | 2 |  |  | 2.324 | [6 empty] | 0.166 | [5 empty] | 0.735
|  |  |  | 111120 | 492 | 26 |  | 110874 |  | - | 111366 |  | VD17 |  | 110674 |  | - | 111566 |  | 892 |  | 4 |  |  | 12.488 | [6 empty] | 0.892 | [5 empty] | 2.94
|  |  |  | Sub-total | 558 | [14 empty] | 1058 |  | 6 | 150.63 | 903.78 | 14.812 | 175.36 | 2597.4323 | 0 |  | 226.18 | 0 | 1.058 | 438.31 | 463.732 | 0 | 474.97 | 0 | 3.675 | 572.73 | 2104.7827 | 0 | 474.97 | 0 | 0 | 655.49 | 0
|  |  | MLA4-2 | 116326 | 32 | 26 |  | 116310 |  | - | 116342 |  | CB17 |  | 116280 |  | - | 116372 |  | 92 |  | 2 |  |  | 0.84 |  |  | 0.448 |  |  |  | 0.06 |  |  | 0.032 |  |  | 0.441
|  |  |  | 118373 | 45 | 26 |  | 118350.5 |  | - | 118395.5 |  | CB18 |  | 118320.5 |  | - | 118425.5 |  | 105 |  | 2 |  |  | 0.84 |  |  | 0.63 |  |  |  | 0.06 |  |  | 0.045 |  |  | 0.441
|  |  |  | Sub-total | 77 | [14 empty] | 197 |  | 4 | 150.63 | 602.52 | 1.68 | 175.36 | 294.6048 | 1.078 |  | 226.18 | 243.822 | 0.12 | 438.31 | 52.5972 | 0.077 | 474.97 | 36.5727 | 0.882 | 572.73 | 505.1479
|  |  | MLA4-3 | 124400 | 412 | 26 |  | 124194 |  | - | 124606 |  | VD18 |  | 123994 |  | - | 124806 |  | 812 |  | 4 |  |  | 11.368 | [6 empty] | 0.812 | [5 empty] | 2.94
|  |  |  | Sub-total | 412 | [14 empty] | 812 |  | 4 | 150.63 | 602.52 | 11.368 | 175.36 | 1993.4925 | 0 |  | 226.18 | 0 | 0.812 | 438.31 | 355.9077 | 0 | 474.97 | 0 | 2.94 | 572.73 | 1683.8262 | 0 | 474.97 | 0 | 0 | 655.49 | 0
|  | PKGA5 | MLA5-1 | 125700 | 846 | 26 |  | 125277 |  | - | 126123 |  | LRB20 |  | 125077 |  | - | 126323 |  | 1246 |  | 4 |  |  | 5.6 |  |  | 11.844 |  |  |  | 0.4 |  |  | 0.846 |  |  | 2.94 |  |  | 5.6 |  |  | 3.384
|  |  |  | 127200 | 652 | 26 |  | 126874 |  | - | 127526 |  | VD19 |  | 126674 |  | - | 127726 |  | 1052 |  | 4 |  |  | 14.728 | [6 empty] | 1.052 | [5 empty] | 2.94
|  |  |  | 128180 | 292 | 26 |  | 128034 |  | - | 128326 |  | VD20 |  | 127934 |  | - | 128426 |  | 492 |  | 4 |  |  | 6.888 | [6 empty] | 0.492 | [5 empty] | 1.47
|  |  |  | Sub-total | 1790 | [14 empty] | 2790 |  | 12 | 150.63 | 1807.56 | 27.216 | 175.36 | 4772.5978 | 11.844 |  | 226.18 | 2678.8759 | 1.944 | 438.31 | 852.0746 | 0.846 | 474.97 | 401.8246 | 7.35 | 572.73 | 4209.5655 | 5.6 | 474.97 | 2659.832 | 3.384 | 655.49 | 2218.1782
B. Expressway, 5. Bridge (BR, Flyover (FO))
| Danang | PKG01 | ML01-1 | 0 | 220 | 12 | [6 empty] | FO01 |  | 0 | [6 empty] | 4 |  |  | 6.2 | [6 empty] | 0.62 | [5 empty] | 1.26
|  |  |  | 590 | 45 | 9 | [6 empty] | FO02 |  | 590 | [6 empty] | 2 |  |  | 4.45 | [6 empty] | 0.445 | [5 empty] | 1.26
|  |  |  | Sub-total | 265 | [16 empty] | 6 | 150.63 | 903.78 | 10.65 | 175.36 | 1867.584 |  |  |  |  | 1.065 | 438.31 | 466.8001 |  |  |  | 2.52 | 572.73 | 1443.2796
| Quang Nam | PKG02 | ML02-1 | 9585 | 45 | 12 | [6 empty] | FO03 |  | 9585 | [6 empty] | 2 |  |  | 4.45 | [6 empty] | 0.445 | [5 empty] | 1.26
|  |  |  | Sub-total | 45 | [16 empty] | 2 | 150.63 | 301.26 | 4.45 | 175.36 | 780.352 |  |  |  |  | 0.445 | 438.31 | 195.048 |  |  |  | 1.26 | 572.73 | 721.6398
|  | PKGA1 | MLA1-1 | 66334 | 185 | 12 | [6 empty] | FO04 |  | 66334 | [6 empty] | 4 |  |  | 5.85 | [6 empty] | 0.585 | [5 empty] | 1.26
|  |  |  | Sub-total | 185 | [16 empty] | 4 | 150.63 | 602.52 | 5.85 | 175.36 | 1025.856 |  |  |  |  | 0.585 | 438.31 | 256.4113 |  |  |  | 1.26 | 572.73 | 721.6398
|  |  | MLA1-3 | 78481 | 187 | 7.5 | [6 empty] | FO05 |  | 78481 | [6 empty] | 4 |  |  | 5.87 | [6 empty] | 0.587 | [5 empty] | 1.26
|  |  |  | 80071 | 117 | 7.5 | [6 empty] | FO06 |  | 80071 | [6 empty] | 4 |  |  | 5.17 | [6 empty] | 0.517 | [5 empty] | 1.26
|  |  |  | Sub-total | 304 | [16 empty] | 8 | 150.63 | 1205.04 | 11.04 | 175.36 | 1935.9744 |  |  |  |  | 1.104 | 438.31 | 483.8942 |  |  |  | 2.52 | 572.73 | 1443.2796
|  | PKGA2 | MLA2-1 | 85940 | 117 | 7.5 | [6 empty] | FO07 |  | 85940 | [6 empty] | 4 |  |  | 5.17 | [6 empty] | 0.517 | [5 empty] | 1.26
|  |  |  | Sub-total | 117 | [16 empty] | 4 | 150.63 | 602.52 | 5.17 | 175.36 | 906.6112 |  |  |  |  | 0.517 | 438.31 | 226.6063 |  |  |  | 1.26 | 572.73 | 721.6398
|  |  | MLA2-2 | 89335 | 47 | 7.5 | [6 empty] | FO08 |  | 89335 | [6 empty] | 2 |  |  | 4.47 | [6 empty] | 0.447 | [5 empty] | 1.26
|  |  |  | Sub-total | 47 | [16 empty] | 2 | 150.63 | 301.26 | 4.47 | 175.36 | 783.8592 |  |  |  |  | 0.447 | 438.31 | 195.9246 |  |  |  | 1.26 | 572.73 | 721.6398
|  |  | MLA2-3 | 99710 | 47 | 9 | [6 empty] | FO09 |  | 99710 | [6 empty] | 2 |  |  | 4.47 | [6 empty] | 0.447 | [5 empty] | 1.26
|  |  |  | Sub-total | 47 | [16 empty] | 2 | 150.63 | 301.26 | 4.47 | 175.36 | 783.8592 |  |  |  |  | 0.447 | 438.31 | 195.9246 |  |  |  | 1.26 | 572.73 | 721.6398
| Quang Ngai | PKGA3 | MLA3-2 | 108478 | 117 | 12 | [6 empty] | FO10 |  | 108478 | [6 empty] | 4 |  |  | 5.17 | [6 empty] | 0.517 | [5 empty] | 1.26
|  |  |  | Sub-total | 117 | [16 empty] | 4 | 150.63 | 602.52 | 5.17 | 175.36 | 906.6112 |  |  |  |  | 0.517 | 438.31 | 226.6063 |  |  |  | 1.26 | 572.73 | 721.6398
|  | PKGA4 | MLA4-1 | 112411 | 49 | 12 | [6 empty] | FO11 |  | 112411 | [6 empty] | 2 |  |  | 4.49 | [6 empty] | 0.449 | [5 empty] | 1.26
|  |  |  | 114755 | 117 | 7.5 | [6 empty] | FO12 |  | 114755 | [6 empty] | 4 |  |  | 5.17 | [6 empty] | 0.517 | [5 empty] | 1.26
|  |  |  | Sub-total | 166 | [16 empty] | 6 | 150.63 | 903.78 | 9.66 | 175.36 | 1693.9776 |  |  |  |  | 0.966 | 438.31 | 423.4075 |  |  |  | 2.52 | 572.73 | 1443.2796
|  |  | MLA4-2 | 115242 | 117 | 7.5 | [6 empty] | FO13 |  | 115242 | [6 empty] | 4 |  |  | 5.17 | [6 empty] | 0.517 | [5 empty] | 1.26
|  |  |  | 116888 | 117 | 7.5 | [6 empty] | FO14 |  | 116888 | [6 empty] | 4 |  |  | 5.17 | [6 empty] | 0.517 | [5 empty] | 1.26
|  |  |  | 118065 | 117 | 7.5 | [6 empty] | FO15 |  | 118065 | [6 empty] | 4 |  |  | 5.17 | [6 empty] | 0.517 | [5 empty] | 1.26
|  |  |  | 119508 | 187 | 12 | [6 empty] | FO16 |  | 119508 | [6 empty] | 4 |  |  | 5.87 | [6 empty] | 0.587 | [5 empty] | 1.26
|  |  |  | Sub-total | 538 | [16 empty] | 16 | 150.63 | 2410.08 | 21.38 | 175.36 | 3749.1968 |  |  |  |  | 2.138 | 438.31 | 937.1068 |  |  |  | 5.04 | 572.73 | 2886.5592
|  |  | MLA4-3 | 120316 | 117 | 7.5 | [6 empty] | FO17 |  | 120316 | [6 empty] | 4 |  |  | 5.17 | [6 empty] | 0.517 | [5 empty] | 1.26
|  |  |  | 122568 | 117 | 7.5 | [6 empty] | FO18 |  | 122568 | [6 empty] | 4 |  |  | 5.17 | [6 empty] | 0.517 | [5 empty] | 1.26
|  |  |  | Sub-total | 234 | [16 empty] | 8 | 150.63 | 1205.04 | 10.34 | 175.36 | 1813.2224 |  |  |  |  | 1.034 | 438.31 | 453.2125 |  |  |  | 2.52 | 572.73 | 1443.2796
|  | PKGA5 | MLA5-1 | 128948 | 187 | 12 | [6 empty] | FO19 |  | 128948 | [6 empty] | 4 |  |  | 5.87 | [6 empty] | 0.587 | [5 empty] | 1.26
|  |  |  | Sub-total | 187 | [16 empty] | 4 | 150.63 | 602.52 | 5.87 | 175.36 | 1029.3632 |  |  |  |  | 0.587 | 438.31 | 257.288 |  |  |  | 1.26 | 572.73 | 721.6398
B. Expressway, 5. Bridge (BR, Interchange Rampway Bridge (IRB))
| Danang | PKG01 | ML01-1 | 0 | 66.15 | 10.5 | [6 empty] | IRB01 |  | 0 | [6 empty] | Included in 8. Interchange (IC)
|  |  |  | 0 | 40.15 | 10.5 | [6 empty] | IRB02 |  | 0
|  |  |  | Sub-total | 106.3
| Quang Nam | PKG03 | ML03-1 | 20805 | 255 | 12 | [6 empty] | IRB03 |  | 20805
|  |  |  | Sub-total | 255
|  | PKG05 | ML05-2 | 40776 | 38 | 12 | [6 empty] | IRB04 |  | 40776
|  |  |  | Sub-total | 38
|  | PKG07 | ML07-3 | 64200 | 290 | 12 | [6 empty] | IRB05 |  | 64200
|  |  |  | Sub-total | 290
|  | PKGA2 | MLA2-1 | 83800 | 119 | 17.5 | [6 empty] | IRB06 |  | 83800
|  |  |  | Sub-total | 119
| Quang Ngai | PKGA3 | MLA3-1 | 102255 | 154 | 22.5 | [6 empty] | IRB07 |  | 102255
|  |  |  | 102255 | 224 | 17.5 | [6 empty] | IRB08 |  | 102255
|  |  |  | 102255 | 119 | 7.5 | [6 empty] | IRB09 |  | 102255
|  |  |  | 102255 | 119 | 7.5 | [6 empty] | IRB10 |  | 102255
|  |  |  | Sub-total | 616
|  | PKGA4 | MLA4-1 | 112615 | 49 | 13.5 | [6 empty] | IRB11 |  | 112615
|  |  |  | Sub-total | 49
|  |  | MLA4-3 | 123915 | 189 | 13.5 | [6 empty] | IRB12 |  | 123915
|  |  |  | Sub-total | 189
Jurisdiction |  | Construction | Survey | Features of Bridge | [8 empty] | Survey Section | [8 empty] | Qty and Price
|  | Contract No. | Package | Station | Length | Width |  | Section |  |  |  |  | Section | [6 empty] | Length |  | 12.1 Secondary Control Point |  |  | Planimetric | [6 empty] | Profile | [5 empty] | 12.6 Cross-section |  |  | 12.7 River Profile |  |  | 12.8 River Cross-section
[5 empty] | (m) | (m) | [6 empty] | (m) | [6 empty] | (m) |  |  |  |  | 12.2 On Shore |  |  | 12.3 Off Shore |  |  |  | 12.4 On Shore |  |  | 12.5 Off Shore |  |  | (Approach Road)
[22 empty] | Qty | Unit Price | Amount | Qty | Unit Price | Amount | Qty |  | Unit Price | Amount | Qty | Unit Price | Amount | Qty | Unit Price | Amount | Qty | Unit Price | Amount | Qty | Unit Price | Amount | Qty | Unit Price | Amount
[22 empty] | (nos.) | (USD) | (USD) | (ha) | (USD) | (USD) | (ha) |  | (USD) | (USD) | (km) | (USD) | (USD) | (km) | (USD) | (USD) | (km) | (USD) | (USD) | (km) | (USD) | (USD) | (km) | (USD) | (USD)
C. Linking Road, 12. Bridge (BR)
| Quang Ngai | PKGA5 | MLA5-2 | 132934 | 42 | 12 |  | 132913 |  | - | 132955 |  | ORB09 |  | 132883 |  | - | 132985 |  | 102 |  | 2 |  |  | 0.6 |  |  | 0.42 |  |  |  | 0.06 |  |  | 0.042 |  |  | 0.189 |  |  | 0.1 |  |  | 0.084
|  |  |  | 134726 | 42 | 12 |  | 134705 |  | - | 134747 |  | VD21 |  | 134675 |  | - | 134777 |  | 102 |  | 2 |  |  | 1.02 | [6 empty] | 0.102 | [5 empty] | 0.189
|  |  |  | Sub-total | 84 | [14 empty] | 204 |  | 4 | 150.63 | 602.52 | 1.62 | 175.36 | 284.0832 | 0.42 |  | 226.18 | 94.9956 | 0.162 | 438.31 | 71.0062 | 0.042 | 474.97 | 19.9487 | 0.378 | 572.73 | 216.4919 | 0.1 | 474.97 | 47.497 | 0.084 | 655.49 | 55.0612
|  |  | MLA5-3 | 138599 | 33 | 12 |  | 138582.5 |  | - | 138615.5 |  | ORB10 |  | 138552.5 |  | - | 138645.5 |  | 93 |  | 2 |  |  | 0.6 |  |  | 0.33 |  |  |  | 0.06 |  |  | 0.033 |  |  | 0.189 |  |  | 0.1 |  |  | 0.066
|  |  |  | Sub-total | 201 | [14 empty] | 501 |  | 2 | 150.63 | 301.26 | 0.6 | 175.36 | 105.216 | 0.33 |  | 226.18 | 74.6394 | 0.06 | 438.31 | 26.2986 | 0.033 | 474.97 | 15.674 | 0.189 | 572.73 | 108.246 | 0.1 | 474.97 | 47.497 | 0.066 | 655.49 | 43.2623

## 4.2.4CB
Item |  |  |  | Expressway |  |  |  |  | Linking Road
|  |  |  | WT |  |  | RD |  | WT
|  |  |  | Canal (Re-alignment) |  | Other WT |  |  | Other WT
| Profile |  | Length | 100 |  | 100 | 400 |  | 100
| Cross-section |  | Width | 40 |  |  | 60
|  |  | Pitch | 20 |  |  | 20
Jurisdiction |  | Construction |  | Survey | No. | Station | Size | Qty and Price | [9 empty] | Remarks
|  | Contract No. |  | Package |  |  |  | 6.1 Profile (1/500) |  |  |  | 6.2 Profile (1/200) |  |  | 6.3 Cross-section
[8 empty] | Qty |  | Unit Price | Amount | Qty | Unit Price | Amount | Qty | Unit Price | Amount
[8 empty] | (km) |  | (USD) | (USD) | (km) | (USD) | (USD) | (km) | (USD) | (USD)
B. Expressway, 6. Culvert Box (CB, Main Line (ML))
| Danang | PKG01 |  | ML01-1 | WT001 | -155 | 2(420x360) |  |  |  |  | 0.1 | [6 empty] | Widening (Existing CB(WT) on Danang Bypass)
[5 empty] | WT002 | 1160 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | RD001 | 1162 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD002 | 3049 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD003 | 3692 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | Sub-total |  |  | 1.2 |  | 438.31 | 525.972 | 0.2 | 438.31 | 87.662 | 3.6 | 572.73 | 2061.828
|  |  |  | ML01-2 | RD004 | 4281 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD005 | 4528 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD006 | 4929 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD007 | 5239 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD008 | 5517 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD009 | 5678 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD010 | 6031 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD011 | 7364 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | Sub-total |  |  | 3.2 |  | 438.31 | 1402.592 |  |  |  | 9.6 | 572.73 | 5498.208
| Quang Nam | PKG02 |  | ML02-1 | RD012 | 9028 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD013 | 9300 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT003 | 9391 | 1(200x200) |  |  |  |  | 0.1 |  |  | 0.2 |  |  |  | Connect to/from CN03
[5 empty] | RD014 | 9434 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD015 | 9772 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD016 | 10766 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT004 | 11088 | 1(200x200) |  |  |  |  | 0.1 |  |  | 0.2 |  |  |  | Connect to/from CN04
[5 empty] | RD017 | 11270 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD018 | 11519 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD019 | 12256 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | Sub-total |  |  | 3.2 |  | 438.31 | 1402.592 | 0.2 | 438.31 | 87.662 | 10 | 572.73 | 5727.3
|  |  |  | ML02-2 | WT005 | 13028 | 1(200x200) |  |  |  |  | 0.1 |  |  | 0.2 |  |  |  | Connect to/from CN06
[5 empty] | RD020 | 14122 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT006 | 14269 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | RD021 | 14376 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD022 | 14468 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT007 | 14700 | 1(200x200) |  |  |  |  | 0.1 |  |  | 0.2 |  |  |  | Connect to/from CN07
[5 empty] | WT008 | 14946 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | RD023 | 16193 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD024 | 16775 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD025 | 16943 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | Sub-total |  |  | 2.4 |  | 438.31 | 1051.944 | 0.4 | 438.31 | 175.324 | 7.6 | 572.73 | 4352.748
|  | PKG03 |  | ML03-1 | RD026 | 18062 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD027 | 18221 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT009 | 19060 | 2(300x320) |  |  |  |  | 0.1
[5 empty] | RD028 | 19095 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD029 | 19380 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD030 | 19570 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD031 | 19680 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD032 | 21000 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD033 | 21150 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD034 | 21500 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | Sub-total |  |  | 3.6 |  | 438.31 | 1577.916 | 0.1 | 438.31 | 43.831 | 10.8 | 572.73 | 6185.484
| Quang Nam | PKG04 |  | ML04-1 | RD035 | 22200 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD036 | 23310 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD037 | 24100 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD038 | 24600 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD039 | 24760 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD040 | 25200 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD041 | 26000 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT010 | 26100 | 2(300x320) |  |  |  |  | 0.1
[5 empty] | WT011 | 26480 | 2(300x320) |  |  |  |  | 0.1
[5 empty] | Sub-total |  |  | 2.8 |  | 438.31 | 1227.268 | 0.2 | 438.31 | 87.662 | 8.4 | 572.73 | 4810.932
|  |  |  | ML04-2 | WT012 | 27200 | 2(300x320) |  |  |  |  | 0.1
[5 empty] | RD042 | 29260 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD043 | 30020 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD044 | 30210 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD045 | 30300 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD046 | 30700 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD047 | 31300 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD048 | 32000 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | Sub-total |  |  | 2.8 |  | 438.31 | 1227.268 | 0.1 | 438.31 | 43.831 | 8.4 | 572.73 | 4810.932
|  | PKG05 |  | ML05-1 | WT013 | 34200 | 2(300x320) |  |  |  |  | 0.1
[5 empty] | Sub-total |  |  | 0 |  | 438.31 | 0 | 0.1 | 438.31 | 43.831 | 0 | 572.73 | 0
|  |  |  | ML05-2 | WT014 | 35860 | 2(300x300) |  |  |  |  | 0.1
[5 empty] | RD049 | 36580 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD050 | 37560 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD051 | 38880 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD052 | 40360 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD053 | 41560 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | Sub-total |  |  | 2 |  | 438.31 | 876.62 | 0.1 | 438.31 | 43.831 | 6 | 572.73 | 3436.38
|  | PKG06 |  | ML06-1 | RD054 | 42330 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT015 | 44700 | 2(300x300) |  |  |  |  | 0.1 |  |  | 0.2 |  |  |  | Connect to/from CN09
[5 empty] | RD055 | 45060 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD056 | 46440 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | Sub-total |  |  | 1.2 |  | 438.31 | 525.972 | 0.1 | 438.31 | 43.831 | 3.8 | 572.73 | 2176.374
|  |  |  | ML06-2 | RD057 | 47440 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD058 | 48500 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD059 | 48920 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD060 | 49420 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD061 | 50300 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD062 | 50700 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD063 | 51900 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | Sub-total |  |  | 2.8 |  | 438.31 | 1227.268 |  |  |  | 8.4 | 572.73 | 4810.932
|  | PKG07 |  | ML07-1 | RD064 | 52500 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD065 | 52950 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD066 | 53300 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD067 | 53700 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD068 | 54700 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD069 | 55260 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD070 | 55940 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | Sub-total |  |  | 2.8 |  | 438.31 | 1227.268 |  |  |  | 8.4 | 572.73 | 4810.932
|  |  |  | ML07-2 | RD071 | 56890 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD072 | 57960 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD073 | 58700 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD074 | 59913 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | Sub-total |  |  | 1.6 |  | 438.31 | 701.296 |  |  |  | 4.8 | 572.73 | 2749.104
|  |  |  | ML07-3 | RD075 | 60480 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD076 | 61645 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT016 | 62720 | 1(300x300) |  |  |  |  | 0.1 |  |  | 0.2 |  |  |  | Connect to/from CN11
[5 empty] | RD077 | 62829 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD078 | 63656 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD079 | 64090 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD080 | 64240 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT017 | 64252 | 1(300x320) |  |  |  |  | 0.1
[5 empty] | RD081 | 64492 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT018 | 64982 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | Sub-total |  |  | 2.8 |  | 438.31 | 1227.268 | 0.3 | 438.31 | 131.493 | 8.6 | 572.73 | 4925.478
| Quang Nam | PKGA1 |  | MLA1-1 | RD082 | 65339 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD083 | 65680 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD084 | 66678 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD085 | 67468 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD086 | 68100 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD087 | 68470 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD088 | 69179 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT019 | 70245 | 2(300x300) |  |  |  |  | 0.1
[5 empty] | RD089 | 70275 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD090 | 70700 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | Sub-total |  |  | 3.6 |  | 438.31 | 1577.916 | 0.1 | 438.31 | 43.831 | 10.8 | 572.73 | 6185.484
|  |  |  | MLA1-2 | RD091 | 71900 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD092 | 72705 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT020 | 73200 | 1(300x300) |  |  |  |  | 0.1
[5 empty] | RD093 | 73628 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT021 | 73800 | 1(300x300) |  |  |  |  | 0.1
[5 empty] | WT022 | 74080 | 1(300x300) |  |  |  |  | 0.1
[5 empty] | WT023 | 74500 | 1(300x300) |  |  |  |  | 0.1
[5 empty] | RD094 | 74840 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD095 | 75454 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | Sub-total |  |  | 2 |  | 438.31 | 876.62 | 0.4 | 438.31 | 175.324 | 6 | 572.73 | 3436.38
|  |  |  | MLA1-3 | WT024 | 80600 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | WT025 | 81100 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | Sub-total | [6 empty] | 0.2 | 438.31 | 87.662
|  | PKGA2 |  | MLA2-1 | WT026 | 82341 | 2(300x300) |  |  |  |  | 0.1
[5 empty] | WT027 | 82679 | 2(300x300) |  |  |  |  | 0.1
[5 empty] | WT028 | 83400 | 2(300x300) |  |  |  |  | 0.1
[5 empty] | WT029 | 84400 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | WT030 | 84800 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | Sub-total | [6 empty] | 0.5 | 438.31 | 219.155
|  |  |  | MLA2-2 | RD096 | 87795 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT031 | 90400 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | RD097 | 91159 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | RD098 | 92337 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | Sub-total |  |  | 1.2 |  | 438.31 | 525.972 | 0.1 | 438.31 | 43.831 | 3.6 | 572.73 | 2061.828
|  |  |  | MLA2-3 | RD099 | 93396 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT032 | 93399 | 2(200x200) |  |  |  |  | 0.1
[5 empty] | WT033 | 93629 | 2(200x200) |  |  |  |  | 0.1
[5 empty] | WT034 | 94500 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | WT035 | 95000 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | WT036 | 96118 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | RD100 | 96500 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT037 | 96600 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | WT038 | 97400 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | WT039 | 98300 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | RD101 | 98920 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT040 | 99227 | 2(200x200) |  |  |  |  | 0.1
[5 empty] | Sub-total |  |  | 1.2 |  | 438.31 | 525.972 | 0.9 | 438.31 | 394.479 | 3.6 | 572.73 | 2061.828
| Quang Ngai | PKGA3 |  | MLA3-1 | RD102 | 101849 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT041 | 102500 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | RD103 | 104954 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | Sub-total |  |  | 0.8 |  | 438.31 | 350.648 | 0.1 | 438.31 | 43.831 | 2.4 | 572.73 | 1374.552
|  |  |  | MLA3-2 | RD104 | 106021 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT042 | 109663 | 2(300x300) |  |  |  |  | 0.1
[5 empty] | Sub-total |  |  | 0.4 |  | 438.31 | 175.324 | 0.1 | 438.31 | 43.831 | 1.2 | 572.73 | 687.276
|  | PKGA4 |  | MLA4-1 | WT043 | 110200 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | WT044 | 110400 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | WT045 | 110567 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | WT046 | 112311 | 2(300x300) |  |  |  |  | 0.1
[5 empty] | Sub-total | [6 empty] | 0.4 | 438.31 | 175.324
|  |  |  | MLA4-2 | RD105 | 116275 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT047 | 119481 | 1(300x300) |  |  |  |  | 0.1
[5 empty] | Sub-total |  |  | 0.4 |  | 438.31 | 175.324 | 0.1 | 438.31 | 43.831 | 1.2 | 572.73 | 687.276
| Quang Ngai | PKGA4 |  | MLA4-3 | WT048 | 123096 | 1(300x300) |  |  |  |  | 0.1
[5 empty] | WT049 | 123281 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | Sub-total | [6 empty] | 0.2 | 438.31 | 87.662
|  | PKGA5 |  | MLA5-1 | WT050 | 127847 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | WT051 | 128402 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | WT052 | 128743 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | WT053 | 129339 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | RD106 | 130000 | 500x350 | 0.4 | [6 empty] | 1.2
[5 empty] | WT054 | 130482 | 3(350x350) |  |  |  |  | 0.1
[5 empty] | WT055 | 130630 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | WT056 | 131435 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | Sub-total |  |  | 0.4 |  | 438.31 | 175.324 | 0.7 | 438.31 | 306.817 | 1.2 | 572.73 | 687.276
B. Expressway, 6. Culvert Box (CB, Interchange (IC))
| Quang Ngai | PKGA4 |  | MLA4-3 | WT057 | 123915 | 3(300x300) |  |  |  |  | 0.1 | [6 empty] | IR (Quang Ngai North IC)
[5 empty] | Sub-total | [6 empty] | 0.1 | 438.31 | 43.831
|  | PKGA5 |  | MLA5-1 | WT058 | 130750 | 3(350x350) |  |  |  |  | 0.1 | [6 empty] | IR (Quang Ngai IC)
[5 empty] | Sub-total | [6 empty] | 0.1 | 438.31 | 43.831
Jurisdiction |  | Construction |  | Survey | No. | Station | Size | Qty and Price | [9 empty] | Remarks
|  | Contract No. |  | Package |  |  |  | 13.1 Profile (1/500) |  |  |  | 13.2 Profile (1/200) |  |  | 13.3 Cross-section
[8 empty] | Qty |  | Unit Price | Amount | Qty | Unit Price | Amount | Qty | Unit Price | Amount
[8 empty] | (km) |  | (USD) | (USD) | (km) | (USD) | (USD) | (km) | (USD) | (USD)
C. Linking Road, 13. Culvert Box (CB)
| #REF! | #REF! |  | MLA5-2 | WT059 | 131868 | 1(150x150) |  |  |  |  | 0.1
[5 empty] | WT060 | 132440 | 1(150x150) |  |  |  |  | 0.1
[5 empty] | WT061 | 133343 | 2(250x250) |  |  |  |  | 0.1
[5 empty] | WT062 | 133600 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | WT063 | 133696 | 2(200x200) |  |  |  |  | 0.1
[5 empty] | WT064 | 134226 | 1(150x150) |  |  |  |  | 0.1
[5 empty] | WT065 | 134391 | 2(150x150) |  |  |  |  | 0.1
[5 empty] | WT066 | 134828 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | WT067 | 135142 | 2(250x250) |  |  |  |  | 0.1
[5 empty] | WT068 | 135646 | 1(100x100) |  |  |  |  | 0.1
[5 empty] | WT069 | 135699 | 1(100x100) |  |  |  |  | 0.1
[5 empty] | WT070 | 135969 | 1(100x100) |  |  |  |  | 0.1
[5 empty] | Sub-total | [6 empty] | 1.2 | 438.31 | 525.972
|  |  |  | MLA5-3 | WT071 | 136077 | 1(100x100) |  |  |  |  | 0.1
[5 empty] | WT072 | 136218 | 1(150x150) |  |  |  |  | 0.1
[5 empty] | WT073 | 136356 | 2(200x200) |  |  |  |  | 0.1
[5 empty] | WT074 | 136469 | 1(100x100) |  |  |  |  | 0.1
[5 empty] | WT075 | 136738 | 2(250x250) |  |  |  |  | 0.1
[5 empty] | WT076 | 136975 | 2(100x100) |  |  |  |  | 0.1
[5 empty] | WT077 | 137095 | 2(100x100) |  |  |  |  | 0.1
[5 empty] | WT078 | 137224 | 2(200x200) |  |  |  |  | 0.1
[5 empty] | WT079 | 137825 | 2(300x300) |  |  |  |  | 0.1
[5 empty] | WT080 | 138422 | 1(250x250) |  |  |  |  | 0.1
[5 empty] | WT081 | 138672 | 2(150x150) |  |  |  |  | 0.1
[5 empty] | WT082 | 139465 | 1(200x200) |  |  |  |  | 0.1
[5 empty] | Sub-total | [6 empty] | 1.2 | 438.31 | 525.972

## 4.2.5CP
Item |  |  | Expressway |  |  | Linking Road
|  |  | Canal (Re-alignment) |  | CP (2D150) | CP (2D150)
| Profile (Length) |  | 100 |  | 100 | 100
Jurisdiction |  | Construction | Survey | No. | Station | Size | Qty and Price |  |  | Remarks
|  | Contract No. | Package |  |  |  | 7.1 Profile
[7 empty] | Qty | Unit Price | Amount
[7 empty] | (km) | (USD) | (USD)
B. Expressway, 7. Culvert Pipe (CB, Main Line (ML))
| Danang | PKG01 | ML01-1 | CP001 | 62 | 2D150 | 0.1
|  |  |  | CP002 | 431 | 1D150
|  |  |  | CP003 | 885 | 2D150 | 0.1
|  |  |  | CP004 | 3211 | 1D150 | 0.1 |  |  |  | Connect to/from CN01
|  |  |  | CP005 | 3512 | 1D150
|  |  |  | Sub-total |  |  | 0.3 | 438.31 | 131.493
|  |  | ML01-2 | CP006 | 4926 | 1D150
|  |  |  | CP007 | 5520 | 1D150
|  |  |  | CP008 | 5681 | 1D150
|  |  |  | CP009 | 5761 | 1D150
|  |  |  | Sub-total |  |  | 0 | 438.31 | 0
| Quang Nam | PKG02 | ML02-1 | CP010 | 8220 | 1D150 | 0.1 |  |  |  | Connect to/from CN02
|  |  |  | CP011 | 8738 | 1D150
|  |  |  | CP012 | 9774 | 1D150
|  |  |  | CP013 | 10763 | 1D150
|  |  |  | CP014 | 11272 | 1D150
|  |  |  | CP015 | 12012 | 1D150
|  |  |  | CP016 | 12256 | 1D150
|  |  |  | CP017 | 12427 | 1D150
|  |  |  | CP018 | 12753 | 1D150 | 0.1 |  |  |  | Connect to/from CN05
|  |  |  | Sub-total |  |  | 0.2 | 438.31 | 87.662
|  |  | ML02-2 | CP019 | 13162 | 1D150
|  |  |  | CP020 | 13460 | 1D150
|  |  |  | CP021 | 15409 | 1D150
|  |  |  | CP022 | 15593 | 1D150
|  |  |  | CP023 | 15848 | 1D150 | 0.1 |  |  |  | Connect to/from CN08
|  |  |  | Sub-total |  |  | 0.1 | 438.31 | 43.831
|  | PKG04 | ML04-1 | CP024 | 24200 | 1D150
Sub-total
|  |  | ML04-2 | CP025 | 27550 | 1D150
|  |  |  | CP026 | 27950 | 2D150 | 0.1
|  |  |  | CP027 | 28200 | 2D150 | 0.1
|  |  |  | CP028 | 28850 | 1D150
|  |  |  | CP029 | 29000 | 1D150
|  |  |  | CP030 | 29650 | 1D150
|  |  |  | CP031 | 30200 | 1D150
|  |  |  | CP032 | 30400 | 1D150
|  |  |  | CP033 | 31200 | 1D150
|  |  |  | Sub-total |  |  | 0.2 | 438.31 | 87.662
|  | PKG05 | ML05-1 | CP034 | 32600 | 1D150
|  |  |  | CP035 | 32750 | 1D150
|  |  |  | CP036 | 33100 | 2D150 | 0.1
|  |  |  | CP037 | 33400 | 1D150
|  |  |  | CP038 | 33850 | 1D150
|  |  |  | CP039 | 34300 | 1D150
|  |  |  | Sub-total |  |  | 0.1 | 438.31 | 43.831
|  |  | ML05-2 | CP040 | 35050 | 1D150
|  |  |  | CP041 | 35480 | 1D150
|  |  |  | CP042 | 36600 | 1D150
|  |  |  | CP043 | 37600 | 1D150
|  |  |  | CP044 | 37900 | 1D150
|  |  |  | CP045 | 39950 | 1D150
|  |  |  | CP046 | 40550 | 1D150
|  |  |  | CP047 | 40800 | 1D150
|  |  |  | CP048 | 41750 | 1D150
Sub-total
| Quang Nam | PKG06 | ML06-1 | CP049 | 42700 | 1D150
|  |  |  | CP050 | 42880 | 1D150
|  |  |  | CP051 | 43680 | 1D150
|  |  |  | CP052 | 43900 | 1D150
|  |  |  | CP053 | 46300 | 1D150
|  |  |  | CP054 | 46550 | 1D150
Sub-total
|  |  | ML06-2 | CP055 | 46900 | 1D150
|  |  |  | CP056 | 47130 | 1D150
|  |  |  | CP057 | 48100 | 1D150
|  |  |  | CP058 | 48420 | 1D150
|  |  |  | CP059 | 48890 | 1D150
|  |  |  | CP060 | 49400 | 1D150
|  |  |  | CP061 | 49640 | 1D150
|  |  |  | CP062 | 50160 | 1D150
|  |  |  | CP063 | 50340 | 2D150 | 0.1
|  |  |  | CP064 | 50600 | 1D150
|  |  |  | CP065 | 51000 | 1D150
|  |  |  | CP066 | 51500 | 1D150
|  |  |  | CP067 | 51850 | 1D150
|  |  |  | Sub-total |  |  | 0.1 | 438.31 | 43.831
|  | PKG07 | ML07-1 | CP068 | 52490 | 2D150 | 0.1
|  |  |  | CP069 | 52900 | 1D150
|  |  |  | CP070 | 53400 | 1D150
|  |  |  | CP071 | 53800 | 1D150
|  |  |  | CP072 | 54300 | 2D150 | 0.1
|  |  |  | CP073 | 55200 | 1D150
|  |  |  | CP074 | 55900 | 1D150
|  |  |  | Sub-total |  |  | 0.2 | 438.31 | 87.662
|  |  | ML07-2 | CP075 | 56500 | 1D150
|  |  |  | CP076 | 56800 | 1D150
|  |  |  | CP077 | 57300 | 1D150
|  |  |  | CP078 | 57500 | 1D150
|  |  |  | CP079 | 59100 | 1D150
|  |  |  | CP080 | 59500 | 1D150
|  |  |  | CP081 | 59800 | 1D150
Sub-total
|  |  | ML07-3 | CP082 | 62216 | 1D150 | 0.1 |  |  |  | Connect to/from CN10
|  |  |  | CP083 | 62400 | 1D150
|  |  |  | Sub-total |  |  | 0.1 | 438.31 | 43.831
|  | PKGA1 | MLA1-1 | CP084 | 65487 | 2D150 | 0.1
|  |  |  | CP085 | 67188 | 1D150
|  |  |  | CP086 | 68640 | 1D150
|  |  |  | CP087 | 69237 | 1D150
|  |  |  | Sub-total |  |  | 0.1 | 438.31 | 43.831
|  |  | MLA1-2 | CP088 | 71360 | 1D150
|  |  |  | CP089 | 71650 | 1D150 | 0.1 |  |  |  | Connect to/from CN16
|  |  |  | CP090 | 71938 | 1D150
|  |  |  | CP091 | 72316 | 1D150
|  |  |  | CP092 | 72528 | 1D150
|  |  |  | CP093 | 72707 | 1D150
|  |  |  | CP094 | 72831 | 1D150
|  |  |  | CP095 | 72955 | 1D150
|  |  |  | CP096 | 75750 | 1D150
|  |  |  | CP097 | 76000 | 1D150
|  |  |  | Sub-total |  |  | 0.1 | 438.31 | 43.831
|  |  | MLA1-3 | CP098 | 76400 | 1D150
|  |  |  | CP099 | 77000 | 1D150
|  |  |  | CP100 | 77400 | 1D150
|  |  |  | CP101 | 78200 | 1D150
|  |  |  | CP102 | 78800 | 1D150
|  |  |  | CP103 | 79800 | 2D150 | 0.1
|  |  |  | Sub-total |  |  | 0.1 | 438.31 | 43.831
| Quang Nam | PKGA2 | MLA2-1 | CP104 | 85941 | 1D150
|  |  |  | CP105 | 86300 | 2D150 | 0.1
|  |  |  | CP106 | 86800 | 2D150 | 0.1
|  |  |  | CP107 | 87000 | 1D150
|  |  |  | Sub-total |  |  | 0.2 | 438.31 | 87.662
|  |  | MLA2-2 | CP108 | 87500 | 1D150
|  |  |  | CP109 | 88500 | 1D150
|  |  |  | CP110 | 89000 | 1D150
|  |  |  | CP111 | 89674 | 1D150
|  |  |  | CP112 | 91162 | 1D150
|  |  |  | CP113 | 91500 | 1D150
|  |  |  | CP114 | 92334 | 1D150
Sub-total
|  |  | MLA2-3 | CP115 | 93100 | 1D150
|  |  |  | CP116 | 95200 | 1D150
|  |  |  | CP117 | 95579 | 1D150
|  |  |  | CP118 | 99400 | 1D150
|  |  |  | CP119 | 100000 | 1D150
Sub-total
| Quang Ngai | PKGA3 | MLA3-1 | CP120 | 100600 | 1D150
|  |  |  | CP121 | 101200 | 1D150
|  |  |  | CP122 | 101846 | 1D150
|  |  |  | CP123 | 103000 | 1D150
|  |  |  | CP124 | 103400 | 1D150
|  |  |  | CP125 | 104700 | 1D150
|  |  |  | CP126 | 105000 | 1D150
Sub-total
|  |  | MLA3-2 | CP127 | 105900 | 1D150
|  |  |  | CP128 | 106300 | 1D150
|  |  |  | CP129 | 107100 | 1D150
|  |  |  | CP130 | 108000 | 1D150
Sub-total
|  | PKGA4 | MLA4-1 | CP131 | 112411 | 1D150
|  |  |  | CP132 | 113447 | 1D150
|  |  |  | CP133 | 114180 | 1D150
|  |  |  | CP134 | 114975 | 1D150
Sub-total
|  |  | MLA4-2 | CP135 | 116441 | 1D150
|  |  |  | CP136 | 116892 | 1D150
|  |  |  | CP137 | 117356 | 1D150
|  |  |  | CP138 | 118547 | 1D150
|  |  |  | CP139 | 118958 | 1D150
|  |  |  | CP140 | 119234 | 1D150
|  |  |  | CP141 | 119687 | 1D150
Sub-total
|  |  | MLA4-3 | CP142 | 120687 | 1D150
|  |  |  | CP143 | 120985 | 1D150
|  |  |  | CP144 | 121144 | 1D150
|  |  |  | CP145 | 121287 | 1D150
|  |  |  | CP146 | 121555 | 1D150
|  |  |  | CP147 | 121946 | 1D150
|  |  |  | CP148 | 122029 | 1D150
|  |  |  | CP149 | 122580 | 1D150
|  |  |  | CP150 | 123131 | 1D150
|  |  |  | CP151 | 123647 | 1D150
|  |  |  | CP152 | 123927 | 1D150
|  |  |  | CP153 | 124073 | 1D150
Sub-total
| Quang Ngai | PKGA5 | MLA5-1 | CP154 | 129246 | 1D150
|  |  |  | CP155 | 129905 | 1D150
|  |  |  | CP156 | 130246 | 1D150
|  |  |  | CP157 | 130394 | 1D150
|  |  |  | CP158 | 131000 | 1D150
Sub-total
B. Expressway, 7. Culvert Pipe (CB, Interchange (IC))
| Danang | PKG01 | ML01-1 | CP159 | 0 | 1D150 |  |  |  |  | IR (Tuy Loan IC)
Sub-total
| Quang Nam | PKG03 | ML03-1 | CP160 | 20805 | 1D150 |  |  |  |  | IR (My Son IC)
|  |  |  | CP161 | 20805 | 1D150 |  |  |  |  | IR (My Son IC)
Sub-total
|  | PKGA2 | MLA2-1 | CP162 | 83800 | 1D150 |  |  |  |  | IR (Chu Lai IC)
|  |  |  | CP163 | 83800 | 1D150 |  |  |  |  | IR (Chu Lai IC)
Sub-total
| Quang Ngai | PKGA3 | MLA3-1 | CP164 | 102255 | 1D150 |  |  |  |  | IR (Dung Quat IC)
|  |  |  | CP165 | 102255 | 1D150 |  |  |  |  | IR (Dung Quat IC)
Sub-total
|  | PKGA4 | MLA4-1 | CP166 | 112615 | 1D150 |  |  |  |  | IR (Binh Son IC)
|  |  |  | CP167 | 112615 | 1D150 |  |  |  |  | IR (Binh Son IC)
Sub-total
|  |  | MLA4-3 | CP168 | 123915 | 1D150 |  |  |  |  | IR (Quang Ngai North IC)
Sub-total
Jurisdiction |  | Construction | Survey | No. | Station | Size | Qty and Price |  |  | Remarks
|  | Contract No. | Package |  |  |  | 14.1 Profile
[7 empty] | Qty | Unit Price | Amount
[7 empty] | (km) | (USD) | (USD)
C. Linking Road, 14. Culvert Pipe (CP)
| Quang Ngai | PKGA5 | MLA5-2 | CP169 | 131605 | 1D150
|  |  |  | CP170 | 133265 | 1D100
|  |  |  | CP171 | 133394 | 1D150
|  |  |  | CP172 | 133893 | 1D100
|  |  |  | CP173 | 134686 | 1D150
|  |  |  | CP174 | 134880 | 1D150
|  |  |  | CP175 | 134969 | 1D150
|  |  |  | CP176 | 135456 | 1D150
Sub-total
|  |  | MLA5-3 | CP177 | 137361 | 1D100
|  |  |  | CP178 | 137461 | 1D100
|  |  |  | CP179 | 137724 | 1D100
|  |  |  | CP180 | 138265 | 1D100
|  |  |  | CP181 | 138353 | 1D100
|  |  |  | CP182 | 138803 | 1D100
|  |  |  | CP183 | 138903 | 1D100
|  |  |  | CP184 | 139006 | 1D100
|  |  |  | CP185 | 139108 | 1D100
|  |  |  | CP186 | 139212 | 1D100
|  |  |  | CP187 | 139316 | 1D100
Sub-total

## 4.2.6IC
Item |  |  | Rampway
| Cross-section (Width) |  | 100
| Cross-section (Pitch) |  | 20
| Cross-section (Transition) |  | 5%
Jurisdiction |  | Construction | Survey | No. | Station | Qty and Price | [14 empty] | Remarks
|  | Contract No. | Package |  |  | 9.1 Secondary Control Point |  |  | 9.2 Secondary Leveling Network |  |  | 9.3 Planimetric |  |  | 9.4 Profile (Rampway) |  |  | 9.5 Cross-section (Rampway)
[6 empty] | Qty | Unit Price | Amount | Qty | Unit Price | Amount | Qty | Unit Price | Amount | Qty | Unit Price | Amount | Qty | Unit Price | Amount
[6 empty] | (nos.) | (USD) | (USD) | (km) | (USD) | (USD) | (ha) | (USD) | (USD) | (km) | (USD) | (USD) | (km) | (USD) | (USD)
B. Expressway, 9. Interchange (IC)
| Danang | PKG01 | ML01-1 | IC01 | 0 | 8 |  |  | 2 |  |  | 60 |  |  | 3.86 |  |  | 20.265 |  |  |  | Tuy Loan IC
|  |  |  | Sub-total |  | 8 | 150.63 | 1205.04 | 2 | 67.29 | 134.58 | 60 | 175.36 | 10521.6 | 3.86 | 438.31 | 1691.8766 | 20.265 | 572.73 | 11606.3735
| Quang Nam | PKG03 | ML03-1 | IC02 | 20805 | 8 |  |  | 2 |  |  | 27 |  |  | 2.5 |  |  | 13.125 |  |  |  | My Son IC (Including TG, TP and TPO)
|  |  |  | Sub-total |  | 8 | 150.63 | 1205.04 | 2 | 67.29 | 134.58 | 27 | 175.36 | 4734.72 | 2.5 | 438.31 | 1095.775 | 13.125 | 572.73 | 7517.0813
|  | PKG05 | ML05-2 | IC03 | 40776 | 8 |  |  | 2 |  |  | 33 |  |  | 2.46 |  |  | 12.915 |  |  |  | Ha Lam IC (Including TG, TP and TPO)
|  |  |  | Sub-total |  | 8 | 150.63 | 1205.04 | 2 | 67.29 | 134.58 | 33 | 175.36 | 5786.88 | 2.46 | 438.31 | 1078.2426 | 12.915 | 572.73 | 7396.808
|  | PKG07 | ML07-3 | IC04 | 64200 | 8 |  |  | 2 |  |  | 28 |  |  | 2.43 |  |  | 12.81 |  |  |  | Tam Ky IC (Including TG, TP and TPO)
|  |  |  | Sub-total |  | 8 | 150.63 | 1205.04 | 2 | 67.29 | 134.58 | 28 | 175.36 | 4910.08 | 2.43 | 438.31 | 1065.0933 | 12.81 | 572.73 | 7336.6713
|  | PKGA2 | MLA2-1 | IC05 | 83800 | 8 |  |  | 2 |  |  | 28 |  |  | 1.92 |  |  | 10.08 |  |  |  | Chu Lai IC (Including TG, TP and TPO)
|  |  |  | Sub-total |  | 8 | 150.63 | 1205.04 | 2 | 67.29 | 134.58 | 28 | 175.36 | 4910.08 | 1.92 | 438.31 | 841.5552 | 10.08 | 572.73 | 5773.1184
| Quang Ngai | PKGA3 | MLA3-1 | IC06 | 102255 | 8 |  |  | 2 |  |  | 28 |  |  | 1.58 |  |  | 8.295 |  |  |  | Dung Quat IC (Including TG, TP and TPO)
|  |  |  | Sub-total |  | 8 | 150.63 | 1205.04 | 2 | 67.29 | 134.58 | 28 | 175.36 | 4910.08 | 1.58 | 438.31 | 692.5298 | 8.295 | 572.73 | 4750.7954
|  | PKGA4 | MLA4-1 | IC07 | 112615 | 8 |  |  | 2 |  |  | 28 |  |  | 1.93 |  |  | 10.185 |  |  |  | Binh Son IC (Including TG, TP and TPO)
|  |  |  | Sub-total |  | 8 | 150.63 | 1205.04 | 2 | 67.29 | 134.58 | 28 | 175.36 | 4910.08 | 1.93 | 438.31 | 845.9383 | 10.185 | 572.73 | 5833.2551
|  |  | MLA4-3 | IC08 | 123915 | 8 |  |  | 2 |  |  | 28 |  |  | 1.84 |  |  | 9.66 |  |  |  | Quang Ngai North IC (Including TG, TP and TPO)
|  |  |  | Sub-total |  | 8 | 150.63 | 1205.04 | 2 | 67.29 | 134.58 | 28 | 175.36 | 4910.08 | 1.84 | 438.31 | 806.4904 | 9.66 | 572.73 | 5532.5718
|  | PKGA5 | MLA5-1 | IC09 | 130750 | 8 |  |  | 2 |  |  | 16 |  |  | 0.88 |  |  | 4.62 |  |  |  | Quang Ngai IC
|  |  |  | Sub-total |  | 8 | 150.63 | 1205.04 | 2 | 67.29 | 134.58 | 16 | 175.36 | 2805.76 | 0.88 | 438.31 | 385.7128 | 4.62 | 572.73 | 2646.0126

## 4.2.7BL
Jurisdiction |  | Construction | Survey | No. | Station | Qty and Price |  |  | Remarks
|  | Contract No. | Package |  |  | 10.1 Planimetric
[6 empty] | Qty | Unit Price | Amount
[6 empty] | (ha) | (USD) | (USD)
B. Expressway, 10. Building (BL)
| Danang | PKG01 | ML01-1 | BL01 | 950 | 2.8 |  |  |  | TMC
|  |  |  | Sub-total |  | 2.8 | 175.36 | 491.008
|  |  | ML01-2 | BL02 | 4750 | 2.84 |  |  |  | TB including TP and TPO
|  |  |  | Sub-total |  | 2.84 | 175.36 | 498.0224
| Quang Nam | PKG04 | ML04-2 | BL03 | 29130 | 1.8 |  |  |  | PA
|  |  |  | Sub-total |  | 1.8 | 175.36 | 315.648
|  | PKG07 | ML07-3 | BL04 | 64750 | 0.98 |  |  |  | EOO
|  |  |  | Sub-total |  | 0.98 | 175.36 | 171.8528
|  | PKGA1 | MLA1-1 | BL05 | 69600 | 7.4 |  |  |  | SA
|  |  |  | Sub-total |  | 7.4 | 175.36 | 1297.664
|  | PKGA2 | MLA2-3 | BL06 | 98800 | 1.8 |  |  |  | PA
|  |  |  | Sub-total |  | 1.8 | 175.36 | 315.648
| Quang Ngai | PKGA5 | MLA5-1 | BL07 | 129800 | 2.84 |  |  |  | TB including TP and TPO
|  |  |  | Sub-total |  | 2.84 | 175.36 | 498.0224

## 4.2.8IS
Item |  |  | Linking Road (IC), NH1A |  | Other Roads
| Planimetric (Width) |  | 100 |  | 50
| Profile (Length) |  | 400 |  | 100
| Cross-section (Width) |  | 60 |  | 30
| Cross-section (Pitch) |  | 20 |  | 20
Jurisdiction |  | Construction | Survey | No. | Station | Qty and Price | [8 empty] | Remarks
|  | Contract No. | Package |  |  | 15.1 Planimetric |  |  | 15.2 Profile |  |  | 15.3 Cross-section
[6 empty] | Qty | Unit Price | Amount | Qty | Unit Price | Amount | Qty | Unit Cost | Amount
[6 empty] | (ha) | (USD) | (USD) | (km) | (USD) | (USD) | (km) | (USD) | (USD)
C. Linking Road, 15. Intersection (IS)
| Danang | PKG01 | ML01-1 | IS01 | 0 | 4 |  |  | 0.4 |  |  | 1.2 |  |  |  | NH14B (Tuy Loan IC)
|  |  |  | Sub-total |  | 4 | 175.36 | 701.44 | 0.4 | 438.31 | 175.324 | 1.2 | 572.73 | 687.276
| Quang Nam | PKG03 | ML03-1 | IS02 | 20805 | 4 |  |  | 0.4 |  |  | 1.2 |  |  |  | DR610 (My Son IC)
|  |  |  | Sub-total |  | 4 | 175.36 | 701.44 | 0.4 | 438.31 | 175.324 | 1.2 | 572.73 | 687.276
|  | PKG05 | ML05-2 | IS03 | 40776 | 4 |  |  | 0.4 |  |  | 1.2 |  |  |  | NH14E (Ha Lam IC)
|  |  |  | Sub-total |  | 4 | 175.36 | 701.44 | 0.4 | 438.31 | 175.324 | 1.2 | 572.73 | 687.276
|  | PKG07 | ML07-3 | IS04 | 64200 | 4 |  |  | 0.4 |  |  | 1.2 |  |  |  | DR616 (Tam Ky IC)
|  |  |  | Sub-total |  | 4 | 175.36 | 701.44 | 0.4 | 438.31 | 175.324 | 1.2 | 572.73 | 687.276
|  | PKGA2 | MLA2-1 | IS05 | 83800 | 4 |  |  | 0.4 |  |  | 1.2 |  |  |  | Chu Lai Industrial Road (Chu Lai IC)
|  |  |  | Sub-total |  | 4 | 175.36 | 701.44 | 0.4 | 438.31 | 175.324 | 1.2 | 572.73 | 687.276
| Quang Ngai | PKGA3 | MLA3-1 | IS06 | 102255 | 4 |  |  | 0.4 |  |  | 1.2 |  |  |  | Dung Quant Industrial Road (Dung Quat IC)
|  |  |  | Sub-total |  | 4 | 175.36 | 701.44 | 0.4 | 438.31 | 175.324 | 1.2 | 572.73 | 687.276
|  | PKGA4 | MLA4-1 | IS07 | 112615 | 4 |  |  | 0.4 |  |  | 1.2 |  |  |  | Tra Bong - Binh Long Road (Binh Son IC)
|  |  |  | Sub-total |  | 4 | 175.36 | 701.44 | 0.4 | 438.31 | 175.324 | 1.2 | 572.73 | 687.276
|  |  | MLA4-3 | IS08 | 123915 | 4 |  |  | 0.4 |  |  | 1.2 |  |  |  | PR623 (Quang Ngai North IC)
|  |  |  | Sub-total |  | 4 | 175.36 | 701.44 | 0.4 | 438.31 | 175.324 | 1.2 | 572.73 | 687.276
|  | PKGA5 | MLA5-1 | IS09 | 130750 | 4 |  |  | 0.4 |  |  | 1.2 |  |  |  | PR625 (Quang Ngai IC)
|  |  |  | Sub-total |  | 4 | 175.36 | 701.44 | 0.4 | 438.31 | 175.324 | 1.2 | 572.73 | 687.276
|  |  | MLA5-2 | IS10 | 133371 | 0.5 |  |  | 0.1 |  |  | 0.15
|  |  |  | IS11 | 134222 | 0.5 |  |  | 0.1 |  |  | 0.15
|  |  |  | IS12 | 135415 | 0.5 |  |  | 0.1 |  |  | 0.15
|  |  |  | Sub-total |  | 1.5 | 175.36 | 263.04 | 0.3 | 438.31 | 131.493 | 0.45 | 572.73 | 257.7285
|  |  | MLA5-3 | IS13 | 137215 | 0.5 |  |  | 0.1 |  |  | 0.15
|  |  |  | IS14 | 139522 | 4 |  |  | 0.4 |  |  | 1.2 |  |  |  | Existing NH1A
|  |  |  | Sub-total |  | 4.5 | 175.36 | 789.12 | 0.5 | 438.31 | 219.155 | 1.35 | 572.73 | 773.1855

## 4.2.9CN
Item |  |  |  | Canal
| Cross-section |  | Width | 40
|  |  | Pitch | 20
Jurisdiction |  | Construction |  | Survey | No. | Station | Qty and Price | [5 empty] | Remarks
|  | Contract No. |  | Package |  |  | 8.1 Profile |  |  | 8.2 Cross-section
[7 empty] | Qty | Unit Price | Amount | Qty | Unit Price | Amount
[7 empty] | (km) | (USD) | (USD) | (km) | (USD) | (USD)
B. Expressway, 8. Canal (CN, Re-alignment)
| Danang | PKG01 |  | ML01-2 | CN01 | 3211 | 0.46 |  |  | 0.92 |  |  |  | Connect to/from CP004
[5 empty] | Sub-total |  | 0.46 | 438.31 | 201.6226 | 0.92 | 572.73 | 526.9116
| Quang Nam | PKG02 |  | ML02-1 | CN02 | 8220 | 0.2 |  |  | 0.4 |  |  |  | Connect to/from CP010
[5 empty] | CN03 | 9391 | 0.2 |  |  | 0.4 |  |  |  | Connect to/from WT003
[5 empty] | CN04 | 11088 | 0.4 |  |  | 0.8 |  |  |  | Connect to/from WT004
[5 empty] | CN05 | 12753 | 0.2 |  |  | 0.4 |  |  |  | Connect to/from CP018
[5 empty] | Sub-total |  | 1 | 438.31 | 438.31 | 2 | 572.73 | 1145.46
|  |  |  | ML02-2 | CN06 | 13028 | 0.15 |  |  | 0.32 |  |  |  | Connect to/from WT005
[5 empty] | CN07 | 14700 | 0.2 |  |  | 0.4 |  |  |  | Connect to/from WT007
[5 empty] | CN08 | 15848 | 0.2 |  |  | 0.4 |  |  |  | Connect to/from CP023
[5 empty] | Sub-total |  | 0.55 | 438.31 | 241.0705 | 1.12 | 572.73 | 641.4576
|  | PKG06 |  | ML06-1 | CN09 | 44700 | 0.143 |  |  | 0.28 |  |  |  | Connect to/from WT015
[5 empty] | Sub-total |  | 0.143 | 438.31 | 62.6783 | 0.28 | 572.73 | 160.3644
|  | PKG07 |  | ML07-3 | CN10 | 62216 | 0.125 |  |  | 0.24 |  |  |  | Connect to/from CP082
[5 empty] | CN11 | 62720 | 0.255 |  |  | 0.52 |  |  |  | Connect to/from WT016
[5 empty] | Sub-total |  | 0.38 | 438.31 | 166.5578 | 0.76 | 572.73 | 435.2748
|  |  |  | MLA1-1 | CN12 | 66200 | 0.36 |  |  | 0.72 |  |  |  | Connect to/from SB07
[5 empty] | CN13 | 66815 | 0.13 |  |  | 0.28 |  |  |  | Roadside, KM066+750 - KM066+880
[5 empty] | CN14 | 67178 | 0.395 |  |  | 0.8 |  |  |  | Roadside, KM066+980 - KM067+375
[5 empty] | CN15 | 71000 | 0.366 |  |  | 0.72 |  |  |  | Connect to/from CB06
[5 empty] | Sub-total |  | 1.251 | 438.31 | 548.3258 | 2.52 | 572.73 | 1443.2796
|  |  |  | MLA1-2 | CN16 | 71650 | 0.12 |  |  | 0.24 |  |  |  | Connect to/from CP089
[5 empty] | Sub-total |  | 0.12 | 438.31 | 52.5972 | 0.24 | 572.73 | 137.4552