## Chronicle
Case1
Case4 | 110803 | 工区分の変更
DDコンサルで66%、VECCが14%で合計80%
Case3 | 110713 | TEDIヘルプシナリオ
| 110521 | Explained to PMU85/MrCanh
Case2 |  | 金額ベースのデマケ
DDコンサルで60%、VECCが14%で合計74%
| 110427a | VEC協議後、BMTとINPELを入れ替えた。
| 110427 | Explained to VEC/MrSanh
Case1 |  | 距離ベースのデマケ

## Case4_Summary
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  | Total | TEDI | TEDI-S | 533 | VECC | TienKhai | INPEL | EGS | BMT | ThanhCong | TanPhat | ATH | ICTC
Topo (2011.09)
| Control Point | 88678.2312 | 1: 88678.2312
|  | 100% | 1: 100%
| Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88678.2312
|  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Geo (2011.09) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Hydrological |  |  | 1: 211808
Material Source |  |  | 1: 17565
Traffic |  |  | 1: 6000
Total |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## Case4_GeoCost0903
Jurisdiction |  | Road |  | Construction Contract Package (Civil Works) |  |  |  |  | Survey Package | [6 empty] | Cost (USD) | Topo | Geo | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  | Classification |  | No. | Section |  |  | Length | No. |  | Section |  |  | Equation | Length | (Proposal) | Firm | Firm | TEDI | TEDI-S | 533 | VECC | TienKhai | INPEL | EGS | BMT | ThanhCong | TanPhat | ATH | ICTC
| Danang |  | Expressway | PKG01 | -800 | - | 8000 | 8800 | 1 | ML01-1 | -800 | - | 4000 | 0 | 4800 |  | VECC | VECC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 2 | ML01-2 | 4000 | - | 8000 | 0 | 4000 |  | VECC | VECC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Quang Nam |  |  | PKG02 | 8000 | - | 17000 | 9000 | 3 | ML02-1 | 8000 | - | 13000 | 0 | 5000 |  | VECC | ThanhCong | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 4 | ML02-2 | 13000 | - | 17000 | 0 | 4000 |  | VECC | ThanhCong | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PKG03 | 17000 | - | 22000 | 5059.78 | 5 | ML03-1 | 17000 | - | 22000 | -59.78 | 5059.78 |  | TEDI | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PKG04 | 22000 | - | 32000 | 10000 | 6 | ML04-1 | 22000 | - | 26800 | 0 | 4800 |  | EGS | EGS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 7 | ML04-2 | 26800 | - | 32000 | 0 | 5200 |  | EGS | ICTC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PKG05 | 32000 | - | 42000 | 10000 | 8 | ML05-1 | 32000 | - | 35000 | 0 | 3000 |  | TEDI | TEDI-S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 9 | ML05-2 | 35000 | - | 42000 | 0 | 7000 |  | TEDI-S | TEDI-S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PKG06 | 42000 | - | 52000 | 10000 | 10 | ML06-1 | 42000 | - | 46600 | 0 | 4600 |  | TEDI-S | TanPhat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 11 | ML06-2 | 46600 | - | 52000 | 0 | 5400 |  | TEDI-S | TanPhat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PKG07 | 52000 | - | 65000 | 13000 | 12 | ML07-1 | 52000 | - | 56000 | 0 | 4000 |  | 533 | 533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 13 | ML07-2 | 56000 | - | 60000 | 0 | 4000 |  | 533 | 533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 14 | ML07-3 | 60000 | - | 65000 | 0 | 5000 |  | 533 | 533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PKGA1 | 65000 | - | 81500 | 16557.32 | 15 | MLA1-1 | 65000 | - | 70000 | 0 | 5000 |  | TEDI | ATH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 16 | MLA1-2 | 70000 | - | 76000 | -57.32 | 6057.32 |  | TEDI | ATH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 17 | MLA1-3 | 76000 | - | 81500 | 0 | 5500 |  | TEDI | INPEL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PKGA2 | 81500 | - | 100000 | 18200 | 18 | MLA2-1 | 81500 | - | 87000 | 0 | 5500 |  | TEDI | INPEL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 19 | MLA2-2 | 87000 | - | 93000 | 0 | 6000 |  | TEDI | ThanhCong | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 20 | MLA2-3 | 93000 | - | 100000 | 300 | 6700 |  | TEDI | ThanhCong | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Quang Ngai |  |  | PKGA3 | 100000 | - | 110000 | 10173.22 | 21 | MLA3-1 | 100000 | - | 105000 | -173.22 | 5173.22 |  | TEDI | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 22 | MLA3-2 | 105000 | - | 110000 | 0 | 5000 |  | TEDI | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PKGA4 | 110000 | - | 125000 | 15000 | 23 | MLA4-1 | 110000 | - | 115000 | 0 | 5000 |  | TEDI | TienKhai | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 24 | MLA4-2 | 115000 | - | 120000 | 0 | 5000 |  | TEDI | BMT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 25 | MLA4-3 | 120000 | - | 125000 | 0 | 5000 |  | TEDI | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PKGA5 | 125000 | - | 139522 | 14522 | 26 | MLA5-1 | 125000 | - | 131500 | 0 | 6500 |  | TEDI | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Linking Road | [5 empty] | 27 | MLA5-2 | 131500 | - | 136000 | 0 | 4500 |  | TEDI | BMT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 28 | MLA5-3 | 136000 | - | 139522 | 0 | 3522 |  | TEDI | BMT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | [7 empty] | 140312.32 | [6 empty] | 140312.32 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Geotechnical Survey for PKG8 (O&M Buildings) is included in each Survey Package above | [18 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## GeoBase(110906)
Jurisdiction |  | Road |  | Construction Contract Package (Civil Works) |  |  |  |  | Survey Package | [6 empty] | Estimated Cost (USD)
|  | Classification |  | No. | Section |  |  | Length | No. |  | Section |  |  | Equation | Length | a. Proposal | b. Proposal | c. Sep. 2011
[c/Σ(c)]*Σ(a)
| Danang |  | Expressway | PKG01 | -800 | - | 8000 | 8800 | 1 | ML01-1 | -800 | - | 4000 | 0 | 4800 | 121654.1036 | 131778.7923 | 159531.5352
[9 empty] | 2 | ML01-2 | 4000 | - | 8000 | 0 | 4000 | 86441.0848 | 112628.6333 | 136348.334
| Quang Nam |  |  | PKG02 | 8000 | - | 17000 | 9000 | 3 | ML02-1 | 8000 | - | 13000 |  | 5000 | 88308.9517 | 92397.6978 | 111856.7436
[9 empty] | 4 | ML02-2 | 13000 | - | 17000 | 0 | 4000 | 65780.9538 | 61759.8852 | 74766.5776
|  |  |  | PKG03 | 17000 | - | 22000 | 5059.78 | 5 | ML03-1 | 17000 | - | 22000 | -59.78 | 5059.78 | 144918.3463 | 151778.6432 | 183743.3744
|  |  |  | PKG04 | 22000 | - | 32000 | 10000 | 6 | ML04-1 | 22000 | - | 26800 | 0 | 4800 | 97614.3261 | 107417.9757 | 130040.3068
[9 empty] | 7 | ML04-2 | 26800 | - | 32000 | 0 | 5200 | 35893.257 | 26113.881 | 31613.49
|  |  |  | PKG05 | 32000 | - | 42000 | 10000 | 8 | ML05-1 | 32000 | - | 35000 | 0 | 3000 | 16822.1616 | 36333.5149 | 43985.3888
[9 empty] | 9 | ML05-2 | 35000 | - | 42000 | 0 | 7000 | 46835.933 | 45090.2397 | 54586.2884
|  |  |  | PKG06 | 42000 | - | 52000 | 10000 | 10 | ML06-1 | 42000 | - | 46600 | 0 | 4600 | 33474.1338 | 29359.4366 | 35542.5628
[9 empty] | 11 | ML06-2 | 46600 | - | 52000 | 0 | 5400 | 25345.5358 | 16366.1579 | 19812.8868
|  |  |  | PKG07 | 52000 | - | 65000 | 13000 | 12 | ML07-1 | 52000 | - | 56000 | 0 | 4000 | 23068.1382 | 13616.0964 | 16483.6596
[9 empty] | 13 | ML07-2 | 56000 | - | 60000 | 0 | 4000 | 25726.8357 | 19886.8403 | 24075.0284
[9 empty] | 14 | ML07-3 | 60000 | - | 65000 | 0 | 5000 | 38066.5433 | 27710.8214 | 33546.7476
|  |  |  | PKGA1 | 65000 | - | 81500 | 16557.32 | 15 | MLA1-1 | 65000 | - | 70000 | 0 | 5000 | 45213.4252 | 39417.0888 | 47718.3664
[9 empty] | 16 | MLA1-2 | 70000 | - | 76000 | -57.32 | 6057.32 | 29405.0965 | 18484.516 | 22377.3732
[9 empty] | 17 | MLA1-3 | 76000 | - | 81500 | 0 | 5500 | 23593.8539 | 26613.2367 | 32218.0104
|  |  |  | PKGA2 | 81500 | - | 100000 | 18200 | 18 | MLA2-1 | 81500 | - | 87000 | 0 | 5500 | 36297.5391 | 37045.1585 | 44846.9052
[9 empty] | 19 | MLA2-2 | 87000 | - | 93000 | 0 | 6000 | 38734.0211 | 54555.7698 | 66045.2684
[9 empty] | 20 | MLA2-3 | 93000 | - | 100000 | 300 | 6700 | 30465.724 | 18275.7823 | 22124.68
| Quang Ngai |  |  | PKGA3 | 100000 | - | 110000 | 10173.22 | 21 | MLA3-1 | 100000 | - | 105000 | -173.22 | 5173.22 | 59079.002 | 59550.3241 | 72091.6808
[9 empty] | 22 | MLA3-2 | 105000 | - | 110000 | 0 | 5000 | 84850.6979 | 55228.8741 | 66860.1292
|  |  |  | PKGA4 | 110000 | - | 125000 | 15000 | 23 | MLA4-1 | 110000 | - | 115000 | 0 | 5000 | 30490.8961 | 82276.6715 | 99604.2192
[9 empty] | 24 | MLA4-2 | 115000 | - | 120000 | 0 | 5000 | 41001.1053 | 38637.6505 | 46774.7776
[9 empty] | 25 | MLA4-3 | 120000 | - | 125000 | 0 | 5000 | 54422.7755 | 51801.7581 | 62711.2592
|  |  |  | PKGA5 | 125000 | - | 139522 | 14522 | 26 | MLA5-1 | 125000 | - | 131500 | 0 | 6500 | 120152.1483 | 112160.2286 | 135781.2828
|  |  | Linking Road | [5 empty] | 27 | MLA5-2 | 131500 | - | 136000 | 0 | 4500 | 18915.9634 | 9037.054 | 10940.2664
[9 empty] | 28 | MLA5-3 | 136000 | - | 139522 | 0 | 3522 | 17155.4469 | 4405.2712 | 5333.0256
Total | [7 empty] | 140312.32 | [6 empty] | 140312.32 | 1479728 | 1479728 | 1791360.1684
Geotechnical Survey for PKG8 (O&M Buildings) is included in each Survey Package above

## Case4_TopoCost0903
Topographic Survey
Jurisdiction |  | Road |  | Construction Contract Package (Civil Works) |  |  |  |  | Survey Package | [6 empty] | Cost (USD)
|  | Classification |  | No. | Section |  |  | Length | No. |  | Section |  |  |  |  | (Proposal) | Firm | 1 | 2 | 3 | 4 | 5
[14 empty] | Equation |  |  |  | TEDI | TEDI-S | 533 | VECC | EGS
[10 empty] | CP | [5 empty] | 88678.2312 | TEDI | 88678.2312 | 0 | 0 | 0 | 0 | 88678.2312 | 0
| Danang |  | Expressway | PKG01 | -800 | - | 8000 | 8800 | 1 | ML01-1 | -800 | - | 4000 | 0 | 4800 |  | VECC | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 2 | ML01-2 | 4000 | - | 8000 | 0 | 4000 |  | VECC | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Quang Nam |  |  | PKG02 | 8000 | - | 17000 | 9000 | 3 | ML02-1 | 8000 | - | 13000 | 0 | 5000 |  | VECC | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 4 | ML02-2 | 13000 | - | 17000 | 0 | 4000 |  | VECC | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PKG03 | 17000 | - | 22000 | 5059.78 | 5 | ML03-1 | 17000 | - | 22000 | -59.78 | 5059.78 |  | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PKG04 | 22000 | - | 32000 | 10000 | 6 | ML04-1 | 22000 | - | 26800 | 0 | 4800 |  | EGS | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 7 | ML04-2 | 26800 | - | 32000 | 0 | 5200 |  | EGS | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PKG05 | 32000 | - | 42000 | 10000 | 8 | ML05-1 | 32000 | - | 35000 | 0 | 3000 |  | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 9 | ML05-2 | 35000 | - | 42000 | 0 | 7000 |  | TEDI-S | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PKG06 | 42000 | - | 52000 | 10000 | 10 | ML06-1 | 42000 | - | 46600 | 0 | 4600 |  | TEDI-S | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 11 | ML06-2 | 46600 | - | 52000 | 0 | 5400 |  | TEDI-S | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PKG07 | 52000 | - | 65000 | 13000 | 12 | ML07-1 | 52000 | - | 56000 | 0 | 4000 |  | 533 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 13 | ML07-2 | 56000 | - | 60000 | 0 | 4000 |  | 533 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 14 | ML07-3 | 60000 | - | 65000 | 0 | 5000 |  | 533 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PKGA1 | 65000 | - | 81500 | 16557.32 | 15 | MLA1-1 | 65000 | - | 71000 | 0 | 6000 |  | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 16 | MLA1-2 | 71000 | - | 76000 | -57.32 | 5057.32 |  | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 17 | MLA1-3 | 76000 | - | 81500 | 0 | 5500 |  | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PKGA2 | 81500 | - | 100000 | 18200 | 18 | MLA2-1 | 81500 | - | 87000 | 0 | 5500 |  | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 19 | MLA2-2 | 87000 | - | 93000 | 0 | 6000 |  | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 20 | MLA2-3 | 93000 | - | 100000 | 300 | 6700 |  | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Quang Ngai |  |  | PKGA3 | 100000 | - | 110000 | 10173.22 | 21 | MLA3-1 | 100000 | - | 105000 | -173.22 | 5173.22 |  | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 22 | MLA3-2 | 105000 | - | 110000 | 0 | 5000 |  | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PKGA4 | 110000 | - | 125000 | 15000 | 23 | MLA4-1 | 110000 | - | 115000 | 0 | 5000 |  | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 24 | MLA4-2 | 115000 | - | 120000 | 0 | 5000 |  | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 25 | MLA4-3 | 120000 | - | 125000 | 0 | 5000 |  | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PKGA5 | 125000 | - | 131500 | 6500 | 26 | MLA5-1 | 125000 | - | 131500 | 0 | 6500 |  | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Linking Road |  | 131500 | - | 136500 | 5000 | 27 | MLA5-2 | 131500 | - | 136500 | 0 | 5000 |  | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 136500 | - | 139522 | 3022 | 28 | MLA5-3 | 136500 |  | 139522 | 0 | 3022 |  | TEDI | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | [7 empty] | 140312.32 | [6 empty] | 140312.32 | 88678.2312 |  | 88678.2312 | 0 | 0 | 0 | 0 | 88678.2312
[18 empty] | 100% | 0% | 0% | 0% | 0% | 100%
Updated Section in 2010
Km0+000 - Km16+000
Km60+000 - Km73+000
Km109+000 - Km131+500
Km131+500 - Km139+631

## Case4_TopoDistance0804
Topographic Survey
Jurisdiction |  | Road |  | Construction Contract Package (Civil Works) |  |  |  |  | Survey Package
|  | Classification |  | No. | Section |  |  | Length | No. |  | Section
[14 empty] | Equation |  | Firm | 1 | 2 | 3 | 4 | 5
[10 empty] | CP | [6 empty] | TEDI | TEDI-S | 533 | VECC | EGS
| Danang |  | Expressway | PKG01 | -800 | - | 8000 | 8800 | 1 | ML01-1 | -800 | - | 4000 | 0 | 4800 | VECC | 0 | 0 | 0 | 4800 | 0
[9 empty] | 2 | ML01-2 | 4000 | - | 8000 | 0 | 4000 | VECC | 0 | 0 | 0 | 4000 | 0
| Quang Nam |  |  | PKG02 | 8000 | - | 17000 | 9000 | 3 | ML02-1 | 8000 | - | 13000 | 0 | 5000 | VECC | 0 | 0 | 0 | 5000 | 0
[9 empty] | 4 | ML02-2 | 13000 | - | 17000 | 0 | 4000 | VECC | 0 | 0 | 0 | 4000 | 0
|  |  |  | PKG03 | 17000 | - | 22000 | 5059.78 | 5 | ML03-1 | 17000 | - | 22000 | -59.78 | 5059.78 | TEDI | 5059.78 | 0 | 0 | 0 | 0
|  |  |  | PKG04 | 22000 | - | 32000 | 10000 | 6 | ML04-1 | 22000 | - | 26800 | 0 | 4800 | EGS | 0 | 0 | 0 | 0 | 4800
[9 empty] | 7 | ML04-2 | 26800 | - | 32000 | 0 | 5200 | EGS | 0 | 0 | 0 | 0 | 5200
|  |  |  | PKG05 | 32000 | - | 42000 | 10000 | 8 | ML05-1 | 32000 | - | 35000 | 0 | 3000 | TEDI | 3000 |  | 0 | 0 | 0
[9 empty] | 9 | ML05-2 | 35000 | - | 42000 | 0 | 7000 | TEDI-S | 0 | 7000 | 0 | 0 | 0
|  |  |  | PKG06 | 42000 | - | 52000 | 10000 | 10 | ML06-1 | 42000 | - | 46600 | 0 | 4600 | TEDI-S | 0 | 4600 | 0 | 0 | 0
[9 empty] | 11 | ML06-2 | 46600 | - | 52000 | 0 | 5400 | TEDI-S | 0 | 5400 | 0 | 0 | 0
|  |  |  | PKG07 | 52000 | - | 65000 | 13000 | 12 | ML07-1 | 52000 | - | 56000 | 0 | 4000 | 533 | 0 | 0 | 4000 | 0 | 0
[9 empty] | 13 | ML07-2 | 56000 | - | 60000 | 0 | 4000 | 533 | 0 | 0 | 4000 | 0 | 0
[9 empty] | 14 | ML07-3 | 60000 | - | 65000 | 0 | 5000 | 533 | 0 | 0 | 5000 | 0 | 0
|  |  |  | PKGA1 | 65000 | - | 81500 | 16557.32 | 15 | MLA1-1 | 65000 | - | 71000 | 0 | 6000 | TEDI | 6000 | 0 | 0 | 0 | 0
[9 empty] | 16 | MLA1-2 | 71000 | - | 76000 | -57.32 | 5057.32 | TEDI | 5057.32 | 0 | 0 | 0 | 0
[9 empty] | 17 | MLA1-3 | 76000 | - | 81500 | 0 | 5500 | TEDI | 5500 | 0 | 0 | 0 | 0
|  |  |  | PKGA2 | 81500 | - | 100000 | 18200 | 18 | MLA2-1 | 81500 | - | 87000 | 0 | 5500 | TEDI | 5500 | 0 | 0 | 0 | 0
[9 empty] | 19 | MLA2-2 | 87000 | - | 93000 | 0 | 6000 | TEDI | 6000 | 0 | 0 | 0 | 0
[9 empty] | 20 | MLA2-3 | 93000 | - | 100000 | 300 | 6700 | TEDI | 6700 | 0 | 0 | 0 | 0
| Quang Ngai |  |  | PKGA3 | 100000 | - | 110000 | 10173.22 | 21 | MLA3-1 | 100000 | - | 105000 | -173.22 | 5173.22 | TEDI | 5173.22 | 0 | 0 | 0 | 0
[9 empty] | 22 | MLA3-2 | 105000 | - | 110000 | 0 | 5000 | TEDI | 5000 | 0 | 0 | 0 | 0
|  |  |  | PKGA4 | 110000 | - | 125000 | 15000 | 23 | MLA4-1 | 110000 | - | 115000 | 0 | 5000 | TEDI | 5000 | 0 | 0 | 0 | 0
[9 empty] | 24 | MLA4-2 | 115000 | - | 120000 | 0 | 5000 | TEDI | 5000 | 0 | 0 | 0 | 0
[9 empty] | 25 | MLA4-3 | 120000 | - | 125000 | 0 | 5000 | TEDI | 5000 | 0 | 0 | 0 | 0
|  |  |  | PKGA5 | 125000 | - | 131500 | 6500 | 26 | MLA5-1 | 125000 | - | 131500 | 0 | 6500 | TEDI | 6500 | 0 | 0 | 0 | 0
|  |  | Linking Road |  | 131500 | - | 136500 | 5000 | 27 | MLA5-2 | 131500 | - | 136500 | 0 | 5000 | TEDI | 5000 | 0 | 0 | 0 | 0
[5 empty] | 136500 | - | 139522 | 3022 | 28 | MLA5-3 | 136500 |  | 139522 | 0 | 3022 | TEDI | 3022 | 0 | 0 | 0 | 0
Total | [7 empty] | 140312.32 | [6 empty] | 140312.32 |  | 82512.32 | 17000 | 13000 | 17800 | 10000
[17 empty] | 58.81% | 12.12% | 9.265% | 12.69% | 7.127%
Updated Section in 2010
Km0+000 - Km16+000
Km60+000 - Km73+000
Km109+000 - Km131+500
Km131+500 - Km139+631

## TopoBase(110804)
Topographic Survey
Jurisdiction |  | Road |  | Construction Contract Package (Civil Works) |  |  |  |  | Survey Package | [6 empty] | Estimated Cost (USD)
|  | Classification |  | No. | Section |  |  | Length | No. |  | Section |  |  |  |  | Proposal | 2011.08
Equation
[10 empty] | CP | [5 empty] | 88678.2312 | 165515.9064
| Danang |  | Expressway | PKG01 | -800 | - | 8000 | 8800 | 1 | ML01-1 | -800 | - | 4000 | 0 | 4800 |  | 69693.52
[9 empty] | 2 | ML01-2 | 4000 | - | 8000 | 0 | 4000 |  | 33207.2618
| Quang Nam |  |  | PKG02 | 8000 | - | 17000 | 9000 | 3 | ML02-1 | 8000 | - | 13000 | 0 | 5000 |  | 44041.0106
[9 empty] | 4 | ML02-2 | 13000 | - | 17000 | 0 | 4000 |  | 34559.4831
|  |  |  | PKG03 | 17000 | - | 22000 | 5059.78 | 5 | ML03-1 | 17000 | - | 22000 | -59.78 | 5059.78 |  | 63173.8109
|  |  |  | PKG04 | 22000 | - | 32000 | 10000 | 6 | ML04-1 | 22000 | - | 26800 | 0 | 4800 |  | 32505.6792
[9 empty] | 7 | ML04-2 | 26800 | - | 32000 | 0 | 5200 |  | 37889.8945
|  |  |  | PKG05 | 32000 | - | 42000 | 10000 | 8 | ML05-1 | 32000 | - | 35000 | 0 | 3000 |  | 17708.9905
[9 empty] | 9 | ML05-2 | 35000 | - | 42000 | 0 | 7000 |  | 67398.4046
|  |  |  | PKG06 | 42000 | - | 52000 | 10000 | 10 | ML06-1 | 42000 | - | 46600 | 0 | 4600 |  | 33230.3162
[9 empty] | 11 | ML06-2 | 46600 | - | 52000 | 0 | 5400 |  | 39745.2099
|  |  |  | PKG07 | 52000 | - | 65000 | 13000 | 12 | ML07-1 | 52000 | - | 56000 | 0 | 4000 |  | 31489.163
[9 empty] | 13 | ML07-2 | 56000 | - | 60000 | 0 | 4000 |  | 29633.6773
[9 empty] | 14 | ML07-3 | 60000 | - | 65000 | 0 | 5000 |  | 53249.3845
|  |  |  | PKGA1 | 65000 | - | 81500 | 16557.32 | 15 | MLA1-1 | 65000 | - | 71000 | 0 | 6000 |  | 45610.9845
[9 empty] | 16 | MLA1-2 | 71000 | - | 76000 | -57.32 | 5057.32 |  | 41611.8864
[9 empty] | 17 | MLA1-3 | 76000 | - | 81500 | 0 | 5500 |  | 37219.9481
|  |  |  | PKGA2 | 81500 | - | 100000 | 18200 | 18 | MLA2-1 | 81500 | - | 87000 | 0 | 5500 |  | 50428.6324
[9 empty] | 19 | MLA2-2 | 87000 | - | 93000 | 0 | 6000 |  | 41498.4124
[9 empty] | 20 | MLA2-3 | 93000 | - | 100000 | 300 | 6700 |  | 44442.1836
| Quang Ngai |  |  | PKGA3 | 100000 | - | 110000 | 10173.22 | 21 | MLA3-1 | 100000 | - | 105000 | -173.22 | 5173.22 |  | 45756.4383
[9 empty] | 22 | MLA3-2 | 105000 | - | 110000 | 0 | 5000 |  | 35829.4501
|  |  |  | PKGA4 | 110000 | - | 125000 | 15000 | 23 | MLA4-1 | 110000 | - | 115000 | 0 | 5000 |  | 48686.785
[9 empty] | 24 | MLA4-2 | 115000 | - | 120000 | 0 | 5000 |  | 40531.7396
[9 empty] | 25 | MLA4-3 | 120000 | - | 125000 | 0 | 5000 |  | 48646.8176
|  |  |  | PKGA5 | 125000 | - | 131500 | 6500 | 26 | MLA5-1 | 125000 | - | 131500 | 0 | 6500 |  | 54995.4889
|  |  | Linking Road |  | 131500 | - | 136500 | 5000 | 27 | MLA5-2 | 131500 | - | 136500 | 0 | 5000 |  | 15399.6766
[5 empty] | 136500 | - | 139522 | 3022 | 28 | MLA5-3 | 136500 |  | 139522 | 0 | 3022 |  | 13446.0245
Total | [7 empty] | 140312.32 | [6 empty] | 140312.32 |  | 1317146.1805