## 14B
DELIVERABLES OF SCOPE OF PACKAGE 14 (May 31, 2013)
I | DRAWINGS
S.N. | TITLE |  | TÊN BẢN VẼ |  | DWG NO. | Team / Person | Beginning time | End time | Days | Progress | Draft | Check 1 | Check 2 | Final | Note
| A. GENERAL |  | A. BẢN VẼ CHUNG
1 |  | DRAWING LIST (1/2) |  | DANH MỤC BẢN VẼ (1/2) | PKG14B2-GN-010
2 |  | DRAWING LIST (2/2) |  | DANH MỤC BẢN VẼ (2/2) | PKG14B2-GN-020
| B. TYPICAL CROSS SECTION |  | B. CẮT NGANG ĐẠI DIỆN
3 |  | TYPICAL CROSS SECTION OF EXPRESSWAY (1/3) |  | CẮT NGANG ĐẠI DIỆN ĐƯỜNG CAO TỐC (1/3) | PKG14B2-ML-TC-010
4 |  | TYPICAL CROSS SECTION OF EXPRESSWAY (2/3) |  | CẮT NGANG ĐẠI DIỆN ĐƯỜNG CAO TỐC (2/3) | PKG14B2-ML-TC-020
5 |  | TYPICAL CROSS SECTION OF EXPRESSWAY (3/3) |  | CẮT NGANG ĐẠI DIỆN ĐƯỜNG CAO TỐC (3/3) | PKG14B2-ML-TC-030
|  | TYPICAL CROSS SECTION OF MAINLINE AT NOSE |  | CẮT NGANG ĐẠI DIỆN TUYẾN CHÍNH TẠI MŨI ĐẢO | PKG14B2B-ML-TC--020
|  | TYPICAL CROSS SECTION OF LINKING ROAD |  | CẮT NGANG ĐẠI DIỆN TUYẾN NỐI | PKG14B2B-ML-TC--020
|  | TYPICAL CROSS SECTION OF RAMPWAY |  | CẮT NGANG ĐẠI DIỆN ĐƯỜNG NHÁNH | PKG14B2B-ML-TC--020
| C. PLAN OF TRAFFIC SAFETY |  | C. BÌNH ĐỒ AN TOÀN GIAO THÔNG
| C.1 SCOPE OF PACKAGE A1 (KM65+000 - KM81+150) |  | C.1 PHẠM VI GÓI THẦU A1 (KM65+000 - KM81+150)
|  | PLAN OF TRAFFIC SAFETY (1/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (1/12) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (2/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (2/12) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (3/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (3/12) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (4/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (4/12) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (5/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (5/12) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (6/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (6/12) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (7/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (7/12) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (8/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (8/12) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (9/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (9/12) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (10/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (10/12) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (11/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (11/12) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (12/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (12/12) | PKG14B2-ML-PTS--050
| C.2 SCOPE OF PACKAGE A2 (KM81+150 - KM99+500) |  | C.2 PHẠM VI GÓI THẦU A2 (KM81+150 - KM99+500)
|  | PLAN OF TRAFFIC SAFETY (1/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (1/14) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (2/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (2/14) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (3/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (3/14) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (4/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (4/14) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (5/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (5/14) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (6/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (6/14) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (7/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (7/14) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (8/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (8/14) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (9/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (9/14) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (10/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (10/14) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (11/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (11/14) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (12/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (12/14) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (13/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (13/14) | PKG14B2-ML-PTS--050
|  | PLAN OF TRAFFIC SAFETY (14/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (14/14) | PKG14B2-ML-PTS--050
| C.1 SCOPE OF PACKAGE A3 (KM99+500 - KM110+100) |  | C.1 PHẠM VI GÓI THẦU A3 (KM99+500 - KM110+100)
6 |  | PLAN OF TRAFFIC SAFETY (1/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (1/10) | PKG14B2-ML-PTS-010
7 |  | PLAN OF TRAFFIC SAFETY (2/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (2/10) | PKG14B2-ML-PTS-020
8 |  | PLAN OF TRAFFIC SAFETY (3/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (3/10) | PKG14B2-ML-PTS-030
9 |  | PLAN OF TRAFFIC SAFETY (4/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (4/10) | PKG14B2-ML-PTS-040
10 |  | PLAN OF TRAFFIC SAFETY (5/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (5/10) | PKG14B2-ML-PTS-050
11 |  | PLAN OF TRAFFIC SAFETY (6/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (6/10) | PKG14B2-ML-PTS-060
12 |  | PLAN OF TRAFFIC SAFETY (7/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (7/10) | PKG14B2-ML-PTS-070
13 |  | PLAN OF TRAFFIC SAFETY (8/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (8/10) | PKG14B2-ML-PTS-080
14 |  | PLAN OF TRAFFIC SAFETY (9/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (9/10) | PKG14B2-ML-PTS-090
15 |  | PLAN OF TRAFFIC SAFETY (10/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (10/10) | PKG14B2-ML-PTS-100
| C.2 SCOPE OF PACKAGE A4 (KM110+100 - KM124+700) |  | C.2 PHẠM VI GÓI THẦU A4 (KM110+100 - KM124+700)
16 |  | PLAN OF TRAFFIC SAFETY (1/13) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (1/13) | PKG14B2-ML-PTS-110
17 |  | PLAN OF TRAFFIC SAFETY (2/13) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (2/13) | PKG14B2-ML-PTS-120
18 |  | PLAN OF TRAFFIC SAFETY (3/13) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (3/13) | PKG14B2-ML-PTS-130
19 |  | PLAN OF TRAFFIC SAFETY (4/13) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (4/13) | PKG14B2-ML-PTS-140
20 |  | PLAN OF TRAFFIC SAFETY (5/13) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (5/13) | PKG14B2-ML-PTS-150
21 |  | PLAN OF TRAFFIC SAFETY (6/13) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (6/13) | PKG14B2-ML-PTS-160
22 |  | PLAN OF TRAFFIC SAFETY (7/13) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (7/13) | PKG14B2-ML-PTS-170
23 |  | PLAN OF TRAFFIC SAFETY (8/13) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (8/13) | PKG14B2-ML-PTS-180
24 |  | PLAN OF TRAFFIC SAFETY (9/13) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (9/13) | PKG14B2-ML-PTS-190
25 |  | PLAN OF TRAFFIC SAFETY (10/13) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (10/13) | PKG14B2-ML-PTS-200
26 |  | PLAN OF TRAFFIC SAFETY (11/13) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (11/13) | PKG14B2-ML-PTS-210
27 |  | PLAN OF TRAFFIC SAFETY (12/13) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (12/13) | PKG14B2-ML-PTS-220
28 |  | PLAN OF TRAFFIC SAFETY (13/13) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (13/13) | PKG14B2-ML-PTS-230
| C.3 SCOPE OF PACKAGE A5 (KM124+700 - KM139+203.627) |  | C.3 PHẠM VI GÓI THẦU A5 (KM124+700 - KM139+203.627)
29 |  | PLAN OF TRAFFIC SAFETY (1/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (1/11) | PKG14B2-ML-PTS-240
30 |  | PLAN OF TRAFFIC SAFETY (2/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (2/11) | PKG14B2-ML-PTS-250
31 |  | PLAN OF TRAFFIC SAFETY (3/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (3/11) | PKG14B2-ML-PTS-260
32 |  | PLAN OF TRAFFIC SAFETY (4/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (4/11) | PKG14B2-ML-PTS-270
33 |  | PLAN OF TRAFFIC SAFETY (5/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (5/11) | PKG14B2-ML-PTS-280
34 |  | PLAN OF TRAFFIC SAFETY (6/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (6/11) | PKG14B2-ML-PTS-290
35 |  | PLAN OF TRAFFIC SAFETY (7/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (7/11) | PKG14B2-ML-PTS-300
36 |  | PLAN OF TRAFFIC SAFETY (8/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (8/11) | PKG14B2-ML-PTS-310
37 |  | PLAN OF TRAFFIC SAFETY (9/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (9/11) | PKG14B2-ML-PTS-320
38 |  | PLAN OF TRAFFIC SAFETY (10/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (10/11) | PKG14B2-ML-PTS-330
39 |  | PLAN OF TRAFFIC SAFETY (11/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (11/11) | PKG14B2-ML-PTS-340
| D. PAVEMENT MARKING |  | D. VẠCH SƠN ĐƯỜNG
40 |  | DETAILS OF PAVEMENT MARKINGS (1/3) |  | CHI TIẾT VẠCH SƠN (1/3) | PKG14B2-ML-PM-010
41 |  | DETAILS OF PAVEMENT MARKINGS (2/3) |  | CHI TIẾT VẠCH SƠN (2/3) | PKG14B2-ML-PM-020
42 |  | DETAILS OF PAVEMENT MARKINGS (3/3) |  | CHI TIẾT VẠCH SƠN (3/3) | PKG14B2-ML-PM-030
| E. DETAIL OF TRAFFIC SIGN |  | E. CHI TIẾT BIỂN BÁO
43 |  | DETAILS OF TRAFFIC SIGN (1/6) |  | CHI TIẾT BIỂN BÁO (1/6) | PKG14B2-ML-DTS-010
44 |  | DETAILS OF TRAFFIC SIGN (2/6) |  | CHI TIẾT BIỂN BÁO (2/6) | PKG14B2-ML-DTS-020
45 |  | DETAILS OF TRAFFIC SIGN (3/6) |  | CHI TIẾT BIỂN BÁO (3/6) | PKG14B2-ML-DTS-030
46 |  | DETAILS OF TRAFFIC SIGN (4/6) |  | CHI TIẾT BIỂN BÁO (4/6) | PKG14B2-ML-DTS-040
47 |  | DETAILS OF TRAFFIC SIGN (5/6) |  | CHI TIẾT BIỂN BÁO (5/6) | PKG14B2-ML-DTS-050
48 |  | DETAILS OF TRAFFIC SIGN (6/6) |  | CHI TIẾT BIỂN BÁO (6/6) | PKG14B2-ML-DTS-060
| F. MISCELLANEOUS |  | F. BẢN VẼ KHÁC
49 |  | DETAIL OF TRAFFIC POST SIGN (1/8) |  | CHI TIẾT CỘT BIỂN BÁO (1/8) | PKG14B2-ML-MISC-010
50 |  | DETAIL OF TRAFFIC POST SIGN (2/8) |  | CHI TIẾT CỘT BIỂN BÁO (2/8) | PKG14B2-ML-MISC-020
51 |  | DETAIL OF TRAFFIC POST SIGN (3/8) |  | CHI TIẾT CỘT BIỂN BÁO (3/8) | PKG14B2-ML-MISC-030
52 |  | DETAIL OF TRAFFIC POST SIGN (4/8) |  | CHI TIẾT CỘT BIỂN BÁO (4/8) | PKG14B2-ML-MISC-040
53 |  | DETAIL OF TRAFFIC POST SIGN (5/8) |  | CHI TIẾT CỘT BIỂN BÁO (5/8) | PKG14B2-ML-MISC-050
54 |  | DETAIL OF TRAFFIC POST SIGN (6/8) |  | CHI TIẾT CỘT BIỂN BÁO (6/8) | PKG14B2-ML-MISC-060
55 |  | DETAIL OF TRAFFIC POST SIGN (7/8) |  | CHI TIẾT CỘT BIỂN BÁO (7/8) | PKG14B2-ML-MISC-070
56 |  | DETAIL OF TRAFFIC POST SIGN (8/8_1/2) |  | CHI TIẾT CỘT BIỂN BÁO (8/8_1/2) | PKG14B2-ML-MISC-080
57 |  | DETAIL OF TRAFFIC POST SIGN (8/8_2/2) |  | CHI TIẾT CỘT BIỂN BÁO (8/8_2/2) | PKG14B2-ML-MISC-081
58 |  | DETAIL OF GUARDRAIL, TYPE 1 |  | CHI TIẾT TƯỜNG HỘ LAN, LOẠI 1 | PKG14B2-ML-MISC-090
59 |  | DETAIL OF GUARDRAIL, TYPE 2 |  | CHI TIẾT TƯỜNG HỘ LAN, LOẠI 2 | PKG14B2-ML-MISC-100
60 |  | DETAIL OF GUARDRAIL, TYPE 1A |  | CHI TIẾT TƯỜNG HỘ LAN, LOẠI 1A | PKG14B2-ML-MISC-110
61 |  | DETAIL OF GUARDRAIL, TYPE 1B |  | CHI TIẾT TƯỜNG HỘ LAN, LOẠI 1B | PKG14B2-ML-MISC-120
62 |  | DETAIL OF GUARDRAIL, TYPE 2B |  | CHI TIẾT TƯỜNG HỘ LAN, LOẠI 2B | PKG14B2-ML-MISC-121
63 |  | DETAIL OF GUARDRAIL AT RAMP NOSE |  | CHI TIẾT TƯỜNG HỘ LAN VỊ TRÍ TÁCH NHẬP DÒNG | PKG14B2-ML-MISC-130
64 |  | DETAIL OF GUARD POST & KM POST |  | CHI TIẾT CỌC TIÊU & CỌC KM | PKG14B2-ML-MISC-140
65 |  | DETAIL OF GUIDE SIGN-GANTRY POST (1/2) |  | CHI TIẾT CỘT BiỂN BÁO-GIÁ TAY VƯƠN (2/2) | PKG14B2-ML-MISC-150
66 |  | DETAIL OF GUIDE SIGN-GANTRY POST (2/2) |  | CHI TIẾT CỘT BiỂN BÁO-GIÁ TAY VƯƠN (2/2) | PKG14B2-ML-MISC-151
67 |  | DETAIL OF ANTI GLARE PLATE |  | CHI TIẾT TẤM CHỐNG LÓA | PKG14B2-ML-MISC-160
68 |  | DETAIL OF FENCE (1/2) |  | CHI TIẾT HÀNG RÀO (1/2) | PKG14B2-ML-MISC-170
69 |  | DETAIL OF FENCE (2/2) |  | CHI TIẾT HÀNG RÀO (2/2) | PKG14B2-ML-MISC-171
70 |  | UNIT QUANTITY OF GUARD FENCE, ANTI-GLAR SCREEN AND GUARD RAIL |  | KHỐI LƯỢNG ĐƠN VỊ CHO HÀNG RÀO, TẤM CHỐNG LÓA VÀ HỘ LAN | PKG14B2-ML-MISC-172
| G. QUANTITY REPORT |  | G. BÁO CÁO KHỐI LƯỢNG
| G.1 SUMMARY QUANTITY |  | G.1 TỔNG HỢP KHỐI LƯỢNG
71 |  | PKG14B2 |  | PKG14B2
72 |  | MAINLINE |  | TUYẾN CHÍNH
73 |  | CROSSING ROAD |  | ĐƯỜNG NGANG
74 |  | FRONTAGE ROAD |  | ĐƯỜNG GOM
| G.2 STATISTIC TABLE |  | G.2 BẢNG THỐNG KÊ
| G.2.1 TRAFFIC SIGN |  | G.2.1 BIỂN BÁO
75 |  | MAINLINE |  | TUYẾN CHÍNH
76 |  | CROSSING ROAD |  | ĐƯỜNG NGANG
77 |  | FRONTAGE ROAD |  | ĐƯỜNG GOM
| G.2.2 GUARD RAIL |  | G.2.2 HỘ LAN
78 |  | MAINLINE |  | TUYẾN CHÍNH
79 |  | CROSSING ROAD |  | ĐƯỜNG NGANG
80 |  | FRONTAGE ROAD |  | ĐƯỜNG GOM
| G.2.3 GUARD POST |  | G.2.3 CỌC TIÊU
81 |  | MAINLINE |  | TUYẾN CHÍNH
82 |  | CROSSING ROAD |  | ĐƯỜNG NGANG
83 |  | FRONTAGE ROAD |  | ĐƯỜNG GOM

## WB (hidden)
DELIVERABLES OF SCOPE OF PACKAGE 14 (May 31, 2013)
I | DRAWINGS
S.N. | TITLE |  | TÊN BẢN VẼ |  | DWG NO. | Team / Person | Beginning time | End time | Days | Progress | Draft | Check 1 | Check 2 | Final | Note
| A. GENERAL |  | A. BẢN VẼ CHUNG
1 |  | DRAWING LIST (1/2) |  | DANH MỤC BẢN VẼ (1/2) | PKG14B-GN-010
2 |  | DRAWING LIST (2/2) |  | DANH MỤC BẢN VẼ (2/2) | PKG14B-GN-020
| B. TYPICAL CROSS SECTION |  | B. CẮT NGANG ĐẠI DIỆN
3 |  | TYPICAL CROSS SECTION OF EXPRESSWAY (1/4) |  | CẮT NGANG ĐẠI DIỆN ĐƯỜNG CAO TỐC (1/4) | PKG14B-ML-TC-010
4 |  | TYPICAL CROSS SECTION OF EXPRESSWAY (2/4) |  | CẮT NGANG ĐẠI DIỆN ĐƯỜNG CAO TỐC (2/4) | PKG14B-ML-TC-020
5 |  | TYPICAL CROSS SECTION OF EXPRESSWAY (3/4) |  | CẮT NGANG ĐẠI DIỆN ĐƯỜNG CAO TỐC (3/4) | PKG14B-ML-TC-030
6 |  | TYPICAL CROSS SECTION OF EXPRESSWAY (4/4) |  | CẮT NGANG ĐẠI DIỆN ĐƯỜNG CAO TỐC (4/4) | PKG14B-ML-TC-040
|  | TYPICAL CROSS SECTION OF LINKING ROAD |  | CẮT NGANG ĐẠI DIỆN TUYẾN NỐI
|  | TYPICAL CROSS SECTION OF RAMPWAY |  | CẮT NGANG ĐẠI DIỆN ĐƯỜNG NHÁNH
| C. PLAN OF TRAFFIC SAFETY |  | C. BÌNH ĐỒ AN TOÀN GIAO THÔNG
| C.1 SCOPE OF PACKAGE A1 (KM65+000 - KM81+150) |  | C.1 PHẠM VI GÓI THẦU A1 (KM65+000 - KM81+150)
7 |  | PLAN OF TRAFFIC SAFETY (1/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (1/12) | PKG14B-ML-PTS-010
8 |  | PLAN OF TRAFFIC SAFETY (2/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (2/12) | PKG14B-ML-PTS-020
9 |  | PLAN OF TRAFFIC SAFETY (3/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (3/12) | PKG14B-ML-PTS-030
10 |  | PLAN OF TRAFFIC SAFETY (4/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (4/12) | PKG14B-ML-PTS-040
11 |  | PLAN OF TRAFFIC SAFETY (5/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (5/12) | PKG14B-ML-PTS-050
12 |  | PLAN OF TRAFFIC SAFETY (6/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (6/12) | PKG14B-ML-PTS-060
13 |  | PLAN OF TRAFFIC SAFETY (7/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (7/12) | PKG14B-ML-PTS-070
14 |  | PLAN OF TRAFFIC SAFETY (8/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (8/12) | PKG14B-ML-PTS-080
15 |  | PLAN OF TRAFFIC SAFETY (9/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (9/12) | PKG14B-ML-PTS-090
16 |  | PLAN OF TRAFFIC SAFETY (10/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (10/12) | PKG14B-ML-PTS-100
17 |  | PLAN OF TRAFFIC SAFETY (11/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (11/12) | PKG14B-ML-PTS-110
18 |  | PLAN OF TRAFFIC SAFETY (12/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (12/12) | PKG14B-ML-PTS-120
| C.2 SCOPE OF PACKAGE A2 (KM81+150 - KM99+500) |  | C.2 PHẠM VI GÓI THẦU A2 (KM81+150 - KM99+500)
19 |  | PLAN OF TRAFFIC SAFETY (1/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (1/14) | PKG14B-ML-PTS-190
20 |  | PLAN OF TRAFFIC SAFETY (2/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (2/14) | PKG14B-ML-PTS-200
21 |  | PLAN OF TRAFFIC SAFETY (3/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (3/14) | PKG14B-ML-PTS-210
22 |  | PLAN OF TRAFFIC SAFETY (4/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (4/14) | PKG14B-ML-PTS-220
23 |  | PLAN OF TRAFFIC SAFETY (5/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (5/14) | PKG14B-ML-PTS-230
24 |  | PLAN OF TRAFFIC SAFETY (6/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (6/14) | PKG14B-ML-PTS-240
25 |  | PLAN OF TRAFFIC SAFETY (7/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (7/14) | PKG14B-ML-PTS-250
26 |  | PLAN OF TRAFFIC SAFETY (8/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (8/14) | PKG14B-ML-PTS-260
27 |  | PLAN OF TRAFFIC SAFETY (9/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (9/14) | PKG14B-ML-PTS-270
28 |  | PLAN OF TRAFFIC SAFETY (10/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (10/14) | PKG14B-ML-PTS-280
29 |  | PLAN OF TRAFFIC SAFETY (11/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (11/14) | PKG14B-ML-PTS-290
30 |  | PLAN OF TRAFFIC SAFETY (12/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (12/14) | PKG14B-ML-PTS-300
31 |  | PLAN OF TRAFFIC SAFETY (13/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (13/14) | PKG14B-ML-PTS-310
32 |  | PLAN OF TRAFFIC SAFETY (14/14) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (14/14) | PKG14B-ML-PTS-320
| C.3 SCOPE OF PACKAGE A3 (KM99+500 - KM110+100) |  | C.3 PHẠM VI GÓI THẦU A3 (KM99+500 - KM110+100)
33 |  | PLAN OF TRAFFIC SAFETY (1/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (1/10) | PKG14B-ML-PTS-330
34 |  | PLAN OF TRAFFIC SAFETY (2/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (2/10) | PKG14B-ML-PTS-340
35 |  | PLAN OF TRAFFIC SAFETY (3/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (3/10) | PKG14B-ML-PTS-350
36 |  | PLAN OF TRAFFIC SAFETY (4/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (4/10) | PKG14B-ML-PTS-360
37 |  | PLAN OF TRAFFIC SAFETY (5/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (5/10) | PKG14B-ML-PTS-370
38 |  | PLAN OF TRAFFIC SAFETY (6/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (6/10) | PKG14B-ML-PTS-380
39 |  | PLAN OF TRAFFIC SAFETY (7/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (7/10) | PKG14B-ML-PTS-390
40 |  | PLAN OF TRAFFIC SAFETY (8/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (8/10) | PKG14B-ML-PTS-400
41 |  | PLAN OF TRAFFIC SAFETY (9/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (9/10) | PKG14B-ML-PTS-410
42 |  | PLAN OF TRAFFIC SAFETY (10/10) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (10/10) | PKG14B-ML-PTS-420
| C.4 SCOPE OF PACKAGE A4 (KM110+100 - KM124+700) |  | C.4 PHẠM VI GÓI THẦU A4 (KM110+100 - KM124+700)
43 |  | PLAN OF TRAFFIC SAFETY (1/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (1/12) | PKG14B-ML-PTS-430
44 |  | PLAN OF TRAFFIC SAFETY (2/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (2/12) | PKG14B-ML-PTS-440
45 |  | PLAN OF TRAFFIC SAFETY (3/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (3/12) | PKG14B-ML-PTS-450
46 |  | PLAN OF TRAFFIC SAFETY (4/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (4/12) | PKG14B-ML-PTS-460
47 |  | PLAN OF TRAFFIC SAFETY (5/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (5/12) | PKG14B-ML-PTS-470
48 |  | PLAN OF TRAFFIC SAFETY (6/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (6/12) | PKG14B-ML-PTS-480
49 |  | PLAN OF TRAFFIC SAFETY (7/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (7/12) | PKG14B-ML-PTS-490
50 |  | PLAN OF TRAFFIC SAFETY (8/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (8/12) | PKG14B-ML-PTS-500
51 |  | PLAN OF TRAFFIC SAFETY (9/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (9/12) | PKG14B-ML-PTS-510
52 |  | PLAN OF TRAFFIC SAFETY (10/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (10/12) | PKG14B-ML-PTS-520
53 |  | PLAN OF TRAFFIC SAFETY (11/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (11/12) | PKG14B-ML-PTS-530
54 |  | PLAN OF TRAFFIC SAFETY (12/12) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (12/12) | PKG14B-ML-PTS-540
| C.5 SCOPE OF PACKAGE A5 (KM124+700 - KM139+203.627) |  | C.5 PHẠM VI GÓI THẦU A5 (KM124+700 - KM139+203.627)
55 |  | PLAN OF TRAFFIC SAFETY (1/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (1/11) | PKG14B-ML-PTS-550
56 |  | PLAN OF TRAFFIC SAFETY (2/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (2/11) | PKG14B-ML-PTS-560
57 |  | PLAN OF TRAFFIC SAFETY (3/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (3/11) | PKG14B-ML-PTS-570
58 |  | PLAN OF TRAFFIC SAFETY (4/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (4/11) | PKG14B-ML-PTS-580
59 |  | PLAN OF TRAFFIC SAFETY (5/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (5/11) | PKG14B-ML-PTS-590
60 |  | PLAN OF TRAFFIC SAFETY (6/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (6/11) | PKG14B-ML-PTS-600
61 |  | PLAN OF TRAFFIC SAFETY (7/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (7/11) | PKG14B-ML-PTS-610
62 |  | PLAN OF TRAFFIC SAFETY (8/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (8/11) | PKG14B-ML-PTS-620
63 |  | PLAN OF TRAFFIC SAFETY (9/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (9/11) | PKG14B-ML-PTS-630
64 |  | PLAN OF TRAFFIC SAFETY (10/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (10/11) | PKG14B-ML-PTS-640
65 |  | PLAN OF TRAFFIC SAFETY (11/11) |  | BÌNH ĐỒ AN TOÀN GIAO THÔNG (11/11) | PKG14B-ML-PTS-650
| D. PAVEMENT MARKING |  | D. VẠCH SƠN ĐƯỜNG
66 |  | DETAILS OF PAVEMENT MARKINGS (1/3) |  | CHI TIẾT VẠCH SƠN (1/3) | PKG14B-ML-PM-010
67 |  | DETAILS OF PAVEMENT MARKINGS (2/3) |  | CHI TIẾT VẠCH SƠN (2/3) | PKG14B-ML-PM-020
68 |  | DETAILS OF PAVEMENT MARKINGS (3/3) |  | CHI TIẾT VẠCH SƠN (3/3) | PKG14B-ML-PM-030
| E. DETAIL OF TRAFFIC SIGN |  | E. CHI TIẾT BIỂN BÁO
69 |  | DETAILS OF TRAFFIC SIGN (1/8) |  | CHI TIẾT BIỂN BÁO (1/8) | PKG14B-ML-DTS-010
70 |  | DETAILS OF TRAFFIC SIGN (2/8) |  | CHI TIẾT BIỂN BÁO (2/8) | PKG14B-ML-DTS-020
71 |  | DETAILS OF TRAFFIC SIGN (3/8) |  | CHI TIẾT BIỂN BÁO (3/8) | PKG14B-ML-DTS-030
72 |  | DETAILS OF TRAFFIC SIGN (4/8) |  | CHI TIẾT BIỂN BÁO (4/8) | PKG14B-ML-DTS-040
73 |  | DETAILS OF TRAFFIC SIGN (5/8) |  | CHI TIẾT BIỂN BÁO (5/8) | PKG14B-ML-DTS-050
74 |  | DETAILS OF TRAFFIC SIGN (6/8) |  | CHI TIẾT BIỂN BÁO (6/8) | PKG14B-ML-DTS-060
75 |  | DETAILS OF TRAFFIC SIGN (7/8) |  | CHI TIẾT BIỂN BÁO (7/8) | PKG14B-ML-DTS-070
76 |  | DETAILS OF TRAFFIC SIGN (8/8) |  | CHI TIẾT BIỂN BÁO (8/8) | PKG14B-ML-DTS-080
| F. MISCELLANEOUS |  | F. BẢN VẼ KHÁC
77 |  | DETAIL OF TRAFFIC POST SIGN (1/8) |  | CHI TIẾT CỘT BIỂN BÁO (1/8) | PKG14B-ML-MISC-010
78 |  | DETAIL OF TRAFFIC POST SIGN (2/8) |  | CHI TIẾT CỘT BIỂN BÁO (2/8) | PKG14B-ML-MISC-020
79 |  | DETAIL OF TRAFFIC POST SIGN (3/8) |  | CHI TIẾT CỘT BIỂN BÁO (3/8) | PKG14B-ML-MISC-030
80 |  | DETAIL OF TRAFFIC POST SIGN (4/8) |  | CHI TIẾT CỘT BIỂN BÁO (4/8) | PKG14B-ML-MISC-040
81 |  | DETAIL OF TRAFFIC POST SIGN (5/8) |  | CHI TIẾT CỘT BIỂN BÁO (5/8) | PKG14B-ML-MISC-050
82 |  | DETAIL OF TRAFFIC POST SIGN (6/8) |  | CHI TIẾT CỘT BIỂN BÁO (6/8) | PKG14B-ML-MISC-060
83 |  | DETAIL OF TRAFFIC POST SIGN (7/8) |  | CHI TIẾT CỘT BIỂN BÁO (7/8) | PKG14B-ML-MISC-070
84 |  | DETAIL OF TRAFFIC POST SIGN (8/8) |  | CHI TIẾT CỘT BIỂN BÁO (8/8) | PKG14B-ML-MISC-080
85 |  | DETAIL OF GUARDRAIL, TYPE 1 |  | CHI TIẾT TƯỜNG HỘ LAN, LOẠI 1 | PKG14B-ML-MISC-090
86 |  | DETAIL OF GUARDRAIL, TYPE 2 |  | CHI TIẾT TƯỜNG HỘ LAN, LOẠI 2 | PKG14B-ML-MISC-100
87 |  | DETAIL OF GUARDRAIL, TYPE 1A |  | CHI TIẾT TƯỜNG HỘ LAN, LOẠI 1A | PKG14B-ML-MISC-110
88 |  | DETAIL OF GUARDRAIL, TYPE 2A |  | CHI TIẾT TƯỜNG HỘ LAN, LOẠI 2A | PKG14B-ML-MISC-120
89 |  | DETAIL OF GUARDRAIL AT RAMP NOSE, AT BRIDGE APPROACH, AT TERMINAL |  | CHI TIẾT TƯỜNG HỘ LAN VỊ TRÍ TÁCH NHẬP DÒNG, TẠI ĐƯỜNG ĐẦU CẦU, TẠI ĐIỂM ĐẦU VÀ CUỐI | PKG14B-ML-MISC-130
90 |  | DETAIL OF DELINEATOR, KM POST |  | CHI TIẾT CỌC TIÊU, CỌC KM | PKG14B-ML-MISC-140
91 |  | DETAIL OF TRAFFIC MIRROR |  | CHI TIẾT GƯƠNG CẦU LỒI | PKG14B-ML-MISC-150
92 |  | DETAIL OF ANTI GLARE PLATE |  | CHI TIẾT TẤM CHỐNG LÓA | PKG14B-ML-MISC-160
93 |  | DETAIL OF FENCE |  | CHI TIẾT HÀNG RÀO | PKG14B-ML-MISC-170
| G. QUANTITY REPORT |  | G. BÁO CÁO KHỐI LƯỢNG
| G.1 SUMMARY QUANTITY |  | G.1 TỔNG HỢP KHỐI LƯỢNG
94 |  | PKG14B |  | PKG14B
95 |  | MAINLINE |  | TUYẾN CHÍNH
96 |  | CROSSING ROAD |  | ĐƯỜNG NGANG
97 |  | FRONTAGE ROAD |  | ĐƯỜNG GOM
| G.2 STATISTIC TABLE |  | G.2 BẢNG THỐNG KÊ
| G.2.1 TRAFFIC SIGN |  | G.2.1 BIỂN BÁO
98 |  | MAINLINE |  | TUYẾN CHÍNH
99 |  | CROSSING ROAD |  | ĐƯỜNG NGANG
100 |  | FRONTAGE ROAD |  | ĐƯỜNG GOM
| G.2.2 GUARD RAIL |  | G.2.2 HỘ LAN
101 |  | MAINLINE |  | TUYẾN CHÍNH
102 |  | CROSSING ROAD |  | ĐƯỜNG NGANG
103 |  | FRONTAGE ROAD |  | ĐƯỜNG GOM
| G.2.3 GUARD POST |  | G.2.3 CỌC TIÊU
104 |  | MAINLINE |  | TUYẾN CHÍNH
105 |  | CROSSING ROAD |  | ĐƯỜNG NGANG
106 |  | FRONTAGE ROAD |  | ĐƯỜNG GOM

## Version7_EditbyVachira (hidden)
DELIVERABLES OF PACKAGE A4 (As of 13 Oct 2012)_____Vachira (DDR)
I | DRAWINGS
S.N. | TITLE |  | DWG NO. | Team / Person | Progress | Draft | Check 1 | Check 2 | Final | Note
A. GENERAL
1 |  | DRAWING LIST (1/8) | PKGA4-GN-010 | Thuan | 75% | ✔ | ✔ |  |  | Translation
2 |  | DRAWING LIST (2/8) | PKGA4-GN-020 | Thuan | 75% | ✔ | ✔ |  |  | Translation
3 |  | DRAWING LIST (3/8) | PKGA4-GN-030 | Thuan | 75% | ✔ | ✔ |  |  | Translation
4 |  | DRAWING LIST (4/8) | PKGA4-GN-040 | Thuan | 75% | ✔ | ✔ |  |  | Translation
5 |  | DRAWING LIST (5/8) | PKGA4-GN-050 | Thuan | 75% | ✔ | ✔ |  |  | Translation
6 |  | DRAWING LIST (6/8) | PKGA4-GN-060 | Thuan | 75% | ✔ | ✔ |  |  | Translation
7 |  | DRAWING LIST (7/8) | PKGA4-GN-070 | Thuan | 75% | ✔ | ✔ |  |  | Translation
8 |  | DRAWING LIST (8/8) | PKGA4-GN-080 | Thuan | 75% | ✔ | ✔ |  |  | Translation
9 |  | LOCATION MAP | PKGA4-GN-090
10 |  | LEGEND | PKGA4-GN-100 | Thuan | 100% | ✔ | ✔
11 |  | ABBREVIATION AND SYMBOL | PKGA4-GN-110 | Thuan | 100% | ✔ | ✔
12 |  | GENERAL NOTES | PKGA4-GN-120 | Thuan | 100% | ✔ | ✔
13 |  | DETAIL OF GEOMETRIC DESIGN (1), THROUGHWAY | PKGA4-GN-130 | Thuan | 100% | ✔ | ✔
14 |  | DETAIL OF GEOMETRIC DESIGN (2), INTERCHANGE | PKGA4-GN-140 | Thuan | 100% | ✔ | ✔
B. ALIGNMENT LAYOUT AND SURVEY CONTROLS
15 |  | ALIGNMENT LAYOUT (1/5) | PKGA4-ML-AL-010 | Thuan | 90% | ✔ | ✔ |  |  | Imput derailed table (chau)
16 |  | ALIGNMENT LAYOUT (2/5) | PKGA4-ML-AL-020 | Thuan | 90% | ✔ | ✔ |  |  | Imput derailed table (chau)
17 |  | ALIGNMENT LAYOUT (3/5) | PKGA4-ML-AL-030 | Thuan | 90% | ✔ | ✔ |  |  | Imput derailed table (chau)
18 |  | ALIGNMENT LAYOUT (4/5) | PKGA4-ML-AL-040 | Thuan | 90% | ✔ | ✔ |  |  | Imput derailed table (chau)
19 |  | ALIGNMENT LAYOUT (5/5) | PKGA4-ML-AL-050 | Thuan | 90% | ✔ | ✔ |  |  | Imput derailed table (chau)
20 |  | TRAVERSE NETWORK OF SURVEY CONTROLS (1/5) | PKGA4-ML-AL-060 | Thuan | 90% | ✔ | ✔
21 |  | TRAVERSE NETWORK OF SURVEY CONTROLS (2/5) | PKGA4-ML-AL-070 | Thuan | 90% | ✔ | ✔
22 |  | TRAVERSE NETWORK OF SURVEY CONTROLS (3/5) | PKGA4-ML-AL-080 | Thuan | 90% | ✔ | ✔
23 |  | TRAVERSE NETWORK OF SURVEY CONTROLS (4/5) | PKGA4-ML-AL-090 | Thuan | 90% | ✔ | ✔
24 |  | TRAVERSE NETWORK OF SURVEY CONTROLS (5/5) | PKGA4-ML-AL-100 | Thuan | 90% | ✔ | ✔
C. TYPICAL CROSS SECTIONS
25 |  | TYPICAL CROSS SECTION ON NORMAL EMBANKMENT | PKGA4-ML-TC-010 | Thuan | 95% | ✔ | ✔
26 |  | TYPICAL CROSS SECTION ON SOIL EXCAVATION | PKGA4-ML-TC-020 | Thuan | 95% | ✔ | ✔
27 |  | TYPICAL CROSS SECTION ON ROCK EXCAVATION | PKGA4-ML-TC-030 | Thuan | 95% | ✔ | ✔
28 |  | TYPICAL CROSS SECTION A HAFT EXCAVATION AND EMBANKMENT; SUPERELEVATION | PKGA4-ML-TC-040 | Thuan | 95% | ✔ | ✔
29 |  | TYPICAL CROSS SECTION DEEP EXCAVATION WITH 6 LANES AND CLIMBING LANE | PKGA4-ML-TC-050 | Thuan | 95% | ✔ | ✔
30 |  | TYPCAL CROSS SECTION AT BRIDGE APPROACH | PKGA4-ML-TC-060 | Thuan | 95% | ✔ | ✔
31 |  | TYPCAL CROSS SECTION AT FLYOVER | PKGA4-ML-TC-070 | Thuan | 95% | ✔ | ✔
32 |  | TYPICAL CROSS SECTION DEEP EXCAVATION AND HIGH EMBANKMENT | PKGA4-ML-TC-080 | Thuan | 95% | ✔ | ✔
D. PLAN AND PROFILE
33 |  | PLAN AND PROFILE (STA.110+100 - STA.110+780) | PKGA4-ML-PP-010 | Thuan | 90% | ✔ | ✔ |  |  | Information, slope protection, waterway culvert
34 |  | PLAN AND PROFILE (STA.110+780 - STA.111+460) | PKGA4-ML-PP-020 | Thuan | 90% | ✔ | ✔ |  |  | Information, slope protection, waterway culvert
35 |  | PLAN AND PROFILE (STA.111+460 - STA.112+140) | PKGA4-ML-PP-030 | Thuan | 90% | ✔ | ✔ |  |  | Information, slope protection, waterway culvert
36 |  | PLAN AND PROFILE (STA.112+140 - STA.112+820) | PKGA4-ML-PP-040 | Thuan | 90% | ✔ | ✔ |  |  | Information, slope protection, waterway culvert
37 |  | PLAN AND PROFILE (STA.112+820 - STA.113+500) | PKGA4-ML-PP-050 | Thuan | 90% | ✔ | ✔ |  |  | Information, slope protection, waterway culvert
38 |  | PLAN AND PROFILE (STA.113+500 - STA.114+180) | PKGA4-ML-PP-060 | Thuan | 90% | ✔ | ✔ |  |  | Information, slope protection, waterway culvert
39 |  | PLAN AND PROFILE (STA.114+180 - STA.114+860) | PKGA4-ML-PP-070 | Thuan | 90% | ✔ | ✔ |  |  | Information, slope protection, waterway culvert
40 |  | PLAN AND PROFILE (STA.114+860 - STA.115+540) | PKGA4-ML-PP-080 | Thuan | 90% | ✔ | ✔ |  |  | Information, slope protection, waterway culvert
41 |  | PLAN AND PROFILE (STA.115+540 - STA.116+220) | PKGA4-ML-PP-090 | Thuan | 90% | ✔ | ✔ |  |  | Information, slope protection, waterway culvert
42 |  | PLAN AND PROFILE (STA.116+220 - STA.116+900) | PKGA4-ML-PP-100 | Thuan | 90% | ✔ | ✔ |  |  | Information, slope protection, waterway culvert
43 |  | PLAN AND PROFILE (STA.116+900 - STA.117+580) | PKGA4-ML-PP-110 | Thuan | 90% | ✔ | ✔ |  |  | Information, waterway culvert
44 |  | PLAN AND PROFILE (STA.117+580 - STA.118+260) | PKGA4-ML-PP-120 | Manh | 90% | ✔ | ✔ |  |  | Information, waterway culvert
45 |  | PLAN AND PROFILE (STA.118+260 - STA.118+940) | PKGA4-ML-PP-130 | Manh | 90% | ✔ | ✔ |  |  | Information, waterway culvert
46 |  | PLAN AND PROFILE (STA.118+940 - STA.119+620) | PKGA4-ML-PP-140 | Manh | 90% | ✔ | ✔ |  |  | Information, waterway culvert
47 |  | PLAN AND PROFILE (STA.119+620 - STA.120+300) | PKGA4-ML-PP-150 | Manh | 90% | ✔ | ✔ |  |  | Information, waterway culvert
48 |  | PLAN AND PROFILE (STA.120+300 - STA.120+980) | PKGA4-ML-PP-160 | Manh | 90% | ✔ | ✔ |  |  | Information, waterway culvert
49 |  | PLAN AND PROFILE (STA.120+980 - STA.121+660) | PKGA4-ML-PP-170 | Manh | 90% | ✔ | ✔ |  |  | Information, waterway culvert
50 |  | PLAN AND PROFILE (STA.121+660 - STA.122+340) | PKGA4-ML-PP-180 | Manh | 90% | ✔ | ✔ |  |  | Information, waterway culvert
51 |  | PLAN AND PROFILE (STA.122+340 - STA.123+020) | PKGA4-ML-PP-190 | Manh | 90% | ✔ | ✔ |  |  | Information, waterway culvert
52 |  | PLAN AND PROFILE (STA.123+020 - STA.123+700) | PKGA4-ML-PP-200 | Manh | 90% | ✔ | ✔ |  |  | Information, waterway culvert
53 |  | PLAN AND PROFILE (STA.123+700 - STA.124+380) | PKGA4-ML-PP-210 | Manh | 90% | ✔ | ✔ |  |  | Information, waterway culvert
54 |  | PLAN AND PROFILE (STA.124+380 - STA.124+700) | PKGA4-ML-PP-220 | Manh | 90% | ✔ | ✔ |  |  | Information, waterway culvert
E. BINH SON INTERCHANGE
E.1 ALIGNMENT LAYOUT AND SURVEY CONTROLS
55 |  | LAYOUT AND KEYPLAN - BINH SON IC | PKGA4-IC1-AL-010 | Dat | 0%
56 |  | ALIGNMENT LAYOUT - BINH SON IC (1/4) | PKGA4-IC1-AL-020 | Dat | 100% | ✔ | ✔ |  |  |  | (1:4,000)
57 |  | ALIGNMENT LAYOUT - BINH SON IC (2/4) | PKGA4-IC1-AL-030 | Dat | 100% | ✔ | ✔ |  |  |  | (1:4,000)
58 |  | ALIGNMENT LAYOUT - BINH SON IC (3/4) | PKGA4-IC1-AL-040 | Dat | 100% | ✔ | ✔ |  |  |  | (1:4,000)
59 |  | ALIGNMENT LAYOUT - BINH SON IC (4/4) | PKGA4-IC1-AL-050 | Dat | 100% | ✔ | ✔ |  |  |  | (1:4,000)
E.2 TYPICAL CROSS SECTIONS
60 |  | KEY PLAN OF SECTION ARRANGEMENT - BINH SON IC | PKGA4-IC1-TC-010 | Ngoc | 0%
61 |  | TYPICAL CROSS SECTIONS OF RAMPS -BINH SON IC (1/5) | PKGA4-IC1-TC-020 | Ngoc | 100% | ✔ | ✔ |  |  |  | As Shown
62 |  | TYPICAL CROSS SECTIONS OF RAMPS -BINH SON IC (2/5) | PKGA4-IC1-TC-030 | Ngoc | 100% | ✔ | ✔ |  |  |  | As Shown
63 |  | TYPICAL CROSS SECTIONS OF RAMPS -BINH SON IC (3/5) | PKGA4-IC1-TC-040 | Ngoc | 100% | ✔ | ✔ |  |  |  | As Shown
64 |  | TYPICAL CROSS SECTIONS OF RAMPS -BINH SON IC (4/5) | PKGA4-IC1-TC-050 | Ngoc | 100% | ✔ | ✔ |  |  |  | As Shown
65 |  | TYPICAL CROSS SECTIONS OF RAMPS -BINH SON IC (5/5) | PKGA4-IC1-TC-060 | Ngoc | 100% | ✔ | ✔
66 |  | TYPICAL CROSS SECTION AT TOLL PLAZA - BINH SON IC | PKGA4-IC1-TC-070 | Ngoc | 100% | ✔ | ✔ |  |  |  | As Shown
67 |  | DETAILS OF PAVEMENT STRUCTURE - BINH SON IC | PKGA4-IC1-TC-080 | Ngoc | 0% | [5 empty] | As Shown
E.3 PLAN AND PROFILE
68 |  | PLAN OF BINH SON IC (1/6) | PKGA4-IC1-PP-010 | Dat | 100% | ✔ | ✔ |  |  |  | (1:2,000)
69 |  | PLAN OF BINH SON IC (2/6) | PKGA4-IC1-PP-020 | Dat | 100% | ✔ | ✔ |  |  |  | (1:2,000)
70 |  | PLAN OF BINH SON IC (3/6) | PKGA4-IC1-PP-030 | Dat | 100% | ✔ | ✔ |  |  |  | (1:2,000)
71 |  | PLAN OF BINH SON IC (4/6) | PKGA4-IC1-PP-040 | Dat | 100% | ✔ | ✔ |  |  |  | (1:2,000)
72 |  | PLAN OF BINH SON IC (5/6) | PKGA4-IC1-PP-050 | Dat | 100% | ✔ | ✔ |  |  |  | (1:2,000)
73 |  | PLAN OF BINH SON IC (6/6) | PKGA4-IC1-PP-060 | Dat | 100% | ✔ | ✔ |  |  |  | (1:2,000)
74 |  | PROFILE OF EXPRESSWAY AT BINH SON IC (1/4) | PKGA4-IC1-PP-070 | Ngoc | 100% | ✔ | ✔ |  |  |  | (H:V=2000:400)
75 |  | PROFILE OF EXPRESSWAY AT BINH SON IC (2/4) | PKGA4-IC1-PP-080 | Ngoc | 100% | ✔ | ✔ |  |  |  | (H:V=2000:400)
76 |  | PROFILE OF EXPRESSWAY AT BINH SON IC (3/4) | PKGA4-IC1-PP-090 | Ngoc | 100% | ✔ | ✔
77 |  | PROFILE OF EXPRESSWAY AT BINH SON IC (4/4) | PKGA4-IC1-PP-100 | Ngoc | 100% | ✔ | ✔
78 |  | PROFILE OF PR622 (1/4) | PKGA4-IC1-PP-110 | Ngoc | 100% | ✔ | ✔ |  |  |  | (H:V=2000:400)
79 |  | PROFILE OF PR622 (2/4) | PKGA4-IC1-PP-120 | Ngoc | 100% | ✔ | ✔ |  |  |  | (H:V=2000:400)
80 |  | PROFILE OF PR622 (3/4) | PKGA4-IC1-PP-130 | Ngoc | 100% | ✔ | ✔
81 |  | PROFILE OF PR622 (4/4) | PKGA4-IC1-PP-140 | Ngoc | 100% | ✔ | ✔
82 |  | PROFILE OF RAMP A - BINH SON IC | PKGA4-IC1-PP-150 | Ngoc | 100% | ✔ | ✔ |  |  |  | (H:V=2000:400)
83 |  | PROFILE OF RAMP A1 - BINH SON IC (1/4) | PKGA4-IC1-PP-160 | Ngoc | 100% | ✔ | ✔ |  |  |  | (H:V=2000:400)
84 |  | PROFILE OF RAMP A1 - BINH SON IC (2/4) | PKGA4-IC1-PP-170 | Ngoc | 100% | ✔ | ✔ |  |  |  | (H:V=2000:400)
85 |  | PROFILE OF RAMP A1 - BINH SON IC (3/4) | PKGA4-IC1-PP-180 | Ngoc | 100% | ✔ | ✔
86 |  | PROFILE OF RAMP A1 - BINH SON IC (4/4) | PKGA4-IC1-PP-190 | Ngoc | 100% | ✔ | ✔
87 |  | PROFILE OF RAMP A1T & A1P - BINH SON IC | PKGA4-IC1-PP-200 | Ngoc | 100% | ✔ | ✔
88 |  | PROFILE OF RAMP B - BINH SON IC | PKGA4-IC1-PP-210 | Ngoc | 100% | ✔ | ✔ |  |  |  | (H:V=2000:400)
89 |  | PROFILE OF RAMP C - BINH SON IC | PKGA4-IC1-PP-220 | Ngoc | 100% | ✔ | ✔ |  |  |  | (H:V=2000:400)
90 |  | PROFILE OF RAMP D - BINH SON IC | PKGA4-IC1-PP-230 | Ngoc | 100% | ✔ | ✔ |  |  |  | (H:V=2000:400)
F. QUANG NGAI NORTH INTERCHANGE
F.1 ALIGNMENT LAYOUT AND SURVEY CONTROLS
91 |  | LAYOUT AND KEYPLAN - QUANG NGAI NORTH IC | PKGA4-IC2-AL-010 | Dat | 0%
92 |  | ALIGNMNET LAYOUT - QUANG NGAI NORTH IC (1/4) | PKGA4-IC2-AL-020 | Dat | 100% | ✔ | ✔
93 |  | ALIGNMNET LAYOUT - QUANG NGAI NORTH IC (2/4) | PKGA4-IC2-AL-030 | Dat | 100% | ✔ | ✔
94 |  | ALIGNMNET LAYOUT - QUANG NGAI NORTH IC (3/4) | PKGA4-IC2-AL-040 | Dat | 100% | ✔ | ✔
95 |  | ALIGNMNET LAYOUT - QUANG NGAI NORTH IC (4/4) | PKGA4-IC2-AL-050 | Dat | 100% | ✔ | ✔
F.2 TYPICAL CROSS SECTIONS
96 |  | KEY PLAN OF SECTION ARRANGEMENT - QUANG NGAI NORTH IC | PKGA4-IC2-TC-010 | Ngoc | 0%
97 |  | TYPICAL CROSS SECTIONS OF RAMPS - QUANG NGAI NORTH IC (1/4) | PKGA4-IC2-TC-020 | Ngoc | 100% | ✔ | ✔
98 |  | TYPICAL CROSS SECTIONS OF RAMPS - QUANG NGAI NORTH IC (2/4) | PKGA4-IC2-TC-030 | Ngoc | 100% | ✔ | ✔
99 |  | TYPICAL CROSS SECTIONS OF RAMPS - QUANG NGAI NORTH IC (3/4) | PKGA4-IC2-TC-040 | Ngoc | 100% | ✔ | ✔
100 |  | TYPICAL CROSS SECTIONS OF RAMPS - QUANG NGAI NORTH IC (4/4) | PKGA4-IC2-TC-050 | Ngoc | 100% | ✔ | ✔
101 |  | TYPICAL CROSS SECTION AT TOLL PLAZA - QUANG NGAI NORTH IC | PKGA4-IC2-TC-060 | Ngoc | 100% | ✔ | ✔
102 |  | DETAILS OF PAVEMENT STRUCTURE - QUANG NGAI IC | PKGA4-IC2-TC-070 | Ngoc | 0%
103 |  | DETAILS OF CONCRETE PAVEMENT AT TOLL PLAZA - QUANG NGAI IC | PKGA4-IC2-TC-080 | Ngoc | 0%
F.3 PLAN AND PROFILE
104 |  | PLAN OF QUANG NGAI NORTH IC (1/6) | PKGA4-IC2-PP-010 | Dat | 100% | ✔ | ✔
105 |  | PLAN OF QUANG NGAI NORTH IC (2/6) | PKGA4-IC2-PP-020 | Dat | 100% | ✔ | ✔
106 |  | PLAN OF QUANG NGAI NORTH IC (3/6) | PKGA4-IC2-PP-030 | Dat | 100% | ✔ | ✔
107 |  | PLAN OF QUANG NGAI NORTH IC (4/6) | PKGA4-IC2-PP-040 | Dat | 100% | ✔ | ✔
108 |  | PLAN OF QUANG NGAI NORTH IC (5/6) | PKGA4-IC2-PP-050 | Dat | 100% | ✔ | ✔
109 |  | PLAN OF QUANG NGAI NORTH IC (6/6) | PKGA4-IC2-PP-060 | Dat | 100% | ✔ | ✔
110 |  | PROFILE OF EXPRESSWAY - QUANG NGAI NORTH IC (1/4) | PKGA4-IC2-PP-070 | Ngoc | 100% | ✔ | ✔
111 |  | PROFILE OF EXPRESSWAY - QUANG NGAI NORTH IC (2/4) | PKGA4-IC2-PP-080 | Ngoc | 100% | ✔ | ✔
112 |  | PROFILE OF EXPRESSWAY - QUANG NGAI NORTH IC (3/4) | PKGA4-IC2-PP-090 | Ngoc | 100% | ✔ | ✔
113 |  | PROFILE OF EXPRESSWAY - QUANG NGAI NORTH IC (4/4) | PKGA4-IC2-PP-100 | Ngoc | 100% | ✔ | ✔
114 |  | PROFILE OF PR 623B - QUANG NGAI NORTH IC (1/2) | PKGA4-IC2-PP-110 | Ngoc | 100% | ✔ | ✔
115 |  | PROFILE OF PR 623B - QUANG NGAI NORTH IC (2/2) | PKGA4-IC2-PP-120 | Ngoc | 100% | ✔ | ✔
116 |  | PROFILE OF RAMP A - QUANG NGAI NORTH IC | PKGA4-IC2-PP-130 | Ngoc | 100% | ✔ | ✔
117 |  | PROFILE OF RAMP B - QUANG NGAI NORTH IC | PKGA4-IC2-PP-140 | Ngoc | 100% | ✔ | ✔
118 |  | PROFILE OF RAMP C1 - QUANG NGAI NORTH IC (1/3) | PKGA4-IC2-PP-150 | Ngoc | 100% | ✔ | ✔
119 |  | PROFILE OF RAMP C1 - QUANG NGAI NORTH IC (1/3) | PKGA4-IC2-PP-160 | Ngoc | 100% | ✔ | ✔
120 |  | PROFILE OF RAMP C1 - QUANG NGAI NORTH IC (1/3) | PKGA4-IC2-PP-170 | Ngoc | 100% | ✔ | ✔
121 |  | PROFILE OF RAMP C1T & C1P - QUANG NGAI NORTH IC | PKGA4-IC2-PP-180 | Ngoc | 100% | ✔ | ✔
122 |  | PROFILE OF RAMP C - QUANG NGAI NORTH IC | PKGA4-IC2-PP-190 | Ngoc | 100% | ✔ | ✔
123 |  | PROFILE OF RAMP D - QUANG NGAI NORTH IC | PKGA4-IC2-PP-200 | Ngoc | 100% | ✔ | ✔
G. PARKING AREA
G.1 TYPICAL CROSS SECTIONS
124 |  | TYPICAL CROSS SECTIONS OF PARKING AREA (1/4) | PKGA4-PA-TC-010 | Manh | 95% | ✔ | ✔ |  |  | Nose, Ramp terminal, center
125 |  | TYPICAL CROSS SECTIONS OF PARKING AREA (2/4) | PKGA4-PA-TC-020 | Manh | 95% | ✔ | ✔ |  |  | Nose, Ramp terminal, center
126 |  | TYPICAL CROSS SECTIONS OF PARKING AREA (3/4) | PKGA4-PA-TC-030 | Manh | 95% | ✔ | ✔ |  |  | Nose, Ramp terminal, center
127 |  | TYPICAL CROSS SECTIONS OF PARKING AREA (4/4) | PKGA4-PA-TC-040 | Manh | 95% | ✔ | ✔ |  |  | Nose, Ramp terminal, center
G.2 PLAN AND PROFILE
128 |  | GENERAL LAYOUT OF PARKING AREA | PKGA4-PA-PP-010 | Manh | 95% | ✔ | ✔
129 |  | PLAN AND PROFILE OF WEST RAMP OF PARKING AREA (1/3) | PKGA4-PA-PP-020 | Manh | 95% | ✔ | ✔
130 |  | PLAN AND PROFILE OF WEST RAMP OF PARKING AREA (2/3) | PKGA4-PA-PP-030 | Manh | 95% | ✔ | ✔
131 |  | PLAN AND PROFILE OF WEST RAMP OF PARKING AREA (3/3) | PKGA4-PA-PP-040 | Manh | 95% | ✔ | ✔
132 |  | PLAN AND PROFILE OF EAST RAMP OF PARKING AREA (1/3) | PKGA4-PA-PP-050 | Manh | 95% | ✔ | ✔
133 |  | PLAN AND PROFILE OF EAST RAMP OF PARKING AREA (2/3) | PKGA4-PA-PP-060 | Manh | 95% | ✔ | ✔
134 |  | PLAN AND PROFILE OF EAST RAMP OF PARKING AREA (3/3) | PKGA4-PA-PP-070 | Manh | 95% | ✔ | ✔
135 |  | PLAN AND PROFILE OF ACCESS ROAD TO PARKING AREA (WEST SIDE) | PKGA4-PA-PP-080 | Manh | 95% | ✔ | ✔
136 |  | PLAN AND PROFILE OF ACCESS ROAD TO PARKING AREA (EAST SIDE) | PKGA4-PA-PP-090 | Manh | 95% | ✔ | ✔
H. CROSSING ROADS
H.1 TYPICAL CROSS SECTIONS
137 |  | SCHEDULE OF CROSSING ROADS | PKGA4-CR-TC-010 | Manh | 0%
138 |  | TYPICAL CROSS SECTION AND PAVEMENT DETAILS OF CROSSING ROADS (1/4) | PKGA4-CR-TC-020 | Manh | 95% | ✔ | ✔ |  |  | Type AH, A, B, C based on standard 315
139 |  | TYPICAL CROSS SECTION AND PAVEMENT DETAILS OF CROSSING ROADS (2/4) | PKGA4-CR-TC-030 | Manh | 95% | ✔ | ✔ |  |  | Type AH, A, B, C based on standard 316
140 |  | TYPICAL CROSS SECTION AND PAVEMENT DETAILS OF CROSSING ROADS (3/4) | PKGA4-CR-TC-040 | Manh | 95% | ✔ | ✔ |  |  | Type AH, A, B, C based on standard 317
141 |  | TYPICAL CROSS SECTION AND PAVEMENT DETAILS OF CROSSING ROADS (4/4) | PKGA4-CR-TC-050 | Manh | 95% | ✔ | ✔ |  |  | Type AH, A, B, C based on standard 318
H.2 PLAN AND PROFILE
142 |  | PLAN AND PROFILE OF CROSSING ROAD AT KM111+720, FLYOVER | PKGA4-CR-PP-010 | Thuan | 90% | ✔ | ✔ |  |  | Information
143 |  | PLAN AND PROFILE OF CROSSING ROAD AT KM114+407, UNDERPASS | PKGA4-CR-PP-020 | Thuan | 90% | ✔ | ✔ |  |  | Information
144 |  | PLAN AND PROFILE OF CROSSING ROAD AT KM115+983 (UNDER RIVER BRIDGE) | PKGA4-CR-PP-030 | Thuan | 90% | ✔ | ✔ |  |  | Information
145 |  | PLAN AND PROFILE OF CROSSING ROAD AT KM116+570, FLYOVER | PKGA4-CR-PP-040 | Thuan | 90% | ✔ | ✔ |  |  | Information
146 |  | PLAN AND PROFILE OF CROSSING ROAD AT KM117+000, UNDERPASS | PKGA4-CR-PP-050 | Thuan | 90% | ✔ | ✔ |  |  | Information
147 |  | PLAN AND PROFILE OF CROSSING ROAD AT KM117+900, UNDERPASS | PKGA4-CR-PP-060 | Manh | 90% | ✔ | ✔ |  |  | Information
148 |  | PLAN AND PROFILE OF CROSSNG ROAD AT KM118+050 (UNDER CANAL BRIDGE) | PKGA4-CR-PP-070 | Manh | 90% | ✔ | ✔ |  |  | Information
149 |  | PLAN AND PROFILE OF CROSSING ROAD AT KM119+170, FLYOVER | PKGA4-CR-PP-080 | Manh | 90% | ✔ | ✔ |  |  | Information
150 |  | PLAN AND PROFILE OF CROSSING ROAD AT KM120+020, UNDERPASS | PKGA4-CR-PP-090 | Manh | 90% | ✔ | ✔ |  |  | Information
151 |  | PLAN AND PROFILE OF CROSSING ROAD AT KM120+530, UNDERPASS | PKGA4-CR-PP-100 | Manh | 90% | ✔ | ✔ |  |  | Information
152 |  | PLAN AND PROFILE OF CROSSING ROAD AT KM121+485, UNDERPASS | PKGA4-CR-PP-110 | Manh | 90% | ✔ | ✔ |  |  | Information
153 |  | PLAN AND PROFILE OF CROSSING ROAD AT KM122+260, UNDERPASS | PKGA4-CR-PP-120 | Manh | 90% | ✔ | ✔ |  |  | Information
I. FRONTAGE ROADS
I.1 TYPICAL CROSS SECTIONS
154 |  | SCHEDULE OF FRONTAGE ROADS | PKGA4-FR-TC-010 | Manh | 0%
155 |  | TYPICAL CROSS SECTION AND PAVEMENT DETAILS OF FRONTAGE ROADS | PKGA4-FR-TC-020 | DRD | 0% |  |  |  |  | Type AH, A, B, C based on standard 315
I.2 PLAN AND PROFILE
156 |  | PLAN AND PROFILE OF FRONTAGE ROAD AT KM110+100 (LEFT) | PKGA4-FR-PP-020 | Thuan | 75% | ✔ | ✔ |  |  | Information, presentation
157 |  | PLAN AND PROFILE OF FRONTAGE ROAD AT KM110+100 (RIGHT) | PKGA4-FR-PP-030 | Thuan | 75% | ✔ | ✔ |  |  | Information, presentation
158 |  | PLAN AND PROFILE OF FRONTAGE ROAD AT KM114+400 (LEFT) | PKGA4-FR-PP-040 | Thuan | 75% | ✔ | ✔ |  |  | Information, presentation
159 |  | PLAN AND PROFILE OF FRONTAGE ROAD AT KM118+060 (LEFT) | PKGA4-FR-PP-050 | Manh | 95% | ✔ | ✔ |  |  | Information, presentation
160 |  | PLAN AND PROFILE OF FRONTAGE ROAD AT KM118+060 (RIGHT) | PKGA4-FR-PP-060 | Manh | 95% | ✔ | ✔ |  |  | Information, presentation
161 |  | PLAN AND PROFILE OF FRONTAGE ROAD AT KM119+520 (RIGHT) | PKGA4-FR-PP-070 | Manh | 95% | ✔ | ✔ |  |  | Information, presentation
162 |  | PLAN AND PROFILE OF FRONTAGE ROAD AT KM120+000 (LEFT) | PKGA4-FR-PP-080 | Manh | 95% | ✔ | ✔ |  |  | Information, presentation
J. DRAINAGE WORKS
J.1 THROUGHWAY (MAIN LINE)
J.1.1 DRAINAGE PLAN - THROUGHWAY (MAIN LINE)
163 |  | SCHEDULE OF OPEN DITCHES | PKGA4-DR-ML-PL-010 | DDR
164 |  | SCHEDULE OF SHOULDER DITCHES | PKGA4-DR-ML-PL-020 | DDR
165 |  | SCHEDULE OF MEDIAN DITCHES | PKGA4-DR-ML-PL-030 | DDR
166 |  | DRAINAGE PLAN (STA. 110+100 - STA. 110+439 | PKGA4-DR-ML-PL-040 | Hung | 90% | ✔ | ✔
167 |  | DRAINAGE PLAN (STA. 110+439 - STA. 110+788 | PKGA4-DR-ML-PL-050 | Hung | 90% | ✔ | ✔
168 |  | DRAINAGE PLAN (STA. 110+788 - STA. 111+137 | PKGA4-DR-ML-PL-060 | Hung | 90% | ✔ | ✔
169 |  | DRAINAGE PLAN (STA. 111+137 - STA. 111+486 | PKGA4-DR-ML-PL-070 | Hung | 90% | ✔ | ✔
170 |  | DRAINAGE PLAN (STA. 111+486 - STA. 111+835 | PKGA4-DR-ML-PL-080 | Hung | 90% | ✔ | ✔
171 |  | DRAINAGE PLAN (STA. 111+835 - STA. 112+184 | PKGA4-DR-ML-PL-090 | Hung | 90% | ✔ | ✔
172 |  | DRAINAGE PLAN (STA. 112+184 - STA. 112+533 | PKGA4-DR-ML-PL-100 | Hung | 90% | ✔ | ✔
173 |  | DRAINAGE PLAN (STA. 112+533 - STA. 112+882 | PKGA4-DR-ML-PL-110 | Hung | 90% | ✔ | ✔
174 |  | DRAINAGE PLAN (STA. 112+882 - STA. 113+231 | PKGA4-DR-ML-PL-120 | Hung | 90% | ✔ | ✔
175 |  | DRAINAGE PLAN (STA. 113+231 - STA. 113+580 | PKGA4-DR-ML-PL-130 | Hung | 90% | ✔ | ✔
176 |  | DRAINAGE PLAN (STA. 113+580 - STA. 113+929 | PKGA4-DR-ML-PL-140 | Hung | 90% | ✔ | ✔
177 |  | DRAINAGE PLAN (STA. 113+929 - STA. 114+278 | PKGA4-DR-ML-PL-150 | Hung | 90% | ✔ | ✔
178 |  | DRAINAGE PLAN (STA. 114+278 - STA. 114+627 | PKGA4-DR-ML-PL-160 | Hung | 90% | ✔ | ✔
179 |  | DRAINAGE PLAN (STA. 114+627 - STA. 114+976 | PKGA4-DR-ML-PL-170 | Hung | 90% | ✔ | ✔
180 |  | DRAINAGE PLAN (STA. 114+976 - STA. 115+325 | PKGA4-DR-ML-PL-180 | Hung | 90% | ✔ | ✔
181 |  | DRAINAGE PLAN (STA. 115+325 - STA. 115+674 | PKGA4-DR-ML-PL-190 | Hung | 90% | ✔ | ✔
182 |  | DRAINAGE PLAN (STA. 115+674 - STA. 116+023 | PKGA4-DR-ML-PL-200 | Hung | 90% | ✔ | ✔
183 |  | DRAINAGE PLAN (STA. 116+023 - STA. 116+372 | PKGA4-DR-ML-PL-210 | Hung | 90% | ✔ | ✔
184 |  | DRAINAGE PLAN (STA. 116+372 - STA. 116+721 | PKGA4-DR-ML-PL-220 | Hung | 90% | ✔ | ✔
185 |  | DRAINAGE PLAN (STA. 116+721 - STA. 117+070 | PKGA4-DR-ML-PL-230 | Hung | 90% | ✔ | ✔
186 |  | DRAINAGE PLAN (STA. 117+070 - STA. 117+419 | PKGA4-DR-ML-PL-240 | Hung | 90% | ✔ | ✔
187 |  | DRAINAGE PLAN (STA. 117+419 - STA. 117+768 | PKGA4-DR-ML-PL-250 | Hung | 90% | ✔ | ✔
188 |  | DRAINAGE PLAN (STA. 117+768 - STA. 118+117 | PKGA4-DR-ML-PL-260 | Hung | 90% | ✔ | ✔
189 |  | DRAINAGE PLAN (STA. 118+117 - STA. 118+466 | PKGA4-DR-ML-PL-270 | Hung | 90% | ✔ | ✔
190 |  | DRAINAGE PLAN (STA. 118+466 - STA. 118+815 | PKGA4-DR-ML-PL-280 | Hung | 90% | ✔ | ✔
191 |  | DRAINAGE PLAN (STA. 118+815 - STA. 119+164 | PKGA4-DR-ML-PL-290 | Hung | 90% | ✔ | ✔
192 |  | DRAINAGE PLAN (STA. 119+164 - STA. 119+513 | PKGA4-DR-ML-PL-300 | Hung | 90% | ✔ | ✔
193 |  | DRAINAGE PLAN (STA. 119+513 - STA. 119+862 | PKGA4-DR-ML-PL-310 | Hung | 90% | ✔ | ✔
194 |  | DRAINAGE PLAN (STA. 119+862 - STA. 120+211 | PKGA4-DR-ML-PL-320 | Hung | 90% | ✔ | ✔
195 |  | DRAINAGE PLAN (STA. 120+211 - STA. 120+560 | PKGA4-DR-ML-PL-330 | Hung | 90% | ✔ | ✔
196 |  | DRAINAGE PLAN (STA. 120+560 - STA. 120+909 | PKGA4-DR-ML-PL-340 | Hung | 90% | ✔ | ✔
197 |  | DRAINAGE PLAN (STA. 120+909 - STA. 121+258 | PKGA4-DR-ML-PL-350 | Hung | 90% | ✔ | ✔
198 |  | DRAINAGE PLAN (STA. 121+258 - STA. 121+607 | PKGA4-DR-ML-PL-360 | Hung | 90% | ✔ | ✔
199 |  | DRAINAGE PLAN (STA. 121+607 - STA. 121+956 | PKGA4-DR-ML-PL-370 | Hung | 90% | ✔ | ✔
200 |  | DRAINAGE PLAN (STA. 121+956 - STA. 122+305 | PKGA4-DR-ML-PL-380 | Hung | 90% | ✔ | ✔
201 |  | DRAINAGE PLAN (STA. 122+305 - STA. 122+654 | PKGA4-DR-ML-PL-390 | Hung | 90% | ✔ | ✔
202 |  | DRAINAGE PLAN (STA. 122+654 - STA. 123+003 | PKGA4-DR-ML-PL-400 | Hung | 90% | ✔ | ✔
203 |  | DRAINAGE PLAN (STA. 123+003 - STA. 123+352 | PKGA4-DR-ML-PL-410 | Hung | 90% | ✔ | ✔
204 |  | DRAINAGE PLAN (STA. 123+352 - STA. 123+701 | PKGA4-DR-ML-PL-420 | Hung | 90% | ✔ | ✔
205 |  | DRAINAGE PLAN (STA. 123+701 - STA. 124+050 | PKGA4-DR-ML-PL-430 | Hung | 90% | ✔ | ✔
206 |  | DRAINAGE PLAN (STA. 124+050 - STA. 124+399 | PKGA4-DR-ML-PL-440 | Hung | 90% | ✔ | ✔
207 |  | DRAINAGE PLAN (STA. 124+399 - STA. 124+700 | PKGA4-DR-ML-PL-450 | Hung | 90% | ✔ | ✔
J.1.2 LONGITUDINAL PIPE - THROUGHWAY (MAIN LINE)
208 |  | SCHEDULE OF LONGITUDINAL PIPES | PKGA4-DR-ML-LN-010 | DDR | 0%
209 |  | PLAN & PROFILE OF LONGITUDINAL PIPE (UNDER MEDIAN) (1/6) | PKGA4-DR-ML-LN-020 | Hoa/Hung | 75% | ✔ |  |  |  | Mr. Hoa
210 |  | PLAN & PROFILE OF LONGITUDINAL PIPE (UNDER MEDIAN) (2/6) | PKGA4-DR-ML-LN-030 | Hoa/Hung | 75% | ✔ |  |  |  | Mr. Hoa
211 |  | PLAN & PROFILE OF LONGITUDINAL PIPE (UNDER MEDIAN) (3/6) | PKGA4-DR-ML-LN-040 | Hoa/Hung | 75% | ✔ |  |  |  | Mr. Hoa
212 |  | PLAN & PROFILE OF LONGITUDINAL PIPE (UNDER MEDIAN) (4/6) | PKGA4-DR-ML-LN-050 | Hoa/Hung | 75% | ✔ |  |  |  | Mr. Hoa
213 |  | PLAN & PROFILE OF LONGITUDINAL PIPE (UNDER MEDIAN) (5/6) | PKGA4-DR-ML-LN-060 | Hoa/Hung | 75% | ✔ |  |  |  | Mr. Hoa
214 |  | PLAN & PROFILE OF LONGITUDINAL PIPE (UNDER MEDIAN) (6/6) | PKGA4-DR-ML-LN-070 | Hoa/Hung | 75% | ✔ |  |  |  | Mr. Hoa
J.1.3 BOX CULVERT - THROUGHWAY (MAIN LINE)
215 |  | SCHEDULE OF BOX CULVERTS | PKGA4-DR-ML-BC-010 | DDR | 0%
216 |  | PLAN LAYOUT OF BOX CULVERT , KM110+140; KM110+253 | PKGA4-DR-ML-BC-020 | Son | 90% | ✔ | ✔
217 |  | GENERAL VIEW OF BOX CULVERT 1-(2.0x2.0), KM110+140 (1/2) | PKGA4-DR-ML-BC-030 | Son | 90% | ✔ | ✔
218 |  | GENERAL VIEW OF BOX CULVERT 1-(2.0x2.0), KM110+140 (2/2) | PKGA4-DR-ML-BC-040 | Son | 90% | ✔ | ✔
219 |  | GENERAL VIEW OF BOX CULVERT 2-(1.5x1.5), KM110+253 (1/2) | PKGA4-DR-ML-BC-050 | Son | 90% | ✔ | ✔
220 |  | GENERAL VIEW OF BOX CULVERT 2-(1.5x1.5), KM110+253 (2/2) | PKGA4-DR-ML-BC-060 | Son | 90% | ✔ | ✔
221 |  | PLAN LAYOUT OF BOX CULVERT 1-(2.5x2.5), KM110+677 | PKGA4-DR-ML-BC-070 | Son | 90% | ✔ | ✔
222 |  | GENERAL VIEW OF BOX CULVERT 1-(2.5x2.5), KM110+677 (1/2) | PKGA4-DR-ML-BC-080 | Son | 90% | ✔ | ✔
223 |  | GENERAL VIEW OF BOX CULVERT 1-(2.5x2.5), KM110+677 (2/2) | PKGA4-DR-ML-BC-090 | Son | 90% | ✔ | ✔
224 |  | PLAN LAYOUT OF BOX CULVERT 1-(3.0x3.0), KM110+890 | PKGA4-DR-ML-BC-100 | Son | 90% | ✔ | ✔
225 |  | GENERAL VIEW OF BOX CULVERT 1-(3.0x3.0), KM110+890 (1/2) | PKGA4-DR-ML-BC-110 | Son | 90% | ✔ | ✔
226 |  | GENERAL VIEW OF BOX CULVERT 1-(3.0x3.0), KM110+890 (2/2) | PKGA4-DR-ML-BC-120 | Son | 90% | ✔ | ✔
227 |  | PLAN LAYOUT OF BOX CULVERT 1-(2.0x2.0), KM113+152 | PKGA4-DR-ML-BC-130 | Son | 90% | ✔ | ✔
228 |  | GENERAL VIEW OF BOX CULVERT 1-(2.0x2.0), KM113+152 (1/2) | PKGA4-DR-ML-BC-140 | Son | 90% | ✔ | ✔
229 |  | GENERAL VIEW OF BOX CULVERT 1-(2.0x2.0), KM113+152 (2/2) | PKGA4-DR-ML-BC-150 | Son | 90% | ✔ | ✔
230 |  | PLAN LAYOUT OF BOX CULVERT 1-(2.0x2.0), KM113+860 | PKGA4-DR-ML-BC-160 | Son | 90% | ✔ | ✔
231 |  | GENERAL VIEW OF BOX CULVERT 1-(2.0x2.0), KM113+860 (1/2) | PKGA4-DR-ML-BC-170 | Son | 90% | ✔ | ✔
232 |  | GENERAL VIEW OF BOX CULVERT 1-(2.0x2.0), KM113+860 (2/2) | PKGA4-DR-ML-BC-180 | Son | 90% | ✔ | ✔
233 |  | PLAN LAYOUT OF BOX CULVERT 2-(3.0x3.0), KM116+220 | PKGA4-DR-ML-BC-190 | Son | 90% | ✔ | ✔
234 |  | GENERAL VIEW OF BOX CULVERT 2-(3.0x3.0), KM116+220 (1/2) | PKGA4-DR-ML-BC-200 | Son | 90% | ✔ | ✔
235 |  | GENERAL VIEW OF BOX CULVERT 2-(3.0x3.0), KM116+220 (2/2) | PKGA4-DR-ML-BC-210 | Son | 90% | ✔ | ✔
236 |  | PLAN LAYOUT OF BOX CULVERT 3-(3.0x3.0), KM118+919 | PKGA4-DR-ML-BC-220 | Son | 90% | ✔ | ✔
237 |  | GENERAL VIEW OF BOX CULVERT 3-(3.0x3.0), KM118+919 (1/2) | PKGA4-DR-ML-BC-230 | Son | 90% | ✔ | ✔
238 |  | GENERAL VIEW OF BOX CULVERT 3-(3.0x3.0), KM118+919 (2/2) | PKGA4-DR-ML-BC-240 | Son | 90% | ✔ | ✔
239 |  | PLAN LAYOUT OF BOX CULVERT, KM119+140; 119+160.66 (OFF: 56.46M L); 119+197; 0+313.39 (PR622C) | PKGA4-DR-ML-BC-250 | Son | 90% | ✔ | ✔
240 |  | GENERAL VIEW OF BOX CULVERT 1-(2.0x1.5), KM119+140 (1/2) | PKGA4-DR-ML-BC-260 | Son | 90% | ✔ | ✔
241 |  | GENERAL VIEW OF BOX CULVERT 1-(2.0x1.5), KM119+140 (2/2) | PKGA4-DR-ML-BC-270 | Son | 90% | ✔ | ✔
242 |  | GENERAL VIEW OF BOX CULVERT 3-(3.0x2.0), KM119+160.66 (OFF: 56.46M L) (1/2) | PKGA4-DR-ML-BC-280 | Son | 90% | ✔ | ✔
243 |  | GENERAL VIEW OF BOX CULVERT 3-(3.0x2.0), KM119+160.66 (OFF: 56.46M L) (2/2) | PKGA4-DR-ML-BC-290 | Son | 90% | ✔ | ✔
244 |  | GENERAL VIEW OF BOX CULVERT 2-(2.0x2.0), KM119+197 (1/2) | PKGA4-DR-ML-BC-300 | Son | 90% | ✔ | ✔
245 |  | GENERAL VIEW OF BOX CULVERT 2-(2.0x2.0), KM119+197 (2/2) | PKGA4-DR-ML-BC-310 | Son | 90% | ✔ | ✔
246 |  | GENERAL VIEW OF BOX CULVERT 2-(2.0x2.0), KM0+313.39 (PR 622C) (1/2) | PKGA4-DR-ML-BC-320 | Son | 90% | ✔ | ✔
247 |  | GENERAL VIEW OF BOX CULVERT 2-(2.0x2.0), KM0+313.39 (PR 622C) (2/2) | PKGA4-DR-ML-BC-330 | Son | 90% | ✔ | ✔
248 |  | PLAN LAYOUT OF BOX CULVERT 2-(2.0x2.0), KM120+260 | PKGA4-DR-ML-BC-340 | Son | 90% | ✔ | ✔
249 |  | GENERAL VIEW OF BOX CULVERT 2-(2.0x2.0), KM120+260 (1/2) | PKGA4-DR-ML-BC-350 | Son | 90% | ✔ | ✔
250 |  | GENERAL VIEW OF BOX CULVERT 2-(2.0x2.0), KM120+260 (2/2) | PKGA4-DR-ML-BC-360 | Son | 90% | ✔ | ✔
251 |  | PLAN LAYOUT OF BOX CULVERT 1-(2.5x2.5), KM120+664; KM120+750 | PKGA4-DR-ML-BC-370 | Son | 90% | ✔ | ✔
252 |  | GENERAL VIEW OF BOX CULVERT 1-(2.5x2.5), KM120+664 (1/2) | PKGA4-DR-ML-BC-380 | Son | 90% | ✔ | ✔
253 |  | GENERAL VIEW OF BOX CULVERT 1-(2.5x2.5), KM120+664 (2/2) | PKGA4-DR-ML-BC-390 | Son | 90% | ✔ | ✔
254 |  | GENERAL VIEW OF BOX CULVERT 1-(2.0x2.0), KM120+750 (1/2) | PKGA4-DR-ML-BC-400 | Son | 90% | ✔ | ✔
255 |  | GENERAL VIEW OF BOX CULVERT 1-(2.0x2.0), KM120+750 (2/2) | PKGA4-DR-ML-BC-410 | Son | 90% | ✔ | ✔
256 |  | PLAN LAYOUT OF BOX CULVERT 1-(3.0x2.0), KM121+241 | PKGA4-DR-ML-BC-420 | Son | 90% | ✔ | ✔
257 |  | GENERAL VIEW OF BOX CULVERT 1-(3.0x2.0), KM121+241 (1/2) | PKGA4-DR-ML-BC-430 | Son | 90% | ✔ | ✔
258 |  | GENERAL VIEW OF BOX CULVERT 1-(3.0x2.0), KM121+241 (2/2) | PKGA4-DR-ML-BC-440 | Son | 90% | ✔ | ✔
259 |  | PLAN LAYOUT OF BOX CULVERT 1-(2.0x2.0), KM121+457 | PKGA4-DR-ML-BC-450 | Son | 90% | ✔ | ✔
260 |  | GENERAL VIEW OF BOX CULVERT 1-(2.0x2.0), KM121+457 (1/2) | PKGA4-DR-ML-BC-460 | Son | 90% | ✔ | ✔
261 |  | GENERAL VIEW OF BOX CULVERT 1-(2.0x2.0), KM121+457 (2/2) | PKGA4-DR-ML-BC-470 | Son | 90% | ✔ | ✔
262 |  | PLAN LAYOUT OF BOX CULVERT 1-(2.5x2.5), KM122+464.5 | PKGA4-DR-ML-BC-480 | Son | 90% | ✔ | ✔
263 |  | GENERAL VIEW OF BOX CULVERT 1-(2.5x2.5), KM122+464.5 (1/2) | PKGA4-DR-ML-BC-490 | Son | 90% | ✔ | ✔
264 |  | GENERAL VIEW OF BOX CULVERT 1-(2.5x2.5), KM122+464.5 (2/2) | PKGA4-DR-ML-BC-500 | Son | 90% | ✔ | ✔
265 |  | PLAN LAYOUT OF BOX CULVERT 2-(3.0x2.0), KM122+726 | PKGA4-DR-ML-BC-510 | Son | 90% | ✔ | ✔
266 |  | GENERAL VIEW OF BOX CULVERT 2-(3.0x2.0), KM122+726 (1/2) | PKGA4-DR-ML-BC-520 | Son | 90% | ✔ | ✔
267 |  | GENERAL VIEW OF BOX CULVERT 2-(3.0x2.0), KM122+726 (2/2) | PKGA4-DR-ML-BC-530 | Son | 90% | ✔ | ✔
J.1.4 PIPE CULVERT - THROUGHWAY (MAIN LINE)
268 |  | SCHEDULE OF PIPE CULVERTS | PKGA4-DR-ML-PC-010 | DDR | 0%
269 |  | PLAN LAYOUT OF PIPE CULVERT D1.5, KM110+280 | PKGA4-DR-ML-PC-020 | Hung | 90% | ✔ | ✔
270 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM110+280 (1/2) | PKGA4-DR-ML-PC-030 | Hung | 90% | ✔ | ✔
271 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM110+280 (2/2) | PKGA4-DR-ML-PC-040 | Hung | 90% | ✔ | ✔
272 |  | PLAN LAYOUT OF PIPE CULVERT D1.5, KM113+680 | PKGA4-DR-ML-PC-050 | Hung | 90% | ✔ | ✔
273 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM113+680 (1/2) | PKGA4-DR-ML-PC-060 | Hung | 90% | ✔ | ✔
274 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM113+680 (2/2) | PKGA4-DR-ML-PC-070 | Hung | 90% | ✔ | ✔
275 |  | PLAN LAYOUT OF PIPE CULVERT D1.5, KM114+430 | PKGA4-DR-ML-PC-080 | Hung | 90% | ✔ | ✔
276 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM114+430 (1/2) | PKGA4-DR-ML-PC-090 | Hung | 90% | ✔ | ✔
277 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM114+430 (2/2) | PKGA4-DR-ML-PC-100 | Hung | 90% | ✔ | ✔
278 |  | PLAN LAYOUT OF PIPE CULVERT D1.5, KM114+678 | PKGA4-DR-ML-PC-110 | Hung | 90% | ✔ | ✔
279 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM114+678 (1/2) | PKGA4-DR-ML-PC-120 | Hung | 90% | ✔ | ✔
280 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM114+678 (2/2) | PKGA4-DR-ML-PC-130 | Hung | 90% | ✔ | ✔
281 |  | PLAN LAYOUT OF PIPE CULVERT D1.5, KM116+045 | PKGA4-DR-ML-PC-140 | Hung | 90% | ✔ | ✔
282 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM116+045 (1/2) | PKGA4-DR-ML-PC-150 | Hung | 90% | ✔ | ✔
283 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM116+045 (2/2) | PKGA4-DR-ML-PC-160 | Hung | 90% | ✔ | ✔
284 |  | PLAN LAYOUT OF PIPE CULVERT D1.5, KM116+800 | PKGA4-DR-ML-PC-170 | Hung | 90% | ✔ | ✔
285 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM116+800 (1/2) | PKGA4-DR-ML-PC-180 | Hung | 90% | ✔ | ✔
286 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM116+800 (2/2) | PKGA4-DR-ML-PC-190 | Hung | 90% | ✔ | ✔
287 |  | PLAN LAYOUT OF PIPE CULVERT D1.5, KM117+063.5 052 | PKGA4-DR-ML-PC-200 | Hung | 90% | ✔ | ✔
288 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM117+063.5 052 (1/2) | PKGA4-DR-ML-PC-210 | Hung | 90% | ✔ | ✔
289 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM117+063.5 052 (2/2) | PKGA4-DR-ML-PC-220 | Hung | 90% | ✔ | ✔
290 |  | PLAN LAYOUT OF PIPE CULVERT D1.5, KM117+920 | PKGA4-DR-ML-PC-230 | Hung | 90% | ✔ | ✔
291 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM117+920 (1/2) | PKGA4-DR-ML-PC-240 | Hung | 90% | ✔ | ✔
292 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM117+920 (2/2) | PKGA4-DR-ML-PC-250 | Hung | 90% | ✔ | ✔
293 |  | PLAN LAYOUT OF PIPE CULVERT D1.5, KM118+160 | PKGA4-DR-ML-PC-260 | Hung | 90% | ✔ | ✔
294 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM118+160 (1/2) | PKGA4-DR-ML-PC-270 | Hung | 90% | ✔ | ✔
295 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM118+160 (2/2) | PKGA4-DR-ML-PC-280 | Hung | 90% | ✔ | ✔
296 |  | PLAN LAYOUT OF PIPE CULVERT D1.5, KM118+632.50 | PKGA4-DR-ML-PC-290 | Hung | 90% | ✔ | ✔
297 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM118+632.50 (1/2) | PKGA4-DR-ML-PC-300 | Hung | 90% | ✔ | ✔
298 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM118+632.50 (2/2) | PKGA4-DR-ML-PC-310 | Hung | 90% | ✔ | ✔
299 |  | PLAN LAYOUT OF PIPE CULVERT D1.5, KM119+380 | PKGA4-DR-ML-PC-320 | Hung | 90% | ✔ | ✔
300 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM119+380 (1/2) | PKGA4-DR-ML-PC-330 | Hung | 90% | ✔ | ✔
301 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM119+380 (2/2) | PKGA4-DR-ML-PC-340 | Hung | 90% | ✔ | ✔
302 |  | PLAN LAYOUT OF PIPE CULVERT D1.5, KM120+063.50 | PKGA4-DR-ML-PC-350 | Hung | 90% | ✔ | ✔
303 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM120+063.50 (1/2) | PKGA4-DR-ML-PC-360 | Hung | 90% | ✔ | ✔
304 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM120+063.50 (2/2) | PKGA4-DR-ML-PC-370 | Hung | 90% | ✔ | ✔
305 |  | PLAN LAYOUT OF PIPE CULVERT D1.5, KM121+045.78 | PKGA4-DR-ML-PC-380 | Hung | 90% | ✔ | ✔
306 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM121+045.78 (1/2) | PKGA4-DR-ML-PC-390 | Hung | 90% | ✔ | ✔
307 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM121+045.78 (2/2) | PKGA4-DR-ML-PC-400 | Hung | 90% | ✔ | ✔
308 |  | PLAN LAYOUT OF PIPE CULVERT D1.5, KM121+703.00 | PKGA4-DR-ML-PC-410 | Hung | 90% | ✔ | ✔
309 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM121+703.00 (1/2) | PKGA4-DR-ML-PC-420 | Hung | 90% | ✔ | ✔
310 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM121+703.00 (2/2) | PKGA4-DR-ML-PC-430 | Hung | 90% | ✔ | ✔
311 |  | PLAN LAYOUT OF PIPE CULVERT D1.5, KM124+641.50 | PKGA4-DR-ML-PC-440 | Hung | 90% | ✔ | ✔
312 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM124+641.50 (1/2) | PKGA4-DR-ML-PC-450 | Hung | 90% | ✔ | ✔
313 |  | GENERAL VIEW OF PIPE CULVERT D1.5, KM124+641.50 (2/2) | PKGA4-DR-ML-PC-460 | Hung | 90% | ✔ | ✔
J.2 BINH SON INTERCHANGE
J.2.1 DRAINAGE PLAN - BINH SON IC
314 |  | SCHEDULE OF OPEN DITCHES | PKGA4-DR-IC1-PL-010 | DDR
315 |  | SCHEDULE OF SHOULDER DITCHES | PKGA4-DR-IC1-PL-020 | DDR
316 |  | SCHEDULE OF MEDIAN DITCHES | PKGA4-DR-IC1-PL-030 | DDR
317 |  | DRAINAGE PLAN - BINH SON IC | PKGA4-DR-IC1-PL-040 | Hoa/Hung | 90% | ✔ | ✔
318 |  | DRAINAGE PLAN - BINH SON IC (1/6) | PKGA4-DR-IC1-PL-050 | Hoa/Hung | 90% | ✔ | ✔
319 |  | DRAINAGE PLAN - BINH SON IC (2/6) | PKGA4-DR-IC1-PL-060 | Hoa/Hung | 90% | ✔ | ✔
320 |  | DRAINAGE PLAN - BINH SON IC (3/6) | PKGA4-DR-IC1-PL-070 | Hoa/Hung | 90% | ✔ | ✔
321 |  | DRAINAGE PLAN - BINH SON IC (4/6) | PKGA4-DR-IC1-PL-080 | Hoa/Hung | 90% | ✔ | ✔
322 |  | DRAINAGE PLAN - BINH SON IC (5/6) | PKGA4-DR-IC1-PL-090 | Hoa/Hung | 90% | ✔ | ✔
323 |  | DRAINAGE PLAN - BINH SON IC (6/6) | PKGA4-DR-IC1-PL-100 | Hoa/Hung | 90% | ✔ | ✔
J.2.2 LONGITUDINAL PIPES - BINH SON IC
324 |  | SCHEDULE OF LONGITUDINAL PIPES | PKGA4-DR-IC1-LN-010 | Hoa | 90% | ✔ | ✔
325 |  | PLAN & PROFILE OF LONGITUDINAL PIPE - BINH SON IC (1/16) | PKGA4-DR-IC1-LN-020 | Hoa | 90% | ✔ | ✔
326 |  | PLAN & PROFILE OF LONGITUDINAL PIPE - BINH SON IC (2/16) | PKGA4-DR-IC1-LN-030 | Hoa | 90% | ✔ | ✔
327 |  | PLAN & PROFILE OF LONGITUDINAL PIPE - BINH SON IC (3/16) | PKGA4-DR-IC1-LN-040 | Hoa | 90% | ✔ | ✔
328 |  | PLAN & PROFILE OF LONGITUDINAL PIPE - BINH SON IC (4/16) | PKGA4-DR-IC1-LN-050 | Hoa | 90% | ✔ | ✔
329 |  | PLAN & PROFILE OF LONGITUDINAL PIPE - BINH SON IC (5/16) | PKGA4-DR-IC1-LN-060 | Hoa | 90% | ✔ | ✔
330 |  | PLAN & PROFILE OF LONGITUDINAL PIPE - BINH SON IC (6/16) | PKGA4-DR-IC1-LN-070 | Hoa | 90% | ✔ | ✔
331 |  | PLAN & PROFILE OF LONGITUDINAL PIPE - BINH SON IC (7/16) | PKGA4-DR-IC1-LN-080 | Hoa | 90% | ✔ | ✔
332 |  | PLAN & PROFILE OF LONGITUDINAL PIPE - BINH SON IC (8/16) | PKGA4-DR-IC1-LN-090 | Hoa | 90% | ✔ | ✔
333 |  | PLAN & PROFILE OF LONGITUDINAL PIPE - BINH SON IC (9/16) | PKGA4-DR-IC1-LN-100 | Hoa | 90% | ✔ | ✔
334 |  | PLAN & PROFILE OF LONGITUDINAL PIPE - BINH SON IC (10/16) | PKGA4-DR-IC1-LN-110 | Hoa | 90% | ✔ | ✔
335 |  | PLAN & PROFILE OF LONGITUDINAL PIPE - BINH SON IC (11/16) | PKGA4-DR-IC1-LN-120 | Hoa | 90% | ✔ | ✔
336 |  | PLAN & PROFILE OF LONGITUDINAL PIPE - BINH SON IC (12/16) | PKGA4-DR-IC1-LN-130 | Hoa | 90% | ✔ | ✔
337 |  | PLAN & PROFILE OF LONGITUDINAL PIPE - BINH SON IC (13/16) | PKGA4-DR-IC1-LN-140 | Hoa | 90% | ✔ | ✔
338 |  | PLAN & PROFILE OF LONGITUDINAL PIPE - BINH SON IC (14/16) | PKGA4-DR-IC1-LN-150 | Hoa | 90% | ✔ | ✔
339 |  | PLAN & PROFILE OF LONGITUDINAL PIPE - BINH SON IC (15/16) | PKGA4-DR-IC1-LN-160 | Hoa | 90% | ✔ | ✔
340 |  | PLAN & PROFILE OF LONGITUDINAL PIPE - BINH SON IC (16/16) | PKGA4-DR-IC1-LN-170 | Hoa | 90% | ✔ | ✔
J.2.3 BOX CULVERTS - BINH SON IC
341 |  | SCHEDULE OF BOX CULVERTS | PKGA4-DR-IC1-BC-010 | DDR | 0%
342 |  | GENERAL VIEW OF BOX CULVERT 1-(2.5x2.5), KM111+980 (1/2) | PKGA4-DR-IC1-BC-020 | Son | 90% | ✔ | ✔ |  |  | Move from F2.2 (Finally, No Changes)
343 |  | GENERAL VIEW OF BOX CULVERT 1-(2.5x2.5), KM111+980 (2/2) | PKGA4-DR-IC1-BC-030 | Son | 90% | ✔ | ✔ |  |  | Move from F2.2 (Finally, No Changes)
344 |  | GENERAL VIEW OF BOX CULVERT 1-(1.25x1.25), KM112+867 (1/2) | PKGA4-DR-IC1-BC-040 | Hung | 90% | ✔ | ✔
345 |  | GENERAL VIEW OF BOX CULVERT 1-(1.25x1.25), KM112+867 (2/2) | PKGA4-DR-IC1-BC-050 | Hung | 90% | ✔ | ✔
346 |  | GENERAL VIEW OF BOX CULVERT 1-(2.0x2.0) ON PR622, KM67+447.45 (1/2) | PKGA4-DR-IC1-BC-060 | Son | 75% | ✔ |  |  |  | Change from CP to CB
347 |  | GENERAL VIEW OF BOX CULVERT 1-(2.0x2.0) ON PR622, KM67+447.45 (2/2) | PKGA4-DR-IC1-BC-070 | Son | 75% | ✔ |  |  |  | Change from CP to CB
J.2.4 PIPE CULVERTS - BINH SON IC
348 |  | SCHEDULE OF PIPE CULVERTS | PKGA4-DR-IC1-PC-010 | DDR | 0%
349 |  | GENERAL VIEW OF PIPE CULVERT D1.5 ON RAMP-A1, KM0+68.41 (1/2) | PKGA4-DR-IC1-PC-020 | Hung | 90% | ✔ | ✔
350 |  | GENERAL VIEW OF PIPE CULVERT D1.5 ON RAMP-A1, KM0+68.41 (2/2) | PKGA4-DR-IC1-PC-030 | Hung | 90% | ✔ | ✔
351 |  | GENERAL VIEW OF PIPE CULVERT D1.0 ON RAMP-A1, KM0+766.0 (1/2) | PKGA4-DR-IC1-PC-040 | Hung | 90% | ✔ | ✔
352 |  | GENERAL VIEW OF PIPE CULVERT D1.0 ON RAMP-A1, KM0+766.0 (2/2) | PKGA4-DR-IC1-PC-050 | Hung | 90% | ✔ | ✔
J.3 QUANG NGAI NORTH INTERCHANGE
J.3.1 DRAINAGE PLAN - QUANG NGAI NORTH IC
353 |  | SCHEDULE OF OPEN DITCHES | PKGA4-DR-IC2-PL-010 | DDR
354 |  | SCHEDULE OF SHOULDER DITCHES | PKGA4-DR-IC2-PL-020 | DDR
355 |  | SCHEDULE OF MEDIAN DITCHES | PKGA4-DR-IC2-PL-030 | DDR
356 |  | DRAINAGE PLAN - QUANG NGAI NORTH IC | PKGA4-DR-IC2-PL-040 | Hoa/Hung | 90% | ✔ | ✔
357 |  | DRAINAGE PLAN - QUANG NGAI NORTH IC (1/5) | PKGA4-DR-IC2-PL-050 | Hoa/Hung | 90% | ✔ | ✔
358 |  | DRAINAGE PLAN - QUANG NGAI NORTH IC (2/5) | PKGA4-DR-IC2-PL-060 | Hoa/Hung | 90% | ✔ | ✔
359 |  | DRAINAGE PLAN - QUANG NGAI NORTH IC (3/5) | PKGA4-DR-IC2-PL-070 | Hoa/Hung | 90% | ✔ | ✔
360 |  | DRAINAGE PLAN - QUANG NGAI NORTH IC (4/5) | PKGA4-DR-IC2-PL-080 | Hoa/Hung | 90% | ✔ | ✔
361 |  | DRAINAGE PLAN - QUANG NGAI NORTH IC (5/5) | PKGA4-DR-IC2-PL-090 | Hoa/Hung | 90% | ✔ | ✔
J.3.2 LONGITUDINAL PIPES - QUANG NGAI NORTH IC
362 |  | SCHEDULE OF LONGITUDINAL PIPES | PKGA4-DR-IC2-LN-010 | DDR | 0%
363 |  | PLAN & PROFILE OF LONGITUDINAL PIPE - QUANG NGAI NORTH IC | PKGA4-DR-IC2-LN-020 | Hoa | 90% | ✔ | ✔
J.3.3 BOX CULVERTS - QUANG NGAI NORTH IC
364 |  | SCHEDULE OF BOX CULVERTS | PKGA4-DR-IC2-BC-010 | DDR | 0%
365 |  | GENERAL VIEW OF BOX CULVERT 2-(2.5x2.5), KM123+502 (1/2) | PKGA4-DR-IC2-BC-020 | Son | 90% | ✔ | ✔
366 |  | GENERAL VIEW OF BOX CULVERT 2-(2.5x2.5), KM123+502 (2/2) | PKGA4-DR-IC2-BC-030 | Son | 90% | ✔ | ✔
J.3.4 PIPE CULVERTS - QUANG NGAI NORTH IC
367 |  | SCHEDULE OF PIPE CULVERTS | PKGA4-DR-IC2-PC-040 | DDR | 0%
368 |  | GENERAL VIEW OF PIPE CULVERT D1.0 ON RAMP-A, KM0+180.46 (1/2) | PKGA4-DR-IC2-PC-050 | Hung | 90% | ✔ | ✔
369 |  | GENERAL VIEW OF PIPE CULVERT D1.0 ON RAMP-A, KM0+180.46 (2/2) | PKGA4-DR-IC2-PC-060 | Hung | 90% | ✔ | ✔
370 |  | GENERAL VIEW OF PIPE CULVERT D1.0 ON RAMP-B, KM0+380.0 (1/2) | PKGA4-DR-IC2-PC-070 | Hung | 90% | ✔ | ✔
371 |  | GENERAL VIEW OF PIPE CULVERT D1.0 ON RAMP-B, KM0+380.0 (2/2) | PKGA4-DR-IC2-PC-080 | Hung | 90% | ✔ | ✔
372 |  | GENERAL VIEW OF PIPE CULVERT D1.0 ON RAMP-C, KM0+100.0 (1/2) | PKGA4-DR-IC2-PC-090 | Hung | 90% | ✔ | ✔
373 |  | GENERAL VIEW OF PIPE CULVERT D1.0 ON RAMP-C, KM0+100.0 (2/2) | PKGA4-DR-IC2-PC-100 | Hung | 90% | ✔ | ✔
374 |  | GENERAL VIEW OF PIPE CULVERT D1.0 ON RAMP-D, KM0+384.50 (1/2) | PKGA4-DR-IC2-PC-110 | Hung | 90% | ✔ | ✔
375 |  | GENERAL VIEW OF PIPE CULVERT D1.0 ON RAMP-D, KM0+384.50 (2/2) | PKGA4-DR-IC2-PC-120 | Hung | 90% | ✔ | ✔
376 |  | GENERAL VIEW OF PIPE CULVERT D1.5 ON RAMP-C1, KM0+50.0 (1/2) | PKGA4-DR-IC2-PC-130 | Hung | 90% | ✔ | ✔
377 |  | GENERAL VIEW OF PIPE CULVERT D1.5 ON RAMP-C1, KM0+50.0 (2/2) | PKGA4-DR-IC2-PC-140 | Hung | 90% | ✔ | ✔
J.4 PARKING AREA
378 |  | SCHEDULE OF OPEN DITCHES | PKGA4-DR-PA-010 | DDR
379 |  | SCHEDULE OF SHOULDER DITCHES | PKGA4-DR-PA-020 | DDR
380 |  | SCHEDULE OF MEDIAN DITCHES | PKGA4-DR-PA-030 | DDR
381 |  | DRAINAGE PLAN OF PARKING AREA (1/3) | PKGA4-DR-PA-040 | Hung | 90% | ✔ | ✔ |  |  | General layout, profile, detail facility
382 |  | DRAINAGE PLAN OF PARKING AREA (2/3) | PKGA4-DR-PA-050 | Hung | 90% | ✔ | ✔ |  |  | General layout, profile, detail facility
383 |  | DRAINAGE PLAN OF PARKING AREA (3/3) | PKGA4-DR-PA-060 | Hung | 90% | ✔ | ✔ |  |  | General layout, profile, detail facility
J.5 CROSSING ROADS AND FRONTAGE ROADS
384 |  | SCHEDULE OF OPEN DITCHES | PKGA4-DR-CR/FR-010 | DDR
385 |  | SCHEDULE OF CROSS BOX CULVERTS | PKGA4-DR-CR/FR-020 | DDR
J.6 RELOCATION OF IRRIGATION AND OTHER CANALS
J.6.1 RELOCATION OF IRRIGATION AND OTHER CANALS
386 |  | SCHEDULE OF RELOCATION CANAL | PKGA4-DR-RC-010 | DDR
387 |  | PLAN AND PROFILE OF RELOCATION CANAL, KM116+010 | PKGA4-DR-RC-020 | Duy | 100% | ✔ | ✔
388 |  | PLAN AND PROFILE OF RELOCATION CANAL, KM119+140 | PKGA4-DR-RC-030 | Duy | 100% | ✔ | ✔
389 |  | PLAN AND PROFILE OF RELOCATION CANAL, KM122+726 | PKGA4-DR-RC-040 | Duy | 100% | ✔ | ✔
390 |  | PLAN AND PROFILE OF RELOCATION CANAL, KM122+966.37 (1/5) | PKGA4-DR-RC-050 | Duy | 100% | ✔ | ✔
391 |  | PLAN AND PROFILE OF RELOCATION CANAL, KM122+966.37 (2/5) | PKGA4-DR-RC-060 | Duy | 100% | ✔ | ✔
392 |  | PLAN AND PROFILE OF RELOCATION CANAL, KM122+966.37 (3/5) | PKGA4-DR-RC-070 | Duy | 100% | ✔ | ✔
393 |  | PLAN AND PROFILE OF RELOCATION CANAL, KM122+966.37 (4/5) | PKGA4-DR-RC-080 | Duy | 100% | ✔ | ✔
394 |  | PLAN AND PROFILE OF RELOCATION CANAL, KM122+966.37 (5/5) | PKGA4-DR-RC-090 | Duy | 100% | ✔ | ✔
395 |  | PLAN AND PROFILE OF RELOCATION CANAL, KM123+502 | PKGA4-DR-RC-100 | Duy | 100% | ✔ | ✔
396 |  | PLAN AND PROFILE OF RELOCATION CANAL, KM124+153.70 | PKGA4-DR-RC-110 | Duy | 100% | ✔ | ✔
J.6.2 BOX CULVERTS IN/NEAR RELOCATED IRRIGATION AND OTHER CANALS
397 |  | SCHEDULE OF BOX CULVERT (in Relocation Canal passing under exist.irrigation canal)) | PKGA4-DR-RC-BC-010 | DDR
398 |  | GENERAL VIEW OF BOX CULVERT 3-(3.0x2.0), KM1+145 OF CANAL (1/2) | PKGA4-DR-RC-BC-020 | Duy/Son | 75% | ✔ |  |  |  | From J.5, Plan in Reloc.Canal-KM122+966.37(5/5)
399 |  | GENERAL VIEW OF BOX CULVERT 3-(3.0x2.0), KM1+145 OF CANAL (2/2) | PKGA4-DR-RC-BC-030 | Duy/Son | 75% | ✔ |  |  |  | From J.5, Plan in Reloc.Canal-KM122+966.37(5/5)
J.7 DRAINAGE STRUCTURE DETAILS
J.7.1 OPEN DITCHES
400 |  | DETAILS OF DITCHES (1/3) | PKGA4-DR-DD-OP-010 | Hoa | 90% | ✔ | ✔
401 |  | DETAILS OF DITCHES (2/3) | PKGA4-DR-DD-OP-020 | Hoa | 90% | ✔ | ✔
402 |  | DETAILS OF DITCHES (3/3) | PKGA4-DR-DD-OP-030 | Hoa | 90% | ✔ | ✔
403 |  | DETAILS OF CASCADE DROP (1/2) | PKGA4-DR-DD-OP-040 | Hoa | 90% | ✔ | ✔
404 |  | DETAILS OF CASCADE DROP (2/2) | PKGA4-DR-DD-OP-050 | Hoa | 90% | ✔ | ✔
J.7.2 SHOULDER DICTHES
405 |  | SHOULDER DRAINAGE CROSS STRUCTURE (1/2) | PKGA4-DR-DD-SHD-010 | Hoa | 90% | ✔ | ✔
406 |  | SHOULDER DRAINAGE CROSS STRUCTURE (2/2) | PKGA4-DR-DD-SHD-020 | Hoa | 90% | ✔ | ✔
J.7.3 MEDIAN DICTHES
407 |  | MEDIAN DRAINAGE CROSS STRUCTURE (1/2) | PKGA4-DR-DD-MD-010 | Hoa | 90% | ✔ | ✔
408 |  | MEDIAN DRAINAGE CROSS STRUCTURE (2/2) | PKGA4-DR-DD-MD-020 | Hoa | 90% | ✔ | ✔
J.7.4 CATCH BASIN AND MANHOLES
409 |  | DETAILS OF CATCH BASIN AND MANHOLE (1/27) | PKGA4-DR-DD-CBMH-010 | Hoa | 90% | ✔ | ✔
410 |  | DETAILS OF CATCH BASIN AND MANHOLE (2/27) | PKGA4-DR-DD-CBMH-020 | Hoa | 90% | ✔ | ✔
411 |  | DETAILS OF CATCH BASIN AND MANHOLE (3/27) | PKGA4-DR-DD-CBMH-030 | Hoa | 90% | ✔ | ✔
412 |  | DETAILS OF CATCH BASIN AND MANHOLE (4/27) | PKGA4-DR-DD-CBMH-040 | Hoa | 90% | ✔ | ✔
413 |  | DETAILS OF CATCH BASIN AND MANHOLE (5/27) | PKGA4-DR-DD-CBMH-050 | Hoa | 90% | ✔ | ✔
414 |  | DETAILS OF CATCH BASIN AND MANHOLE (6/27) | PKGA4-DR-DD-CBMH-060 | Hoa | 90% | ✔ | ✔
415 |  | DETAILS OF CATCH BASIN AND MANHOLE (7/27) | PKGA4-DR-DD-CBMH-070 | Hoa | 90% | ✔ | ✔
416 |  | DETAILS OF CATCH BASIN AND MANHOLE (8/27) | PKGA4-DR-DD-CBMH-080 | Hoa | 90% | ✔ | ✔
417 |  | DETAILS OF CATCH BASIN AND MANHOLE (9/27) | PKGA4-DR-DD-CBMH-090 | Hoa | 90% | ✔ | ✔
418 |  | DETAILS OF CATCH BASIN AND MANHOLE (10/27) | PKGA4-DR-DD-CBMH-100 | Hoa | 90% | ✔ | ✔
419 |  | DETAILS OF CATCH BASIN AND MANHOLE (11/27) | PKGA4-DR-DD-CBMH-110 | Hoa | 90% | ✔ | ✔
420 |  | DETAILS OF CATCH BASIN AND MANHOLE (12/27) | PKGA4-DR-DD-CBMH-120 | Hoa | 90% | ✔ | ✔
421 |  | DETAILS OF CATCH BASIN AND MANHOLE (13/27) | PKGA4-DR-DD-CBMH-130 | Hoa | 90% | ✔ | ✔
422 |  | DETAILS OF CATCH BASIN AND MANHOLE (14/27) | PKGA4-DR-DD-CBMH-140 | Hoa | 90% | ✔ | ✔
423 |  | DETAILS OF CATCH BASIN AND MANHOLE (15/27) | PKGA4-DR-DD-CBMH-150 | Hoa | 90% | ✔ | ✔
424 |  | DETAILS OF CATCH BASIN AND MANHOLE (16/27) | PKGA4-DR-DD-CBMH-160 | Hoa | 90% | ✔ | ✔
425 |  | DETAILS OF CATCH BASIN AND MANHOLE (17/27) | PKGA4-DR-DD-CBMH-170 | Hoa | 90% | ✔ | ✔
426 |  | DETAILS OF CATCH BASIN AND MANHOLE (18/27) | PKGA4-DR-DD-CBMH-180 | Hoa | 90% | ✔ | ✔
427 |  | DETAILS OF CATCH BASIN AND MANHOLE (19/27) | PKGA4-DR-DD-CBMH-190 | Hoa | 90% | ✔ | ✔
428 |  | DETAILS OF CATCH BASIN AND MANHOLE (20/27) | PKGA4-DR-DD-CBMH-200 | Hoa | 90% | ✔ | ✔
429 |  | DETAILS OF CATCH BASIN AND MANHOLE (21/27) | PKGA4-DR-DD-CBMH-210 | Hoa | 90% | ✔ | ✔
430 |  | DETAILS OF CATCH BASIN AND MANHOLE (22/27) | PKGA4-DR-DD-CBMH-220 | Hoa | 90% | ✔ | ✔
431 |  | DETAILS OF CATCH BASIN AND MANHOLE (23/27) | PKGA4-DR-DD-CBMH-230 | Hoa | 90% | ✔ | ✔
432 |  | DETAILS OF CATCH BASIN AND MANHOLE (24/27) | PKGA4-DR-DD-CBMH-240 | Hoa | 90% | ✔ | ✔
433 |  | DETAILS OF CATCH BASIN AND MANHOLE (25/27) | PKGA4-DR-DD-CBMH-250 | Hoa | 90% | ✔ | ✔
434 |  | DETAILS OF CATCH BASIN AND MANHOLE (26/27) | PKGA4-DR-DD-CBMH-260 | Hoa | 90% | ✔ | ✔
435 |  | DETAILS OF CATCH BASIN AND MANHOLE (27/27) | PKGA4-DR-DD-CBMH-270 | Hoa | 90% | ✔ | ✔
J.7.5 BOX CULVERTS
xxx |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-DS-TYPE I (0.50x0.50) | PKGA4-DR-DD-BC-xxx | Hung | 100% | ✔ | ✔ |  |  | Add:Side Ditch underpass Crossing Road
xxx |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-DS-TYPE I (0.75x0.75) | PKGA4-DR-DD-BC-xxx | Hung | 100% | ✔ | ✔ |  |  | Add:Side Ditch underpass Crossing Road
436 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-DS-TYPE I (1.25x1.25) | PKGA4-DR-DD-BC-010 | Hung | 100% | ✔ | ✔ |  |  | Add:CB to underpass exist.irrigation canal
437 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-DS-TYPE I (2.0x1.5) | PKGA4-DR-DD-BC-020 | Son | 100% | ✔ | ✔
438 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-DS-TYPE I (2.0x2.0) | PKGA4-DR-DD-BC-030 | Son | 100% | ✔ | ✔
439 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-DS-TYPE II (2.0x2.0) | PKGA4-DR-DD-BC-040 | Son | 100% | ✔ | ✔
440 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-DS-TYPE IV (2.0x2.0) | PKGA4-DR-DD-BC-050 | Son | 100% | ✔ | ✔
441 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-DS-TYPE I (2.5x2.5) | PKGA4-DR-DD-BC-060 | Son | 100% | ✔ | ✔
442 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-DS-TYPE II (2.5x2.5) | PKGA4-DR-DD-BC-070 | Son | 100% | ✔ | ✔
443 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-DS-TYPE IV (2.5x2.5) | PKGA4-DR-DD-BC-080 | Son | 100% | ✔ | ✔
444 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-DS-TYPE I (3.0x2.0) | PKGA4-DR-DD-BC-090 | Son | 100% | ✔ | ✔
445 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-DS-TYPE II 2x(1.5x1.5) | PKGA4-DR-DD-BC-100 | Son | 100% | ✔ | ✔
446 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-DS-TYPE I 2x(2.0x2.0) | PKGA4-DR-DD-BC-110 | Son | 100% | ✔ | ✔
447 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-DS-TYPE I 2x(2.5x2.5) | PKGA4-DR-DD-BC-120 | Son | 100% | ✔ | ✔
448 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-DS-TYPE I 2x(3.0x2.0) | PKGA4-DR-DD-BC-130 | Son | 100% | ✔ | ✔
449 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-DS-TYPE I 2x(3.0x3.0) | PKGA4-DR-DD-BC-140 | Son | 100% | ✔ | ✔
450 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-DS-TYPE I 3x(3.0x2.0) | PKGA4-DR-DD-BC-150 | Son | 100% | ✔ | ✔
451 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-DS-TYPE I 3x(3.0x3.0) | PKGA4-DR-DD-BC-160 | Son | 100% | ✔ | ✔
J.7.6 PIPE CULVERTS
452 |  | DETAILS REINFORCEMENT OF RC PIPE CULVERT CP-DS-TYPE (D400 -:- D1000) (1/11) | PKGA4-DR-DD-PC-010 | Hoa | 90% | ✔ | ✔
453 |  | DETAILS REINFORCEMENT OF RC PIPE CULVERT CP-DS-TYPE (D400 -:- D1000) (2/11) | PKGA4-DR-DD-PC-020 | Hoa | 90% | ✔ | ✔
454 |  | DETAILS REINFORCEMENT OF RC PIPE CULVERT CP-DS-TYPE (D400 -:- D1000) (3/11) | PKGA4-DR-DD-PC-030 | Hoa | 90% | ✔ | ✔
455 |  | DETAILS REINFORCEMENT OF RC PIPE CULVERT CP-DS-TYPE (D400 -:- D1000) (4/11) | PKGA4-DR-DD-PC-040 | Hoa | 90% | ✔ | ✔
456 |  | DETAILS REINFORCEMENT OF RC PIPE CULVERT CP-DS-TYPE (D400 -:- D1000) (5/11) | PKGA4-DR-DD-PC-050 | Hoa | 90% | ✔ | ✔
457 |  | DETAILS REINFORCEMENT OF RC PIPE CULVERT CP-DS-TYPE (D400 -:- D1000) (6/11) | PKGA4-DR-DD-PC-060 | Hoa | 90% | ✔ | ✔
458 |  | DETAILS REINFORCEMENT OF RC PIPE CULVERT CP-DS-TYPE (D400 -:- D1000) (7/11) | PKGA4-DR-DD-PC-070 | Hoa | 90% | ✔ | ✔
459 |  | DETAILS REINFORCEMENT OF RC PIPE CULVERT CP-DS-TYPE (D400 -:- D1000) (8/11) | PKGA4-DR-DD-PC-080 | Hoa | 90% | ✔ | ✔
460 |  | DETAILS REINFORCEMENT OF RC PIPE CULVERT CP-DS-TYPE (D400 -:- D1000) (9/11) | PKGA4-DR-DD-PC-090 | Hoa | 90% | ✔ | ✔
461 |  | DETAILS REINFORCEMENT OF RC PIPE CULVERT CP-DS-TYPE (D400 -:- D1000) (10/11) | PKGA4-DR-DD-PC-100 | Hoa | 90% | ✔ | ✔
462 |  | DETAILS REINFORCEMENT OF RC PIPE CULVERT CP-DS-TYPE (D400 -:- D1000) (11/11) | PKGA4-DR-DD-PC-110 | Hoa | 90% | ✔ | ✔
463 |  | REINFORCEMENT DETAIL OF PIPE CULVERT CP-DS-TYPE I D1.0M (K31) | PKGA4-DR-DD-PC-120 | Hung | 100% | ✔ | ✔
464 |  | REINFORCEMENT DETAIL OF PIPE CULVERT CP-DS-TYPE I D1.5M (K32) | PKGA4-DR-DD-PC-130 | Hung | 100% | ✔ | ✔
465 |  | REINFORCEMENT DETAIL OF PIPE CULVERT CP-DS-TYPE II D1.5M (K33) | PKGA4-DR-DD-PC-140 | Hung | 100% | ✔ | ✔
466 |  | REINFORCEMENT DETAIL OF PIPE CULVERT CP-DS-TYPE III D1.5M (K34) | PKGA4-DR-DD-PC-150 | Hung | 100% | ✔ | ✔
xxx |  | SETTLEMENT JOINT OF PIPE CULVERT D1.0M | PKGA4-DR-DD-PC-xxx | Hung | 100% | ✔ | ✔ |  |  | Added details for CP
xxx |  | SUPPORTING PACK FOR CULVERT OF PIPE CULVERT D1.0M | PKGA4-DR-DD-PC-xxx | Hung | 100% | ✔ | ✔ |  |  | Added details for CP
467 |  | SETTLEMENT JOINT OF PIPE CULVERT D1.5M | PKGA4-DR-DD-PC-160 | Hung | 100% | ✔ | ✔
468 |  | SUPPORTING PACK FOR CULVERT OF PIPE CULVERT D1.5M | PKGA4-DR-DD-PC-170 | Hung | 100% | ✔ | ✔
K. GEOTECHNICAL WORKS
K.1 GENERAL SLOPE PROTECTION
469 |  | DETAILS OF SLOPE PROTECTION (1/2) | PKGA4-GT-GN-010 | Manh | 0% |  |  |  |  | Sodding, Grassing, etc
470 |  | DETAILS OF SLOPE PROTECTION (2/2) | PKGA4-GT-GN-020 | Manh | 0% |  |  |  |  | Sodding, Grassing, etc
K.2 DEEP EXCAVATION
471 |  | LOCATION MAP OF POSITIONS OF DEEP EXCAVATION | PKGA4-GT-DE-010 | DGT/Thuan | 100% | ✔
472 |  | TYPICAL CROSS SECTION OF SLOPE PROTECTION MEASURES (1/4) KM111+425 | PKGA4-GT-DE-020 | DGT/Thuan | 50% | ✔
473 |  | TYPICAL CROSS SECTION OF SLOPE PROTECTION MEASURES (2/4) KM112+300 | PKGA4-GT-DE-030 | DGT/Thuan | 50% | ✔
474 |  | TYPICAL CROSS SECTION OF SLOPE PROTECTION MEASURES (3/4) KM112+650 | PKGA4-GT-DE-040 | DGT/Thuan | 50% | ✔
475 |  | TYPICAL CROSS SECTION OF SLOPE PROTECTION MEASURES (4/4) KM114+080 | PKGA4-GT-DE-050 | DGT/Thuan | 50% | ✔
476 |  | PLAN OF SLOPE PROTECTION MEASURES (1/3) KM111+100-KM111+820 | PKGA4-GT-DE-060 | DGT/Thuan | 50% | ✔
477 |  | PLAN OF SLOPE PROTECTION MEASURES (2/3) KM112+120-KM113+120 | PKGA4-GT-DE-070 | DGT/Thuan | 50% | ✔
478 |  | PLAN OF SLOPE PROTECTION MEASURES (3/3) KM113+960-KM114+320 | PKGA4-GT-DE-080 | DGT/Thuan | 50% | ✔
479 |  | SLOPE PROTECTION MEASURES IN DETAIL (1) SHOTCRETE FRAME | PKGA4-GT-DE-090 | DGT/Thuan | 50% | ✔
480 |  | SLOPE PROTECTION MEASURES IN DETAIL (2) BAR INSERTION | PKGA4-GT-DE-100 | DGT/Thuan | 50% | ✔
481 |  | SLOPE PROTECTION MEASURES IN DETAIL (3) GROUNDANCHOR -A | PKGA4-GT-DE-110 | DGT/Thuan | 50% | ✔
482 |  | SLOPE PROTECTION MEASURES IN DETAIL (4) GROUNDANCHOR -B | PKGA4-GT-DE-120 | DGT/Thuan | 50% | ✔
483 |  | SLOPE PROTECTION MEASURES IN DETAIL (5) PRE-CAST BLOCK FACING | PKGA4-GT-DE-130 | DGT/Thuan | 50% | ✔
484 |  | SLOPE PROTECTION MEASURES IN DETAIL (6) MORTARED STONE WORK | PKGA4-GT-DE-140 | DGT/Thuan | 50% | ✔
K.3 HIGH EMBANKMENT
485 |  | LOCATION MAP OF POSITIONS OF HIGH EMBANKMENT | PKGA4-GT-HE-010 | DGT/Manh | 0%
486 |  | TYPICAL CROSS SECTION OF HIGH EMBANKMENT | PKGA4-GT-HE-020 | DGT/Manh | 0%
487 |  | PLAN OF HIGH EMBANKMENT (1/2) | PKGA4-GT-HE-030 | DGT/Manh | 0%
488 |  | PLAN OF HIGH EMBANKMENT (2/2) | PKGA4-GT-HE-040 | DGT/Manh | 0%
489 |  | SLOPE PROTECTION MEASURES IN DETAIL (1) | PKGA4-GT-HE-050 | DGT/Manh | 0%
490 |  | SLOPE PROTECTION MEASURES IN DETAIL (2) | PKGA4-GT-HE-060 | DGT/Manh | 0%
491 |  | SLOPE PROTECTION MEASURES IN DETAIL (3) | PKGA4-GT-HE-070 | DGT/Manh | 0%
492 |  | SLOPE PROTECTION MEASURES IN DETAIL (4) | PKGA4-GT-HE-080 | DGT/Manh | 0%
493 |  | SLOPE PROTECTION MEASURES IN DETAIL (5) | PKGA4-GT-HE-090 | DGT/Manh | 0%
494 |  | SLOPE PROTECTION MEASURES IN DETAIL (6) | PKGA4-GT-HE-100 | DGT/Manh | 0%
L. ROAD STRUCTURE WORKS
L.1 RESIDENTIAL UNDERPASSES
L.1.1 GENERAL VIEW
495 |  | GENERAL VIEW OF UNDERPASS AT KM114+407 (1/2) | PKGA4-RS-RUP-GV-010 | DDR/Son | 95% | ✔ | ✔
496 |  | GENERAL VIEW OF UNDERPASS AT KM114+407 (2/2) | PKGA4-RS-RUP-GV-020 | DDR/Son | 95% | ✔ | ✔
497 |  | GENERAL VIEW OF UNDERPASS AT KM117+000 (1/2) | PKGA4-RS-RUP-GV-030 | DDR/Son | 95% | ✔ | ✔
498 |  | GENERAL VIEW OF UNDERPASS AT KM117+900 (2/2) | PKGA4-RS-RUP-GV-040 | DDR/Son | 95% | ✔ | ✔
499 |  | GENERAL VIEW OF UNDERPASS AT KM117+900 (1/2) | PKGA4-RS-RUP-GV-050 | DDR/Son | 95% | ✔ | ✔
500 |  | GENERAL VIEW OF UNDERPASS AT KM117+900 (2/2) | PKGA4-RS-RUP-GV-060 | DDR/Son | 95% | ✔ | ✔
501 |  | GENERAL VIEW OF UNDERPASS AT KM120+020 (1/2) | PKGA4-RS-RUP-GV-070 | DDR/Son | 95% | ✔ | ✔
502 |  | GENERAL VIEW OF UNDERPASS AT KM120+020 (2/2) | PKGA4-RS-RUP-GV-080 | DDR/Son | 95% | ✔ | ✔
503 |  | GENERAL VIEW OF UNDERPASS AT KM120+530 (1/2) | PKGA4-RS-RUP-GV-090 | DDR/Son | 95% | ✔ | ✔
504 |  | GENERAL VIEW OF UNDERPASS AT KM120+530 (2/2) | PKGA4-RS-RUP-GV-100 | DDR/Son | 95% | ✔ | ✔
505 |  | GENERAL VIEW OF UNDERPASS AT KM121+485 (1/2) | PKGA4-RS-RUP-GV-110 | DDR/Son | 95% | ✔ | ✔
506 |  | GENERAL VIEW OF UNDERPASS AT KM121+485 (2/2) | PKGA4-RS-RUP-GV-120 | DDR/Son | 95% | ✔ | ✔
507 |  | GENERAL VIEW OF UNDERPASS AT KM122+260 (1/2) | PKGA4-RS-RUP-GV-130 | DDR/Son | 95% | ✔ | ✔
508 |  | GENERAL VIEW OF UNDERPASS AT KM122+260 (2/2) | PKGA4-RS-RUP-GV-140 | DDR/Son | 95% | ✔ | ✔
L.1.2 STRUCTURE DETAILES (1), BOX CULVERTS
509 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-UP-TYPE C I 3.0x3.0 | PKGA4-RS-RUP-BC-010 | DDR/Son | 95% | ✔ | ✔ |  |  | Prepare for each at final
510 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-UP-TYPE C II 3.0x3.0 | PKGA4-RS-RUP-BC-020 | DDR/Son | 95% | ✔ | ✔ |  |  | Prepare for each at final
511 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-UP-TYPE B I 4.0x3.0 | PKGA4-RS-RUP-BC-030 | DDR/Son | 95% | ✔ | ✔ |  |  | Prepare for each at final
512 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-UP-TYPE B II 4.0x3.0 | PKGA4-RS-RUP-BC-040 | DDR/Son | 95% | ✔ | ✔ |  |  | Prepare for each at final
513 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-UP-TYPE A I 5.0x3.5 | PKGA4-RS-RUP-BC-050 | DDR/Son | 95% | ✔ | ✔ |  |  | Prepare for each at final
514 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-UP-TYPE A II 5.0x3.5 | PKGA4-RS-RUP-BC-060 | DDR/Son | 95% | ✔ | ✔ |  |  | Prepare for each at final
515 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-UP-TYPE I 5.0x4.0 | PKGA4-RS-RUP-BC-070 | DDR/Son | 95% | ✔ | ✔ |  |  | Prepare for each at final
516 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-UP-TYPE II 5.0x4.0 | PKGA4-RS-RUP-BC-080 | DDR/Son | 95% | ✔ | ✔ |  |  | Prepare for each at final
517 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-UP-TYPE AH I 6.5x4.5 | PKGA4-RS-RUP-BC-090 | DDR/Son | 95% | ✔ | ✔ |  |  | Prepare for each at final
518 |  | REINFORCEMENT DETAIL OF BOX CULVERT CB-UP-TYPE AH II 6.5x4.5 | PKGA4-RS-RUP-BC-100 | DDR/Son | 95% | ✔ | ✔ |  |  | Prepare for each at final
L.1.3 STRUCTURE DETAILES (2), APROACH SLABS
519 |  | APPROACH SLAB | PKGA4-RS-RUP-ASLB-010 | DDR/Son | 0%
520 |  | REINFORCEMENT DETAIL OF APPROACH SLAB, TYPE 60 DEGREE | PKGA4-RS-RUP-ASLB-020 | DDR/Son | 100% | ✔ | ✔
521 |  | REINFORCEMENT DETAIL OF APPROACH SLAB, TYPE 70 DEGREE | PKGA4-RS-RUP-ASLB-030 | DDR/Son | 100% | ✔ | ✔
522 |  | REINFORCEMENT DETAIL OF APPROACH SLAB, TYPE 80 DEGREE | PKGA4-RS-RUP-ASLB-040 | DDR/Son | 100% | ✔ | ✔
523 |  | REINFORCEMENT DETAIL OF APPROACH SLAB, TYPE 90 DEGREE | PKGA4-RS-RUP-ASLB-050 | DDR/Son | 100% | ✔ | ✔
M. MISCELLANEOUS
524 |  | SCHEDULE OF MEDIAN | PKGA4-MISC-010 | Manh | 0% |  |  |  |  | Section table
525 |  | SCHEDULE OF GUARD FENCE | PKGA4-MISC-020 | Manh | 0% |  |  |  |  | Section table
526 |  | DETAILS OF WIDENING MEDIAN AT FLYOVER | PKGA4-MISC-030 | Manh | 100% | ✔ | ✔
527 |  | DETAILS OF MEDIAN | PKGA4-MISC-040 | Manh | 100% | ✔ | ✔
528 |  | DETAILS OF GUARD RAIL | PKGA4-MISC-050 | Manh | 100% | ✔ | ✔
529 |  | DETAILS OF GUARD FENCE | PKGA4-MISC-060 | Manh | 100% | ✔ | ✔
N. TRAFFIC SAFETY (REFERENCE ONLY)
N.1 GENERAL LAYOUT
530 |  | GENERAL LAYOUT OF TRAFFIC SIGNS (1/12) | PKGA4-RF-TS-GL-010 | DRD | 100% | ✔ | ✔
531 |  | GENERAL LAYOUT OF TRAFFIC SIGNS (2/12) | PKGA4-RF-TS-GL-020 | DRD | 100% | ✔ | ✔
532 |  | GENERAL LAYOUT OF TRAFFIC SIGNS (3/12) | PKGA4-RF-TS-GL-030 | DRD | 100% | ✔ | ✔
533 |  | GENERAL LAYOUT OF TRAFFIC SIGNS (4/12) | PKGA4-RF-TS-GL-040 | DRD | 100% | ✔ | ✔
534 |  | GENERAL LAYOUT OF TRAFFIC SIGNS (5/12) | PKGA4-RF-TS-GL-050 | DRD | 100% | ✔ | ✔
535 |  | GENERAL LAYOUT OF TRAFFIC SIGNS (6/12) | PKGA4-RF-TS-GL-060 | DRD | 100% | ✔ | ✔
536 |  | GENERAL LAYOUT OF TRAFFIC SIGNS (7/12) | PKGA4-RF-TS-GL-070 | DRD | 100% | ✔ | ✔
537 |  | GENERAL LAYOUT OF TRAFFIC SIGNS (8/12) | PKGA4-RF-TS-GL-080 | DRD | 100% | ✔ | ✔
538 |  | GENERAL LAYOUT OF TRAFFIC SIGNS (9/12) | PKGA4-RF-TS-GL-090 | DRD | 100% | ✔ | ✔
539 |  | GENERAL LAYOUT OF TRAFFIC SIGNS (10/12) | PKGA4-RF-TS-GL-100 | DRD | 100% | ✔ | ✔
540 |  | GENERAL LAYOUT OF TRAFFIC SIGNS (11/12) | PKGA4-RF-TS-GL-110 | DRD | 100% | ✔ | ✔
541 |  | GENERAL LAYOUT OF TRAFFIC SIGNS (12/12) | PKGA4-RF-TS-GL-120 | DRD | 100% | ✔ | ✔
N.2 PAVEMENT MARKING
542 |  | DETAILS OF PAVEMENT MARKINGS (1/3) | PKGA4-RF-TS-PM-010 | DRD | 100% | ✔ | ✔
543 |  | DETAILS OF PAVEMENT MARKINGS (2/3) | PKGA4-RF-TS-PM-020 | DRD | 100% | ✔ | ✔
544 |  | DETAILS OF PAVEMENT MARKINGS (3/3) | PKGA4-RF-TS-PM-030 | DRD | 100% | ✔ | ✔
N.3 DETAILES OF TRAFFIC SIGNS
545 |  | DETAILS OF TRAFFIC SIGN (1/11) | PKGA4-RF-TS-DD-010 | DRD | 100% | ✔ | ✔
546 |  | DETAILS OF TRAFFIC SIGN (2/11) | PKGA4-RF-TS-DD-020 | DRD | 100% | ✔ | ✔
547 |  | DETAILS OF TRAFFIC SIGN (3/11) | PKGA4-RF-TS-DD-030 | DRD | 100% | ✔ | ✔
548 |  | DETAILS OF TRAFFIC SIGN (4/11) | PKGA4-RF-TS-DD-040 | DRD | 100% | ✔ | ✔
549 |  | DETAILS OF TRAFFIC SIGN (5/11) | PKGA4-RF-TS-DD-050 | DRD | 100% | ✔ | ✔
550 |  | DETAILS OF TRAFFIC SIGN (6/11) | PKGA4-RF-TS-DD-060 | DRD | 100% | ✔ | ✔
551 |  | DETAILS OF TRAFFIC SIGN (7/11) | PKGA4-RF-TS-DD-070 | DRD | 100% | ✔ | ✔
552 |  | DETAILS OF TRAFFIC SIGN (8/11) | PKGA4-RF-TS-DD-080 | DRD | 100% | ✔ | ✔
553 |  | DETAILS OF TRAFFIC SIGN (9/11) | PKGA4-RF-TS-DD-090 | DRD | 100% | ✔ | ✔
554 |  | DETAILS OF TRAFFIC SIGN (10/11) | PKGA4-RF-TS-DD-100 | DRD | 100% | ✔ | ✔
555 |  | DETAILS OF TRAFFIC SIGN (11/11) | PKGA4-RF-TS-DD-110 | DRD | 100% | ✔ | ✔
N.4 MISCELLANEOUS
556 |  | DETAILS OF KM POST AND KM STATION | PKGA4-RF-TS-MISC-010 | DRD | 100% | ✔ | ✔
557 |  | DETAILS OF BRIDGE NAME SIGNS | PKGA4-RF-TS-MISC-020 | DRD | 100% | ✔ | ✔
O. ELECTRICAL WORKS (REFERENCE ONLY)
558 |  | POWER SUPPLY LOCATION MAP | PKGA4-RF-ELEC-010 | ITS | 100% | ✔
559 |  | SINGLE LINE DIAGRAM - BINH SON IC | PKGA4-RF-ELEC-020 | ITS | 100% | ✔
560 |  | SINGLE LINE DIAGRAM - QUANG NGAI NORTH IC | PKGA4-RF-ELEC-030 | ITS | 100% | ✔
561 |  | SINGLE LINE DIAGRAM - PARKING AREA (STA.120+900) | PKGA4-RF-ELEC-040 | ITS | 100% | ✔
562 |  | GENERAL LAYOUT FOR SUBSTATION - BINH SON IC | PKGA4-RF-ELEC-050 | ITS | 100% | ✔
563 |  | GENERAL LAYOUT FOR SUBSTATION - QUANG NGAI NORTH IC | PKGA4-RF-ELEC-060 | ITS | 100% | ✔
564 |  | GENERAL LAYOUT FOR SUBSTATION - PARKING AREA (STA.120+900) | PKGA4-RF-ELEC-070 | ITS | 100% | ✔
565 |  | GENERAL LAYOUT FOR LIGHTING AND CONDUIT SYSTEM BINH SON IC (1/6) | PKGA4-RF-ELEC-080 | ITS | 100% | ✔
566 |  | GENERAL LAYOUT FOR LIGHTING AND CONDUIT SYSTEM BINH SON IC (2/6) | PKGA4-RF-ELEC-090 | ITS | 100% | ✔
567 |  | GENERAL LAYOUT FOR LIGHTING AND CONDUIT SYSTEM BINH SON IC (3/6) | PKGA4-RF-ELEC-100 | ITS | 100% | ✔
568 |  | GENERAL LAYOUT FOR LIGHTING AND CONDUIT SYSTEM BINH SON IC (4/6) | PKGA4-RF-ELEC-110 | ITS | 100% | ✔
569 |  | GENERAL LAYOUT FOR LIGHTING AND CONDUIT SYSTEM BINH SON IC (5/6) | PKGA4-RF-ELEC-120 | ITS | 100% | ✔
570 |  | GENERAL LAYOUT FOR LIGHTING AND CONDUIT SYSTEM BINH SON IC (6/6) | PKGA4-RF-ELEC-130 | ITS | 100% | ✔
571 |  | GENERAL LAYOUT FOR LIGHTING AND CONDUIT SYSTEM QUANG NGAI NORTH IC (1/5) | PKGA4-RF-ELEC-140 | ITS | 100% | ✔
572 |  | GENERAL LAYOUT FOR LIGHTING AND CONDUIT SYSTEM QUANG NGAI NORTH IC (2/5) | PKGA4-RF-ELEC-150 | ITS | 100% | ✔
573 |  | GENERAL LAYOUT FOR LIGHTING AND CONDUIT SYSTEM QUANG NGAI NORTH IC (3/5) | PKGA4-RF-ELEC-160 | ITS | 100% | ✔
574 |  | GENERAL LAYOUT FOR LIGHTING AND CONDUIT SYSTEM QUANG NGAI NORTH IC (4/5) | PKGA4-RF-ELEC-170 | ITS | 100% | ✔
575 |  | GENERAL LAYOUT FOR LIGHTING AND CONDUIT SYSTEM QUANG NGAI NORTH IC (5/5) | PKGA4-RF-ELEC-180 | ITS | 100% | ✔
576 |  | GENERAL LAYOUT FOR LIGHTING AND CONDUIT SYSTEM PARKING AREA (STA.120+900) (1/3) | PKGA4-RF-ELEC-190 | ITS | 100% | ✔
577 |  | GENERAL LAYOUT FOR LIGHTING AND CONDUIT SYSTEM PARKING AREA (STA.120+900) (2/3) | PKGA4-RF-ELEC-200 | ITS | 100% | ✔
578 |  | GENERAL LAYOUT FOR LIGHTING AND CONDUIT SYSTEM PARKING AREA (STA.120+900) (3/3) | PKGA4-RF-ELEC-210 | ITS | 100% | ✔
579 |  | TYPICAL CROSS SECTION (1/6) | PKGA4-RF-ELEC-220 | ITS | 100% | ✔
580 |  | TYPICAL CROSS SECTION (2/6) | PKGA4-RF-ELEC-230 | ITS | 100% | ✔
581 |  | TYPICAL CROSS SECTION (3/6) | PKGA4-RF-ELEC-240 | ITS | 100% | ✔
582 |  | TYPICAL CROSS SECTION (4/6) | PKGA4-RF-ELEC-250 | ITS | 100% | ✔
583 |  | TYPICAL CROSS SECTION (5/6) | PKGA4-RF-ELEC-260 | ITS | 100% | ✔
584 |  | TYPICAL CROSS SECTION (6/6) | PKGA4-RF-ELEC-270 | ITS | 100% | ✔
585 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM110+100.00 - KM110+780.00 | PKGA4-RF-ELEC-280 | ITS | 100% | ✔
586 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM110+780.00 - KM111+460.00 | PKGA4-RF-ELEC-290 | ITS | 100% | ✔
587 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM111+460.00 - KM112+140.00 | PKGA4-RF-ELEC-300 | ITS | 100% | ✔
588 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM112+140.00 - KM112+820.00 | PKGA4-RF-ELEC-310 | ITS | 100% | ✔
589 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM112+820.00 - KM113+500.00 | PKGA4-RF-ELEC-320 | ITS | 100% | ✔
590 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM113+500.00 - KM114+180.00 | PKGA4-RF-ELEC-330 | ITS | 100% | ✔
591 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM114+180.00 - KM114+860.00 | PKGA4-RF-ELEC-340 | ITS | 100% | ✔
592 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM114+860.00 - KM115+540.00 | PKGA4-RF-ELEC-350 | ITS | 100% | ✔
593 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM114+180.00 - KM114+860.00 | PKGA4-RF-ELEC-360 | ITS | 100% | ✔
594 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM116+220.00 - KM116+900.00 | PKGA4-RF-ELEC-370 | ITS | 100% | ✔
595 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM116+900.00 - KM117+580.00 | PKGA4-RF-ELEC-380 | ITS | 100% | ✔
596 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM117+580.00 - KM118+260.00 | PKGA4-RF-ELEC-390 | ITS | 100% | ✔
597 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM118+260.00 - KM118+940.00 | PKGA4-RF-ELEC-400 | ITS | 100% | ✔
598 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM118+940.00 - KM119+640.00 | PKGA4-RF-ELEC-410 | ITS | 100% | ✔
599 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM119+640.00 - KM120+320.00 | PKGA4-RF-ELEC-420 | ITS | 100% | ✔
600 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM120+320.00 - KM121+000.00 | PKGA4-RF-ELEC-430 | ITS | 100% | ✔
601 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM121+000.00 - KM121+680.00 | PKGA4-RF-ELEC-440 | ITS | 100% | ✔
602 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM121+680.00 - KM122+360.00 | PKGA4-RF-ELEC-450 | ITS | 100% | ✔
603 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM122+360.00 - KM123+040.00 | PKGA4-RF-ELEC-460 | ITS | 100% | ✔
604 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM123+040.00 - KM123+720.00 | PKGA4-RF-ELEC-470 | ITS | 100% | ✔
605 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM123+720.00 - KM124+220.00 | PKGA4-RF-ELEC-480 | ITS | 100% | ✔
606 |  | GENERAL LAYOUT FOR CONDUIT SYSTEM KM124+220.00 - KM124+700.00 | PKGA4-RF-ELEC-490 | ITS | 100% | ✔
607 |  | GENERAL LAYOUT OF TOLL PLAZA | PKGA4-RF-ELEC-500 | ITS | 100% | ✔
608 |  | DETAIL OF 12M LIGHTING POLE | PKGA4-RF-ELEC-510 | ITS | 100% | ✔
609 |  | DETAIL OF 25M HIGH MAST LIGHTING | PKGA4-RF-ELEC-520 | ITS | 100% | ✔
610 |  | DETAIL OF ROAD LUMINAIRE | PKGA4-RF-ELEC-530 | ITS | 100% | ✔
611 |  | SUBSTATION EQUIPMENT | PKGA4-RF-ELEC-540 | ITS | 100% | ✔
612 |  | MANHOLE DETAIL | PKGA4-RF-ELEC-550 | ITS | 100% | ✔
613 |  | PULL BOX DETAIL (PB-B) | PKGA4-RF-ELEC-560 | ITS | 100% | ✔
614 |  | PULL BOX DETAIL (PB-E) | PKGA4-RF-ELEC-570 | ITS | 100% | ✔
II | CROSS SECTION DRAWINGS
|  | CROSS SECTIONS EVERY 20m at 1:200 scale 730 sheets in TOTAL | PKGA4-RW-CS-001
|  | CROSS SECTIONS EVERY 20m at 1:200 scale 730 sheets in TOTAL | PKGA4-RW-CS-730
III | STRUCTURAL CALCULATIONS
STRUCTURAL CALCULATION OF RESIDENTIAL UNDERPASSES
STRUCTURAL CALCULATION OF WATERWAY BOX CULVERTS
IV | STABILITY ANALYSIS
V | QUANTITY CALCULATIONS
VI | DETAILED DESIGN REPORT (ROAD)