|  | Ministry of Transport |  |  |
| --- | --- | --- | --- |
|  | Vietnam Expressway Corporation |  |  |
|  | Project Management Unit No. 85 |  |  |

IDA Credit	No.	:	3843-VN

Project ID	No.	:	P106235

Consulting Services

for

Detailed Design for Danang - Quang Ngai Expressway Development Project

Insert Project Perspective View

(Under Preparation by Mr. Lam)

Inception Report (Draft)

December 1, 2011

| The Joint Venture of |  |
| --- | --- |
|  | THAI ENGINEERING CONSULTANTS CO., LTD. |

Ref. No.	:	DQEDD-PMU-xx-11

Date	:	December 1, 2011

Mr. Nguyen Tien Ha

Project Manager

Project Management Unit No. 85 (PMU85)

Fax No. : +84-(38)3834705

Subject:		Submission of Inception Report (IC/R)

Dear Sir,

In accordance with Appendix B - Reporting Requirements in the Contract for Consultants’ Services, we would like to submit fifteen (15) copies of the Inception Report (IC/R) in English and Vietnamese versions, respectively.

Sincerely yours,

Ichizuru ISHIMOTO

Project Manager/Team Leader

c.c.	:	Office Copy

Encl.	:	Inception Report (English: 15 copies, Vietnamese: 15 copies)

Project Location Map

File	:	02_project location map_mae_111004.xlsx

Size	:	A4 Size

Project Route Map

File	:	03_project route map_mae_111004.pdf

Size	:	A3 Long Size

Letter of Submission

Project Location Map

Project Route Map

Table of Contents

Abbreviations

Main Part

Part A	General 		1

A.1	Project Features 		1

A.1.1	Background 		1

A.1.2	Recent Updates 		2

A.1.3	Location 		3

A.1.4	Objectives 		3

A.1.5	Component 		4

A.1.6	Safeguards 		7

A.1.7	Project Cost 		8

A.1.8	Funding Arrangement 		8

A.1.9	Contract Packaging 		9

A.1.10	Project Implementation Structure 		9

A.1.11	Project Implementation Program 		10

A.2	Outline of the Services 		11

A.2.1	General 		11

A.2.2	Objectives 		11

A.2.3	Scope 		11

A.2.4	Work Schedule and Reporting Plan 		12

A.2.5	Organization and Staffing 		18

Part B	Project Management 		22

B.1	Establish and Control Practical Project Management System 		25

Part C	Previous Studies Review and Establishing Detailed Engineering Design Framework 		27

C.1	Review Previous Studies 		27

C.2	Establish Detailed Engineering Design Framework 		27

Part D	Detailed Engineering Design and Procurement Planning 		28

D.1	Contract Packaging 		28

D.1.1	Propose Contract Packaging 		28

D.2	Surveys and Investigations 		28

D.2.1	Collect Relevant Data and Documents 		28

D.2.2	Conduct Topographic Survey 		28

D.2.3	Conduct Hydrological Survey and Analysis 		31

D.2.4	Conduct Geotechnical and Geological Investigations 		33

D.2.5	Conduct Material Source Survey 		35

D.2.6	Conduct Relevant Facilities Survey 		35

D.2.7	Review Traffic Forecasting and Conduct Baseline Surveys 		36

D.2.8	Conduct Independent Land Valuation Survey 		36

D.2.9	Conduct Environmental and Social Surveys 		37

D.3	Civil Engineering Design 		37

D.3.1	Prepare Basic Design of Civil Structures 		37

D.3.2	Prepare Detailed Design of Civil Structures 		37

D.4	O&M Plan and Design 		41

D.4.1	Prepare Institutional and Administrative Arrangement Plan 		41

D.4.2	Prepare O&M Plan 		41

D.4.3	Prepare Basic Design of O&M Buildings 		43

D.5	ITS Plan and Design 		43

D.5.1	Prepare ITS Plan 		43

D.5.2	Prepare Basic Design of ITS Facilities 		43

D.6	Electrical Facilities Design 		44

D.6.1	Prepare Detailed Engineering Design of Electrical Facilities 		44

D.7	Public Utilities Relocation Plan 		44

D.7.1	Prepare Relocation Plan of Public Utilities 		44

D.8	Safeguard 		45

D.8.1	Assist in Updating EIA and EMP 		45

D.8.2	Assist in Preparing and Enforcing CPCSR 		45

D.9	Construction Planning 		47

D.9.1	Prepare Construction Plan 		47

D.10	Project Cost Estimate 		47

D.10.1	Estimate Project Cost 		47

D.11	Procurement Documents 		48

D.11.1	Prepare Procurement Documents 		48

D.12	Project Implementation Program 		48

D.12.1	Prepare Project Implementation Program 		48

Part E	Procurement Assistance 		49

E.1	Assist in Tendering Procedures 		49

Part F	Technology Transfer 		50

F.1	Provide Training to VEC/PMU85 		50

F.2	Provide Training to the Key Local Professional Staff 		51

Appendix

Appendix	1	:	Terms of Reference (Appendix * in the Contract)

Appendix	2	:	Project Management Plan

Appendix	3	:	Baseline Schedule for Progress Monitoring (MS Project)

Appendix	4	:	List of Bridges (F/S-2010)

Appendix	5	:	List of Culverts (F/S-2010)

Abbreviations

XXXXX	:	XXXX XXXX XXXX XXXX XXXX XXXX XXXX XXXX

XXXXX	:	XXXX XXXX XXXX XXXX XXXX XXXX XXXX XXXX

XXXXX	:	XXXX XXXX XXXX XXXX XXXX XXXX XXXX XXXX

XXXXX	:	XXXX XXXX XXXX XXXX XXXX XXXX XXXX XXXX

XXXXX	:	XXXX XXXX XXXX XXXX XXXX XXXX XXXX XXXX

Main Part

General

Project Features

Background

The preparation of Pre-F/S for the Project under BOT scheme was approved by MOT in Decision No. 2654/QD-BGTVT dated on September 11, 2000.  The Pre-F/S report was prepared by PMU85 and approved by the Prime Minister in his letter No. 493/CP-CN dated on April 21, 2003.  Continually, the preparation of F/S was approved by MOT in Decision No. 134/QD-BGTVT dated on January 14, 2004.  The F/S report was also prepared by PMU85 and submitted to MOT in his letter No. 514/BQL-KHDA2 dated on May 11, 2005.  However, this BOT scheme Project did not materialize because of funding sources were not identified at that time.

Two (2) years later, the Project was approved as one (1) of the top priority projects in transport sector by GOVN in Decision No. 412/QD-TTg dated on April 11, 2007.  For carrying forward the Project, GOVN requested JETRO to assist a further study expecting materialization of the Project by a JBIC (currently JICA) loan scheme in June 2007.  JETRO conducted the study and submitted the study report to MOT on April 28, 2008.

In parallel with the JETRO study, WB declared GOVN to be eligible for the IBRD loan in November, 2007 and the Project was identified as the top priority use for the loan.  After submission of the JETRO study report, WB undertook the identification missions in April and June, 2008 and confirmed necessity of updating the JETRO study to meet his requirements and decided to allocate the fund from on-going RNIP (IDA Credit No.: 3843-VN) to conduct the WB supplemental study.  The study report was prepared by PMU85 and submitted to MOT in his letter No. 551/BQl-KHDA2 dated on June 13, 2009.

In response to the supplemental study, WB engaged an international consultant and undertook the WB appraisal study.  In the appraisal study, WB modified the alignment at three (3) sections by taking into consideration social and environmental issues.  Based on the modified alignment, TEDI updated the supplemental study and submitted as the draft F/S report to MOT in April, 2010.  The draft F/S report was also finalized by TEDI in accordance with the MOT appraisal report No. 6188/BGTVT-KHDT dated on September 8, 2011 and submitted by VEC as the F/S report to MOT in September 2010.  The F/S report was approved by MOT in Decision No. 2656/QD-BGTVT dated on September 10, 2010.

In parallel with the F/S approval, WB agreed to allocate the fund from RNIP for D/D and the Prime Minister allowed commencing the procurement of D/D consultant.  Through the procurement procedures, NK-NE-Chodai-TEC JV (the Consultant) was selected and signed the contract with PMU85 on November 15, 2011.  Currently, PMU85 issued NTP in his letter No. ***/***-***** dated on November **, 2011 and D/D was officially commenced from December 1, 2011.

Outline of the Project background is shown in Figure A.1.

Figure A.1   Outline of the Project Background

Recent Updates

Main Updates after Proposals Submission

The Consultant submitted the proposals for Consulting Services for Detailed Design for Danang - Quang Ngai Expressway Development Project (the Services) on June 1, 2010 based on the draft F/S report distributed by VEC/PMU85 in the procurement stage (see A.1.1).  Afterward, various documents for the Project have been issued and updated by the relevant organizations.

Main updates after proposals submission are shown in Table A.1.

Table A.1   Main Updates after Proposals Submission

| No. | Items |  | Issued by | Subject (Summary) | Ref. No. | Date Issued |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | F/S | Approval | MOT | F/S Approval | Decision No. 2656/QD-BGTVT | 10 | Sep., | 2010 |
| 2 |  |  | GOVN Office | Investment Approval and Assigning MOT for F/S Approval | Document No. 4684/VPCP-KTN | 7 | Jul., | 2010 |
| 3 |  | Appraisal | MOT | F/S Appraisal Report | Document No. 6188/BGTVT-KHDT | 8 | Sep., | 2010 |
| 4 |  | Submission | VEC | Submission of F/S Report | Letter No. 384/TTr-VEC | 7 | Sep., | 2010 |
| 5 |  |  |  |  | Letter No. 160/TTr-VEC | 30 | Jul., | 2010 |
| 6 | Safeguards | EIA | MONRE | Approval for Supplemental EIA | Decision No. 2046/QD-BTNMT | 29 | Oct., | 2010 |
| 7 |  | RAP | PM | Approval for RAP (Based on F/S Alignment) | Decision No. 442/TTg-KTN | 23 | Mar., | 2011 |
| 8 | Funding | JICA Loan | GOVN-JICA | L/A | ----- | 15 | Jun., | 2011 |
| 9 |  |  |  | M/D (L/A) | ----- | 17 | Jan., | 2011 |
| 10 |  |  |  | M/D (Appraisal Mission) | ----- | 21 | Oct., | 2010 |
| 11 |  | WB Loan | GOVN-WB | M/D (Appraisal Mission) | ----- | 21 | Apr., | 2011 |
| 12 |  | GOVN | MOT | Approval for Adjustment of Project Investment Structure | Decision No. 666/QD-BGTVT | 6 | Apr., | 2011 |
| 13 |  |  | GOVN Office | VEC’s Responsibilities (Borrowing/Paying Loan) | Document No. 4684/VPCP-KTN | 7 | Jul., | 2010 |
| 14 |  |  | MOF |  | Document No. 695/BTC-QLN | 13 | Aug., | 2010 |
| 15 | Procurement | JICA Portion | MOT | Approval for Procurement Plan (JICA Portion) | Decision No. 1688/QD-BGTVT | 28 | Jul., | 2011 |
| 16 |  | WB Portion | MOT | Approval for Procurement Plan (WB Portion) | Decision No. 1423/QD-BGTVT | 30 | Jun., | 2011 |
| 17 |  | GOVN | MOND | Executing Plan (Searching and De-mining Bombs) | Decision No. 1286/QD-BQP | 20 | Apr., | 2011 |
| 18 | Project Implementation Structure |  | MOT | Assigning PMU85 for Implementation Agency in D/D | Decision No. 2149/QD-BGTVT | 19 | Sep., | 2011 |
| 19 | Project Implementation Program |  | PMU85 | Commencement of Const. Works in 3rd Quarter, 2012 | Letter No. 1816/PMU85-PP2 | 22 | Sep., | 2011 |
| 20 | Request from Quang Nam PPC |  | Quang Nam | Agreement for Re-alignment/Request for Additional IC | Circular No. 346/TB0UBND | 13 | Sep., | 2011 |
| 21 | (Additional IC and Re-alignment) |  |  | Request for Additional IC and Re-alignment Study | Document No. 2107/UBND-KTN | 17 | Jun., | 2011 |
| 22 |  |  | MOT | F/S Approval (including No.23 and 24 below) | Decision No. 2656/QD-BGTVT | 10 | Sep., | 2010 |
| 23 |  |  |  | Notice (for No.24 below) | Notice No. 325 | 6 | Aug., | 2010 |
| 24 |  |  | Quang Nam | Comments on Additional IC and Re-alignment | Document No. 1732/UBND-KTN | 31 | May, | 2010 |

Issues postponed to D/D Stage

The MOT Appraisal Report, Document No. 6188/BGTVT-KHDT dated on September 8, 2010 mentioned that MOT/VEC received the comments on the draft F/S report from relevant organizations and basically modified those items according to their opinions in the F/S report.  However, in Paragraph IV.7, it was also mentioned that some technical issues were unsolved in the F/S stage and those issues would be postponed to the subsequent D/D stage.

Issues postponed to D/D stage are shown in Table A.2.

Table A.2   Issues postponed to D/D Stage

| No. | Items | Issues postponed to D/D Stage |
| --- | --- | --- |
| 1 | Alternative Route | Study and adjust the section passing Duc Bo Shooting field (KM070 – KM080) in Quang Nam Province according to Notice No. 325 |
|  |  | dated on August 6, 2010 issued by MOT |
| 2 | Inundation Analysis | Study more carefully and define exactly where to construct viaducts and drainage culverts to ensure the flood discharge |
| 3 | Requirement for River Bridges | Discuss and agree with localities on hydrological and navigational requirement for river bridges other than four (4) major river bridges |
|  |  | which already agreed with the localities in the F/S stage |
| 4 | Clearance with HVL (500kV) | Discuss and agree with EVN on countermeasures for insufficient vertical clearance between the Project road and existing HVL (500kV) |
|  |  | at two (2) locations (KM004+431 and KM065+959) |
| 5 | Additional Overpass | Discuss and agree with VNR on intersecting mode (at grade or grade separation) at the intersection between the Project road and |
|  |  | existing North-South Railway at KM135+270 (finally, an overpass with 492 m length was approved in the MOT F/S Approval) |
| 6 | ITS | Check in term of technical approach and standards, appropriate investment cost and suitable with current conditions of Vietnam |

Source: MOT Appraisal Report, Document No. 6188/BGTVT-KHDT dated on September 8, 2010

Location

The Project road is a part of the North-South Expressway located in parallel with the existing NH1A and North-South Railway and passing through Danang city, Quang Nam and Quang Ngai provinces in the central region.  The road starts at the intersection of the Danang Bypass and NH14B in Danang city and ends at the connecting point with the planned City Ring Road at existing NH1A in Quang Ngai province.  The major socio-economic developments along the Project road are the Chu Lai Open Economic Zone in Quang Nam province and the Dung Quat Industrial Zone in Quang Ngai province.  As for the cultural properties, the Hoi An Ancient Town and My Son Sanctuary registered with the world heritage (cultural heritage) are existed along the Project road.

Project location map is shown in Figure A.2.

Figure A.2   Project Location Map

Objectives

The main objectives of the Project are to enhance travel efficiency and safety by constructing an expressway from Danang to Quang Ngai, and contributing to economic growth in the central region.

Outline of Project framework and operating effectiveness indicators established by WB and VEC are shown in Figure A.3 and Table A.3, respectively.

Figure A.3   Outline of Project Framework

Table A.3   Operating Effectiveness Indicators established by WB and VEC

| No. | Area/Sections | Quantitative Indicators |  | Baseline | Target |
| --- | --- | --- | --- | --- | --- |
| 1 | Between Danang and Quang Ngai | Travel time | 10 ton freight vehicles | 233 minutes | 20 % reduction |
| 2 |  |  | Passenger vehicles | 158 minutes | 20 % reduction |
| 3 |  | Coefficient of variation (travel time) | 10 ton freight vehicles | 0.19 | 10 % reduction |
| 4 |  |  | Passenger vehicles | 0.08 | 10 % reduction |
| 5 |  | Traffic accidents (no. of fatalities) |  | 185 nos./year | 10 % reduction |

Source:	M/D (WB Appraisal Mission) dated on April 21, 2011

Note:	JICA also agreed to establish the indicators in line with WB in M/D (JICA Appraisal Mission) dated on October 21, 2010

Component

Expressway Construction and O&M Equipment Provision

The main Project components are the expressway construction and O&M equipment provision.

Main features of expressway construction and O&M equipment provision are shown in Table A.4, and Project facilities plan is shown in Figure A.4, respectively.

Table A.4   Main Features of Expressway Construction and O&M Equipment Provision

| No. | Items | Main Features |  | Ref. in TOR |
| --- | --- | --- | --- | --- |
| 1 | Road Length | 139.52 km |  | Component A |
|  |  |  | By Road Class: Expressway section: 131.5 km, Linking road section: 8.02 km | (TOR 1(1)) |
|  |  |  | By Jurisdiction: Danang city: 8.0 km, Quang Nam province: 92.0 km, Quang Ngai province: 39.52 km |  |
|  |  |  | Beginning Point (BP): Intersection of the existing Danang bypass and NH14B in Danang city |  |
|  |  |  | Ending Point (EP): Connecting point with the planned city ring road at the existing NH1A (KM1063+700) in Quang Ngai province |  |
| 2 | Road Classification | Expressway: Type A, Class 120, Linking Road: Class III, Delta |  |  |
| 3 | Design Speed | Expressway: 120 km/hr (Tunnel section: 100 km/hr), Linking Road: 80 km/hr |  |  |
| 4 | Nos. of Lane | 4 lanes (Ultimate stage: Widened to 6 lanes (see Figure A.4)) |  |  |
| 5 | Road With | Expressway: Road and Bridge sections: 26.0 m, Tunnel section: 2@12.75 m=25.5 m, Linking Road: 12.0 m |  |  |
| 6 | Design Frequency | Expressway: 1 %, Linking Road: 4 % |  |  |
| 7 | Bridge | 131 bridges (L=15,486.85 m)1) |  |  |
|  |  |  | Large River Bridge (LRB, L>100 m): 20 bridges (L=5,687.55 m)2), Other River Bridge (ORB, L<100 m): 10 bridges (L=603.85 m), |  |
|  |  |  | Stream Bridge (SB): 8 bridges (L=354.90 m), Canal Bridge (CB): 18 bridges (L=666.00 m), |  |
|  |  |  | Viaduct (VD): 21 bridges (L=3,073.45 m), Overpass (OP): 23 bridges (L=1,186.80 m)1), |  |
|  |  |  | Interchange Rampway Bridge (IRB): 12 bridges (L=1,662.30 m), Flyover (FO): 19 bridges (L=2,252.00 m) |  |
| 8 | Major River Bridge | 4 bridges (L=2,670.00 m) |  |  |
|  |  |  | Thu Bong River (KM017+662): Ky Lam Bridge (L=962.00 m), Ba Ren River (KM020+185): Chiem Son Bridge (L=410.00 m), |  |
|  |  |  | Tra Bong River (KM109+320): Tra Bong Bridge (L=452.00 m), Tra Khuc River (KM125+700): Tra Khuc Bridge (L=846.00 m) |  |
| 9 | Tunnel | 1 tunnel (KM022+900, L=2@540 m) |  |  |
| 10 | Culvert | 375 culverts |  |  |
|  |  |  | Culvert Box: 188 culvert boxes (106 roadway culverts and 82 waterway culverts), Culvert Pipe: 187 culvert pipes |  |
| 11 | Softground | Approximately 3.6 km |  |  |
| 12 | Interchange | 9 interchanges |  |  |
| 13 | Frontage Road | Approximately 59.7 km |  |  |
| 14 | Earth Works | Soil excavation: 10,000,000 m3, Rock excavation: 1,000,000 m3, Filling: 24,000,000m3 |  |  |
| 15 | Electrical Facilities | Power supply, road lighting, tunnel ventilation and safety facilities |  | Component B |
| 16 | ITS | Traffic management, toll collection3) and communication systems |  | (TOR 1(2)) |
| 17 | O&M Building | 26 locations (see Figure A.4) |  | Component C |
|  |  |  | Traffic Management Center (TMC): 1 location, Expressway Operation Office (EOO): 1 location, Toll Plaza Office (TPO): 9 locations, | (TOR 1(3)) |
|  |  |  | Toll Barrier (TB): 2 locations, Toll Gate (TG): 7 locations, Service Area (SA): 2 locations, Parking Area (PA): 4 locations |  |
| 18 | O&M Equipment | O&M vehicles, spare parts, maintenance equipment and consumables |  |  |

Source:	MOT F/S Approval, Decision No. 2656/QD-BGTVT dated on September 10, 2010 (modified discrepancies with the F/S report by the Consultant)

Note:	1)	Including the additional overpass with 492 m at KM135+270 (see No.5, Table A.2)

2)	Including 4 major river bridges (see No.8)

3)	Including electric toll collection system in accordance with MOT Notice No.94/TB-BGTVT dated March 10, 2009

Source:	MOT F/S Approval, Decision No. 2656/QD-BGTVT dated on September 10, 2010 (modified discrepancies with the F/S report by the Consultant)

Note:	1)	Confirmed with the F/S Consultant (not mentioned in the MOT F/S Approval, Decision No. 2656/QD-BGTVT dated on September 10, 2010)

Figure A.4   Project Facilities Plan

Consulting Services

The overall consulting services for the Project are composed of the Detailed Engineering Design (D/D), Construction Supervision (C/S) and Project implementation support for VEC.  The consulting services in this contract (the Services) cover D/D only, without C/S and Project implementation support.

Main scope of overall consulting services is shown in Table A.5.

Table A.5   Main Scope of Overall Consulting Services

| No. | Items |  | Main Scope |
| --- | --- | --- | --- |
| 1 | Detailed Engineering Design (D/D) |  | - Previous studies review and establishing D/D framework |
|  |  |  | - D/D and procurement planning (incl. B/D of O&M/ITS package) |
|  |  |  | - Procurement assistance (civil work packages) |
| 2 | Construction Supervision (C/S) |  | - B/D and procurement documents review (O&M/ITS package) |
|  |  |  | - Procurement assistance (O&M/ITS package) |
|  |  |  | - D/D review (civil work packages) |
|  |  |  | - C/S (incl. internal social, environmental and resettlement monitoring) |
|  |  |  | - Assisting in establishment of an O&M unit (incl. capacity development) |
|  |  |  | - Assisting in defect liability inspections |
| 3 | Project Implementation | Integrated Project Review and | - D/D appraisal |
|  | Support for VEC | Monitoring Services | - Traffic safety audit |
|  |  |  | - Construction quality inspection |
|  |  |  | - Social and environmental external monitoring |
|  |  |  | - Resettlement external monitoring |
|  |  |  | - Overall project monitoring and evaluation |
|  |  |  | - Expressway user information and HIV/AIDS campaign |
|  |  | Financial Audit | - Annual project financial external audit |
|  |  | Financial Capacity Development | - Financial capacity development for VEC |

Source:	Decision No. 1423/QD-BGTVT dated on June 30, 2011, Decision No. 1688/QD-BGTVT dated on July 28, 2011

M/D (JICA Appraisal Mission) dated on October 21, 2010, M/D (WB Appraisal Mission) dated on April 21, 2011

Establishment of an O&M Unit

The O&M framework of the expressway section is under consideration.  Based on the F/S report, the estimated financial return by operating the expressway is low in early stage because of the forecasted traffic volume is small.  Therefore, O&M concessions are not attractive for private sectors, and the expressway is expected to operate by an O&M unit to be established under VEC in early stage.

Expected O&M framework for Project road (expressway section) is shown in Figure A.5.

Note:	1)	Various administrative arrangements such as level of services and its inspection system, accounting and auditing systems, toll rate setting and subsidies

Figure A.5   Expected O&M Framework for Project Road (Expressway Section)

Safeguards

Social and Environmental Assessment

The original EIA report based on the JETRO study was prepared by PMU85, and approved by MONRE in Decision No. 2378/QD-BTNMT dated on November 12, 2008.  The supplemental EIA report based on the F/S alignment was also prepared by PMU85 and approved by MONRE in Decision No. 2046/QD-BTNMT dated on October 29, 2010.

Social and environmental assessment framework for Project road is shown in Figure A.6.

Figure A.6   Social and Environmental Assessment Framework for Project Road

Land Acquisition and Resettlement

RAP based on the F/S alignment was prepared by PMU85 and approved by the Prime Minister in Decision No. 442/TTg-KTN dated on March 23, 2011.

Land acquisition area and no. of resettlement households for Project road is shown in Table A.6, and CPCSR framework for Project road is shown in Figure A.7, respectively.

Table A.6   Land Acquisition Area and Nos. of Resettlement Households for Project Road

| No. | Item | Unit | Danang | Quang Nam | Quang Ngai | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Land Acquisition Area | sq.m | 506,014 (5%) | 6,425,285 (67%) | 2,658,838 (28%) | 9,590,137 (100%) |
| 2 | Resettlement Households | nos. | 85 (7%) | 771 (60%) | 430 (33%) | 1,286 (100%) |

Source:	Decision No. 442/TTg-KTN dated on March 23, 2011

Figure A.7   CPCSR Framework for Project Road

Project Cost

The total investment cost was approved by MOT in Decision No. 2656/QD-BGTVT dated on September 10, 2011, and it amounts to 27,968 Bil.VND (equivalent to 1,472 Mil.USD).

Total investment cost is shown in Table A.7.

Table A.7   Total Investment Cost

| No. | Items | Foreign Loans | State Budget | Total1) |  |
| --- | --- | --- | --- | --- | --- |
|  |  | (Mil.USD) | (Bil.VND) | (Equiv. to Bil.VND) | (Equiv. to Mil.USD) |
| 1 | Construction Cost | 904 |  | 17,179 | 904 |
| 2 | Equipment Cost | 31 |  | 580 | 31 |
| 3 | Consulting Services Cost | 53 |  | 1,003 | 53 |
| 4 | Project Management Cost |  | 68 | 68 | 4 |
| 5 | Other Cost | 32 |  | 606 | 32 |
| 6 | Land Acquisition and Compensation Cost |  | 1,074 | 1,074 | 56 |
| 7 | Contingency | 200 | 114 | 3,927 | 206 |
| 8 | VAT |  | 1,943 | 1,943 | 102 |
| 9 | Loan Interest and Financial Fees2) | 84 |  | 1,588 | 84 |
| Total |  | 1,304 | 3,199 | 27,968 | 1,472 |

Source:	Decision No. 2656/QD-BGTVT dated on September 10, 2010

Note:	1)	Exchange rate: 1USD = 19,000VND

2)	Interest during construction, front-end fees, commitment charge and service charges

Funding Arrangement

The investment cost is financed by JICA, WB and counterpart fund and it was approved by MOT in Decision No. 2656/QD-BGTVT dated on September 10, 2010.  VEC is responsible for borrowing and re-paying the loans and it was decided by GOVN Office and MOF in Document No. 4684/VPCP-KTN dated on July 7, 2010 and Document No. 695/BTC-QLN dated on August 13, 2010.

JICA signed L/A on June 15, 2011 and finances the civil works from Danang to Tam Ky section, electrical works, O&M building works and O&M/ITS equipment procurement for whole section, C/S, other cost, contingency and loan interest and financial fees for JICA portion.

WB finances the D/D cost for whole section through ongoing RNIP (IDA Credit No.: 3843-VN).  In addition, WB approved to provide a loan and two (2) credits by the Executive Directors on May 24, 2011 and finances the civil works from Tam Ky to Quang Ngai section, C/S, other cost, contingency and loan interest and financial fees for WB portion, and project implementation support for VEC.

Funding arrangement among WB, JICA and GOVN is shown in Table A.8.

Table A.8   Funding Demarcation among WB, JICA and GOVN

| No. | Item |  |  | Section | Funding Demarcation |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | JICA1) | WB1) | GOVN |
| 1 | Construction (Civil Works) |  |  | Danang to Tam Ky | ● |  |  |
|  |  |  |  | Tam Ky to Quang Ngai |  | ● |  |
| 2 | Electrical, ITS Facilities and O&M Building Works, and O&M Equipment Provision |  |  | Whole Section | ● |  |  |
| 3 | Consulting | D/D |  | Whole Section |  | ● |  |
|  | Services | C/S | Civil Works | Danang to Tam Ky | ● |  |  |
|  |  |  |  | Tam Ky to Quang Ngai |  | ● |  |
|  |  |  | Electrical/O&M/ITS Works and Equipment Provision | Whole Section | ● |  |  |
|  |  | Project Implementation | Integrated Project Review and Monitoring Services | Whole Section |  | ● |  |
|  |  | Support for VEC | Financial Audit | Whole Section |  | ● |  |
|  |  |  | Financial Capacity Development | Whole Section |  | ● |  |
| 4 | Project Management, Land Acquisition and Compensation, Contingency and VAT |  |  | Whole Section |  |  | ● |

Source:	Decision No. 2656/QD-BGTVT dated on September 10, 2010

M/D (JICA Appraisal Mission) dated on October 21, 2010, M/D (WB Appraisal Mission) dated on April 21, 2011

Note:	1)	Including other cost, contingency and loan interest and financial fees in each portion

Contract Packaging

The procurement plan for JICA portion including construction contract packaging was approved by MOT in Decision No. 1688/QD-BGTVT dated on July 28, 2011.  As for the WB portion, it was also approved by MOT in Decision No. 1423/QD-BGTVT dated on June 30, 2011.

Afterwards, the Consultant updated the construction contract packaging as follows, and it was approved by MOT in ******** No. ****/**-***** dated on **** **, 2011.

Dividing PKG3 into Ky Lam Bridge (PKG3a) and remaining section (PKG3b) (see A.1.11).

Re-defining the package boundaries based on the modified alignment (see D.3.1(4))

Updated construction contract packaging is shown in Table A.9.

Table A.9   Updated Construction Contract Packaging

| Contract Packaging |  |  |  |  | Lenders |  |
| --- | --- | --- | --- | --- | --- | --- |
| Items | Jurisdiction | No. | Station1) | Length1) | JICA | WB |
| Civil Works | Danang | PKG1 | KM000+000 - KM008+000 | 8.00 km | ● |  |
|  | Quang Nam | PKG2 | KM008+000 - KM016+750 | 8.75 km | ● |  |
|  |  | PKG3a | KM016+750 - KM018+750 | 2.00 km | ● |  |
|  |  | PKG3b | KM018+750 - KM021+000 | 2.25 km | ● |  |
|  |  | PKG4 | KM021+000 - KM032+600 | 11.60 km | ● |  |
|  |  | PKG5 | KM032+600 - KM041+000 | 8.40 km | ● |  |
|  |  | PKG6 | KM041+000 - KM052+000 | 11.00 km | ● |  |
|  |  | PKG7 | KM052+000 - KM064+500 | 12.50 km | ● |  |
|  |  | PKGA1 | KM064+500 - KM081+150 | 16.65 km |  | ● |
|  |  | PKGA2 | KM081+150 - KM099+500 | 18.35 km |  | ● |
|  | Quang Ngai | PKGA3 | KM099+500 - KM109+870 | 10.37 km |  | ● |
|  |  | PKGA4 | KM109+870 - KM124+700 | 14.83 km |  | ● |
|  |  | PKGA5 | KM124+700 - KM139+200 | 14.50 km |  | ● |
|  | Total |  |  | 139.20 km |  |  |
| Electrical/O&M Building/ITS Works and Equipment Provision | All | PKG13 | KM000+000 - KM131+180 | 131.18 km | ● |  |

Source:	******** No. ****/**-***** dated on ********* **, ****

Note:	1)	Based on the modified alignment in D.3.1 Work Item (4) (station and section length are not based on F/S alignment)

Project Implementation Structure

MOT designated VEC as the Project Owner in Decision No. 220/QD-BGTVT dated on January 22, 2010 and also appointed PMU85 as the Project Implementation Agency for the D/D stage in Decision No. 2149/QD-BGTVT dated on September 19, 2011.  As for the construction stage, MOT approved that PMU85 (JICA portion) and PMU1 (WB portion) would be the Project Implementation Units by signing the principle contracts with VEC in Decision No. 2656/QD-BGTVT dated on September 10, 2011.

Project implementation structure is shown in Figure A.8.

Note:	1)	Project Implementation Support for VEC (see Table A.5)

Figure A.8   Project Implementation Structure

Project Implementation Program

The Project Implementation Program (I/P) was agreed among JICA, WB and GOVN during the JICA Appraisal in October, 2010.  However, this program is delayed 11 months at present.

After receiving NTP for the Services, the Consultant updated the Project I/P, and it was approved by MOT in Decision No. **/**-***** dated on ******* **, ****.

Main considerations in updated Project I/P are shown in Table A.10, and updated Project I/P is shown in Figure A.9, respectively.

Table A.10   Main Considerations in Updated Project I/P

| No. | Items | Contents |
| --- | --- | --- |
| 1 | Commencement of Construction Works | The realization for commencing construction works within September 2012 is required by the Minutes |
|  | (1st Priority, within September 2012) | of Contract Negotiation for the Services dated on October 15, 2011. Based on the Consultant’s study, |
|  |  | Ky Lam Bridge was selected as the priority package by design and land acquisition ease; then, PKG3 |
|  |  | was divided into Ky Lam Bridge (PKG3a) and remaining sections (PKG3b). |
| 2 | Construction Period | The construction period of all civil work packages were defined 36 months in the following Decisions: |
|  | (Civil Work Packages) | - MOT Decision No. 1688/QD-BGTVT dated on July 28, 2011 (Procurement Plan, JICA Portion) |
|  |  | - MOT Decision No. 1423/QD-BGTVT dated on June 30, 2011 (Procurement Plan, WB Portion) |
|  |  | Based on the Consultant’s estimate, the construction period for PKG1 (Softground Section), |
|  |  | PKG3a (Ky Lam Bridge) and PKGA5 (incl. Tra Khuc Bridge) were extended to 42 months. |
| 3 | Completion of D/D of Three (3) Packages | Draft D/D of first three (3) packages is required to complete within 6th month by the Minutes of |
|  | (2nd Priority, within 6th month) | Contract Negotiation for the Services dated on October 15, 2011. In consideration of land acquisition |
|  |  | and design ease and fairness among provinces PKG1 and PKGA4 were selected as the priority packages. |

Figure A.9   Updated Project I/P

Outline of the Services

General

This Inception Report (IC/R) is for Consulting Services for Detailed Design for Danang - Quang Ngai Expressway Development Project (the Services) in accordance with the Consulting Services Contract between PMU85 and NK-NE-Chodai-TEC JV (the Consultant) signed on November 15, 2011.

Objectives

The objectives of the Services are to ensure the preparation of D/D and assist VEC/PMU85 in tendering procedures with the most efficient and timely manner to deliver the required outputs in accordance with the Project I/P.

Furthermore, appropriate technology transfers for VEC, PMU85, relevant organizations and key local professional staff are also required as a specific component in the Services to ensure smooth execution of the Project and sustainable development of the expressway network in Vietnam.

Scope

Mode

The Services are carried out by the 2 modes as shown in Table A.11.

Table A.11   Mode of the Services

| No. | Mode | Contents |
| --- | --- | --- |
| 1 | Primary Tasks | Arrangement for managing the Services by the Consultant, who is fully responsible to VEC/PMU85, for |
|  |  | adequacy and quality of the end outputs of the Services assuring duly compliance of the Services |
|  |  | assuring duly compliance of the scope of the Services specified in the Contract. |
| 2 | Assistance Tasks | The Consultant provides technical advice and assistance in carrying out the works to be accomplished |
|  |  | by VEC/PMU85 through the Consultant’s professional ability; however, the Consultant is not responsible |
|  |  | for the end outputs. |

Scope

The documents related to scope of the Services are shown in Table A.12.

Table A.12   Documents related to Scope of the Services

| No. | Stage | Documents | Date Issued |  |  | Ref. in Contract |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Tender | Original RFP | 12 | Feb., | 2010 |  |
| 2 |  | Minutes of Pre-proposal Conference | 26 | Feb., | 2010 |  |
| 3 |  | Clarifications on RFP | 22 | Mar., | 2010 |  |
| 4 |  | Revised RFP (Addendum No.1) | 9 | Apr., | 2010 |  |
| 5 |  | Clarifications on RFP | 22 | Apr., | 2010 |  |
| 6 |  | Clarifications on RFP | 29 | Apr., | 2010 |  |
| 7 |  | Revised RFP (Addendum No.2) | 27 | May, | 2010 | Appendix ** |
| 8 | Proposals | Technical Proposal | 1 | Jun., | 2010 | Appendix ** |
| 9 | Contract Negotiation | Minutes of Contract Negotiation (1st) | 26 | May, | 2011 | Appendix ** |
| 10 |  | Minutes of Contract Negotiation (2nd) | 15 | Oct., | 2011 | Appendix ** |

Work Items

The Consultant established the work items for the Services according to the Technical Proposal, and those are satisfied the required scope of the Services listed in Table A.12.

Summary of work items is shown in Table A.13, and work methodology based on the detailed work items is described in Parts B to F, subsequently.

Table A.13   Summary of Work Items

| Work Items |  |  |  | Ref. Appendix A in Contract |
| --- | --- | --- | --- | --- |
| Part B | Project Management |  |  | Proposed Task |
|  | B.1 | Establish and control practical management system |  | Proposed Task |
| Part C | Previous Studies Review and Establishing Detailed Engineering Design Framework |  |  | 3.2 |
|  | C.1 | Review previous studies |  | 3.2(1) |
|  | C.2 | Establish detailed engineering design framework |  | 3.2(2) |
| Part D | Detailed Engineering Design and Procurement Planning |  |  | 3.3 |
|  | D.1 | Contract Packaging |  | 3.3.1 |
|  |  | D.1.1 | Propose contract packaging | 3.3.1 |
|  | D.2 | Surveys and Investigations |  | 3.3.2 |
|  |  | D.2.1 | Collect relevant data and documents | 3.3.2(1) |
|  |  | D.2.2 | Conduct topographic survey | 3.3.2(2)(i), 3.5 |
|  |  | D.2.3 | Conduct hydrological survey and analysis | 3.3.2(2)(ii) |
|  |  | D.2.4 | Conduct geotechnical and geological investigations | 3.3.2(2)(iii) |
|  |  | D.2.5 | Conduct material source survey | 3.3.2(2)(iv) |
|  |  | D.2.6 | Conduct relevant facilities survey | 3.3.2(2)(v) |
|  |  | D.2.7 | Review traffic forecasting and conduct baseline surveys | 3.3.2(2)(vi) |
|  |  | D.2.8 | Conduct independent land valuation survey | 3.3.2(2)(vii) |
|  |  | D.2.9 | Conduct environmental and social surveys | 3.3.2(2)(viii) |
|  | D.3 | Civil Engineering Design |  | 3.3.3 |
|  |  | D.3.1 | Prepare basic design of civil structures | 3.3.3 |
|  |  | D.3.2 | Prepare detailed engineering design of civil structures | 3.3.3 |
|  | D.4 | O&M Plan and Design |  | 3.3.5 |
|  |  | D.4.1 | Prepare institutional and administrative arrangement plan | 3.3.5 |
|  |  | D.4.2 | Prepare O&M plan | 3.3.5 |
|  |  | D.4.3 | Prepare basic design of O&M buildings | 3.3.5 |
|  | D.5 | ITS Plan and Design |  | 3.3.4 |
|  |  | D.5.1 | Prepare ITS plan | 3.3.4(1) |
|  |  | D.5.2 | Prepare basic design of ITS facilities | 3.3.4(2) |
|  | D.6 | Electrical Facilities Design |  | Proposed Task |
|  |  | D.6.1 | Prepare detailed engineering design of electrical facilities | Proposed Task |
|  | D.7 | Public Utilities Relocation Plan |  | Proposed Task |
|  |  | D.7.1 | Prepare relocation plan of public utilities | Proposed Task |
|  | D.8 | Safeguards |  | 3.3.6, Annex A, Annex B |
|  |  | D.8.1 | Assist in updating EIA and EMP | 3.3.6, Annex A |
|  |  | D.8.2 | Assist in preparing and enforcing CPCSR | 3.3.6, Annex B |
|  | D.9 | Construction Planning |  | 3.3.7 |
|  |  | D.9.1 | Prepare construction plan | 3.3.7 |
|  | D.10 | Project Cost Estimate |  | 3.3.8 |
|  |  | D.10.1 | Estimate Project cost | 3.3.8 |
|  | D.11 | Procurement Documents |  | 3.3.9 |
|  |  | D.11.1 | Prepare procurement documents | 3.3.9 |
|  | D.12 | Project Implementation Program |  | 3.3.10 |
|  |  | D.12.1 | Prepare Project I/P | 3.3.10 |
| Part E | Procurement Assistance |  |  | 3.4 |
|  | E.1 | Assist in tendering procedures |  | 3.4 |
| Part F | Technology Transfer |  |  | 3.6 |
|  | F.1 | Provide training to VEC, PMU85 and relevant organizations |  | 3.6 |
|  | F.2 | Provide training to key local professional staff |  | Proposed Task |

Work Schedule and Reporting Plan

The Services is 14 months in total including the D/D period (12 months).  The D/D schedule is divided into the following 3 priorities to meet the requirements in the Project I/P (see A.1.11).

1st Priority Package	:	Complete D/D within 4th months (PKG3a)

2nd Priority Packages	:	Complete D/D within 6th months (PKG1 and PKGA4)

Non-priority Packages	:	Complete D/D within 12th months (Other PKGs, 10 to 12 months)

The Services was officially commenced from December 1, 2011; however, some work items were commenced in advance from July 15, 2011 as the prior works in accordance with 4th Para, 2. Implementation Plan on the Minutes of Contract Negotiation (1st) signed on 26 May, 2011.

Work schedule and reporting plan is shown in Figure A.10, and baseline schedule for progress monitoring based on the detailed work items is shown in Appendix *, respectively.

Figure A.10   Work Schedule and Reporting Plan (1/5)

Figure A.10   Work Schedule and Reporting Plan (2/5)

Figure A.10   Work Schedule and Reporting Plan (3/5)

Figure A.10   Work Schedule and Reporting Plan (4/5)

Figure A.10   Work Schedule and Reporting Plan (5/5)

Organization and Staffing

Consultant’s Organization

Joint Venture

The Consultant Team consists of NK-NE-Chodai-TEC JV, and jointly and severally responsible for the Services among the JV firms.

Consultant Team

The Consultant Team divides into 6 teams and 4 supporting groups as described below.

Organization structure of the Consultant Team is shown in Figure A.11.

Engineering Group

Management Team

The Management Team is responsible for managing the Services, and all communications in the Services are exchanged through the team.  In the team, we organize the core team which consists of the representatives of each team and secure the consistent communication among the teams.

Civil Design Team

The Civil Design Team is responsible for planning and designing the civil structures and consists of the civil design management, design group and the survey group.

The Civil Design Management is responsible for establishing the design criteria and conditions, standard design of road accessories, culverts and bridges, and supervising the works of the design and survey groups, preparing the technical specifications and assisting the tendering procedures.

The Design Group is responsible for preparing the basic design and detailed engineering design, and consists of two (2) sections and each design fields.

O&M and ITS Team

The O&M and ITS team is responsible for preparing the O&M and ITS plan, basic design of the O&M buildings and ITS facilities, and detailed engineering design of the electrical facilities including the preparation of the technical specifications in the bidding documents.

Cost and Document Team

The Cost and Document Team is responsible for preparing the construction plan, engineer’s cost estimate, procurement plan and documents, and assisting the tendering procedures.

Environmental Team

The Environmental Team works with the relevant organizations for updating EIA and EMP, preparing and enforcing CPCSR, and preparing the requirements for EMP in the bidding documents.

Training Team

The Training Team is responsible for identifying the training needs with VEC, PMU85 and relevant organizations, and preparing and coordinating the training materials in cooperation with the engineers/specialists of the respective fields assign in other teams.

Supporting Group

The Supporting Group assists to the Key Professional Staff in daily works.  The Group consists of four (4) teams, and those are allocated three (3) teams in Danang Main Office and one (1) in Hanoi Sub-office (see A.2.5(1)(d)).

Figure A.11   Organization Structure of the Consultant Team

Home Office Support

NK, the prime consultant of JV firms has the home office support system and utilizes the technical, managerial and operational support including the review and verification of design in the Services.

Conceptual image of NK’s home office support system is shown in Figure A.12

Figure A.12   Conceptual Image of NK’s Home Office Support System

Office Arrangement

PMU85 organized the Project Site Management Department (PSMD) in his Danang office, and Danang CPC, Quang Nam and Quang Ngai PPCs and the Project site are also located in/near Danang city.  Therefore, the Consultant set up the Main Office in Danang city.

On the other hand, the Consultant outsources the D/D of all interchanges and bridges (excluding Ky Lam Bridge, 1st Priority Package) to the Vietnamese sub-consultants in Hanoi city (see A.2.5(2)(a)).  For supervising the outsourcing works, the Consultant set up the Sub-office in Hanoi city.

Office arrangement for Consultant’s team is shown in Table A.14.

Table A.14   Office Arrangement for Consultant’s Team

| No. | Office | Period |  | Address | Tel | Fax |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Danang Main Office | 14 months | (Dec. 2011 to Jan. 2013) | ****************************** | ************** | ************** |
| 2 | Hanoi Sub-office | 8 months | (Apr. 2011 to Nov. 2012) | To be established |  |  |

Staffing

Staffing and Task Assignment

The Consultant established the staffing and task assignment in consistent with the work schedule and reporting plan described in A.2.4.

It is noted that the Consultant outsources the D/D of all interchanges and bridges (excluding Ky Lam Bridge, 1st Priority Package) to the Vietnamese sub-consultants in Hanoi city to minimize the personnel inputs and shorten the design period.

Staffing and task assignment matrix for key professional staff are shown in Table A.15.

Staffing Schedule

We take into account the staffing for the key professional staff as follows:

Arrange the staff who worked with VEC/PMU85 in the past studies;

Arrange the staff who worked together with other team members in the past;

Time schedule for key international professional staff, key local professional staff and supporting staff are shown in Tables A.16 to A.18, respectively.

Table A.15   Task Assignment Matrix for Key Professional Staff

Table A.16   Time Schedule for Key International Professional Staff

Table A.17   Time Schedule for Key Local Professional Staff (1/2)

Table A.17   Time Schedule for Key Local Professional Staff (2/2)

Table A.18   Time Schedule for Supporting Staff