|  | Ministry of Transport |  |  |
| --- | --- | --- | --- |
|  | Vietnam Expressway Corporation |  |  |
|  | Project Management Unit No. 85 |  |  |

IDA Credit	No.	:	3843-VN

Project ID	No.	:	P106235

Consulting Services

for

Detailed Design for Danang - Quang Ngai Expressway Development Project

Insert Project Perspective View

(Under Preparation by Mr. Lam)

Inception Report (Draft)

December **, 2011

| The Joint Venture of |  |
| --- | --- |
|  | THAI ENGINEERING CONSULTANTS CO., LTD. |

Ref. No.	:	DQEDD-PMU-xx-11

Date	:	December **, 2011

Mr. Nguyen Tien Ha

Project Manager

Project Management Unit No. 85 (PMU85)

Fax No. : +84-(38)3834705

Subject:		Submission of Inception Report (IC/R)

Dear Sir,

In accordance with Appendix B - Reporting Requirements in the Contract for Consulting Services, we would like to submit fifteen (15) copies of the Inception Report (IC/R) in English and Vietnamese versions, respectively.

Sincerely yours,

Ichizuru ISHIMOTO

Project Manager/Team Leader

c.c.	:	Office Copy

Encl.	:	Inception Report (English: 15 copies, Vietnamese: 15 copies)

Project Location Map

File	:	02_project location map_mae_111004.xlsx

Size	:	A4 Size

Project Route Map

File	:	03_project route map_mae_111004.pdf

Size	:	A3 Long Size

Letter of Submission

Project Location Map

Project Route Map

Table of Contents

Abbreviations

Main Part

Part A	General 		1

A.1	Project Features 		1

A.1.1	Background 		1

A.1.2	Recent Updates 		2

A.1.3	Location 		3

A.1.4	Objectives 		3

A.1.5	Component 		4

A.1.6	Safeguards 		7

A.1.7	Project Cost 		8

A.1.8	Funding Arrangement 		8

A.1.9	Contract Packaging 		9

A.1.10	Project Implementation Structure 		9

A.1.11	Project Implementation Program 		10

A.2	Outline of the Services 		11

A.2.1	General 		11

A.2.2	Objectives 		11

A.2.3	Scope 		11

A.2.4	Work Schedule and Reporting Plan 		12

A.2.5	Organization and Staffing 		18

Part B	Project Management 		25

B.1	Establish and Control Practical Project Management System 		25

Part C	Previous Studies Review and Establishing Detailed Engineering Design Framework 		27

C.1	Review Previous Studies 		27

C.2	Establish Detailed Engineering Design Framework 		27

Part D	Detailed Engineering Design and Procurement Planning 		28

D.1	Contract Packaging 		28

D.1.1	Propose Contract Packaging 		28

D.2	Surveys and Investigations 		28

D.2.1	Collect Relevant Data and Documents 		28

D.2.2	Conduct Topographic Survey 		28

D.2.3	Conduct Hydrological Survey and Analysis 		31

D.2.4	Conduct Geotechnical and Geological Investigations 		33

D.2.5	Conduct Material Source Survey 		35

D.2.6	Conduct Relevant Facilities Survey 		35

D.2.7	Review Traffic Forecasting and Conduct Baseline Surveys 		36

D.2.8	Conduct Independent Land Valuation Survey 		36

D.2.9	Conduct Environmental and Social Surveys 		37

D.3	Civil Engineering Design 		37

D.3.1	Prepare Basic Design of Civil Structures 		37

D.3.2	Prepare Detailed Design of Civil Structures 		37

D.4	O&M Plan and Design 		41

D.4.1	Prepare Institutional and Administrative Arrangement Plan 		41

D.4.2	Prepare O&M Plan 		41

D.4.3	Prepare Basic Design of O&M Buildings 		43

D.5	ITS Plan and Design 		43

D.5.1	Prepare ITS Plan 		43

D.5.2	Prepare Basic Design of ITS Facilities 		43

D.6	Electrical Facilities Design 		44

D.6.1	Prepare Detailed Engineering Design of Electrical Facilities 		44

D.7	Public Utilities Relocation Plan 		44

D.7.1	Prepare Relocation Plan of Public Utilities 		44

D.8	Safeguard 		45

D.8.1	Assist in Updating EIA and EMP 		45

D.8.2	Assist in Preparing and Enforcing CPCSR 		45

D.9	Construction Planning 		47

D.9.1	Prepare Construction Plan 		47

D.10	Project Cost Estimate 		47

D.10.1	Estimate Project Cost 		47

D.11	Procurement Documents 		48

D.11.1	Prepare Procurement Documents 		48

D.12	Project Implementation Program 		48

D.12.1	Prepare Project Implementation Program 		48

Part E	Procurement Assistance 		49

E.1	Assist in Tendering Procedures 		49

Part F	Technology Transfer 		50

F.1	Provide Training to VEC, PMU85 and Relevant Organizations		50

F.2	Provide Training to the Key Local Professional Staff 		51

Appendix

Appendix	1	:	Terms of Reference (Appendix A in the Contract)

Appendix	2	:	Project Management Plan

Appendix	3	:	Baseline Schedule for Progress Monitoring (MS Project)

Appendix	4	:	List of Bridges (Based on F/S-2010)

Appendix	5	:	List of Culverts (Based on F/S-2010)

Abbreviations

AIDS	:	Acquired Immune Deficiency Syndrome

AM	:	Ante Meridiem

B/D	:	Basic Design

BL	:	Building

BOT	:	Build-Operate-Transfer

BP	:	Beginning Point

B/Q	:	Bill of Quantities

BR	:	Bridge

CARB	:	Compensation, Assistance and Resettlement Boards

CB	:	Culvert Box

CDM	:	Civil Design Management

CID	:	Civil Design Team

COD	:	Cost and Document Team

COR	:	Core Team

COS	:	Cost Estimate

CP	:	Culvert Pipe

CPC	:	City People’s Committee

CPCSR	:	Comprehensive Plan on Compensation, Support and Resettlement

C/S	:	Construction Supervision

CU	:	Triaxial Compression Test

Cv	:	Consolidation Test

DARD	:	Department of Agriculture and Rural Development

D/D	:	Detailed Engineering Design

DE	:	Deep Excavation

DEG	:	Design Group

DMS	:	Detailed Measurement Survey

DOC	:	Document

DOFPP	:	Department of Fire Prevention and Protection

DOLA	:	Department of Land Administration

DONRE	:	Department of Natural Resources and Environment

DOT	:	Department of Transport

DOTP	:	Department of Traffic Office

DPC	:	District People’s Committee

DRC	:	District Resettlement Committee

DRD	:	Drainage Design

ED	:	Evaluation Department

EIA	:	Environmental Impact Assessment

EID	:	Electrical Facility and Intelligent Transport Systems Design

EMP	:	Environmental Management Plan

ENV	:	Environmental Team

EOO	:	Expressway Operation Office

EP	:	Ending Point

ER	:	Existing Road

ESCRD	:	Environmental and Social Considerations Review Division

ETC	:	Electric Toll Collection

EVN	:	Electricity of Vietnam

FIDIC	:	International Federation of Consulting Engineers

FO	:	Flyover

F/S	:	Feasibility Study

GOVN	:	Government of Vietnam

GPS	:	Global Positioning System

GTD	:	Geotechnical Design

GTS	:	Geotechnical Survey

HCMC	:	Ho Chi Minh City

HDS	:	Hydrological Survey

HE	:	High-embankment

HEC-RAS	:	Hydrologic Engineering Centers River Analysis System, US Army Corps of Engineer

HIDO	:	Highway Industry Development Organization, Japan

HIV	:	Human Immunodeficiency Virus

HVL	:	High-voltage Line

IBRD	:	International Bank for Reconstruction and Development

IC	:	Interchange

ICB	:	International Competitive Bidding

ICD	:	Interchange Design

IC/R	:	Inception Report

ID	:	Identification

IDA	:	International Development Association

I/P	:	Implementation Program

IRB	:	Interchange Rampway Bridge

IS	:	Intersection

ITS	:	Intelligent Transport Systems

JBIC	:	Japan Bank for International Cooperation

JEHDRA	:	Japan Expressway Holding and Debt Repayment Agency

JETRO	:	Japan External Trade Organization

JICA	:	Japan International Cooperation Agency

JV	:	Joint Venture

L/A	:	Loan Agreement

LOS	:	Level of Services

LRB	:	Large River Bridge

MBD	:	Major Bridges Design

M/D	:	Minutes of Discussion

MEX	:	Metropolitan Expressway Co., Ltd., Japan

MGT	:	Management Team

ML	:	Maine Line

MLIT	:	Ministry of Land, Infrastructure, Transport and Tourism, Japan

MLS	:	Material Source Survey

MOF	:	Ministry of Finance

MOND	:	Ministry of National Defense

MONRE	:	Ministry of Natural Resources and Environment

MOPS	:	Ministry of Public Security

MOT	:	Ministry of Transport

MRB	:	Major River Bridge

MS	:	Microsoft

NE	:	Nippon Engineering Consultants Co., Ltd., Japan

NEE	:	Normal Embankment and Excavation

NEXCO	:	Nippon Expressway Company Limited, Japan

NH	:	National Highway

NK	:	Nippon Koei Co., Ltd., Japan

NTP	:	Notice to Proceed

OAM	:	Operation and Maintenance

OED	:	Operations Evaluation Department

O&M	:	Operation and Maintenance

OMI	:	Operation and Intelligent Transport Systems Team

OP	:	Overpass

ORB	:	Other River Bridge

ORSE	:	Organization for Road System Enhancement, Japan

PA	:	Parking Area

PAP	:	Project Affected People

PC	:	People’s Committee

PIARC	:	Permanent International Association of Road Congresses

PIS	:	Project Implementation Support for Vietnam Expressway Corporation

PKG	:	Package

PM	:	Prime Minister

PM	:	Post Meridiem

PMBOK	:	Project Management Body of Knowledge

PMU	:	Project Management Unit

PPC	:	Provincial People’s Committee

P/Q	:	Pre-qualification

PSMD	:	Project Site Management Department

PTC2	:	Power Transmission Company No. 2

PVD	:	Pavement Design

QACU	:	Quality Assurance and Compliance Unit

QA/QC	:	Quality Assurance and Quality Control

RAP	:	Resettlement Action Plan

RB	:	River Bridge

RD	:	Roadway

RDD	:	Road Design

RES	:	Resettlement

RFP	:	Request for Proposals

RNIP	:	Road Network Improvement Project

ROW	:	Right of Way

RRD	:	Revetment and River Bed Protection Design

SA	:	Service Area

SAE	:	Social and Environmental

SB	:	Stream Bridge

SED	:	Section Design

SES	:	Socio-economic Survey

SG	:	Softground

SPG	:	Supporting Group

SPT	:	Standard Penetration Test

T/A	:	Technical Assistance

TB	:	Toll Barrier

TEC	:	Thai Engineering Consultants Co., Ltd., Thailand

TEDI	:	Transport Engineering Design Incorporated

TFD	:	Bridge Temporary Facility Design

TG	:	Toll Gate

TMC	:	Traffic Management Center

TN	:	Tunnel

TND	:	Tunnel Design

TOR	:	Terms of reference

TPO	:	Toll Plaza Office

TPS	:	Topographic Survey

TRG	:	Training Team

TRS	:	Traffic Survey

USD	:	United States Dollars

UU	:	Triaxial Compression Test

VAT	:	Value Added Tax

VEC	:	Vietnam Expressway Corporation

VD	:	Viaduct

VICS	:	Vehicle Information and Communication System

VIETTEL	:	Vietnam Military Electronic and Telecommunications Corporation

VND	:	Vietnamese Dong

VNPT	:	Vietnam Posts and Telecommunications Group

VNR	:	Vietnam National Railway

VST	:	Vane Shear Test

WB	:	The World Bank

WT	:	Waterway

Main Part

General

Project Features

Background

The preparation of Pre-F/S for the Project under BOT scheme was approved by MOT in Decision No. 2654/QD-BGTVT dated on September 11, 2000.  The Pre-F/S report was prepared by PMU85 and approved by the Prime Minister in his letter No. 493/CP-CN dated on April 21, 2003.  Continually, the preparation of F/S was approved by MOT in Decision No. 134/QD-BGTVT dated on January 14, 2004.  The F/S report was also prepared by PMU85 and submitted to MOT in his letter No. 514/BQL-KHDA2 dated on May 11, 2005.  However, this BOT scheme Project did not materialize because of funding sources were not identified at that time.

Two (2) years later, the Project was approved as one (1) of the top priority projects in transport sector by GOVN in Decision No. 412/QD-TTg dated on April 11, 2007.  For carrying forward the Project, GOVN requested JETRO to assist a further study expecting materialization of the Project by a JBIC (currently JICA) loan scheme in June 2007.  JETRO conducted the study and submitted the study report to MOT on April 28, 2008.

In parallel with the JETRO study, WB declared GOVN to be eligible for the IBRD loan in November, 2007 and the Project was identified as the top priority use for the loan.  After submission of the JETRO study report, WB undertook the identification missions in April and June, 2008 and confirmed necessity of updating the JETRO study to meet his requirements and decided to allocate the fund from on-going RNIP (IDA Credit No.: 3843-VN) to conduct the WB supplemental study.  The study report was prepared by PMU85 and submitted to MOT in his letter No. 551/BQl-KHDA2 dated on June 13, 2009.

In response to the supplemental study, WB engaged an international consultant and undertook the WB appraisal study.  In the appraisal study, WB modified the alignment at three (3) sections by taking into consideration social and environmental issues.  Based on the modified alignment, TEDI updated the supplemental study and submitted as the draft F/S report to MOT in April, 2010.  The draft F/S report was also finalized by TEDI in accordance with the MOT appraisal report No. 6188/BGTVT-KHDT dated on September 8, 2011 and submitted by VEC as the F/S report to MOT in September 2010.  The F/S report was approved by MOT in Decision No. 2656/QD-BGTVT dated on September 10, 2010.

In parallel with the F/S approval, WB agreed to allocate the fund from RNIP for D/D and the Prime Minister allowed commencing the procurement of D/D consultant.  Through the procurement procedures, NK-NE-Chodai-TEC JV (the Consultant) was selected and signed the contract with PMU85 on November 15, 2011.  Currently, PMU85 issued NTP in his letter No. 1612/PMU85-PP2 dated on November 17, 2011 and D/D was officially commenced from December 1, 2011.

Outline of the Project background is shown in Figure A.1.

Figure A.1   Outline of the Project Background

Recent Updates

Main Updates after Proposals Submission

The Consultant submitted the proposals for Consulting Services for Detailed Design for Danang - Quang Ngai Expressway Development Project (the Services) on June 1, 2010 based on the draft F/S report distributed by VEC/PMU85 in the procurement stage (see A.1.1).  Afterward, various documents for the Project have been issued and updated by the relevant organizations.

Main updates after proposals submission are shown in Table A.1.

Table A.1   Main Updates after Proposals Submission

| No. | Items |  | Issued by | Subject (Summary) | Ref. No. | Date Issued |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | F/S | Approval | MOT | F/S Approval | Decision No. 2656/QD-BGTVT | 10 | Sep., | 2010 |
| 2 |  |  | GOVN Office | Investment Approval and Assigning MOT for F/S Approval | Document No. 4684/VPCP-KTN | 7 | Jul., | 2010 |
| 3 |  | Appraisal | MOT | F/S Appraisal Report | Document No. 6188/BGTVT-KHDT | 8 | Sep., | 2010 |
| 4 |  | Submission | VEC | Submission of F/S Report | Letter No. 384/TTr-VEC | 7 | Sep., | 2010 |
| 5 |  |  |  |  | Letter No. 160/TTr-VEC | 30 | Jul., | 2010 |
| 6 | Safeguards | EIA | MONRE | Approval for Supplemental EIA | Decision No. 2046/QD-BTNMT | 29 | Oct., | 2010 |
| 7 |  | RAP | PM | Approval for RAP (Based on F/S Alignment) | Decision No. 442/TTg-KTN | 23 | Mar., | 2011 |
| 8 | Funding | JICA Loan | GOVN-JICA | L/A | ----- | 15 | Jun., | 2011 |
| 9 |  |  |  | M/D (L/A) | ----- | 17 | Jan., | 2011 |
| 10 |  |  |  | M/D (Appraisal Mission) | ----- | 21 | Oct., | 2010 |
| 11 |  | WB Loan | GOVN-WB | M/D (Appraisal Mission) | ----- | 21 | Apr., | 2011 |
| 12 |  | GOVN | MOT | Approval for Adjustment of Project Investment Structure | Decision No. 666/QD-BGTVT | 6 | Apr., | 2011 |
| 13 |  |  | GOVN Office | VEC’s Responsibilities (Borrowing/Paying Loan) | Document No. 4684/VPCP-KTN | 7 | Jul., | 2010 |
| 14 |  |  | MOF |  | Document No. 695/BTC-QLN | 13 | Aug., | 2010 |
| 15 | Procurement | JICA Portion | MOT | Approval for Procurement Plan (JICA Portion) | Decision No. 1688/QD-BGTVT | 28 | Jul., | 2011 |
| 16 |  | WB Portion | MOT | Approval for Procurement Plan (WB Portion) | Decision No. 1423/QD-BGTVT | 30 | Jun., | 2011 |
| 17 |  | GOVN | MOND | Executing Plan (Searching and De-mining Bombs) | Decision No. 1286/QD-BQP | 20 | Apr., | 2011 |
| 18 | Project Implementation Structure |  | MOT | Assigning PMU85 for Implementation Agency in D/D | Decision No. 2149/QD-BGTVT | 19 | Sep., | 2011 |
| 19 | Project Implementation Program |  | PMU85 | Commencement of Const. Works in 3rd Quarter, 2012 | Letter No. 1816/PMU85-PP2 | 22 | Sep., | 2011 |
| 20 | Request from Quang Nam PPC |  | Quang Nam | Agreement for Re-alignment/Request for Additional IC | Circular No. 346/TB0UBND | 13 | Sep., | 2011 |
| 21 | (Additional IC and Re-alignment) |  |  | Request for Additional IC and Re-alignment Study | Document No. 2107/UBND-KTN | 17 | Jun., | 2011 |
| 22 |  |  | MOT | F/S Approval (including No.23 and 24 below) | Decision No. 2656/QD-BGTVT | 10 | Sep., | 2010 |
| 23 |  |  |  | Notice (for No.24 below) | Notice No. 325 | 6 | Aug., | 2010 |
| 24 |  |  | Quang Nam | Comments on Additional IC and Re-alignment | Document No. 1732/UBND-KTN | 31 | May, | 2010 |

Issues postponed to D/D Stage

The MOT Appraisal Report, Document No. 6188/BGTVT-KHDT dated on September 8, 2010 mentioned that MOT/VEC received the comments on the draft F/S report from relevant organizations and basically modified those items according to their opinions in the F/S report.  However, in Paragraph IV.7, it was also mentioned that some technical issues were unsolved in the F/S stage and those issues would be postponed to the subsequent D/D stage.

Issues postponed to D/D stage are shown in Table A.2.

Table A.2   Issues postponed to D/D Stage

| No. | Items | Issues postponed to D/D Stage |
| --- | --- | --- |
| 1 | Alternative Route | Study and adjust the section passing Duc Bo Shooting field (KM070 – KM080) in Quang Nam Province according to Notice No. 325 |
|  |  | dated on August 6, 2010 issued by MOT |
| 2 | Inundation Analysis | Study more carefully and define exactly where to construct viaducts and drainage culverts to ensure the flood discharge |
| 3 | Requirement for River Bridges | Discuss and agree with localities on hydrological and navigational requirement for river bridges other than four (4) major river bridges |
|  |  | which already agreed with the localities in the F/S stage |
| 4 | Clearance with HVL (500kV) | Discuss and agree with EVN on countermeasures for insufficient vertical clearance between the Project road and existing HVL (500kV) |
|  |  | at two (2) locations (KM004+431 and KM065+959) |
| 5 | Additional Overpass | Discuss and agree with VNR on intersecting mode (at grade or grade separation) at the intersection between the Project road and |
|  |  | existing North-South Railway at KM135+270 (finally, an overpass with 492 m length was approved in the MOT F/S Approval) |
| 6 | ITS | Check in term of technical approach and standards, appropriate investment cost and suitable with current conditions of Vietnam |

Source: MOT Appraisal Report, Document No. 6188/BGTVT-KHDT dated on September 8, 2010

Location

The Project road is a part of the North-South Expressway located in parallel with the existing NH1A and North-South Railway and passing through Danang city, Quang Nam and Quang Ngai provinces in the central region.  The road starts at the intersection of the Danang Bypass and NH14B in Danang city and ends at the connecting point with the planned City Ring Road at existing NH1A in Quang Ngai province.  The major socio-economic developments along the Project road are the Chu Lai Open Economic Zone in Quang Nam province and the Dung Quat Industrial Zone in Quang Ngai province.  As for the cultural properties, the Hoi An Ancient Town and My Son Sanctuary registered with the world heritage (cultural heritage) are existed along the Project road.

Project location map is shown in Figure A.2.

Figure A.2   Project Location Map

Objectives

The main objectives of the Project are to enhance travel efficiency and safety by constructing an expressway from Danang to Quang Ngai, and contributing to economic growth in the central region.

Outline of Project framework and operating effectiveness indicators established by WB and VEC are shown in Figure A.3 and Table A.3, respectively.

Figure A.3   Outline of Project Framework

Table A.3   Operating Effectiveness Indicators established by WB and VEC

| No. | Area/Sections | Quantitative Indicators |  | Baseline | Target |
| --- | --- | --- | --- | --- | --- |
| 1 | Between Danang and Quang Ngai | Travel time | 10 ton freight vehicles | 233 minutes | 20 % reduction |
| 2 |  |  | Passenger vehicles | 158 minutes | 20 % reduction |
| 3 |  | Coefficient of variation (travel time) | 10 ton freight vehicles | 0.19 | 10 % reduction |
| 4 |  |  | Passenger vehicles | 0.08 | 10 % reduction |
| 5 |  | Traffic accidents (no. of fatalities) |  | 185 nos./year | 10 % reduction |

Source:	M/D (WB Appraisal Mission) dated on April 21, 2011

Note:	JICA also agreed to establish the indicators in line with WB in M/D (JICA Appraisal Mission) dated on October 21, 2010

Component

Expressway Construction and O&M Equipment Provision

The main Project components are the expressway construction and O&M equipment provision.

Main features of expressway construction and O&M equipment provision are shown in Table A.4, and Project facilities plan is shown in Figure A.4, respectively.

Table A.4   Main Features of Expressway Construction and O&M Equipment Provision

| No. | Items | Main Features |  | Ref. in TOR |
| --- | --- | --- | --- | --- |
| 1 | Road Length | 139.52 km |  | Component A |
|  |  |  | By Road Class: Expressway section: 131.5 km, Linking road section: 8.02 km | (TOR 1(1)) |
|  |  |  | By Jurisdiction: Danang city: 8.0 km, Quang Nam province: 92.0 km, Quang Ngai province: 39.52 km |  |
|  |  |  | Beginning Point (BP): Intersection of the existing Danang bypass and NH14B in Danang city |  |
|  |  |  | Ending Point (EP): Connecting point with the planned city ring road at the existing NH1A (KM1063+700) in Quang Ngai province |  |
| 2 | Road Classification | Expressway: Type A, Class 120, Linking Road: Class III, Delta |  |  |
| 3 | Design Speed | Expressway: 120 km/hr (Tunnel section: 100 km/hr), Linking Road: 80 km/hr |  |  |
| 4 | Nos. of Lane | 4 lanes (Ultimate stage: Widened to 6 lanes (see Figure A.4)) |  |  |
| 5 | Road With | Expressway: Road and Bridge sections: 26.0 m, Tunnel section: 2@12.75 m=25.5 m, Linking Road: 12.0 m |  |  |
| 6 | Design Frequency | Expressway: 1 %, Linking Road: 4 % |  |  |
| 7 | Bridge | 131 bridges (L=15,486.85 m)1) |  |  |
|  |  |  | Large River Bridge (LRB, L>100 m): 20 bridges (L=5,687.55 m)2), Other River Bridge (ORB, L<100 m): 10 bridges (L=603.85 m), |  |
|  |  |  | Stream Bridge (SB): 8 bridges (L=354.90 m), Canal Bridge (CB): 18 bridges (L=666.00 m), |  |
|  |  |  | Viaduct (VD): 21 bridges (L=3,073.45 m), Overpass (OP): 23 bridges (L=1,186.80 m)1), |  |
|  |  |  | Interchange Rampway Bridge (IRB): 12 bridges (L=1,662.30 m), Flyover (FO): 19 bridges (L=2,252.00 m) |  |
| 8 | Major River Bridge | 4 bridges (L=2,670.00 m) |  |  |
|  |  |  | Thu Bong River (KM017+662): Ky Lam Bridge (L=962.00 m), Ba Ren River (KM020+185): Chiem Son Bridge (L=410.00 m), |  |
|  |  |  | Tra Bong River (KM109+320): Tra Bong Bridge (L=452.00 m), Tra Khuc River (KM125+700): Tra Khuc Bridge (L=846.00 m) |  |
| 9 | Tunnel | 1 tunnel (KM022+900, L=2@540 m) |  |  |
| 10 | Culvert | 375 culverts |  |  |
|  |  |  | Culvert Box: 188 culvert boxes (106 roadway culverts and 82 waterway culverts), Culvert Pipe: 187 culvert pipes |  |
| 11 | Softground | Approximately 3.6 km |  |  |
| 12 | Interchange | 9 interchanges |  |  |
| 13 | Frontage Road | Approximately 59.7 km |  |  |
| 14 | Earth Works | Soil excavation: 10,000,000 m3, Rock excavation: 1,000,000 m3, Filling: 24,000,000m3 |  |  |
| 15 | Electrical Facilities | Power supply, road lighting, tunnel ventilation and safety facilities |  | Component B |
| 16 | ITS | Traffic management, toll collection3) and communication systems |  | (TOR 1(2)) |
| 17 | O&M Building | 26 locations (see Figure A.4) |  | Component C |
|  |  |  | Traffic Management Center (TMC): 1 location, Expressway Operation Office (EOO): 1 location, Toll Plaza Office (TPO): 9 locations, | (TOR 1(3)) |
|  |  |  | Toll Barrier (TB): 2 locations, Toll Gate (TG): 7 locations, Service Area (SA): 2 locations, Parking Area (PA): 4 locations |  |
| 18 | O&M Equipment | O&M vehicles, spare parts, maintenance equipment and consumables |  |  |

Source:	MOT F/S Approval, Decision No. 2656/QD-BGTVT dated on September 10, 2010 (modified discrepancies with the F/S report by the Consultant)

Note:	1)	Including the additional overpass with 492 m at KM135+270 (see No.5, Table A.2)

2)	Including 4 major river bridges (see No.8)

3)	Including electric toll collection system in accordance with MOT Notice No.94/TB-BGTVT dated March 10, 2009

Source:	MOT F/S Approval, Decision No. 2656/QD-BGTVT dated on September 10, 2010 (modified discrepancies with the F/S report by the Consultant)

Note:	1)	Confirmed with the F/S Consultant (not mentioned in the MOT F/S Approval, Decision No. 2656/QD-BGTVT dated on September 10, 2010)

Figure A.4   Project Facilities Plan

Consulting Services

The overall consulting services for the Project are composed of the Detailed Engineering Design (D/D), Construction Supervision (C/S) and Project implementation support for VEC.  The consulting services in this contract (the Services) cover D/D only, without C/S and Project implementation support.

Main scope of overall consulting services is shown in Table A.5.

Table A.5   Main Scope of Overall Consulting Services

| No. | Items |  | Main Scope |
| --- | --- | --- | --- |
| 1 | Detailed Engineering Design (D/D) |  | - Previous studies review and establishing D/D framework |
|  |  |  | - D/D and procurement planning (incl. B/D of O&M/ITS package) |
|  |  |  | - Procurement assistance (civil work packages) |
| 2 | Construction Supervision (C/S) |  | - B/D and procurement documents review (O&M/ITS package) |
|  |  |  | - Procurement assistance (O&M/ITS package) |
|  |  |  | - D/D review (civil work packages) |
|  |  |  | - C/S (incl. internal social, environmental and resettlement monitoring) |
|  |  |  | - Assisting in establishment of an O&M unit (incl. capacity development) |
|  |  |  | - Assisting in defect liability inspections |
| 3 | Project Implementation | Integrated Project Review and | - D/D appraisal |
|  | Support for VEC | Monitoring Services | - Traffic safety audit |
|  |  |  | - Construction quality inspection |
|  |  |  | - Social and environmental external monitoring |
|  |  |  | - Resettlement external monitoring |
|  |  |  | - Overall project monitoring and evaluation |
|  |  |  | - Expressway user information and HIV/AIDS campaign |
|  |  | Financial Audit | - Annual project financial external audit |
|  |  | Financial Capacity Development | - Financial capacity development for VEC |

Source:	Decision No. 1423/QD-BGTVT dated on June 30, 2011, Decision No. 1688/QD-BGTVT dated on July 28, 2011

M/D (JICA Appraisal Mission) dated on October 21, 2010, M/D (WB Appraisal Mission) dated on April 21, 2011

Establishment of an O&M Unit

The O&M framework of the expressway section is under consideration.  Based on the F/S report, the estimated financial return by operating the expressway is low in early stage because of the forecasted traffic volume is small.  Therefore, O&M concessions are not attractive for private sectors, and the expressway is expected to operate by an O&M unit to be established under VEC in early stage.

Expected O&M framework for Project road (expressway section) is shown in Figure A.5.

Note:	1)	Various administrative arrangements such as level of services and its inspection system, accounting and auditing systems, toll rate setting and subsidies

Figure A.5   Expected O&M Framework for Project Road (Expressway Section)

Safeguards

Social and Environmental Assessment

The original EIA report based on the JETRO study was prepared by PMU85, and approved by MONRE in Decision No. 2378/QD-BTNMT dated on November 12, 2008.  The supplemental EIA report based on the F/S alignment was also prepared by PMU85 and approved by MONRE in Decision No. 2046/QD-BTNMT dated on October 29, 2010.

Social and environmental assessment framework for Project road is shown in Figure A.6.

Figure A.6   Social and Environmental Assessment Framework for Project Road

Land Acquisition and Resettlement

RAP based on the F/S alignment was prepared by PMU85 and approved by the Prime Minister in Decision No. 442/TTg-KTN dated on March 23, 2011.

Land acquisition area and no. of resettlement households for Project road is shown in Table A.6, and CPCSR framework for Project road is shown in Figure A.7, respectively.

Table A.6   Land Acquisition Area and Nos. of Resettlement Households for Project Road

| No. | Item | Unit | Danang | Quang Nam | Quang Ngai | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Land Acquisition Area | sq.m | 506,014 (5%) | 6,425,285 (67%) | 2,658,838 (28%) | 9,590,137 (100%) |
| 2 | Resettlement Households | nos. | 85 (7%) | 771 (60%) | 430 (33%) | 1,286 (100%) |

Source:	Decision No. 442/TTg-KTN dated on March 23, 2011

Figure A.7   CPCSR Framework for Project Road

Project Cost

The total investment cost was approved by MOT in Decision No. 2656/QD-BGTVT dated on September 10, 2011, and it amounts to 27,968 Bil.VND (equivalent to 1,472 Mil.USD).

Total investment cost is shown in Table A.7.

Table A.7   Total Investment Cost

| No. | Items | Foreign Loans | State Budget | Total1) |  |
| --- | --- | --- | --- | --- | --- |
|  |  | (Mil.USD) | (Bil.VND) | (Equiv. to Bil.VND) | (Equiv. to Mil.USD) |
| 1 | Construction Cost | 904 |  | 17,179 | 904 |
| 2 | Equipment Cost | 31 |  | 580 | 31 |
| 3 | Consulting Services Cost | 53 |  | 1,003 | 53 |
| 4 | Project Management Cost |  | 68 | 68 | 4 |
| 5 | Other Cost | 32 |  | 606 | 32 |
| 6 | Land Acquisition and Compensation Cost |  | 1,074 | 1,074 | 56 |
| 7 | Contingency | 200 | 114 | 3,927 | 206 |
| 8 | VAT |  | 1,943 | 1,943 | 102 |
| 9 | Loan Interest and Financial Fees2) | 84 |  | 1,588 | 84 |
| Total |  | 1,304 | 3,199 | 27,968 | 1,472 |

Source:	Decision No. 2656/QD-BGTVT dated on September 10, 2010

Note:	1)	Exchange rate: 1USD = 19,000VND

2)	Interest during construction, front-end fees, commitment charge and service charges

Funding Arrangement

The investment cost is financed by JICA, WB and counterpart fund and it was approved by MOT in Decision No. 2656/QD-BGTVT dated on September 10, 2010.  VEC is responsible for borrowing and re-paying the loans and it was decided by GOVN Office and MOF in Document No. 4684/VPCP-KTN dated on July 7, 2010 and Document No. 695/BTC-QLN dated on August 13, 2010.

JICA signed L/A on June 15, 2011 and finances the civil works from Danang to Tam Ky section, electrical works, O&M building works and O&M/ITS equipment procurement for whole section, C/S, other cost, contingency and loan interest and financial fees for JICA portion.

WB finances the D/D cost for whole section through on-going RNIP (IDA Credit No.: 3843-VN).  In addition, WB approved to provide a loan and two (2) credits by the Executive Directors on May 24, 2011 and finances the civil works from Tam Ky to Quang Ngai section, C/S, other cost, contingency and loan interest and financial fees for WB portion, and project implementation support for VEC.

Funding arrangement among WB, JICA and GOVN is shown in Table A.8.

Table A.8   Funding Demarcation among WB, JICA and GOVN

| No. | Item |  |  | Section | Funding Demarcation |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | JICA1) | WB1) | GOVN |
| 1 | Construction (Civil Works) |  |  | Danang to Tam Ky | ● |  |  |
|  |  |  |  | Tam Ky to Quang Ngai |  | ● |  |
| 2 | Electrical, ITS Facilities and O&M Building Works, and O&M Equipment Provision |  |  | Whole Section | ● |  |  |
| 3 | Consulting | D/D |  | Whole Section |  | ● |  |
|  | Services | C/S | Civil Works | Danang to Tam Ky | ● |  |  |
|  |  |  |  | Tam Ky to Quang Ngai |  | ● |  |
|  |  |  | Electrical/O&M/ITS Works and Equipment Provision | Whole Section | ● |  |  |
|  |  | Project Implementation | Integrated Project Review and Monitoring Services | Whole Section |  | ● |  |
|  |  | Support for VEC | Financial Audit | Whole Section |  | ● |  |
|  |  |  | Financial Capacity Development | Whole Section |  | ● |  |
| 4 | Project Management, Land Acquisition and Compensation, Contingency and VAT |  |  | Whole Section |  |  | ● |

Source:	Decision No. 2656/QD-BGTVT dated on September 10, 2010

M/D (JICA Appraisal Mission) dated on October 21, 2010, M/D (WB Appraisal Mission) dated on April 21, 2011

Note:	1)	Including other cost, contingency and loan interest and financial fees in each portion

Contract Packaging

The procurement plan for JICA portion including construction contract packaging was approved by MOT in Decision No. 1688/QD-BGTVT dated on July 28, 2011.  As for the WB portion, it was also approved by MOT in Decision No. 1423/QD-BGTVT dated on June 30, 2011.

Afterwards, the Consultant updated the construction contract packaging as follows, and it was approved by MOT in ******** No. ****/**-***** dated on **** **, 2011.

Dividing PKG3 into Ky Lam Bridge (PKG3a) and remaining section (PKG3b) (see A.1.11).

Re-defining the package boundaries based on the modified alignment (see D.3.1(4))

Updated construction contract packaging is shown in Table A.9.

Table A.9   Updated Construction Contract Packaging

| Contract Packaging |  |  |  |  | Lenders |  |
| --- | --- | --- | --- | --- | --- | --- |
| Items | Jurisdiction | No. | Station1) | Length1) | JICA | WB |
| Civil Works | Danang | PKG1 | KM000+000 - KM008+000 | 8.00 km | ● |  |
|  | Quang Nam | PKG2 | KM008+000 - KM016+750 | 8.75 km | ● |  |
|  |  | PKG3a | KM016+750 - KM018+750 | 2.00 km | ● |  |
|  |  | PKG3b | KM018+750 - KM021+000 | 2.25 km | ● |  |
|  |  | PKG4 | KM021+000 - KM032+600 | 11.60 km | ● |  |
|  |  | PKG5 | KM032+600 - KM041+000 | 8.40 km | ● |  |
|  |  | PKG6 | KM041+000 - KM052+000 | 11.00 km | ● |  |
|  |  | PKG7 | KM052+000 - KM064+500 | 12.50 km | ● |  |
|  |  | PKGA1 | KM064+500 - KM081+150 | 16.65 km |  | ● |
|  |  | PKGA2 | KM081+150 - KM099+500 | 18.35 km |  | ● |
|  | Quang Ngai | PKGA3 | KM099+500 - KM109+870 | 10.37 km |  | ● |
|  |  | PKGA4 | KM109+870 - KM124+700 | 14.83 km |  | ● |
|  |  | PKGA5 | KM124+700 - KM139+200 | 14.50 km |  | ● |
|  | Total |  |  | 139.20 km |  |  |
| Electrical/O&M Building/ITS Works and Equipment Provision | All | PKG13 | KM000+000 - KM131+180 | 131.18 km | ● |  |

Source:	******** No. ****/**-***** dated on ********* **, ****

Note:	1)	Based on the modified alignment in D.3.1 Work Item (4) (station and section length are not based on F/S alignment)

Project Implementation Structure

MOT designated VEC as the Project Owner in Decision No. 220/QD-BGTVT dated on January 22, 2010 and also appointed PMU85 as the Project Implementation Agency for the D/D stage in Decision No. 2149/QD-BGTVT dated on September 19, 2011.  As for the construction stage, MOT approved that PMU85 (JICA portion) and PMU1 (WB portion) would be the Project Implementation Units by signing the principle contracts with VEC in Decision No. 2656/QD-BGTVT dated on September 10, 2011.

Project implementation structure is shown in Figure A.8.

Note:	1)	Project Implementation Support for VEC (see Table A.5)

Figure A.8   Project Implementation Structure

Project Implementation Program

The Project Implementation Program (I/P) was agreed among JICA, WB and GOVN during the JICA Appraisal in October, 2010.  However, this program is delayed 11 months at present.

After receiving NTP for the Services, the Consultant updated the Project I/P, and it was approved by MOT in Decision No. **/**-***** dated on ******* **, ****.

Main considerations in updated Project I/P are shown in Table A.10, and updated Project I/P is shown in Figure A.9, respectively.

Table A.10   Main Considerations in Updated Project I/P

| No. | Items | Contents |
| --- | --- | --- |
| 1 | Commencement of Construction Works | The realization for commencing construction works within September 2012 is required by the Minutes |
|  | (1st Priority, within September 2012) | of Contract Negotiation for the Services dated on October 15, 2011. Based on the Consultant’s study, |
|  |  | Ky Lam Bridge was selected as the priority package by design and land acquisition ease; then, PKG3 |
|  |  | was divided into Ky Lam Bridge (PKG3a) and remaining sections (PKG3b). |
| 2 | Construction Period | The construction period of all civil work packages were defined 36 months in the following Decisions: |
|  | (Civil Work Packages) | - MOT Decision No. 1688/QD-BGTVT dated on July 28, 2011 (Procurement Plan, JICA Portion) |
|  |  | - MOT Decision No. 1423/QD-BGTVT dated on June 30, 2011 (Procurement Plan, WB Portion) |
|  |  | Based on the Consultant’s estimate, the construction period for PKG1 (Softground Section), |
|  |  | PKG3a (Ky Lam Bridge) and PKGA5 (incl. Tra Khuc Bridge) were extended to 42 months. |
| 3 | Completion of D/D of Three (3) Packages | Draft D/D of first three (3) packages is required to complete within 6th month by the Minutes of |
|  | (2nd Priority, within 6th month) | Contract Negotiation for the Services dated on October 15, 2011. In consideration of land acquisition, |
|  |  | design ease and fairness among provinces, PKG1 and PKGA4 were selected as the priority packages. |

Figure A.9   Updated Project I/P

Outline of the Services

General

This Inception Report (IC/R) is for Consulting Services for Detailed Design for Danang - Quang Ngai Expressway Development Project (the Services) in accordance with the Consulting Services Contract between PMU85 and NK-NE-Chodai-TEC JV (the Consultant) signed on November 15, 2011.

Objectives

The objectives of the Services are to ensure the preparation of D/D and assist VEC/PMU85 in tendering procedures with the most efficient and timely manner to deliver the required outputs in accordance with the Project I/P.

Furthermore, appropriate technology transfers for VEC, PMU85, relevant organizations and key local professional staff are also required as a specific component in the Services to ensure smooth execution of the Project and sustainable development of the expressway network in Vietnam.

Scope

Mode

The Services are carried out by the 2 modes as shown in Table A.11.

Table A.11   Mode of the Services

| No. | Mode | Contents |
| --- | --- | --- |
| 1 | Primary Tasks | Arrangement for managing the Services by the Consultant, who is fully responsible to VEC/PMU85, for |
|  |  | adequacy and quality of the end outputs of the Services assuring duly compliance of the Services |
|  |  | assuring duly compliance of the scope of the Services specified in the Contract. |
| 2 | Assistance Tasks | The Consultant provides technical advice and assistance in carrying out the works to be accomplished |
|  |  | by VEC/PMU85 through the Consultant’s professional ability; however, the Consultant is not responsible |
|  |  | for the end outputs. |

Scope

The documents related to scope of the Services are shown in Table A.12.

Table A.12   Documents related to Scope of the Services

| No. | Stage | Documents | Date Issued |  |  | Ref. in Contract |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Tender | Original RFP | 12 | Feb., | 2010 |  |
| 2 |  | Minutes of Pre-proposal Conference | 26 | Feb., | 2010 |  |
| 3 |  | Clarifications on RFP | 22 | Mar., | 2010 |  |
| 4 |  | Revised RFP (Addendum No.1) | 9 | Apr., | 2010 |  |
| 5 |  | Clarifications on RFP | 22 | Apr., | 2010 |  |
| 6 |  | Clarifications on RFP | 29 | Apr., | 2010 |  |
| 7 |  | Revised RFP (Addendum No.2) | 27 | May, | 2010 |  |
| 8 | Proposals | Technical Proposal | 1 | Jun., | 2010 |  |
| 9 | Contract Negotiation | Minutes of Contract Negotiation (1st) | 26 | May, | 2011 | Beginning of the Contract |
| 10 |  | Minutes of Contract Negotiation (2nd) | 15 | Oct., | 2011 | Beginning of the Contract |
| 11 |  | Description of the Services (Terms of Reference) | 15 | Oct., | 2011 | Section IV, Appendix A |
| 12 |  | Reporting Requirements | 15 | Oct., | 2011 | Section IV, Appendix B |

Work Items

The Consultant established the work items for the Services according to the Technical Proposal, and those are satisfied the required scope of the Services listed in Table A.12.

Summary of work items is shown in Table A.13, and work methodology based on the detailed work items is described in Parts B to F, subsequently.

Table A.13   Summary of Work Items

| Work Items |  |  |  | Ref. Appendix A in Contract |
| --- | --- | --- | --- | --- |
| Part B | Project Management |  |  | Additional Task |
|  | B.1 | Establish and control practical management system |  | Additional Task |
| Part C | Previous Studies Review and Establishing Detailed Engineering Design Framework |  |  | 3.2 |
|  | C.1 | Review previous studies |  | 3.2(1) |
|  | C.2 | Establish detailed engineering design framework |  | 3.2(2) |
| Part D | Detailed Engineering Design and Procurement Planning |  |  | 3.3 |
|  | D.1 | Contract Packaging |  | 3.3.1 |
|  |  | D.1.1 | Propose contract packaging | 3.3.1 |
|  | D.2 | Surveys and Investigations |  | 3.3.2 |
|  |  | D.2.1 | Collect relevant data and documents | 3.3.2(1) |
|  |  | D.2.2 | Conduct topographic survey | 3.3.2(2)(i), 3.5 |
|  |  | D.2.3 | Conduct hydrological survey and analysis | 3.3.2(2)(ii) |
|  |  | D.2.4 | Conduct geotechnical and geological investigations | 3.3.2(2)(iii) |
|  |  | D.2.5 | Conduct material source survey | 3.3.2(2)(iv) |
|  |  | D.2.6 | Conduct relevant facilities survey | 3.3.2(2)(v) |
|  |  | D.2.7 | Review traffic forecasting and conduct baseline surveys | 3.3.2(2)(vi) |
|  |  | D.2.8 | Conduct independent land valuation survey | 3.3.2(2)(vii) |
|  |  | D.2.9 | Conduct environmental and social surveys | 3.3.2(2)(viii) |
|  | D.3 | Civil Engineering Design |  | 3.3.3 |
|  |  | D.3.1 | Prepare basic design of civil structures | 3.3.3 |
|  |  | D.3.2 | Prepare detailed engineering design of civil structures | 3.3.3 |
|  | D.4 | O&M Plan and Design |  | 3.3.5 |
|  |  | D.4.1 | Prepare institutional and administrative arrangement plan | 3.3.5 |
|  |  | D.4.2 | Prepare O&M plan | 3.3.5 |
|  |  | D.4.3 | Prepare basic design of O&M buildings | 3.3.5 |
|  | D.5 | ITS Plan and Design |  | 3.3.4 |
|  |  | D.5.1 | Prepare ITS plan | 3.3.4(1) |
|  |  | D.5.2 | Prepare basic design of ITS facilities | 3.3.4(2) |
|  | D.6 | Electrical Facilities Design |  | Additional Task |
|  |  | D.6.1 | Prepare detailed engineering design of electrical facilities | Additional Task |
|  | D.7 | Public Utilities Relocation Plan |  | Additional Task |
|  |  | D.7.1 | Prepare relocation plan of public utilities | Additional Task |
|  | D.8 | Safeguards |  | 3.3.6, Annex A, Annex B |
|  |  | D.8.1 | Assist in updating EIA and EMP | 3.3.6, Annex A |
|  |  | D.8.2 | Assist in preparing and enforcing CPCSR | 3.3.6, Annex B |
|  | D.9 | Construction Planning |  | 3.3.7 |
|  |  | D.9.1 | Prepare construction plan | 3.3.7 |
|  | D.10 | Project Cost Estimate |  | 3.3.8 |
|  |  | D.10.1 | Estimate Project cost | 3.3.8 |
|  | D.11 | Procurement Documents |  | 3.3.9 |
|  |  | D.11.1 | Prepare procurement documents | 3.3.9 |
|  | D.12 | Project Implementation Program |  | 3.3.10 |
|  |  | D.12.1 | Prepare Project I/P | 3.3.10 |
| Part E | Procurement Assistance |  |  | 3.4 |
|  | E.1 | Assist in tendering procedures |  | 3.4 |
| Part F | Technology Transfer |  |  | 3.6 |
|  | F.1 | Provide training to VEC, PMU85 and relevant organizations |  | 3.6 |
|  | F.2 | Provide training to key local professional staff |  | Additional Task |

Work Schedule and Reporting Plan

The Services is 14 months in total including the D/D period (12 months).  The D/D schedule is divided into the following 3 priorities to meet the requirements in the Project I/P (see A.1.11).

1st Priority Package	:	Complete D/D within 4th months (PKG3a)

2nd Priority Packages	:	Complete D/D within 6th months (PKG1 and PKGA4)

Non-priority Packages	:	Complete D/D within 12th months (Other PKGs, 10 to 12 months)

The Services was officially commenced from December 1, 2011; however, some work items were commenced in advance from July 15, 2011 as the prior works in accordance with 4th Para, 2. Implementation Plan on the Minutes of Contract Negotiation (1st) signed on 26 May, 2011.

Work schedule and reporting plan is shown in Figure A.10, and baseline schedule for progress monitoring (MS Project) based on the detailed work items are shown in Appendix 3, respectively.

Figure A.10   Work Schedule and Reporting Plan (1/5)

Figure A.10   Work Schedule and Reporting Plan (2/5)

Figure A.10   Work Schedule and Reporting Plan (3/5)

Figure A.10   Work Schedule and Reporting Plan (4/5)

Figure A.10   Work Schedule and Reporting Plan (5/5)

Organization and Staffing

Consultant’s Organization

Joint Venture

The Consultant Team consists of NK-NE-Chodai-TEC JV, and jointly and severally responsible for the Services among the JV firms.

Consultant Team

The Consultant Team divides into 6 teams and 4 supporting teams as described below.

Organization structure of the Consultant Team is shown in Figure A.11.

Engineering Group

Management Team

The Management Team is responsible for managing the Services, and all communications in the Services are exchanged through the team.  In the team, the Consultant organizes the core team which consists of the representative of each team and secures the consistent communication among the teams.

Civil Design Team

The Civil Design Team is responsible for planning and designing the civil structures and consists of the civil design management, design group and the survey group.

The Civil Design Management is responsible for establishing the design criteria and conditions, standard design of road accessories, culverts and bridges, and supervising the works of the design and survey groups, preparing the technical specifications and assisting the tendering procedures.

The Design Group is responsible for preparing the basic design and detailed engineering design, and consists of two (2) sections and each design fields.

O&M and ITS Team

The O&M and ITS team is responsible for preparing the O&M and ITS plan, basic design of the O&M buildings and ITS facilities, and detailed engineering design of the electrical facilities including the preparation of the technical specifications in the bidding documents.

Cost and Document Team

The Cost and Document Team is responsible for preparing the construction plan, engineer’s cost estimate, procurement plan and documents, and assisting the tendering procedures.

Environmental Team

The Environmental Team works with the relevant organizations for updating EIA and EMP, preparing and enforcing CPCSR, and preparing the requirements for EMP in the bidding documents.

Training Team

The Training Team is responsible for identifying the training needs with VEC, PMU85 and relevant organizations, and preparing and coordinating the training materials in cooperation with the engineers/specialists of the respective fields assign in other teams.

Supporting Group

The Supporting Group assists to the Key Professional Staff in daily works.  The Group consists of four (4) teams, and those are allocated three (3) teams in Danang Main Office and one (1) in Hanoi Sub-office (see A.2.5(1)(d)).

Figure A.11   Organization Structure of the Consultant Team

Home Office Support

NK, the prime consultant of JV firms has the home office support system and utilizes the technical, managerial and operational support including the review and verification of design in the Services.

Conceptual image of NK’s home office support system is shown in Figure A.12

Figure A.12   Conceptual Image of NK’s Home Office Support System

Office Arrangement

PMU85 organized the Project Site Management Department (PSMD) in his Danang office, and Danang CPC, Quang Nam and Quang Ngai PPCs and the Project site are also located in/near Danang city.  Therefore, the Consultant set up the Main Office in Danang city.

On the other hand, the Consultant outsources the D/D of all interchanges and bridges (excluding Ky Lam Bridge, 1st Priority Package) to the Vietnamese sub-consultants in Hanoi city (see A.2.5(2)(a)).  For supervising the outsourcing works, the Consultant set up the Sub-office in Hanoi city.

Office arrangement for Consultant team is shown in Table A.14.

Table A.14   Office Arrangement for Consultant Team

| No. | Office | Period |  | Address | Tel | Fax |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Danang Main Office | 14 months | (Dec. 2011 to Jan. 2013) | ****************************** | ************** | ************** |
| 2 | Hanoi Sub-office | 8 months | (Apr. 2011 to Nov. 2012) | To be established |  |  |

Staffing

Staffing and Task Assignment

The Consultant established the staffing and task assignment in consistent with the work schedule and reporting plan described in A.2.4.

It is noted that the Consultant outsources the D/D of all interchanges and bridges (excluding Ky Lam Bridge, 1st Priority Package) to the Vietnamese sub-consultants in Hanoi city to minimize the personnel inputs and shorten the design period.

Staffing and task assignment matrix for key professional staff are shown in Table A.15.

Staffing Schedule

The Consultant takes into account the staffing for the key professional staff as follows:

Arrange the staff who worked with VEC/PMU85 in the past studies;

Arrange the staff who worked together with other team members in the past;

Time schedule for key international professional staff, key local professional staff and supporting staff are shown in Tables A.16 to A.18, respectively.

Table A.15   Staffing and Task Assignment Matrix for Key Professional Staff

Table A.16   Time Schedule for Key International Professional Staff

Table A.17   Time Schedule for Key Local Professional Staff (1/2)

Table A.17   Time Schedule for Key Local Professional Staff (2/2)

Table A.18   Time Schedule for Supporting Staff

Project Management

Establish and Control Practical Project Management System

The Consultant established the practical Project management system by utilizing PMBOK and its construction extension and customized it to the characteristics of the Services as attached in Appendix 2.  In consideration of the large-scale and complex assignment, the Consultant prioritizes the communication, quality and schedule managements in the Services.

The system was explained by the Consultant in the kick-off meeting on November 25, 2011, and agreed among VEC/PMU85, the Consultant and other relevant organizations for publicizing, gaining consensus and smooth execution of the Services.  Therefore, the Consultant monitors and controls the activities according to the system during the Services.

The system consists of 13 management areas, and the integration management which is one of the management areas consisting of the processes and activities needed to identify, define, combine, unify and coordinate the various processes and activities within the management process groups, is useful for understanding of overall project management system.

Work diagram of project management based on integration management is shown in Figure B.1, and describes the methodology of work items subsequently.

Note:	Not all process interactions and data flow among the inputs, work items and reports are shown in the figure

Figure B.1   Work Diagram of Project Management based on Integration Management

Define the Services

The Consultant prepares the Services charter and its regulations in accordance with the contract of the Services.  The charter consists of the name, targets, requirements, outputs, conditions of completion, budgets, period, organization, responsibility and authority of members, means of communication, and constraints for the Services to be formally authorized the Services among the relevant organizations.

Prepare the Primary Services Scope Statement

The Consultant updates the primary Services scope statement proposed in the proposal with reflection of contract negotiation and defines the needs to be accomplished in the Services.  The statement consists of the objectives, assumptions, constraints and deliverables for the Services and provides a documented basis for making future decisions and for confirming or developing a common understanding of the Services scope among the relevant organizations.

Prepare the Services Management Plan

The Consultant prepares the Services management plan which defines how the Services is executed, monitored and controlled and addresses the communication, quality and schedule managements as explained above.  Based on (1) to (3) above, the Consultant prepares and submits the Inception Report.

Main contents of prioritized three (3) management areas are shown in Table B.1.

Table B.1   Main Contents of Prioritized Three (3) Management Areas

| No. | Management Areas | Main Items | Contents |
| --- | --- | --- | --- |
| 1 | Communication | Communication requirements | - Among the relevant organizations and inside the consultant team |
|  |  | Communication item | - Including format, contents, level of detail, frequency, conveyor and receiver |
|  |  | Medium and technologies | - Meetings, letters, reports, workshops, etc. |
|  |  | Escalation process | - Identifying time frames and channel for escalation of issues |
|  |  | Method for updating | - Required conditions and process for updating |
|  |  | Common terminology | - Definitions for minimizing communication errors |
| 2 | Quality | Quality metrics | - Operational definition for quality control item, process and measurement |
|  |  | Quality checklists | - Structured tool for verifying QA/QC performance |
|  |  | Process improvement | - Process boundaries, configuration and metrics, and performance targets |
|  |  | Quality baseline | - Records for quality objectives |
|  |  | Method for updating | - Required conditions and process for updating |
| 3 | Schedule | Activity definition | - Activity list and attributes, and milestone list |
|  |  | Baseline schedule | - Baseline for progress monitoring and reporting |
|  |  | Monitoring and reporting | - Method for monitoring and reporting including format, contents and frequency |
|  |  | Method for updating | - Required conditions and process for updating |

Kick-off Meeting

Based on the Inception Report, the Consultant holds the kick-off meeting with not only the Project executing agency but also other relevant organizations for publicizing, gaining the consensus and smooth implementation of the Services.

Direct and Manage the Services Execution

The Consultant directs and manages the Services execution in accordance with the process of executing the Services defined in the Services management plan above (3) to achieve the requirements for the Services defined in the primary Services scope statement in above (2).  Information on the status of the management activities being performed to accomplish the Services is routinely collected, and the Consultant compiles and submits the status as the monthly progress report.

Monitor and control the Services

The Consultant monitors and controls the processes used to initiate, plan, execute and close the Services to meet the performance objectives defined in the Services management plan above (3).  Status of the activity is also compiled and submitted as the monthly progress report.

Control Integrated Change

The Consultant controls integrated change which is the process of reviewing all change requests and approving and controlling changes to deliverables and organizational process assets.  The approved changes are reflected to update the Services scope statement above (2) and the Services management plan above (3).  Status in the activity is also compiled and submitted as the monthly progress report.

Close the Services

The Consultant finalizes all of the activities across the process groups to formally close the Services.  Administrative closing procedure is prepared and reflected to direct and manage the Services execution above (5).  All of documents of the management activities are compiled and submitted as the Project completion report.

Previous Studies Review and Establishing Detailed Engineering Design Framework

Review Previous Studies

The Consultant reviews the previous studies especially F/S and safeguard documents to take cognizance of the current arrangements of the Project and extracts the key issues which materially affect to the Services for discussing and obtaining the agreement with VEC/PMU85 and relevant organizations.

Work diagram of previous studies review is shown in Figure C.1, and main contents of previous studies review are shown in Table C.1, respectively.

Figure C.1   Work Diagram of Previous Studies Review

Table C.1   Main Contents of Previous Studies Review

| No. | Category | Main Contents |
| --- | --- | --- |
| 1 | Civil | - Topography, geology and hydrology of the Project area |
|  |  | - Technical standards1), and design criteria and conditions |
|  |  | - Route alignment, geometric design and typical cross sections |
|  |  | - Preliminary design of civil structures |
|  |  | - Construction planning and preliminary Project cost estimates |
|  |  | - Environmental impacts and its mitigation measures and RAP |
| 2 | O&M/ITS | - Existing legal and administrative arrangements |
|  |  | - O&M/ITS standards and plan |
|  |  | - O&M unit establishment plan |
|  |  | - Tariff rate and toll collection system |
|  |  | - Electrical/O&M/ITS facilities and equipment plan |

Note:	1)	Applicable technical standards for the Project were approved by MOT in Decision No. 362/QD-BGTVT dated on February 20, 2009

Establish Detailed Engineering Design Framework

The Consultant establishes the detailed engineering design framework which consists of the primary matters for execution of the Services based on C.1 and obtains the approval from VEC/PMU85 and relevant organizations.

Work diagram of detailed engineering framework is shown in Figure C.2, and main contents of the detailed engineering design framework are shown in Table C.2, respectively.

Figure C.2   Work Diagram of Detailed Engineering Design Framework

Table C.2   Main Contents of the Detailed Engineering Design Framework

| No. | Item | Main Contents |
| --- | --- | --- |
| 1 | Detailed Engineering Design Framework | - Updated applicable technical standards for the Project |
|  |  | - Format and content of the B/Q items, cost estimate and procurement documents |
|  |  | - Updated work schedule of the Services |

Detailed Engineering Design and Procurement Planning

Contract Packaging

Propose Contract Packaging

As described in A.1.9, the Consultant updated the construction contract packaging, and it was approved by MOT in ******** No. ****/**-***** dated on **** **, 2011.

In case further modification is requested by VEC/PMU85, the Consultant studies it taking into account the affection for the D/D works and arrangement of the Project.

Work diagram of contract packaging is shown in Figure D.1,

Figure D.1   Work Diagram of Contract Packaging

Surveys and Investigations

Collect Relevant Data and Documents

The Consultant collects the relevant data and documents for basis of execution of the Services.

Work diagram of relevant data and documents is shown in Figure D.2, and main contents of relevant data and documents are shown in Table D.1, respectively.

Figure D.2   Work Diagram of Relevant Data and Documents

Table D.1   Main Contents of Relevant Data and Documents

| No. | Items | Main Contents |
| --- | --- | --- |
| 1 | Project Documents | - Previous studies report |
|  |  | - Related Decisions and Documents for the Project |
| 2 | Other Data and Documents | - Relevant developing plan and existing facilities data in the Project area |
|  |  | - Report and design document of the relevant project |
|  |  | - Data related to the construction planning and cost estimate proper to the Project area |

Conduct Topographic Survey

The Consultant conducts the topographic and ROW surveys for preparation of engineering design, quantity take-off and CPCSR.  In consideration of the huge survey volumes, the Consultant outsources the site survey works to Vietnamese sub-consultant(s) and supervises their performance by the Survey Engineer.  The selection of sub-consultant(s) and work plan including survey specifications shall be approved by VEC/PMU85.

In consideration of the rainy season, short-period and work procedure of basic design, the Consultant conducts the site survey works in accordance with the following priorities:

1st Priority	:	Control point survey and leveling network (whole section)

2nd Priority	:	Planimetric survey (thruway, sections for survey centerline study)

3rd Priority	:	Remaining surveys for basic design

Non-priority	:	Surveys for detailed engineering design

Work diagram of topographic survey is shown in Figure D.3, and work quantities for topographic survey are shown in Table D.2, respectively.

Figure D.3   Work Diagram of Topographic Survey

Table D.2   Work Quantities for Topographic Survey

Source:	Estimated quantities by the Consultant (as of end of November, 2011)

Conduct Hydrological Survey and Analysis

“National Strategy for Natural Disasters Prevention, Response and Mitigation to 2020” and “Provincial Integrated Disaster Risk Management Plan to 2020” have stressed for building flood resistant roads and widening the openings of bridges and culverts along the roads and railways to facilitate drainage.  Therefore, width of bridges, viaducts and culverts in the Project road is required to design with enough openings that flood conditions in river and on floodplain is not alter from the existing situations.

The Project road passes through floodplains of large rivers; therefore, some sections have severe problems.  The Consultant conducts hydrological and inundation analyses performed as follows:

Identify the sections of Project road where inundation occurs

Determine design high water level in river and on floodplain along the Project road

Check width of bridges and culverts in F/S are enough or not

Optimize the length of bridges and culverts for cost-effectiveness

Work diagram of hydrological survey and analysis is shown in Figure D.4, and describes the methodology of work items subsequently.

Figure D.4   Work Diagram of Hydrological Survey and Analysis

Site Investigation

The Consultant conducts site investigations to acquire the river locations, channels and crossing points with the Project road and updates the specifications for hydrological survey including the river profile and cross-section survey points in the topographic survey (D.2.2).

-(4)	Hydrological Survey

The Consultant outsources the hydrological survey works to Vietnamese sub-consultant(s) and supervises their performance by the Senior Hydrologist.  The selection of sub-consultant(s) and work plan including survey specifications shall be approved by VEC/PMU85.

Work quantities for hydrological survey are shown in Table D.3.

Table D.3   Work Quantities for Hydrological Survey

| No. | Items | Locations and Quantities |
| --- | --- | --- |
| 1 | Historical Water Level | A group of highest one, frequent one, average one and lowest one along the thruway centerline at 1.0 km interval |
|  |  | where existing ground level is less than 25 m from mean sea level and at all planned positions of bridge and culvert. |
| 2 | Water Level | Thrice a day in November and December 2011 at 6:00, 12:00 and 18:00 hours at three (3) positions (one (1) position |
|  |  | at river center, two (2) positions near banks) in four (4) major river bridges. |
| 3 | Water Flow Velocity | Once during high flood in November and December 2011 at three (3) positions (one (1) position at river center, two |
|  |  | (2) positions near banks) in four (4) major river bridges. |

Source:	Estimated quantities by the Consultant (based on F/S)

- (5)	Data Collection

The Consultant collects hydro-meteorological data which is necessary for hydrological analysis.  Those data can be obtained from Hydro-meteorological Data Center in Hanoi.

Hydro-meteorological data collection plan is shown in Table D.4.

Table D.4   Hydro-meteorological Data Collection Plan

| No. | Items | Stations and Periods |
| --- | --- | --- |
| 1 | Annual Maximum Daily Rainfall | Danang (1964 - 2010), Cau Lau (1977 - 2010), Tam Ky (1977 - 2010), Tra My (1979 - 2010), |
|  |  | Tra Bong (1976 - 2010), Quang Ngai (1964 - 2010), Gia Vuc (1981 - 2010) |
| 2 | Annual Maximum Rainfall | Danang (amounts of 5, 15, 30, 45 and 60 minutes duration during 1986 - 2010 or rainfall intensity duration |
|  |  | frequency (IDF) curve with equation and constants) |
| 3 | Meteorological Data | Danang (mean monthly air temperature, wind speed, evaporation and relative humidity during 2001 - 2010) |
| 4 | Annual Maximum River Discharge | Nong Son (Thu Bon River, 1977 - 2010), Thanh My (Vu Gia River, 1977 - 2010), |
|  | (with Catchment Areas) | Son Giang (Tra Khuc River, 1979 - 2010) |
| 5 | Annual Maximum and Minimum | Giao Thuy (Thu Bon River, 1976 - 2010), Ai Nghia (Vu Gia River, 1976 - 2010), |
|  | River Water Levels | Son Giang and Tra Khuc (Tra Khuc River, 1977 - 2010), Cam Le (Other River, 1976 - 2010) |
| 6 | Hourly Water Levels and Rainfalls | Hourly Water Level (7 days): Giao Thuy and Cau Lau (Thu Bong River), Ai Nghia (Vu Gia River), |
|  | (one (1) week, the highest in 2009) | Son Giang and Tra Khuc (Tra Khuc River), Cam Le (Other River) |
|  |  | Hourly Rainfall 7 days): Danang, Tra My, Tam Ky and Quang Ngai |

Source:	Estimated quantities by the Consultant (based on F/S)

- (6)	Rainfall Analysis

The Consultant conducts frequency analysis of annual maximum daily rainfall of stations in the Project area performed to determine 1 % (linking road: 4 %), 5 % and 50 % exceeding probability rainfalls at the stations.  Most commonly used log normal distribution function is employed for the frequency analysis.  As for the coverage of river basin area by a particular rainfall station, it is determined by using Thiessen’s Polygon Method.  Basin rainfalls of 1 % (linking road: 4 %), 5 % and 50 % exceeding probability levels are computed based on the point rainfalls, and hourly distribution pattern of basin rainfall is designed for runoff analysis.

- (7)	Runoff Analysis

The Consultant conducts runoff analysis by using empirical methods (specific discharge method or rational method) or lumped sub-basin model.  The information such as catchment area, rainfall amount and intensities, and sub-basin parameters is collected for runoff analysis.  The lumped sub-basin model is calibrated by observed flood levels in river and on floodplain during high flood in 2009.  The river flow of 1 % (linking road: 4 %), 5 % and 50 % exceeding probabilities is estimated for determining design high water levels in river and on floodplain.

- (8)	River Flow Capacity Estimation

The Consultant checks river flow capacity by employing river flow simulation model.  In case of 1 % (linking road: 4 %) exceeding probability flow is within the flow capacity of river, the design high water level in the river is estimated by unsteady river flow simulation by using HEC-RAS.  In case of 1 % (linking road: 4 %) exceeding probability flow overflows from river bank, inundation analysis is adopted for determining the design high water level in river and on floodplain.

- (9)	Inundation Analysis

The Consultant conducts inundation analysis with input of 1 % (linking road section: 4 %) and 5 % exceeding probabilities basin rainfalls.  The scenarios of inundation analysis are as follows:

1 % (linking road: 4 %) exceeding probability basin rainfall and existing physical conditions of basin

1 % (linking road: 4 %) and 5 % exceeding probability basin rainfall, existing physical conditions of basin, and planned designs (dimensions) and arrangements of thruway bridge, viaduct and culvert

Other scenarios as needed to determine the design high water level in river and on floodplain

The Consultant utilizes MIKE-11 and ArcGIS for inundation analysis and flood maps preparations.  The data used in flood management model developed by JICA’s Disaster Protection Study in Quang Nam and WB’s Flood Risk Management Plan Study in Quang Ngai.

Image of MIKE-11 and ArcGIS is shown in Figure D.5.

| MIKE-11 (Inundation Analysis) | ArcGIS (Mapping) |
| --- | --- |

Figure D.5   Image of MIKE-11 and ArcGIS

- (10)	Cost-benefit Analysis

The Consultant conducts cost-benefit analysis when there is 1 % (linking road: 4 %) exceeding probabilities flow in river.  The Project area is divided into appropriate mesh size considering flood depth and duration.  The damages on properties such as houses, crops and livestock by inundation are considered to assess the inundation loss, and the Consultant utilizes the damage rates in Manual for Economic Analysis of Flood Control Project issued by MLIT-Japan.

Conduct Geotechnical and Geological Investigations

The Consultant conducts the geotechnical and geological investigations for engineering design.  In consideration of huge investigation volumes, the Consultant outsources the site investigation works to Vietnamese sub-consultant(s) and supervises their performance by the Soil/Geotechnical Engineer 2 and Geological Engineer (Tunnel).  The selection of sub-consultant(s) and work plan including investigation specifications shall be approved by VEC/PMU85.

The Consultant conducts the site investigation works in accordance with the following priorities:

1st Priority Investigations	:	PKG3a (1st Priority Package)

2nd Priority Investigations	:	PKG1 and PKGA4 (2nd Priority Packages)

3rd Priority Investigations	:	Other Civil Work Packages (Non-priority Packages)

Non-priority Investigations	:	PKG13 (O&M Package)

The structural plan including bridge plan may be modified from F/S in accordance with the results of several surveys and analyses, especially hydrological and inundation analyses (D.2.3).  Therefore, the commencement of geotechnical and geological investigations shall be taken into account the maturity of the structure plan for avoiding re-investigations.

Work diagram of geotechnical and geological investigations is shown in Figure D.6, and tentative work quantities for geotechnical and geological investigations are shown in Table D.5, respectively.

Figure D.6   Work Diagram of Geotechnical and Geological Investigations

Table D.5   Tentative Work Quantities for Geotechnical and Geological Investigations

Source:	Estimated quantities by the Consultant (based on F/S-2010)

Conduct Material Source Survey

The Consultant conducts material source survey by outsourcing to Vietnamese sub-consultant(s) at locations identified with the local PCs to confirm quality and volume of borrow, sand and rock materials for detailed engineering design and construction planning.  The selection of sub-consultant(s) and work plan including survey specifications shall be approved by VEC/PMU85.

Work diagram of material source survey is shown in Figure D.7, and tentative work quantities for material source survey are shown in Table D.6, respectively.

Figure D.7   Work Diagram of Material Source Survey

Table D.6   Tentative Work Quantities for Material Source Survey

| No. | Item | Unit | Quantities | Remark |
| --- | --- | --- | --- | --- |
| A | Sampling and Laboratory Test |  |  |  |
| 1 | Borrow Material |  |  | 1 location/20 km*140 km = 8 locations |
| 1.1 | Undisturbed Sample Test | nos. | 24 | 3 samples/location*8 locations |
| 1.2 | Standard Compaction Test | nos. | 24 | 3 samples/location*8 locations |
| 1.3 | CBR Test | nos. | 24 | 3 samples/location*8 locations |
| 2 | Rock |  |  |  |
| 2.1 | Rock Sample Test | nos. | 15 | 3 samples/location*5 locations |
| 3 | Fine Sand |  |  |  |
| 3.1 | Sand Sample Test | nos. | 24 | 3 samples/location*8 locations |
| 3.2 | Standard Compaction Test | nos. | 24 | 3 samples/location*8 locations |
| 4 | Coarse Sand |  |  |  |
| 4.1 | Sand Sample Test | nos. | 6 | 3 samples/location*2 locations |

Conduct Relevant Facilities Survey

The Consultant conducts the relevant facilities survey in the Project area to identify the obstacles and cultural properties for extracting the design controls, and evaluates the level of capacity of existing roads and structures for construction planning.

Work diagram of relevant facilities survey is shown in Figure D.8, and main contents of relevant facilities survey is shown in Table D.7, respectively.

Figure D.8   Work Diagram of Relevant Facilities Survey

Table D.7   Main Contents of Relevant Facilities Survey

| No. | Items | Contents |
| --- | --- | --- |
| 1 | Design Controls | - Identify the location, capacity and specification of the obstacles in the Project area |
|  |  | - Identify the cultural buildings, temples, pagodas and relevant legal religious buildings |
| 2 | Construction Planning | - Evaluate current traffic conditions of the existing roads in the Project area |
|  |  | - Identify and evaluate loading capacity of bridges/culverts on potential construction roads |

Review Traffic Forecasting and Conduct Baseline Surveys

The Consultant reviews the traffic demand forecasting in F/S to establish the requirements for the engineering design from the traffic aspects.  In addition, the Consultant reviews the traffic survey data above and other relevant studies around the Project area to collect the available baseline data for the performance indicators in the Project framework (A.1.4).

In case of the appropriate data is not identified, the Consultant conducts the additional traffic survey by outsourcing to the Vietnamese sub-consultant(s).  The selection of sub-consultant(s) and work plan including survey specifications shall be approved by VEC/PMU85.

Work diagram of traffic forecasting review and baseline surveys is shown in Figure D.9, and tentative work quantities for baseline survey is shown in Table D.8, respectively.

Figure D.9   Work Diagram of Traffic Forecasting Review and Baseline Surveys

Table D.8   Tentative Work Quantities for Baseline Survey

| No. | Surveys | Contents |  |
| --- | --- | --- | --- |
| 1 | Traffic Count | Day and Time | 1 weekday and 1 holiday, 24 hours in each day |
|  |  | Location | On the existing NH1A (2 segments Danang to Tam Ky and Tam Ky to Quang Ngai) |
|  |  | Survey Item | Traffic volume and composition on the both directions |
| 2 | Travel Time | Day and Time | 1 weekday and 1 holiday, peak traffic hour identified in the traffic count survey |
|  |  | Location | On the existing NH1A (2 segments Danang to Tam Ky and Tam Ky to Quang Ngai) |
|  |  | Survey Item | Travel time by each vehicle classification on the both directions |
| 3 | Traffic Accident | Period | Annual (the last 3 years) |
|  |  | Location | On the existing NH1A (2 segments Danang to Tam Ky and Tam Ky to Quang Ngai) |
|  |  | Survey Item | Nos. and type of traffic accident |

Conduct Independent Land Valuation Survey

The Consultant conducts the independent land valuation survey by outsourcing to the qualified land valuation consultant who is licensed by MOF and independent of all Project stakeholders to confirm the current market prices of land by location and use in each commune in the Project area.  The selection of sub-consultant and work plan including survey specifications shall be approved by VEC/PMU85.

Work diagram of independent land valuation survey is shown in Figure D.10, and potential land valuation consultants in the Project area is shown in Table D.9, respectively.

Figure D.10   Work Diagram of Independent Land Valuation Survey

Table D.9   Potential Land Valuation Consultants in the Project Area

| No. | City/Province | Name of Consultant | Tel | Fax | e-mail |
| --- | --- | --- | --- | --- | --- |
| 1 | Danang | Danang Valuation & Financial Services Limited Company | 0511-3887628 | 0511-3887532 | divc@vnn.vn |
| 2 | Quang Nam | Quang Nam Financial & Price Consultancy Joint-stock Company | 0510-3811657 | --- | mylangbd@yahoo.com.vn |
| 3 | Quang Ngai | Central Information & Valuation of Cost Joint-stock Company | 055-3818348 | --- | --- |

Conduct Environmental and Social Surveys

The Consultant conducts the site surveys for updating the existing EIA and EMP to confirm the environmental and social conditions in the Project area in accordance with the JICA Guidelines for Environmental and Social Considerations and WB safeguard policies and, if necessary.

Work diagram of environmental and social surveys is shown in Figure D.11.

Figure D.11   Work Diagram of Environmental and Social Surveys

Civil Engineering Design

The Consultant divides the civil engineering design into the basic design (B/D) and detailed engineering design (D/D) stages to proceed the design works efficiently.  The numbers of structure are huge; therefore, the Consultant prepares and utilizes the standard designs to assure the design quality.

Work items and demarcation between B/D and D/D stages is shown in Table D.10.

Prepare Basic Design of Civil Structures

In the B/D stage, the Consultant establishes the fundamental conditions and obtains the approval from VEC/PMU85 and other relevant organizations to avoid the re-design in the D/D stage.

Main contents of B/D stage are summarized below:

Establish design criteria and conditions;

Define typical cross sections;

Define thruway geometric design;

Prepare general view of all thruway bridges;

Prepare thruway culverts, tunnel and interchanges plan.

Work diagram of basic design of civil structures is shown in Figure D.12.

Prepare Detailed Design of Civil Structures

In the D/D stage, the Consultant conducts the remaining plan and design works in accordance with the B/D and outsources all of bridges (excluding Ky Lam Bridge, 1st Priority Package) and interchanges design to Vietnamese sub-consultants who have abundant experiences and resources for minimize the personnel inputs and shorten the design period.

Work diagram of detailed design of civil structures is shown in Figure D.13, and main contents of road safety audit are shown in Table D.11, respectively.

Table D.11   Main Contents of the Road Safety Audit (PIARC Road Safety Manual 2004)

| No. | Classification | Category |  |  | Indicators |
| --- | --- | --- | --- | --- | --- |
| 1 | All Roads | Horizontal alignment |  |  | Curve radius, speed differentials, surface conditions, overturning, super-elevation, |
|  |  |  |  |  | road width, shoulders, roadside sight distance/forgiving road, passing in curve |
|  |  |  |  |  | warning signs and devices, combination of features |
| 2 |  | Vertical | Grade | Downhill | Generalities (stopping distance, brake temperature, compound grades, etc.), |
|  |  | alignment |  |  | location of road sign, drainage capacity and structure, brake check area, arrester beds |
|  |  |  |  | Uphill | Generalities (deceleration rate, speed reduction, etc.), climbing lanes, drainages |
|  |  |  | Curves |  | Generalities (sight distance, etc.), passing (pavement marking), drainages |
| 3 |  | Human factors (driver) |  |  | Strain, workload, perception, lane tracking, choice of speed, orientation, anticipation |
| 4 | Non-access | Sight distance | At grade intersections |  | Stopping, maneuvering, passing sight and decision sight distances, sight triangles |
|  | Control Roads |  | Two-way, two lane roads |  | Stopping, decision, passing and meeting sight distances |
| 5 |  | At grade intersections |  |  | Generalities (intersection type, access control, sight distance, |
|  |  |  |  |  | distance between intersections, conflict points at intersections, etc.) |

Note:	Sight distance and at grade intersection are astride the plural categories in the table

Table D.10   Work Items and Demarcation between B/D and D/D Stages

Legend:	●(B/D), ●(D/D)

Code:	RD(Road), TN(Tunnel), BR(Bridge), RB(River Bridge), LRB(Large River Bridge), ORB(Other River Bridge), MRB(Major River Bridge), CB(Culvert Box), WT(Waterway), CP(Culvert Pipe), BL(Building), IRB(Interchange Rampway Bridge), FO(Flyover)

Note:	1) LRB(L>100 m), ORB(L<100 m), Other LRB (100 m<L<300 m)

2) 4 Bridges (Ky Lam Bridge (LRB08, KM017+662), Chiem Son Bridge (LRB09, KM020+185), Tra Bong Bridge (LRB19, KM109+320), Tra Khuc Bridge (LRB20, KM125+700))

3) Stream Bridge (SB), Canal Bridge (CB), Viaduct (VD), Overpass (OP)

4) Toll Barrier (TB) and Toll Plaza Office (TPO), Service Area (SA), Parking Area (PA), Traffic Management Center (TMC), Expressway Operation Office (EOO)

5) Toll Gate (TG) and Toll Plaza Office (TPO)

6) Civil Works Only

7) Plan and Profile and General View (Bridge)

Note:	1) Revision of thruway geometric design (vertical) and culvert and bridge plan in accordance with hydrological survey and analysis (D.2.3)

2) Thruway plan and profile and general view (thruway bridges)

Figure D.12   Work Diagram of Basic Design of Civil Structures

Note:	Outsourcing work items are (20) structural design (bridge), (21) bridge temporary facility plan, (11) geometric design (interchange), (46) design drawings (D/D) (bridge and interchange only), (47) quantity taking-off (bridge and interchange only)

Figure D.13   Work Diagram of Detailed Design of Civil Structures

O&M Plan and Design

Prepare Institutional and Administrative Arrangement Plan

The Consultant confirms the existing legal and regulatory framework for expressway O&M in Vietnam and studies the necessary institutional and administrative arrangement plan for O&M of the Project road.  Based on the plan, the Consultant holds workshops with the relevant organizations and gains the consensus for work sequence, schedule and organizations in-charge of the arrangement works.

Work diagram of institutional and administrative arrangement plan is shown in Figure D.14, and main items for institutional and administrative arrangement plan are shown in Table D.12, respectively.

Figure D.14   Work Diagram of Institutional and Administrative Arrangement Plan

Table D.12   Main Items for Institutional and Administrative Arrangement Plan

| No. | Items | Contents |
| --- | --- | --- |
| 1 | Institutions | The necessary institutions shall be set up in order to clarify and delineate responsibilities among relevant |
|  |  | organizations involved in O&M. |
| 2 | Standards | O&M works on expressways mainly consists of traffic operation, road maintenance and toll collection. |
|  |  | The establishment of standards for each work is essential in the effective and efficient implementation of works. |
| 3 | Enforcement and Regulation | In order to properly implement expressway operation by the road administrator, administrative demarcation of |
|  |  | responsibilities for traffic enforcement and regulation between the administrator and concerned regular |
|  |  | authority shall be clarified. |

Prepare O&M Plan

The Consultant prepares the O&M plan for the Project road in accordance with the existing legal and regulatory framework confirmed in D.4.1.  As for the items which are not existed and scheduled in the institutional and administrative arrangement plan in D.4.1, the Consultant establishes the assumptions based on overseas practices.

Work diagram of O&M plan is shown in Figure D.15, and describes the methodology of work items subsequently.

Figure D.15   Work Diagram of O&M Plan

- (1)	Establish Basic Assumptions

The Consultant establishes basic assumptions for preparing O&M plan in accordance with the existing legal and regulatory framework confirmed in D.4.1.  As for the items which are not existed and scheduled in the institutional and administrative arrangement plan in D.4.1, the Consultant establishes the assumptions based on overseas practices.

- (2)	Establish LOS

The Consultant establishes LOS by extracting the requirements in MOT Circular on Expressway O&M and utilizing overseas experiences for definition of O&M activity and frequency.

Possible performance indicators for LOS are shown in Table D.13.

Table D.13   Possible Performance Indicators for LOS

| No. | Category | Indicators |
| --- | --- | --- |
| 1 | Availability | Frequency of road closures, transaction time of traffic accidents, duration and work area of maintenance works |
| 2 | Mobility | Average covering speed, traffic density |
| 3 | Accessibility | Capacity of toll gates, transaction system and time of toll gates |
| 4 | Safety | Traffic safety facilities, lighting, enforcement of traffic regulation, traffic accident rate, visibility |
| 5 | Comfortability | Facilities and activity level of SAs/PAs |
| 6 | Emergency Response | Covering time of rescue cars arrival (ambulance and fire fighting cars) |
| 7 | Surface Conditions | Coarseness, roughness and pot holes of road surface |
| 8 | Traffic Information | Traffic congestion/delay, regulation and disaster |
| 9 | Environment Aspect | Noise, air pollution |

- (3)	Define O&M Activity and Frequency

The Consultant defines the O&M activity and frequency in case of regular, traffic regulation and emergency to satisfy LOS established in (2) above in accordance with MOT Circular on Expressway O&M or by utilizing the overseas experiences.  The activity and frequency is taken into account stage-wised strengthening for ensuring LOS in the future traffic growth.

- (4)	Prepare O&M Plan

The Consultant prepares the O&M plan based on (1) to (3) above.  As for the item related to ITS, the Consultant utilizes ITS Standards prepared by JICA T/A to define the basic requirements and system.  Based on this basic requirements and system, the Consultant prepares the functions and specifications for ITS facility and system configuration in D.5.1(3).

Main contents of O&M plan are shown in Table D.14.

Table D.14   Contents of O&M Plan

| No. | Item | Contents |
| --- | --- | --- |
| 1 | O&M Charter | Name, legal status, objectives, policies, responsibilities, targets, budgets, management, organization, staffing |
| 2 | Traffic Management | Traffic surveillance and control system, organization and staffing |
| 3 | Toll Collection | Location of toll plaza, numbers of toll barrier/gate, toll collection system, organization and staffing |
| 4 | SA/PA Services | Location of SAs/PAs, contents of the services, organization and staffing |
| 5 | Maintenance | Maintenance system (including road asset management), organization and staffing |
| 6 | Administration | Organization, personnel, reports and financial management system |
| 7 | O&M Buildings | Layout plan of toll plaza, O&M building and SAs/PAs |
| 8 | O&M Equipment | Procurement, management and maintenance plan of O&M equipment |

- (5)	Prepare O&M Unit Establishment Plan

The Consultant prepares the O&M unit establishment plan including the training program in consideration of the required arrangements and enhancements extracted in (4) above.

- (6)	Estimate O&M Cost

The Consultant estimates the O&M cost both of the Project implementation and operation stages based on (4) to (5) above.  However, the cost in the Project implementation stage is used for the reference, and the detailed cost is estimated in D.10.1.

Based on (1) to (6) above, the Consultant compiles the O&M plan and holds workshops with VEC/PMU85 and relevant organizations.

Prepare Basic Design of O&M Buildings

The Consultants prepares the basic design of O&M buildings based on the O&M plan in D.4.2.  The design covers all of facilities in toll plaza, O&M buildings and SA/PA except communications and electrical facilities which are designed in D.5.2 and D.6.1, respectively.

Work diagram of basic design of O&M buildings is shown in Figure D.16.

Figure D.16   Work Diagram of Basic Design of O&M Buildings

ITS Plan and Design

Prepare ITS Plan

Based on the ITS basic requirements and system in D.4.2(4), the Consultant prepares the ITS development plan which is composed of planning concept, stage development, location of facilities, equipment procurement and implementation plans.  Based on the development plan, the Consultant prepares the basic functions and specifications of ITS facility and system in accordance with ITS Standards prepared by JICA T/A.

Work diagram of ITS plan is shown in Figure D.17, and main contents of ITS basic requirements and system are shown in Table D.15, respectively.

Figure D.17   Work Diagram of ITS Plan

Table D.15   Main Contents of ITS Basic Requirements and System

| No. | Items | Contents |
| --- | --- | --- |
| 1 | Organization | Organization of maintenance, traffic management and toll collection |
| 2 | Traffic Control | Operation system for traffic control including emergency site management |
| 3 | Road Traffic Information (Collection) | Item, contents, frequencies, information flow and operation plan to be collected by ITS |
|  |  | (traffic volume, congestion and accident, over-weight, weathers, disaster, structural conditions) |
| 4 | Road Traffic Information (Provision) | Required road traffic information providing to road users and stakeholders |
| 5 | Toll Collection | Toll collection method and transaction flow |

Prepare Basic Design of ITS Facilities

The Consultant prepares the basic design of ITS facilities, communication system, toll collection facilities and system and obtains the approval from VEC/PNU85.

Work diagram of basic design of ITS facilities is shown in Figure D.18.

Figure D.18   Work Diagram of Basic Design of ITS Facilities

Electrical Facilities Design

Prepare Detailed Engineering Design of Electrical Facilities

The Consultant prepares the detailed engineering design of electrical facilities in relation with the basic design of civil structures (D.3.1), O&M buildings (D.4.3) and ITS facilities (D.5.2).  The works are included to coordinate and agree the power receiving plan with the power suppliers in the Project area.

Work diagram of detailed engineering design of electrical facilities is shown in Figure D.19, and electrical facilities plan in F/S is shown in Table D.16, respectively.

Figure D.19   Work Diagram of Electrical Facilities Design

Table D.16   Electrical Facilities Plan in F/S

| No. | Items | Facilities |
| --- | --- | --- |
| 1 | Power Supply | Power receiving points, receiving power voltages and capacities, and back-up power supply facilities |
| 2 | Road Lighting | Lighting source and output power, height, interval and location of lighting poles, and lighting calculation |
| 3 | Tunnel Ventilation and Safety | Reporting system, information system, fire-fighting facilities, and ventilation facilities, etc. |

Source:	Decision No. 2656/QD-BGTVT dated on September 10, 2010

Public Utilities Relocation Plan

Prepare Relocation Plan of Public Utilities

The Consultant confirms the public utilities which are necessary to relocate by the implementation of the Project based on the topographic survey (D.2.2), relevant facilities survey (D.2.6) and basic design of civil structures (D.3.1).  The Consultant prepares and agrees the relocation plan and cost estimate in cooperation with the relevant agencies.

Work diagram of public utilities relocation plan is shown in Figure D.20, and probable public utilities to be relocated by the Project are shown in Table D.17, respectively.

Figure D.20   Work Diagram of Public Utilities Relocation Plan

Table D.17   Probable Public Utilities to be relocated by the Project

| No. | Public utilities | Owners |
| --- | --- | --- |
| 1 | Electrical Line | Power Transmission Company No.2 (PTC2) |
| 2 | Telecommunication Line | Vietnam Posts and Telecommunications Group (VNPT) or |
|  |  | Vietnam Military Electronic and Telecommunications Corporation (VIETTEL) |
| 3 | Water Supply Pipe | Water Supply Company in each City/Province |
| 4 | Sewerage Pipe | Transport Works Management Company or Drainage Company |
| 5 | Irrigation Canal | Department of Agriculture and Rural Development (DARD) |

Safeguards

Assist in Updating EIA and EMP

The Consultant assists PMU85 in updating EIA and EMP.  The environmental assessment for the Project is required to satisfy not only the Vietnamese law/regulations but also JICA/WB safeguard policies.

The F/S alignment was finalized through the appraisal process to the draft F/S.  However, the used map of existing EIA is too small scale (1/50,000) and not suitable for confirmation of appropriateness of the road alignment.  Therefore, the Consultant reviews and confirms the appropriateness of the F/S alignment with the alternative study based on the adequate scale maps and design details.

In relation with the engineering design, the Consultant analyzes the environmental impacts by the Project and incorporates the environmental requirements to the engineering design.  Based on above, the Consultant develops the mitigation measures and updates the existing EIA and EMP including the preparation of draft TOR for external monitoring by the third party during the construction stage.

Work diagram of updating EIA and EMP is shown in Figure D.21.

Figure D.21   Work Diagram of Updating EIA and EMP

Assist in Preparing and Enforcing CPCSR

The Consultant assists CARB in each DPC in preparing and enforcing CPCSR.  In the kick-off meeting with CARBs, the Consultant confirms the activities, procedures and schedule and obtains the consensus including the measurement for the gaps between the Vietnamese law/regulations and JICA/WB safeguard policies.

The Consultant prepares the Inception Report (Resettlement Monitoring Plan) for the CPCSR activities and reports the internal monitoring results every month to assist the monitoring by PMU85.  As for the external monitoring by independent organizations, the Consultant also assists PMU85 in preparing the draft TOR.

Work diagram of preparing and enforcing CPCSR is shown in Figure D.22, and describes the methodology of work items subsequently.

Figure D.22   Work Diagram of Preparing and Enforcing CPCSR

Prepare Resettlement Monitoring Plan

The Consultant prepares the Inception Report (Resettlement Monitoring Plan) for the CPCSR activities.  In the kick-off meeting with CARBs, the Consultant confirms the activities, procedures and schedule and obtains the consensus including the measurement for the gaps between the Vietnamese law/regulations and JICA/WB safeguard policies.

Assist in Updating Census of PAPs

The Consultant assists CARBs in updating the list of PAPs in RAP in accordance with the ROW survey (D.2.2(11)) and cadastral maps in each PC.

The Consultant also assists CARBs in updating the census of PAPs by utilizing the existing Detailed Measurement Survey (DMS) and Socio-economic Survey (SES) data.

The DMS and SES data was conducted within the past two (2) years in RAP preparation and covers 10 % of the severely affected peoples and 10 % of all other peoples; therefore, the Consultant does not conduct those surveys in the Services.

Assist in Establishing Land Acquisition and Compensation Policy

The Consultant assists CARBs in conducting the consultation and disclosure program to all of key stakeholders and establishes the land acquisition and compensation policy as follows:

Options for compensation and resettlement;

Proposed resettlement sites, infrastructures, amenities and environmental management;

Assistance for generation of income, and restoration of livelihood and quality of life;

Special assistance program for poor and vulnerable PAPs;

Consideration for cultural sites, common properties and traditional resources;

Public consultation and disclosure mechanisms;

Entitlements and grievance procedures;

Unit price for compensation and resettlement;

Institutional, organizational and budgeting arrangements;

Implementation schedule.

Assist in Finalizing CPCSR

Based on the land acquisition and compensation policy above, the Consultant assists CARBs in finalizing the Comprehensive Plan on Compensation, Support and Resettlement (CPCSR) and obtains the approval from the relevant organizations.

Assist in Preparing Draft TOR (External Resettlement Monitoring)

As explained in Figure A.7, PMU85 shall engage the independent organization for conducting the external resettlement monitoring in CPCSR framework.  The Consultant assists PMU85 in preparing the draft TOR for the external resettlement monitoring.

Internal Monitoring (CPCSR)

During the Services, the Consultant prepares and submits internal resettlement monitoring report every month to assist the monitoring by PMU85.

Construction Planning

Prepare Construction Plan

The Consultant prepares the construction methods, schedule, temporary facilities and procurement plan of labors, materials and construction machines to estimate the proper Project cost. Especially, the volume of borrow materials are huge; therefore, the Consultant prepares the mass curve to estimate the proper hauling cost.

Work diagram of construction planning is shown in Figure D.23, and image of construction scheduling and mass curve is shown in Figure D.24, respectively.

Figure D.23   Image of Construction Scheduling and Mass Curve

| Construction Scheduling (MS Project) | Mass Curve |
| --- | --- |

Figure D.24   Image of Construction Scheduling and Mass Curve

Project Cost Estimate

Estimate Project Cost

The Consultant estimates the Project cost and annual fund requirements by contract packages in relation with the construction plan (D.9.1).  The cost estimate conditions are severely affected to the outputs; therefore, the Consultant proposes those conditions in advance and obtains the approval from VEC/PMU85 and other relevant organizations.

Work diagram of Project cost estimate is shown in Figure D.25, and main contents of cost estimate conditions are shown in Table D.26, respectively.

Figure D.25   Work Diagram of Project Cost Estimate

Table D.26   Main Contents of Cost Estimate Conditions

| No. | Item | Contents |
| --- | --- | --- |
| 1 | Time of Cost Estimate | Time applied in the cost estimate (quarter) |
| 2 | Currency | Foreign currency applied in the cost estimate |
| 3 | Exchange Rate | Exchange rate for the foreign currency applied in the cost estimate |
| 4 | Classification Condition of Currency | Classification conditions of foreign and local currencies applied in the cost estimate |
| 5 | Tax Exemption | Items of the tax exemption applied in the cost estimate |
| 6 | Cost Estimate Standards | Cost estimate standards applied in the cost estimate |
|  |  | (productivity, and unit cost of materials, labors, construction machine operation and hauling ) |
| 7 | Price Fluctuation Rate | Price fluctuation rate of the foreign and local currencies applied in the cost estimate |
| 8 | Physical Contingency Rate | Physical contingency rate applied in the cost estimate |

Procurement Documents

Prepare Procurement Documents

The Consultant prepares the procurement plan, P/Q and bidding documents including those evaluation criteria in accordance with the current WB/JICA procurement guidelines and standard forms.

The conditions of contract in the bidding documents are applied the appropriate series of FIDIC, and the technical specifications including EMP with supervision of engineers/specialists in every technical field for ensuring the quality.

Work diagram of procurement documents preparation is shown in Figure D.26.

Figure D.26   Work Diagram of Procurement Documents Preparation

Project Implementation Program

Prepare Project Implementation Program

The current Project I/P is shown in Figure A.9.  The Consultant updated the Project I/P, and it was approved by MOT in Decision No. **/**-***** dated on ******* **, ****.

During the Services, the Consultant studies the construction period in each contract package and updates the Project I/P in accordance with the results of construction planning (D.9), if required.

Work diagram of Project implementation program is shown in Figure D.27.

Figure D.27   Work Diagram of Project Implementation Program

Procurement Assistance

Assist in Tendering Procedures

The Consultant assists VEC/PMU85 in tendering procedures of all civil contract packages in accordance with the JICA/WB procurement guidelines.  In the assistance, the Consultant conducts the independent P/Q and bid evaluations to advise VEC/PMU85 on issues related to contract negotiations.

Work diagram of procurement assistance is shown in Figure E.1.

Figure E.1   Work Diagram of Procurement Assistance

Technology Transfer

Provide Training to VEC, PMU85 and Relevant Organizations

The Consultant provides the appropriate technology transfer to VEC, PMU85 and relevant organizations for enhancing the necessary knowledge and capacity to ensure the smooth execution of the Project and sustainable development of the expressway network in Vietnam.

The objectives of the training are that VEC, PMU85 and relevant organizations acquire the knowledge and capacity which are necessary to manage and control the Project smoothly and to make decisions with sufficient technical backgrounds for the important issues and peculiar matters of expressway in the Project.  Based on the knowledge and capacity acquired by the training program, VEC, PMU85 and relevant organizations are able to manage and control the expressway development projects by themselves.

The Consultant assigns the key professional staff as the Training Specialists and identifies the training needs with VEC, PMU85 and relevant organizations in the beginning of the Services.  Based on the needs above, the Consultant prepares the training plan which consists of the training themes, program, trainees and implementation schedule.  The training schedule is taken into account the work schedule of the Services to provide the workshops at appropriate timing in advance of the execution of the Services.

In corporation with each engineer/specialist in the respective fields, the training specialists prepare the appropriate training materials and hold the workshops to VEC, PMU85 and relevant organizations.

Tentative training themes are as follows:

Project management of all project phases (PMBOK);

Safeguards (WB/JICA safeguards policy);

Expressway road safety and auditing system (PIARC road safety manual);

Expressway administration, O&M, ITS and ETC systems (including overseas study tour).

Work program of technology transfer to VEC, PMU85 and relevant organizations is shown in Figure F.1, and tentative training program of the overseas study tour is shown in Table F.1, respectively.

Figure F.1   Work Diagram of Technology Transfer to VEC, PMU85 and Relevant Organizations

Table F.1   Tentative Training Program of Overseas Study Tour

| Day | Time | Program | Contents | Stay at |
| --- | --- | --- | --- | --- |
| 1 | Night | Move to Narita | - Move from Hanoi to Narita by airplane | Flying overnight |
| 2 | AM | Move to Tokyo | - Move from Narita to Tokyo by car | Tokyo |
|  | PM | Visit to MLIT | - Introduce expressway administrative policy |  |
| 3 | AM | Visit to JEHDRA | - Introduce expressway business and implementation scheme | Tokyo |
|  |  | Visit to ORSE | - Introduce ETC technology and standardized system |  |
|  | PM | Visit to HIDO | - Introduce advanced ITS technology |  |
|  |  | Visit to VICS center | - Introduce traffic information and VICS system |  |
| 4 | AM | Visit to MEX | - Introduce traffic management and O&M system for intra-urban expressway | Tokyo |
|  | PM | Visit to NEXCO | - Introduce traffic management and O&M system for inter-urban expressway |  |
| 5 | AM | Move to Narita | - Move from Tokyo to Narita by car | Hanoi |
|  |  | Move to Hanoi | - Move to Narita to Hanoi by airplane |  |

Provide Training to the Key Local Professional Staff

During the Services, the Consultant provides person-to-person technology transfer to key local professional staff by co-working style in the respective fields.  It is expected that the key local professional staff are acquired day-to-day knowledge and skills necessary for the execution of the Services.

Work diagram of technology transfer to key local professional staff is shown in Figure F.2.

Figure F.2   Work Diagram of Technology Transfer to Key Local Professional Staff

Appendix

Appendix 1: Terms of Reference

(Appendix A in the Contract)

Terms of Reference

Insert Appendix A in the Contract by Ms Thao

Appendix 2: Project Management Plan

Project Management Plan

Under Preparation by Mr. Nagai

Appendix 3: Baseline Schedule for Progress Monitoring

(MS Project)

Baseline Schedule for Progress Monitoring

Under Preparation by Mr. Nagai

Appendix 4: List of Bridges

(Based on F/S-2010)

List of Bridges (Based on F/S-2010)

Insert List of Bridges by Mr. Oba

Appendix 5: List of Culverts

(Based on F/S-2010)

List of Culverts (Based on F/S-2010)

Insert List of Culverts by Mr. Nagai