## Fig.A.1
2000
Approved preparation of BOT Pre-F/S
Approved BOT Pre-F/S
Approved preparation of BOT F/S
Prerpared BOT F/S
Approved as one (1) of top priority projects
Updated JETRO study
Undertook preparation mission
Declared eligibility for IBRD loan
Year
GOVN
JETRO
Not materialized as BOT scheme Project
Undertook identification missions
Prepared study report
Received JETRO study report
WB
Adopted study
Allowed advance procurement
Proceeded procurement process
BOT scheme
2003
2004
2005
2007
2008
2009
JETRO Study
WB Study
Finalized/submit as F/S
TEDI F/S
2011
Contracted/Issued NTP
2010
Approved F/S

## Fig.A.2
My Son
Danang City
BP
Hoi An
Hanoi/East-West Corridor
HCMC
Source: Dung Quat Economic Zone Authority
Dung Quat Economic Zone
Source: Chu Lai Open Economic Zone Authority
Chu Lai Open Economic Zone
North-South Expressway
Project Road
Quang Tri - Da Nang (Plan)
Quang Ngai - Quy Nhon (Plan)
Other Classified Road
Da Nang Bypass
National Highway
Provincial Road
Others
Provincial Border
North-South Railway
World Heritage
EP
LEGEND
Quang Ngai
N
14
14B
1A
14E
Tam Ky
Project Road (L=139.5 km)

## Fig.A.3
Goals
Purpose
Project Design (Summary)
External Conditions (Important Assumptions/Risks)
- Expressway construction and O&M equipment provision (see A.1.5(1))
- Expressway facilities and equipment
- Expressway O&M system and trained staffs
- Enhance traffic efficiency and safety (see Table A.3)
- Grow economies in the central region
- Accelerate development investments in the central region
- Provide appropriate O&M services by the established unit
- Obtain cooperation from inhabitants in the Project area
- Consulting services (see A.1.5(2))
- Project management by VEC/PMU85 (see A.1.10)
Pre-conditions
- Establishment of an O&M unit (see A.1.5(3))
- Land acquisition and resettlement (see A.1.6(2))
- Obtain agreement from inhabitants in the Project area
- Social and environmental assessment (see A.1.6(1))
Outputs
Activities

## Fig.A.4
1A
Danang
Hanoi/
HCMC
Dung Quat
East-West Corridor
Tuy Loan IC
My Son IC
Ha Lam IC
Tam Ky IC
Chu Lai IC
Dung Quat IC
Binh Son IC
Quang Ngai North IC
Quang Ngai IC
KM000+000
KM020+805
KM040+776
KM064+200
KM083+800
KM102+255
KM112+615
KM123+915
KM130+750
20.805 km
19.971 km
23.424 km
19.600 km
18.455 km
10.360 km
11.300 km
6.835 km
KM000+000
KM008+000
KM100+000
KM139+520
Expressway, L=131.5 km
Quang Ngai, L=39.52 km
Quang Nam, L=92.0 km
Danang, L=8.0 km
KM000+000
KM131+500
North-South Expressway
Danang - Quang Ngai
Quang Tri-Danang (Plan)
Quang Ngai-Quy Nhon (Plan)
Other Classified Road
Danang Bypass
National Highway
Provincial/District/City Roads
Provincial/District/City Road (Plan)
Railway
North-South Railway
LEGEND
Project Facilities
Thruway (Expressway)
Linking Road (New Construction)
Interchange (IC)
Viaduct
Major River Bridge
Tunnel
Traffic Management Center (TMC)
Expressway Operation Office (EOO)
Service Area (SA)
Parking Area (PA)
Toll Barrier (TB)
Toll Gate (TG)
Toll Plaza Office (TPO)
14B
PA, KM029+130
SA, KM069+600
TMC, KM000+950
Tuy Loan TPO
My Son
Ha Lam TPO
Tam Ky TPO
Chu Lai TPO
Dung Quat TPO
TB, KM129+800
14E
TPO
Quang Ngai TPO
TN01, KM022+900, L=2@540 m
Chiem Son Bridge (LRB09), KM020+185, L=410.00 m
VD02, KM010+271, L=90.20 m
Ky Lam Bridge (LRB08), KM017+662, L=962.00 m
VD07, KM018+319, L=86.20 m
VD08, KM018+612, L=62.15 m
VD09, KM018+831, L=86.20 m
Tra Bong Bridge (LRB19), KM109+320, L=452.00 m
VD17, KM110+120, L=492.00 m
VD20, KM128+180, L=292.00 m
VD19, KM127+200, L=652.00 m
Tra Khuc Bridge (LRB20), KM125+700, L=846.00 m
BP
EP
Length between ICs
Length by City/Province
Total Length
TB, KM004+750
District
District
Chu Lai
Road
Road
Industrial
Dung Quat
Industrial
Tra Bong-
Road
Provincial
Road
Provincial
Quang Ngai
City Ring Road
610
616
Road
623
Road
625
Quang Ngai
City
Road
Binh Long
EOO, KM064+750
PA, KM098+800
Binh Son
VD03, KM011+904, L=150.25 m
VD04, KM013+210, L=138.30 m
VD05, KM014+873, L=117.20 m
VD06, KM015+171, L=117.20 m
VD10, KM019+350, L=47.10 m
VD11, KM021+900, L=47.10 m
VD13, KM027+900, L=26.10 m
VD14, KM032+440, L=26.10 m
VD15, KM034+120, L=70.15 m
VD16, KM105+328, L=36.00 m
VD18, KM124+400, L=412.00 m
VD12, KM027+000, L=34.10 m
L=42.00 m
Thruway (Embankment Section, Initial Stage&Ultimate Stage1))
Thruway (Cutting Section, Initial Stage&Ultimate Stage1))
Thruway (Bridge Section, Initial Stage&Ultimate Stage1))
Thruway (Tunnel Section, Initial Stage&Ultimate Stage1))
Linking Road (Embankment Section, Initial Stage)
Linking Road (Bridge Section, Initial Stage)
Culvert
Frontage Road
TPO
North TPO
Quang Ngai
-KM000+120, L=49.10 m
VD01 (Widening),
VD21, KM134+726
KM139+520
Linking Road L=8.02 km
12.00
12.00
2@3.50=7.00

## Fig.A.5
Lenders
Operator
User
CPC/PPCs
Ministries
MOT
MOF
VEC
MONRE
MOPS
DOFPPs
Road user
DONREs
DOLAs
DOTPs
DOTs
WB/JICA
Repay loans
Pay taxes
Repay loans
Provide services/
pay toll
Transfer
taxes
Report environ. conditions/
instruct correction
Lease ROW/
pay lease fee
Provide facilities and equip./
provide emergency services
Provide facilities
and equipment/
control traffic
violators
See Note 1)
(O&M unit)

## Fig.A.6
Stage
WB/JICA
VEC/PMU85,1
D/D
Contractors
Consultants
DONREs
MONRE
Construction
Operation
- Supervise and advise to task team (WB: QACU/Safeguard team in regional office, JICA: ESCRD)
- Concur updated EIA
- Approve updated EIA
- Evaluate the Project (WB: OED, JICA: ED)
- Implement EMP
- Assist in updating EIA
- Supervise EMP implementating
- Review and comment to monitoring
- Update EIA
- Monitor (third party)
- Manage EMP implementating
- Assist in monitoring (2 years)
- Evaluate the Project (2 years later)
- Monitor (O&M unit under VEC)
- Review and comment to monitoring
- Conduct interim review (1-2 times/year)
- Review and comment to monitoring
- Review and comment to monitoring (2 years)
Entrust/Report
Internal
External Monitoring
Monitoring

## Fig.A.7
Stage
WB/JICA
VEC/PMU85,1
Consultants
CPC/PPCs
MOT
D/D
Construction
Operation
- Assist in CPCSR and monitoring activities
- Approve CPCSR and supervise enforcing
- Prepare RMP and monitor enforcing
- Review and comment to monitoring
- Monitor (third party)
- Review and comment to monitoring
DPCs
- Prepare and enforce CPCSR (CARBs)
Entrust/Report
- Supervise and advise to task team (WB: QACU/Safeguard team in regional office, JICA: ESCRD)
- Evaluate the Project
- Conduct interim review (1-2 times/year)
- Assist in conducting survey and preparing support plan
- Conduct post-resettlement survey (third party)
(WB: OED, JICA: ED)
- Manage survey and notify to conduct support plan
Entrust/Report
- Instruct to conduct support plan to PAPs
- Review and comment to surveying and planning
- Review and comment to surveying and planning
- Conduct interim review (1-2 times/year)
- Conduct support plan to PAPs (CARBs)
- Concur CPCSR
External Monitoring
Internal
Monitoring
- Prepare support plan to PAPs (third party)
- Concur survey and support plans to PAPs
- Deliberate and supervise CPCSR (DRCs)

## Fig.A.8
Japan International Cooperation Agency (JICA)
The World Bank (WB)
Government of Vietnam (GOVN)
Quang Nam PPC
O&M Unit (to be established)
Ministry of Transport (MOT)
Danang CPC
Lender
Consultant/Contractor
Other Stakeholders
Quang Ngai PPC
JICA Portion
WB Portion
Lender
Project Implementation Agency/Unit
Project Owner
WB Portion
D/D and JICA Portion
D/D
Line Ministry
C/S Consultant
Contractors
PIS1)
Consultants
Vietnam Expressway Corporation (VEC)
D/D Consultant
(the Services)
Project Management Unit No. 85 (PMU85)
Project Management Unit No. 1 (PMU1)
Contractors
C/S Consultant

## Fig.A.9
No. | Items |  |  |  | Months | 2011 | 2012 | 2013 | 2014 | 2015 | 2016
1 |  | Common
11 |  | Loan Sign/ | JICA |  | -----
12 |  | Effectiveness | WB |  | -----
2 |  | D/D (Whole Sections, the Services) |  |  | 14
21 |  | D/D | Civil Work PKGs | 1st Priority: PKG3a | 4
22 |  |  |  | 2nd Priority: PKG1, A5 | 9
23 |  |  |  | Non-Priority: PKG2, 3b-A4 | 12
24 |  |  | Elec./O&M/ITS PKGs (B/D) | PKG13 | 6
25 |  | Land Acquisition and Resettlement |  |  | 10
26 |  | Procurement | Civil Work Contractors | 1st Priority: PKG3a | 10
27 |  |  | (ICB) | 2nd Priority: PKG1, A5 | 10
28 |  |  |  | Non-Priority: PKG2, 3b-A4 | 10
3 |  | Construction (JICA Portion) |  |  | 55
31 |  | Procurement | C/S Consultant (ICB) |  | 6
32 |  | C/S | Civil Work PKGs | PKG1-7 | 49
33 |  |  | Elec./O&M/ITS PKGs | B/D Review | 6
34 |  |  | (PKG13) | Procurement (ICB) | 10
35 |  |  |  | C/S | 30
36 |  | Construction | Civil Work PKGs | 1st Priority: PKG3a | 42
37 |  | Works |  | 2nd Priority: PKG1 | 42
38 |  |  |  | Non-priority: PKG2, 3b-7 | 36
39 |  |  | Elec./O&M/ITS PKGs (PKG13) |  | 30
4 |  | Construction (WB Portion) |  |  | 50
41 |  | Procurement | C/S Consultant (ICB) |  | 6
42 |  | C/S | Civil Work PKGs | PKGA1-A5 | 44
43 |  | Construction | Civil Work PKGs | 2nd Priority: PKGA5 | 42
44 |  | Works |  | Non-priority: PKGA1-A4 | 36
Prior Works
Posterior Works (Intermittent Assignment)
Opening of the Project Road

## Fig.A.10
Calender | [7 empty] | Calender Year |  |  |  | 2011 | [5 empty] | 2012 | [11 empty] | 2013
[8 empty] | Calender Month |  |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
[8 empty] | Cumulative Month |  |  |  | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1st Priority Package (PKG3a) | [7 empty] | Civil Engineering Design
Procurement Assistance
2nd Priority Packages (PKG1, PKGA4) | [7 empty] | Civil Engineering Design
Procurement Assistance
Non-Priority Packages (Other PKGs) | [7 empty] | Civil Engineering Design
Procurement Assistance
Part B |  | Project Management | [8 empty] | 18.5 months
|  | B.1 | Establish and control practical management system | [7 empty] | 18.5 months
Part C |  | Previous Studies Review and Establishing Detailed Engineering Design Framework | [8 empty] | 6.0 months
|  | C.1 | Review previous studies | [7 empty] | 6.0 months
|  | C.2 | Establish detailed engineering design framework | [7 empty] | 5.0 months
Part D |  | Detailed Engineering Design and Procurement Planning | [8 empty] | 18.5 motnhs
D.1 |  | Contract Packaging | [8 empty] | 1.0 months
|  | D.1.1 | Propose contract packaging | [7 empty] | 1.0 months
D.2 |  | Surveys and Investigations | [8 empty] | 12.5 months
|  | D.2.1 | Collect relevant data and documents | [7 empty] | 1.0 months
|  | D.2.2 | Conduct topographic survey | [7 empty] | 9.5 months
|  |  | - Control Point and Topographic Surveys | [7 empty] | 7.5 months
|  |  | - ROW Survey | [7 empty] | 2.0 months
|  | D.2.3 | Conduct hydrological survey and analysis | [7 empty] | 3.0 months
|  | D.2.4 | Conduct geotechnical and geological investigations | [7 empty] | 5.0 months
|  | D.2.5 | Conduct material source survey | [7 empty] | 2.0 months
|  | D.2.6 | Conduct relevant facilities survey | [7 empty] | 3.0 months
|  | D.2.7 | Review traffic forecasting and conduct baseline surveys | [7 empty] | 3.0 months
|  | D.2.8 | Conduct independent land valuation survey | [7 empty] | 4.0 months
|  | D.2.9 | Conduct environmental and social surveys | [7 empty] | 8.0 months
D.3 |  | Civil Engineering Design | [8 empty] | 15.0 months
|  | D.3.1 | Prepare basic design of civil structures | [7 empty] | 7.0 months
|  |  | - 1st Priority Package (PKG3a) | [7 empty] | 4.0 months
|  |  | - 2nd Priority Packages (PKG1/PKGA4) | [7 empty] | 5.0 months
|  |  | - Non-priority Packages (Other PKGs) | [7 empty] | 7.0 months
|  | D.3.2 | Prepare detailed engineering design of civil structures | [7 empty] | 11.0 months
|  |  | - 1st Priority Package (PKG3a) | [7 empty] | 3.0 months
|  |  | - 2nd Priority Packages (PKG1/PKGA4) | [7 empty] | 4.0 months
|  |  | - Non-priority Packages (Other PKGs) | [7 empty] | 8.0 months
D.4 |  | O&M Plan and Design | [8 empty] | 7.0 months
|  | D.4.1 | Prepare institutional and administrative arrangement plan | [7 empty] | 2.0 months
|  | D.4.2 | Prepare O&M plan | [7 empty] | 3.0 months
|  | D.4.3 | Prepare basic design of O&M buildings | [7 empty] | 3.0 months
D.5 |  | ITS Plan and Design | [8 empty] | 5.0 months
|  | D.5.1 | Prepare ITS plan | [7 empty] | 2.0 months
|  | D.5.2 | Prepare basic design of ITS facilities | [7 empty] | 3.0 months
D.6 |  | Electrical Facilities Design | [8 empty] | 5.0 months
|  | D.6.1 | Prepare detailed engineering design of electrical facilities | [7 empty] | 5.0 months
D.7 |  | Public Utilities Relocation Plan | [8 empty] | 2.0 months
|  | D.7.1 | Prepare relocation plan of public utilities | [7 empty] | 2.0 months
D.8 |  | Safeguards | [8 empty] | 14.0 months
|  | D.8.1 | Assist in updating EIA and EMP | [7 empty] | 8.0 months
|  | D.8.2 | Assist in preparing and enforcing CPCSR | [7 empty] | 14.0 months
D.9 |  | Construction Planning | [8 empty] | 10.5 months
|  | D.9.1 | Prepare construction plan | [7 empty] | 10.5 months
D.10 |  | Project Cost Estimate | [8 empty] | 11.5 months
|  | D.10.1 | Estimate Project cost | [7 empty] | 11.5 months
D.11 |  | Procurement Documents | [8 empty] | 14.0 months
|  | D.11.1 | Prepare procurement documents | [7 empty] | 14.0 months
D.12 |  | Project Implementation Program | [8 empty] | 1.0 months
|  | D.12.1 | Prepare Project I/P | [7 empty] | 1.0 months
Part E |  | Procurement Assistance | [8 empty] | 14.0 months
|  | E.1 | Assist in tendering procedures | [7 empty] | 14.0 months
Part F |  | Technology Transfer | [8 empty] | 18.5 months
|  | F.1 | Provide training to VEC, PMU85 and relevant organizations | [7 empty] | 4.0 months
|  | F.2 | Provide training to the key local professional staff | [7 empty] | 18.5 months
: Heavy Rainy Season
Calender | [7 empty] | Calender Year |  |  |  | 2011 | [5 empty] | 2012 | [11 empty] | 2013
[8 empty] | Calender Month |  |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
[8 empty] | Cumulative Month |  |  |  | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
General |  |  |  | 1) | Inception Report |  |  |  | 30 copies | (English: 15, Vietnamese: 15)*01
Reports |  |  |  | 2) | Monthly Progress Reports |  |  |  | 540 copies | (English: 15, Vietnamese: 15)*18
|  |  |  | 3) | Interim Reports |  |  |  | 180 copies | (English: 15, Vietnamese: 15)*06
|  |  |  | 4) | Draft Project Completion Report |  |  |  | 30 copies | (English: 15, Vietnamese: 15)*01
|  |  |  | 5) | Project Completion Report |  |  |  | 30 copies | (English: 15, Vietnamese: 15)*01
|  |  |  | 6) | Review Reports
[5 empty] | a) | Review Report (Civil) |  |  | 30 copies | (English: 15, Vietnamese: 15)*01
[5 empty] | b) | Review Report (O&M/ITS) |  |  | 30 copies | (English: 15, Vietnamese: 15)*01
|  |  |  | 7) | Detailed Engineering Design Framework |  |  |  | 30 copies | (English: 15, Vietnamese: 15)*01
|  |  |  | 8) | Contract Packaging |  |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 9) | Project I/P |  |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 10) | Technology Transfer Reports
[5 empty] | a) | Training Program |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | b) | Training Materials
[6 empty] | i) | Training Material (Project Management, Safeguards) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | ii) | Training Material (Road Safety Audit) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | iii) | Training Material (O&M/ITS) |  | 6 copies | (English: 03, Vietnamese: 03)*01
Technical |  |  |  | Survey Reports
Reports |  |  |  | 11) | Relevant Data and Documents |  |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 12) | Topographic Survey Reports
[5 empty] | a) | Work Plan
[6 empty] | i) | Work Plan (Control Point Survey) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | ii) | Work Plan (Topographic Survey) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | b) | Control Point and Topographic Surveys Report |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 13) | ROW Survey Reports
[5 empty] | a) | Work Plan (ROW Survey) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | b) | ROW Survey Report |  |  | 30 copies | (English: 15, Vietnamese: 15)*01
|  |  |  | 14) | Hydrological/Inundation Analyses Reports
[5 empty] | a) | Work Plan (Hydrological Survey) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | b) | Hydrological Survey Report |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | c) | Hydrological/Inundation Analyses Reports
[6 empty] | i) | Hydrological/Inundation Analyses Report (Danang/Quang Nam) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | ii) | Hydrological/Inundation Analyses Report |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 15) | Geotechnical and Geological Investigations Report
[5 empty] | a) | Work Plan (Geotechnical and Geological Investigations) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | b) | Geotechnical and Geological Investigations Report |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 16) | Material Source Survey Report
[5 empty] | a) | Work Plan (Material Source Survey) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | b) | Material Source Survey Report |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 17) | Relevant Facilities Survey Report |  |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 18) | Traffic Forecasting Review Report |  |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 19) | Baseline Survey Reports (Additional Traffic Survey)
[5 empty] | a) | Work Plan (Baseline Survey) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | b) | Baseline Survey Report (Additional Traffic Survey) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 20) | Independent Land Valuation Survey Reports
[5 empty] | a) | Work Plan (Independent Land Valuation Survey) |  |  | 12 copies | (English: 06, Vietnamese: 06)*01
[5 empty] | b) | Independent Land Valuation Survey Report |  |  | 12 copies | (English: 06, Vietnamese: 06)*01
|  |  |  | 21) | Environmental and Social Survey Report (Site Survey) |  |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
Civil Engineering Design
Basic Design Reports (Civil)
|  |  |  | 22) | Working Design Reports
Design Criteria and Conditions
[5 empty] | a) | Design Criteria and Conditions (Civil 1) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
Typical Cross Sections
[5 empty] | b) | Typical Cross Sections |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
Highway Design
[5 empty] | c) | Geometric Design (Thruway)
[6 empty] | i) | Geometric Design (Thruway, PKG3a) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | ii) | Geometric Design (Thruway, PKG1/PKGA4) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | iii) | Geometric Design (Thruway) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | d) | Interchange Plan
[6 empty] | i) | Interchange Plan (PKG1/PKGA4) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | ii) | Interchange Plan |  | 6 copies | (English: 03, Vietnamese: 03)*01
: Heavy Rainy Season
Calender | [7 empty] | Calender Year |  |  |  | 2011 | [5 empty] | 2012 | [11 empty] | 2013
[8 empty] | Calender Month |  |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
[8 empty] | Cumulative Month |  |  |  | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Technical |  |  |  |  | e) | Frontage Road Plan (by PKG) |  |  | 78 copies | (English: 03, Vietnamese: 03)*13
Reports |  |  |  |  | f) | Culvert Plan (Thruway, by PKG) |  |  | 78 copies | (English: 03, Vietnamese: 03)*13
Bridge Design
[5 empty] | g) | Bridge Plan (Thruway Bridges, by PKG) |  |  | 78 copies | (English: 03, Vietnamese: 03)*13
[5 empty] | h) | Standard Design (Bridge Works) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | i) | Revetment/River Bed Protection Design
[6 empty] | i) | Revetment/River Bed Protection Design (PKG3a) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | ii) | Revetment/River Bed Protection Design (PKG1/PKGA4) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | iii) | Revetment/River Bed Protection Design |  | 6 copies | (English: 03, Vietnamese: 03)*01
Tunnel Design
[5 empty] | j) | Tunnel Plan |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 23) | Basic Design Reports (Civil)
[5 empty] | a) | Basic Design Report (Civil, PKG3a) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | b) | Basic Design Report (Civil, PKG1/PKGA4) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | c) | Basic Design Report (Civil) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
Detailed Engineering Design Reports (Civil)
|  |  |  | 24) | Working Design Reports
Design Criteria and Conditions
[5 empty] | a) | Design Criteria and Conditions (Civil 2, Others) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
Highway Design
[5 empty] | b) | Geometric Design (Others, by PKG, excl. PKG3a)
[6 empty] | i) | Geometric Design (Others, PKG1/PKGA4) |  | 12 copies | (English: 03, Vietnamese: 03)*02
[6 empty] | ii) | Geometric Design (Others, Other PKGs) |  | 60 copies | (English: 03, Vietnamese: 03)*10
[5 empty] | c) | Standard Design (Culvert Works) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
Bridge Design
[5 empty] | d) | Bridge Plan (Other Bridges, by PKG, excl. PKG3a)
[6 empty] | i) | Bridge Plan (Others, PKG1/PKGA4) |  | 12 copies | (English: 03, Vietnamese: 03)*02
[6 empty] | ii) | Bridge Plan (Others, Other PKGs) |  | 60 copies | (English: 03, Vietnamese: 03)*10
[5 empty] | e) | Bridge Temporary Facility Design (by PKG)
[6 empty] | i) | Bridge Temporary Facility Design (PKG3a) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | ii) | Bridge Temporary Facility Design (PKG1/PKGA4) |  | 12 copies | (English: 03, Vietnamese: 03)*02
[6 empty] | iii) | Bridge Temporary Facility Design (Other PKGs) |  | 60 copies | (English: 03, Vietnamese: 03)*10
[5 empty] | f) | Standard Design (Bridge Temporary Facility Works) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
Other Design
[5 empty] | g) | Road Accessory Design (by PKG)
[6 empty] | i) | Road Accessory Design (PKG3a) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | ii) | Road Accessory Design (PKG1/PKGA4) |  | 12 copies | (English: 03, Vietnamese: 03)*02
[6 empty] | iii) | Road Accessory Design (Other PKGs) |  | 60 copies | (English: 03, Vietnamese: 03)*10
[5 empty] | h) | Standard Design (Road Accessory) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | i) | Slope Protection Design (by PKG)
[6 empty] | i) | Slope Protection Design (PKG3a) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | ii) | Slope Protection Design (PKG1/PKGA4) |  | 12 copies | (English: 03, Vietnamese: 03)*02
[6 empty] | iii) | Slope Protection Design (Other PKGs) |  | 60 copies | (English: 03, Vietnamese: 03)*10
[5 empty] | j) | Standard Design (Slope Protection Works) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | k) | Retaining Wall Design (by PKG)
[6 empty] | i) | Retaining Wall Design (PKG3a) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | ii) | Retaining Wall Design (PKG1/PKGA4) |  | 12 copies | (English: 03, Vietnamese: 03)*02
[6 empty] | iii) | Retaining Wall Design (Other PKGs) |  | 60 copies | (English: 03, Vietnamese: 03)*10
[5 empty] | l) | Standard Design (Retaining Wall) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | m) | Softground Treatment Design (by PKG, PKG1/PKG2)
[6 empty] | i) | Slope Protection Design (PKG1) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | ii) | Slope Protection Design (PKG2) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | n) | Standard Design (Softground Treatment) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | o) | Pavement Design (by PKG)
[6 empty] | i) | Pavement Design (PKG3a) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | ii) | Pavement Design (PKG1/PKGA4) |  | 12 copies | (English: 03, Vietnamese: 03)*02
[6 empty] | iii) | Pavement Design (Other PKGs) |  | 60 copies | (English: 03, Vietnamese: 03)*10
[5 empty] | p) | Standard Design (Pavement Works) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
: Heavy Rainy Season
Calender | [7 empty] | Calender Year |  |  |  | 2011 | [5 empty] | 2012 | [11 empty] | 2013
[8 empty] | Calender Month |  |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
[8 empty] | Cumulative Month |  |  |  | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Technical |  |  |  |  | r) | Drainage Design (by PKG)
Reports | [5 empty] | i) | Drainage Design (PKG3a) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | ii) | Drainage Design (PKG1/PKGA4) |  | 12 copies | (English: 03, Vietnamese: 03)*02
[6 empty] | iii) | Drainage Design (Other PKGs) |  | 60 copies | (English: 03, Vietnamese: 03)*10
[5 empty] | s) | Standard Design (Drainage Works) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
Construction Plan
[5 empty] | t) | Construction Plan (by PKG)
[6 empty] | i) | Construction Plan (PKG3a) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | ii) | Construction Plan (PKG1/PKGA4) |  | 12 copies | (English: 03, Vietnamese: 03)*02
[6 empty] | iii) | Construction Plan (Other PKGs) |  | 60 copies | (English: 03, Vietnamese: 03)*10
|  |  |  | 25) | Detailed Engineering Design Reports (Civil)
[5 empty] | a) | Detailed Engineering Design Report (Civil, PKG3a) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | b) | Detailed Engineering Design Reports (Civil, PKG1/PKGA4) |  |  | 12 copies | (English: 03, Vietnamese: 03)*02
[5 empty] | c) | Detailed Engineering Design Reports (Civil, Other PKGs) |  |  | 60 copies | (English: 03, Vietnamese: 03)*10
[5 empty] | d) | Detailed Engineering Design Report (Civil) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 26) | Quantity Reports (Civil)
[5 empty] | a) | Quantity Report (Civil, PKG3a) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | b) | Quantity Reports (Civil, PKG1/PKGA4) |  |  | 12 copies | (English: 03, Vietnamese: 03)*02
[5 empty] | c) | Quantity Reports (Civil, Other PKGs) |  |  | 60 copies | (English: 03, Vietnamese: 03)*10
[5 empty] | d) | Quantity Report (Civil) |  |  | 30 copies | (English: 15, Vietnamese: 15)*01
|  |  |  | 27) | Road Safety Audit Report
Electrical/O&M/ITS Plan and Design
|  |  |  | 28) | Electrical/O&M/ITS Plan
[5 empty] | a) | O&M Plan
[6 empty] | i) | Institutional and Administrative Arrangement Plan |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | ii) | O&M Plan |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | b) | ITS Plan |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | c) | Electrical Facility Plan |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 29) | Draft Basic Design Reports (Electrical/O&M/ITS)
[5 empty] | a) | Design Criteria and Conditions
[6 empty] | i) | Design Criteria and Conditions (O&M) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | ii) | Design Criteria and Conditions (ITS) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | iii) | Design Criteria and Conditions (Electrical) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | b) | Draft Basic Design Report (Electrical/O&M/ITS) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 30) | Quantity Report (Electrical/O&M/ITS) |  |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
Public Utilities Relocation Plan
|  |  |  | 31) | Public Utilities Relocation Plan |  |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
Cost Estimate Reports
|  |  |  | 32) | Cost Estimate Conditions |  |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 33) | Cost Estimate Reports
[5 empty] | a) | Cost Estimate Report (Civil, PKG3a) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | b) | Cost Estimate Reports (Civil, PKG1/PKGA4) |  |  | 12 copies | (English: 03, Vietnamese: 03)*02
[5 empty] | c) | Cost Estimate Reports (Civil, Other PKGs) |  |  | 60 copies | (English: 03, Vietnamese: 03)*10
[5 empty] | d) | Cost Estimate Report (Electrical/O&M/ITS, PKG13) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | e) | Cost Estimate Report |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
Procurement |  |  |  | Procurement Documents
Reports |  |  |  | 34) | Procurement Plan |  |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 35) | Pre-qualification Documents (by PKG)
[5 empty] | a) | Pre-qualification Documents (Civil)
[6 empty] | i) | Pre-qualification Document (Civil, PKG3a) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | ii) | Pre-qualification Documents (Civil, PKG1/PKGA4) |  | 12 copies | (English: 03, Vietnamese: 03)*02
[6 empty] | iii) | Pre-qualification Documents (Civil, Other PKGs) |  | 60 copies | (English: 03, Vietnamese: 03)*10
[5 empty] | b) | Draft Pre-qualification Document (Electrical/O&M/ITS, PKG13) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 36) | Bidding Documents (by PKG)
[5 empty] | a) | Bidding Documents (Civil)
[6 empty] | i) | Bidding Document (Civil, PKG3a) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | ii) | Bidding Documents (Civil, PKG1/PKGA4) |  | 12 copies | (English: 03, Vietnamese: 03)*02
[6 empty] | iii) | Bidding Documents (Civil, Other PKGs) |  | 60 copies | (English: 03, Vietnamese: 03)*10
[5 empty] | b) | Draft Bidding Document (Electrical/O&M/ITS, PKG13) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
: Heavy Rainy Season
Calender | [7 empty] | Calender Year |  |  |  | 2011 | [5 empty] | 2012 | [11 empty] | 2013
[8 empty] | Calender Month |  |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
[8 empty] | Cumulative Month |  |  |  | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Procurement |  |  |  | Tender Assistance Reports
Reports |  |  |  | 37) | P/Q Evaluation Reports (Civil, by PKG)
[5 empty] | a) | P/Q Evaluation Report (Civil, PKG3a) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | b) | P/Q Evaluation Reports (Civil, PKG1/PKGA4) |  |  | 12 copies | (English: 03, Vietnamese: 03)*02
[5 empty] | c) | P/Q Evaluation Reports (Civil, Other PKGs) |  |  | 60 copies | (English: 03, Vietnamese: 03)*10
|  |  |  | 38) | Bid Evaluation Reports (Civil, by PKG)
[5 empty] | a) | Bid Evaluation Report (Civil, PKG3a) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | b) | Bid Evaluation Reports (Civil, PKG1/PKGA4) |  |  | 12 copies | (English: 03, Vietnamese: 03)*02
[5 empty] | c) | Bid Evaluation Reports (Civil, Other PKGs) |  |  | 60 copies | (English: 03, Vietnamese: 03)*10
|  |  |  | 39) | Draft Contract Documents (Civil, by PKG)
[5 empty] | a) | Draft Contract Document (Civil, PKG3a) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | b) | Draft Contract Documents (Civil, PKG1/PKGA4) |  |  | 12 copies | (English: 03, Vietnamese: 03)*02
[5 empty] | c) | Draft Contract Documents (Civil, Other PKGs) |  |  | 60 copies | (English: 03, Vietnamese: 03)*10
Safeguard |  |  |  | Social and Environmental Assessment
Documents |  |  |  | 40) | Brief Report on Appropriateness of F/S Alignment |  |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 41) | Updated Draft EIA and EMP |  |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 42) | Draft Final Updated Draft EIA and EMP |  |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 43) | Draft TOR (External Environmental Monitoring) |  |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
Comprehensive Plan on Compensation, Support and Resettlement (CPCSR)
|  |  |  | 44) | Inception Report (Resettlement Monitoring Plan) |  |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 45) | CPCSR (by Province) |  |  |  | 18 copies | (English: 03, Vietnamese: 03)*03
|  |  |  | 46) | Draft TOR (External Resettlement Monitoring) |  |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 47) | Internal Monitoring Report (CPCSR) |  |  |  | 84 copies | (English: 03, Vietnamese: 03)*14
Discussion |  |  |  | 48) | Alternative Alignment Study Reports
Papers |  |  |  |  | a) | Alternative Alignment Study Report (KM070 - KM080) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | b) | Alternative Alignment Study Report |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
|  |  |  | 49) | Cross Structure Plan (by PKG) |  |  |  | 78 copies | (English: 03, Vietnamese: 03)*13
|  |  |  | 50) | Alternative Study Reports
[5 empty] | a) | Alternative Study Reports (Major River Bridges)
[6 empty] | i) | Alternative Study Report (Ky Lam Bridge) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[6 empty] | ii) | Alternative Study Report (Other Bridges) |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | b) | Alternative Study Report (Location of My Son Interchange) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
[5 empty] | c) | Alternative Study Report (Interchange Type) |  |  | 6 copies | (English: 03, Vietnamese: 03)*01
: Heavy Rainy Season
B/D (4 months)
B/D (7 months)
D/D (11 months)
Plan (4 months)
B/D (3 months)
B/D (5 months)
D/D (4 months)
B/D (7 months)
D/D (6 to 8 months)
Procurement Assistance (10 months)
Procurement Assistance (10 months)
Procurement Assistance (6 months)
D/D (3 months)
Plan (2 months)
B/D (3 months)
D/D (5 months)

## Fig.A.11
Nippon Koei Co., Ltd. Head Office
Home Office Support
Consultant Team
Engineering Group (Key Professional Staff)
Project Management Unit No.85
(PMU85)
Project
Management
Project Manager/Team Leader
Co-Project Manager
Civil Design Team (CID)
Design Group (DEG)
Section Design (SED)
Road Design 1 (RDD1, PKG1-7, L=65.0 km)
Interchange Design (ICD)
Major Bridges Design (MBD)
Tunnel Design (TND)
Geotechnical Design (GTD)
Drainage Design (DRD)
Revetment and River Bed Protection Design (RRD)
Pavement Design (PVD)
Survey Group (SUG)
O&M and ITS Team (OMI)
Topographic Survey (TPS)
Core Team (COR)
Team (MGT)
Civil Design Management (CDM)
Road Design 2 (RDD2, PKGA1-A5, L=74.5 km)
Material Sources Survey (MLS)
Geotechnical Survey (GTS)
Hydrological Survey (HDS)
Traffic Survey (TRS)
Supporting Group (Supporting Staff)
Supporting Group 1 (SPG1)
Supporting Group 2 (SPG2)
Supporting Group 3 (SPG3)
Note: COR consists of representatives of each team
O&M (OAM)
Electrical Facility and ITS Design (EID)
Environmental Team (ENV)
Cost and Document Team (COD)
Cost Estimate (COS)
Document (DOC)
Social and Environmental (SAE)
Resettlement (RES)
Supporting Group 4 (SPG4)
Bridge Temporary Facility Design (TFD)
Training Team (TRG)
Vietnam Expressway Corporation
(VEC)
Project Owner
SPG1
SPG2
SPG3
SPG1
SPG4
SPG4
Imple. Agency
LEGEND
: Home Office Support
: Consultant Team
: Project Implementation Agency
: Project Owner

## Fig.A.12
Consultant Team
Project Manager/Team Leader, Ichizuru ISHIMOTO
Management Team (MGT)
Civil Design Team (CID)
O&M and ITS Team (OMI)
Cost and Document Team (COD)
NK Representative Office in Hanoi
Chief Representative, Masanobu SAKAMOTO
Report/Coordination
WB Representative Office in Hanoi
(1) Technical Support
(2) Managerial Support
(3) Operational Support
Overseas Consulting Administraion
Domestic Consulting Administraion
Systems Engineering Department
Technology/Knowledge
Technology Management Administraion
Advanced Technology
Total Quality Control under ISO 9001/14001
NK Head Office in Tokyo
Environmental Team (ENV)
Training Team (TRG)
Chief Engineers' Group
Transportation Engineering Department
Logistic & Operations Department
Research & Development Center
Supprting Groups (SPGs)

## Tab.A.15
Tasks |  |  |  |  | MGT |  | CID | [43 empty] | OMI | [17 empty] | COD | [5 empty] | ENV | [6 empty] | TRG
[7 empty] | CDM | [5 empty] | DEG | [25 empty] | SUG | [11 empty] | OAM | [9 empty] | EID | [7 empty] | COS |  |  | DOC |  |  | SAE |  |  | RES
[13 empty] | SED | [9 empty] | ICD |  | MBD |  | TND |  | GTD |  |  |  | DRD |  | RRD |  | TFD | PVD/ |  | TPS |  | GTS |  |  |  | HDS |  |  |  | TRS
[13 empty] | RDD1 |  |  |  |  | RDD2 | [19 empty] | MLS
[5 empty] | Project Manager/Team Leader | Co-Project Manager | Senior Highway Engineer | Road Safety Audit Specialist | Senior Bridge Engineer | Highway Engineer 1-2 | Road Safety Audit Specialist | Bridge/Structural Engineer 1-2 | Highway Engineer 1 | Bridge/Structural Engineer 1 | Bridge/Structural Engineer 2 | Highway Engineer 3-4 | Bridge/Structural Engineer 3-4 | Highway Engineer 2 | Bridge/Structural Engineer 3 | Bridge/Structural Engineer 4 | Highway Engineer 5-6 | Bridge/Structural Engineer 5-6 | Senior Interchange Specialist | Interchange Specialist | Bridge/Structural Engineer 5 | Bridge/Structural Engineer 7 | Tunnel Engineer | Tunnel Engineer | Soil/Geotechnical Engineer 1 (Slope) | Soft Ground Treatment Specialist | Soil/Geotechnical Engineer 1 (Slope) | Soft Ground Treatment Specialist | Drainage Engineer | Drainage Engineer 1-2 | River Engineer | River Engineer | Bridge/Structural Engineer 6 | Pavement/Material Engineer | Pavement/material Engineer 1-2 | Survey Engineer | Senior Surveyor 1-3 | Soil/Geotechnical Engineer 2 | Geological Engineer (Tunnel) | Soil/Geotechnical Engineer 2-4 | Geological Engineer (Tunnel) | Senior Hydrologist | Inundation Analyst | Hydraulic Engineer 1-2 | Inundation Analyst | Transport Economist | Operating & Maintenance Specialist | Expressway Management Unit Specialist | Traffic Management Specialist | Asset Management Specialist | Architect | Operating & Maintenance Specialist | Expressway Management Unit Specialist | Traffic Management Specialist | Asset Management Specialist | Architect 1-2 | ITS Specialist | Communication System Engineer | Senior Electrical Engineer | Toll Collection System Specialist | ITS Specialist | Communication System Engineer | Electrical Engineer 1-2 | Toll Collection System Specialist | Construction Planner/Cost Estimator | Cost Estimator 1 | Cost Estimator 2-3 | Senior Procurement/Contract Specialist | Procurement/Contract Specialist 1 | Procurement/Contract Specialist 2 | Social and Environmental Specialist | Senior Environmental Specialist | Environmental Specialist | Resettlement Specialist | Senior Resettlement Specialist | Social and Resettlement Specialist | Cultural and Archaeological Specialist | Training Specialist | Training Specialist
[5 empty] | I1 | L1 | I2 | I3 | I4 | L2-L3 | L4 | L5-L6 | I5 | I6 | I7 | L7-L8 | L9-L10 | I8 | I9 | I10 | L11-L12 | L13-L14 | I11 | L15 | I12 | L16 | I13 | L17 | I14 | I15 | L18 | L19 | I16 | L20-L21 | I17 | L22 | I18 | I19 | L23-L24 | I20 | L25-L27 | I21 | I22 | L28-L30 | L31 | I23 | I24 | L32-L33 | L34 | L35 | I25 | I26 | I27 | I28 | I29 | L36 | L37 | L38 | L39 | L40-L41 | I30 | I31 | I32 | I33 | L42 | L43 | L44-L45 | L46 | I34 | L47 | L48-L49 | I35 | L50 | L51 | I36 | L52 | L53 | I37 | L54 | L55 | L56 | I38 | L57
| Part B | Project Management
|  | B.1 | Establish and control practical project management system |  | ● | ●
| Part C | Previous Studies Review and Establishing Detailed Engineering Design Framework
|  | C.1 | Review previous studies |  | ◎ | ◎ | ● |  | ● | ● |  | ● | [27 empty] | ● | ● |  |  |  |  | ● | ● | ● | ● | ● | ● | ● |  |  |  | ● | ● | [11 empty] | ● | ● |  |  |  |  | ● | ● | ● | ● | ● | ● | ●
|  | C.2 | Establish detailed engineering design framework |  | ● | ● | ● |  | ● | ● |  | ● | [56 empty] | ● | ● |  | ● | ●
| Part D | Detailed Engineering Design and Procurement Planning
|  | D.1 | Contract Packaging
|  |  | D.1.1 | Propose contract packaging | ● | ● | [62 empty] | ● | ● |  | ● | ●
|  | D.2 | Surveys and Investigations
|  |  | D.2.1 | Collect relevant data and documents | ◎ | ◎ | ● |  |  | ● | [58 empty] | ● | ● |  | ● | ●
|  |  | D.2.2 | Conduct topographic survey | ◎ | ◎ | [33 empty] | ● | ●
|  |  | D.2.3 | Conduct hydrological survey and analysis | ◎ | ◎ | [39 empty] | ● | ● | ● | ●
|  |  | D.2.4 | Conduct geotechnical and geological investigations | ◎ | ◎ | [20 empty] | ● | ● | [13 empty] | ● | ● | ● | ●
|  |  | D.2.5 | Conduct material source survey | ◎ | ◎ | [31 empty] | ● | ● |  |  | ● |  | ●
|  |  | D.2.6 | Conduct relevant facilities survey | ◎ | ◎ | ● |  | ● | ● |  | ● | ● |  |  | ● |  | ● |  |  | ● | [24 empty] | ● |  | ● |  | ● | [18 empty] | ● | [5 empty] | ● | ● | ●
|  |  | D.2.7 | Review traffic forecasting and conduct baseline surveys | ◎ | ◎ | ● | [42 empty] | ●
|  |  | D.2.8 | Conduct independent land valuation survey | ◎ | ◎ | [71 empty] | ● | ● | ●
|  |  | D.2.9 | Conduct environmental and social surveys | ◎ | ◎ | [68 empty] | ● | ● | ●
|  | D.3 | Civil Engineering Design
|  |  | D.3.1 | Prepare basic design of civil structures | ◎ | ◎ | ● |  | ● | ● |  | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | [6 empty] | ● | ●
|  |  | D.3.2 | Prepare detailed engineering design of civil structures | ◎ | ◎ | ● | ● | ● | ● | ● | ● | ● | ● |  | ● |  | ● | ● |  | ● |  | ● |  | ● |  | ● | ● | ● | ● | ● | ● | ● | ● |  |  | ● | ● | ●
|  | D.4 | O&M Plan and Design
|  |  | D.4.1 | Prepare institutional and administrative arrangement plan | ◎ | ◎ | [44 empty] | ● | ● |  |  |  | ● | ●
|  |  | D.4.2 | Prepare O&M plan | ◎ | ◎ | [44 empty] | ● | ● | ● | ● |  | ● | ● | ● | ●
|  |  | D.4.3 | Prepare basic design of O&M buildings | ◎ | ◎ | [48 empty] | ● |  |  |  |  | ●
|  | D.5 | ITS Plan and Design
|  |  | D.5.1 | Prepare ITS plan | ◎ | ◎ | [54 empty] | ● |  |  | ● | ● |  |  | ●
|  |  | D.5.2 | Prepare basic design of ITS facilities | ◎ | ◎ | [54 empty] | ● | ● |  | ● | ● | ● |  | ●
|  | D.6 | Electrical Facilities Design
|  |  | D.6.1 | Prepare detailed engineering design of electrical facilities | ◎ | ◎ | [56 empty] | ● |  |  |  | ●
|  | D.7 | Public Utilities Relocation Plan
|  |  | D.7.1 | Prepare relocation plan of public utilities | ◎ | ◎ | ● |  |  | ● | [52 empty] | ● |  |  |  | ●
|  | D.8 | Safeguards
|  |  | D.8.1 | Assist in updating EIA and EMP | ◎ | ◎ | [68 empty] | ● | ● | ●
|  |  | D.8.2 | Assist in preparing and enforcing CPCSR | ◎ | ◎ | [71 empty] | ● | ● | ● | ●
|  | D.9 | Construction Planning
|  |  | D.9.1 | Prepare construction plan | ◎ | ◎ |  |  | ● | [27 empty] | ● | [31 empty] | ●
|  | D.10 | Project Cost Estimate
|  |  | D.10.1 | Estimate Project cost | ◎ | ◎ | [62 empty] | ● | ● | ●
|  | D.11 | Procurement Documents
|  |  | D.11.1 | Prepare procurement documents | ◎ | ◎ | ● |  | ● | ● |  | ● | [42 empty] | ● |  |  |  |  | ● | ● | ● | ● | ● | ● | ● | ● | ● |  |  |  | ● | ● | ● | ● | ● | ●
|  | D.12 | Project Implementation Program
|  |  | D.12.1 | Prepare Project I/P | ● | ● | [62 empty] | ● | ● |  | ● | ●
| Part E | Procurement Assistance
|  | E.1 | Provide training to VEC, PMU85 and relevant organizations |  | ● | ● | ● |  | ● | ● |  | ● | [59 empty] | ● | ● | ●
| Part F | Technology Transfer
|  | F.1 | Provide training to VEC, PMU85 and relevant organizations |  | ● | ● |  | ● |  |  | ● | [39 empty] | ● |  |  |  |  | ● |  |  |  |  | ● |  |  |  | ● | [9 empty] | ● | ● |  | ● | ● |  |  | ● | ●
|  | F.2 | Provide training to key local professional staff |  | ● |  | ● | ● | ● |  |  |  | ● | ● | ● |  |  | ● | ● | ● |  |  | ● |  | ● |  | ● |  | ● | ● |  |  | ● |  | ● |  | ● | ● |  | ● |  | ● | ● |  |  | ● | ● |  |  |  | ● | ● | ● | ● | ● | [5 empty] | ● | ● | ● | ● |  |  |  |  | ● |  |  | ● |  |  | ● |  |  | ● |  |  |  | ●
◎: Management and Guidance ●: In-charge Red: Accountability for the Services Blue: Responsibility for the Team

## Tab.A.16
| Calender |  |  |  |  | Calender Year |  |  |  |  | 2011 | [5 empty] | 2012 | [11 empty] | '13 | Duration
[6 empty] | Calender Month |  |  |  |  | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J
[6 empty] | Cumulative Month |  |  |  |  | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| 1st Priority Package (PKG3a) |  |  |  |  | Civil Engineering Design | [23 empty] | 7
[6 empty] | Procurement Assistance | [23 empty] | 10
| 2nd Priority Packages (PKG1, PKGA4) |  |  |  |  | Civil Engineering Design | [23 empty] | 9
[6 empty] | Procurement Assistance | [23 empty] | 10
| Non-priority Packages (Other PKGs) |  |  |  |  | Civil Engineering Design | [23 empty] | 15
[6 empty] | Procurement Assistance | [23 empty] | 6
No. |  |  | TOR | Position |  |  | Name |  | Firm | Home/ | 2011 | [5 empty] | 2012 | [11 empty] | '13 | Staff-
|  |  | 5.1 | [6 empty] | Field | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | Months
[11 empty] | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Management Team (MGT)
I1 |  |  | 1 |  | Project Manager/Team Leader |  |  | Ichizuru Ishimoto | NK | [Field] | [19 empty] | 14
Civil Design Team (CID)
Civil Design Management (CDM)
I2 |  |  | 2 |  | Senior Highway Engineer |  |  | Akira Magario | NK | [Field] | [19 empty] | 14
I3 |  |  | 21 |  | Road Safety Audit Specialist |  |  | Takehiko Tsuji | NK | [Field] | [19 empty] | 3
I4 |  |  | 5 |  | Senior Bridge Engineer |  |  | Yoshinori Abe | Chodai | [Field] | [19 empty] | 13
Section Design (SED)
Road Design 1 (RDD1, PKG1-7, JICA Section)
I5 |  |  | 3 |  | Highway Engineer 1 |  |  | Koji Nakai | NK | [Field] | [19 empty] | 12
I6 |  |  | 6 |  | Bridge/Structural Engineer 1 |  |  | Tetsuya Maeda | NK | [Field] | [19 empty] | 12
I7 |  |  | 6 |  | Bridge/Structural Engineer 2 |  |  | Yoshiaki Nakakubo | Chodai | [Field] | [19 empty] | 4
Road Design 2 (RDD2, PKGA1-A5, WB Section)
I8 |  |  | 3 |  | Highway Engineer 2 |  |  | Decha Sa-ngaunprasith | TEC | [Field] | [19 empty] | 12
I9 |  |  | 6 |  | Bridge/Structural Engineer 3 |  |  | Hiroo Jin | NE | [Field] | [19 empty] | 12
I10 |  |  | 6 |  | Bridge/Structural Engineer 4 |  |  | Yuichi Sano | NK | [Field] | [19 empty] | 4
Interchange Design (ICD)
I11 |  |  | 4 |  | Senior Interchange Specialist |  |  | Chanchai Techashongs | TEC | [Field] | [19 empty] | 7
Major Bridges Design (MBD)
I12 |  |  | 6 |  | Bridge/Structural Engineer 5 |  |  | Hiroyuki Yokoyama | Chodai | [Field] | [19 empty] | 11
Tunnel Design (TND)
I13 |  |  | 11 |  | Tunnel Engineer |  |  | Wako Noto | NK | [Field] | [19 empty] | 4
Geotechnical Design (GTD)
I14 |  |  | 7 |  | Soil/Geotechnical Engineer 1 (Slope) |  |  | Manoon Arayasiri | TEC | [Field] | [19 empty] | 2
I15 |  |  | 8 |  | Soft Ground Treatment Specialist |  |  | Suvichai Methpreechakul | TEC | [Field] | [19 empty] | 2
Drainage Design(DRD)
I16 |  |  | 23 |  | Drainage Engineer |  |  | Suntichai Horpaopan | TEC | [Field] | [19 empty] | 7
Revetment and River Bed Protection Design (RRD)
I17 |  |  | 23 |  | River Engineer |  |  | Arristeo B. Rabajante | NK | [Field] | [19 empty] | 3
Bridge Temporary Facility Design (TFD)
I18 |  |  | 6 |  | Bridge/Structural Engineer 6 |  |  | Akira Yanagisawa | Chodai | [Field] | [19 empty] | 7
Pavement Design (PVD)/Material Sources Survey (MLS)
I19 |  |  | 9 |  | Pavement/Material Engineer |  |  | Bundit Kitsuwannarut | TEC | [Field] | [19 empty] | 4
Topographic Survey (TPS)
I20 |  |  | 22 |  | Survey Engineer |  |  | Kazuhiro Ishizuka | NK | [Field] | [19 empty] | 7
Geotechnical Survey (GTS)
I21 |  |  | 7 |  | Soil/Geotechnical Engineer 2 |  |  | Jirarote Piyapornpong | TEC | [Field] | [19 empty] | 5
I22 |  |  | 23 |  | Geological Engineer (Tunnel) |  |  | Seichiro Kanai | NK | [Field] | [19 empty] | 2
Hydrological Survey (HDS)
I23 |  |  | 10 |  | Senior Hydrologist |  |  | Khadananda Lamsal | NK | [Field] | [19 empty] | 3
I24 |  |  | 23 |  | Inundation Analyst |  |  | Silver Yance | NK | [Field] | [19 empty] | 2
O&M and ITS Team (OMI)
O&M (OAM)
I25 |  |  | 18 |  | Operating&Maintenance Specialist |  |  | Shigeki Takahashi | NK | [Field] | [19 empty] | 4
I26 |  |  | 19 |  | Expressway Management Unit Specialist |  |  | Yuichi Tsujimoto | NK | [Field] | [19 empty] | 2
I27 |  |  | 23 |  | Traffic Management Specialist |  |  | Hisanori Tomitaka | NK | [Field] | [19 empty] | 2
I28 |  |  | 23 |  | Asset Management Specialist |  |  | Kyoichi Takeuchi | NK | [Field] | [19 empty] | 2
I29 |  |  | 23 |  | Architect |  |  | Yoshinori Yamazaki | NK | [Field] | [19 empty] | 3
Electrical Facility and ITS Design (EID)
I30 |  |  | 15 |  | ITS Specialist |  |  | Koichi Nishimura | NK | [Field] | [19 empty] | 5
I31 |  |  | 16 |  | Communication System Engineer |  |  | Masahiro Sakagami | NK | [Field] | [19 empty] | 3
I32 |  |  | 12 |  | Senior Electrical Engineer |  |  | Eiji Matsuda | NK | [Field] | [19 empty] | 7
I33 |  |  | 17 |  | Toll Collection System Specialist |  |  | Masashi Iwamoto | NK | [Field] | [19 empty] | 4
Cost and Document (COD)
Cost Estimate (COS)
I34 |  |  | 23 |  | Construction Planner/Cost Estimator |  |  | Masayuki Iwashita | NK | [Field] | [19 empty] | 12
Document (DOC)
I35 |  |  | 14 |  | Senior Procurement/Contract Specialist |  |  | Anothai Boonthikul | TEC | [Field] | [19 empty] | 13
Environmental (ENV)
Social and Environmental (SAE)
I36 |  |  | 13 |  | Social and Environmental Specialist |  |  | Yasuhira Minami | NK | [Field] | [19 empty] | 4
Resettlement (RES)
I37 |  |  | 13 |  | Resettlement Specialist |  |  | Vu Ngoc Long | NK | [Field] | [19 empty] | 8
Training (TRG)
I38 |  |  | 20 |  | Training Specialist |  |  | Noppong Unhabhokha | TEC | [Field] | [19 empty] | 4
Total | [9 empty] | [Field] | [19 empty] | 239
Work in Danang Main Office
Work in Hanoi Sub-office
B/D (4)
Procurement Assistance (10)
D/D (3)
B/D (5)
Procurement Assistance (10)
D/D (4)
B/D (7)
Procurement Assistance (6)
D/D (6 to 8)

## Tab.A.17
| Calender |  |  |  |  | Calender Year |  |  |  |  | 2011 | [5 empty] | 2012 | [11 empty] | '13 | Duration
[6 empty] | Calender Month |  |  |  |  | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J
[6 empty] | Cumulative Month |  |  |  |  | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| 1st Priority Package (PKG3a) |  |  |  |  | Civil Engineering Design | [23 empty] | 7
[6 empty] | Procurement Assistance | [23 empty] | 10
| 2nd Priority Packages (PKG1, PKGA4) |  |  |  |  | Civil Engineering Design | [23 empty] | 9
[6 empty] | Procurement Assistance | [23 empty] | 10
| Non-priority Packages (Other PKGs) |  |  |  |  | Civil Engineering Design | [23 empty] | 15
[6 empty] | Procurement Assistance | [23 empty] | 6
No. |  |  | TOR | Position |  |  | Name |  | Firm | Home/ | 2011 | [5 empty] | 2012 | [11 empty] | '13 | Duration
|  |  | 5.2 | [6 empty] | Field | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J
[11 empty] | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Management Team (MGT)
L1 |  |  | 1 |  | Co-Project Manager |  |  | Le Kim An | NK | [Field] | [19 empty] | 14
Civil Design Team (CID)
Civil Design Management (CDM)
L2 |  |  | 2 |  | Highway Engineer 1 (Geometric) |  |  | Tran Dinh Van | NK | [Field] | [19 empty] | 14
L3 |  |  | 2 |  | Highway Engineer 2 (Road Structure) |  |  | Phan Dang Viet Anh | NK | [Field] | [19 empty] | 14
L4 |  |  | 22 |  | Road Safety Audit Specialist |  |  | Tran Quang Huy | NK | [Field] | [19 empty] | 3
L5 |  |  | 3 |  | Bridge/Structural Engineer 1 (Superstructure) |  |  | Le Toan Thang | NK | [Field] | [19 empty] | 14
L6 |  |  | 3 |  | Bridge/Structural Engineer 2 (Subst./Foundation) |  |  | Dao Ngoc Vinh | NK | [Field] | [19 empty] | 14
Section Design (SED)
Road Design 1 (RDD1, PKG1-7, JICA Section)
L7 |  |  | 2 |  | Highway Engineer 3 (Geometric) |  |  | Le Thi Thanh Thuy | NK | [Field] | [19 empty] | 12
L8 |  |  | 2 |  | Highway Engineer 4 (Road Structure) |  |  | Vu Gia Hung | NK | [Field] | [19 empty] | 12
L9 |  |  | 3 |  | Bridge/Structural Engineer 3 |  |  | Do Hong Phuc | NK | [Field] | [9 empty] | (Outsource D/D to sub-consultants) | [9 empty] | 4
L10 |  |  | 3 |  | Bridge/Structural Engineer 4 |  |  | Pham Anh Kiet | NK | [Field] | [9 empty] | (Outsource D/D to sub-consultants) | [9 empty] | 4
Road Design 2 (RDD2, PKGA1-A5, WB Section)
L11 |  |  | 2 |  | Highway Engineer 5 (Geometric) |  |  | Nguyen Dinh Trung | NK | [Field] | [19 empty] | 12
L12 |  |  | 2 |  | Highway Engineer 6 (Road Structure) |  |  | Dao Manh Son | NK | [Field] | [19 empty] | 12
L13 |  |  | 3 |  | Bridge/Structural Engineer 5 |  |  | Le Kien Cuong | NK | [Field] | [9 empty] | (Outsource D/D to sub-consultants) | [9 empty] | 4
L14 |  |  | 3 |  | Bridge/Structural Engineer 6 |  |  | Tran Anh Tuan | NK | [Field] | [9 empty] | (Outsource D/D to sub-consultants) | [9 empty] | 4
Interchange Design (ICD)
L15 |  |  | 22 |  | Interchange Specialist |  |  | Le Thanh Hung | NK | [Field] | [9 empty] | (Outsource D/D to sub-consultants) | [9 empty] | 3
Major Bridges Design (MBD)
L16 |  |  | 3 |  | Bridge/Structural Engineer 7 |  |  | Pham Ngoc Tuan | NK | [Field] | [9 empty] | (Outsource D/D to sub-consultants) | [9 empty] | 4
Tunnel Design (TND)
L17 |  |  | 22 |  | Tunnel Engineer |  |  | Tran Phong Nha | NK | [Field] | [19 empty] | 4
Geotechnical Design (GTD)
L18 |  |  | 4 |  | Soil/Geotechnical Engineer 1 (Slope) |  |  | Quach Thi Thu | NK | [Field] | [19 empty] | 2
L19 |  |  | 22 |  | Soft Ground Treatment Specialist |  |  | Trinh Viet Linh | NK | [Field] | [19 empty] | 2
Drainage Design (DRD)
L20 |  |  | 22 |  | Drainage Engineer 1 |  |  | Nguyen Minh Ngoc | NK | [Field] | [19 empty] | 7
L21 |  |  | 22 |  | Drainage Engineer 2 |  |  | Nguyen Phuc Hoa | NK | [Field] | [19 empty] | 6
Revetment and River Bed Protection Design (RRD)
L22 |  |  | 22 |  | River Engineer |  |  | Nguyen Son | NK | [Field] | [19 empty] | 3
Pavement Design (PVD)/Material Sources Survey (MLS)
L23 |  |  | 5 |  | Pavement/Material Engineer 1 |  |  | Tran Trong Nghia | NK | [Field] | [19 empty] | 4
L24 |  |  | 5 |  | Pavement/Material Engineer 2 |  |  | Nguyen Viet Hai | NK | [Field] | [19 empty] | 3
Topographic Survey (TPS)
L25 |  |  | 8 |  | Senior Surveyor 1 |  |  | Vo Thanh Binh | NK | [Field] | [19 empty] | 1.5
L26 |  |  | 8 |  | Senior Surveyor 2 |  |  | Le Van Thu | NK | [Field] | [19 empty] | 9.5
L27 |  |  | 8 |  | Senior Surveyor 3 |  |  | Nguyen Anh Tuan | NK | [Field] | [19 empty] | 4
Geotechnical Survey (GTS)
L28 |  |  | 4 |  | Soil/Geotechnical Engineer 2 |  |  | Nguyen Doan Tinh | NK | [Field] | [19 empty] | 5
L29 |  |  | 4 |  | Soil/Geotechnical Engineer 3 |  |  | Nguyen Manh Tuan | NK | [Field] | [19 empty] | 4
L30 |  |  | 4 |  | Soil/Geotechnical Engineer 4 |  |  | Trinh Minh Khiem | NK | [Field] | [19 empty] | 4
L31 |  |  | 22 |  | Geological Engineer (Tunnel) |  |  | Tran Ngoc Nhan | NK | [Field] | [19 empty] | 2
Hydrological Survey (HDS)
L32 |  |  | 7 |  | Hydraulic Engineer 1 |  |  | Ngo The Hung | NK | [Field] | [19 empty] | 2
L33 |  |  | 7 |  | Hydraulic Engineer 2 |  |  | Pham Huu Nhu | NK | [Field] | [19 empty] | 2
L34 |  |  | 22 |  | Inundation Analyst |  |  | Nguyen Huy Phuong | NK | [Field] | [19 empty] | 2
Traffic Survey (TRS)
L35 |  |  | 14 |  | Transport Economist |  |  | Vo Hoang Anh | NK | [Field] | [19 empty] | 3
O&M and ITS Team (OMI)
O&M (OAM)
L36 |  |  | 18 |  | Operating & Maintenance Specialist |  |  | Ha Quoc Hieu | NK | [Field] | [19 empty] | 4
L37 |  |  | 19 |  | Expressway Management Unit Specialist |  |  | Le Tung Lam | NK | [Field] | [19 empty] | 2
L38 |  |  | 22 |  | Traffic Management Specialist |  |  | Phan Minh Tuan | NK | [Field] | [19 empty] | 3
L39 |  |  | 22 |  | Asset Management Specialist |  |  | Trinh Ngoc Hai Thang | NK | [Field] | [19 empty] | 2
L40 |  |  | 15 |  | Architect 1 |  |  | Pham Quang Minh | NK | [Field] | [19 empty] | 3
L41 |  |  | 15 |  | Architect 2 |  |  | Ngo Vu Quang Khoa | NK | [Field] | [19 empty] | 2
Electrical Facility and ITS Design (EID)
L42 |  |  | 17 |  | ITS Specialist |  |  | Nguyen Huu Tinh | NK | [Field] | [19 empty] | 5
L43 |  |  | 17 |  | Communication System Engineer |  |  | To Minh Tri | NK | [Field] | [19 empty] | 3
L44 |  |  | 13 |  | Electrical Engineer 1 |  |  | Trinh Dinh Khiem | NK | [Field] | [19 empty] | 7
L45 |  |  | 13 |  | Electrical Engineer 2 |  |  | Vo Hong | NK | [Field] | [19 empty] | 4
L46 |  |  | 22 |  | Toll Collection System Specialist |  |  | Bui Phu Huy | NK | [Field] | [19 empty] | 4
Work in Danang Main Office
| Calender |  |  |  |  | Calender Year |  |  |  |  | 2011 | [5 empty] | 2012 | [11 empty] | '13 | Duration
[6 empty] | Calender Month |  |  |  |  | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J
[6 empty] | Cumulative Month |  |  |  |  | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| 1st Priority Package (PKG3a) |  |  |  |  | Civil Engineering Design | [23 empty] | 7
[6 empty] | Procurement Assistance | [23 empty] | 10
| 2nd Priority Packages (PKG1, PKGA4) |  |  |  |  | Civil Engineering Design | [23 empty] | 9
[6 empty] | Procurement Assistance | [23 empty] | 10
| Non-priority Packages (Other PKGs) |  |  |  |  | Civil Engineering Design | [23 empty] | 15
[6 empty] | Procurement Assistance | [23 empty] | 6
No. |  |  | TOR | Position |  |  | Name |  | Firm | Home/ | 2011 | [5 empty] | 2012 | [11 empty] | '13 | Duration
|  |  | 5.2 | [6 empty] | Field | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J
[11 empty] | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Cost and Document Team (COD)
Cost Estimate (COS)
L47 |  |  | 16 |  | Cost Estimator 1 (Civil Work Packages) |  |  | Nguyen Thi Bich Thuy | NK | [Field] | [19 empty] | 12
L48 |  |  | 16 |  | Cost Estimator 2 (Civil Work Packages) |  |  | Phan Thi Thuy Trinh | NK | [Field] | [19 empty] | 6
L49 |  |  | 16 |  | Cost Estimator 3 (Other Packages) |  |  | Nguyen Thi Sinh | NK | [Field] | [19 empty] | 2
Document (DOC)
L50 |  |  | 6 |  | Procurement/Contract Specialist 1 |  |  | Nguyen The Truong | NK | [Field] | [19 empty] | 16
L51 |  |  | 6 |  | Procurement/Contract Specialist 2 |  |  | Ha Ngoc Anh Minh | NK | [Field] | [19 empty] | 6
Environmental Team (ENV)
Social and Environmental (SAE)
L52 |  |  | 9 |  | Senior Environmental Specialist |  |  | Pham Van Xuan | NK | [Field] | [19 empty] | 8
L53 |  |  | 21 |  | Environmental Specialist |  |  | Pham The Giang | NK | [Field] | [19 empty] | 8
Resettlement (RES)
L54 |  |  | 10 |  | Senior Resettlement Specialist |  |  | To be named | NK | [Field] | [19 empty] | 14
L55 |  |  | 11 |  | Social and Resettlement Specialist |  |  | Ho Thi Thu Thuy | NK | [Field] | [19 empty] | 14
L56 |  |  | 12 |  | Cultural and Archaeological Specialist |  |  | Le Duy Son | NK | [Field] | [19 empty] | 14
Training (TRG)
L57 |  |  | 20 |  | Training Specialist |  |  | To be named | NK | [Field] | [19 empty] | 4
Total | [9 empty] | [Field] | [19 empty] | 357
Work in Danang Main Office

## Tab.A.18
| Calender |  |  |  |  | Calender Year |  |  |  |  | 2011 | [5 empty] | 2012 | [11 empty] | '13 | Duration
[6 empty] | Calender Month |  |  |  |  | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J
[6 empty] | Cumulative Month |  |  |  |  | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| 1st Priority Package (PKG3a) |  |  |  |  | Civil Engineering Design | [23 empty] | 7
[6 empty] | Procurement Assistance | [23 empty] | 10
| 2nd Priority Packages (PKG1, PKGA4) |  |  |  |  | Civil Engineering Design | [23 empty] | 9
[6 empty] | Procurement Assistance | [23 empty] | 10
| Non-priority Packages (Other PKGs) |  |  |  |  | Civil Engineering Design | [23 empty] | 15
[6 empty] | Procurement Assistance | [23 empty] | 6
No. |  |  | TOR | Position |  |  | Name |  | Firm | Home/ | 2011 | [5 empty] | 2012 | [11 empty] | '13 | Duration
|  |  | 5.2 | [6 empty] | Field | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J
[11 empty] | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Supporting Group 1 (SPG1)
S1 |  |  |  |  | Office Manager |  |  | Vu Thi Bich Thao | NK | [Field] | [19 empty] | 18.5
S2 |  |  |  |  | Bilingual Secretary 1 |  |  | Le Thi Hoai Thuong | NK | [Field] | [19 empty] | 17
S3 |  |  |  |  | Accountant |  |  | Phan Thi Huong | NK | [Field] | [19 empty] | 16
S4 |  |  |  |  | Translator 1 |  |  | Nguyen Thi Kieu Vy | NK | [Field] | [19 empty] | 17
S5 |  |  |  |  | Translator 2 |  |  | Huynh Thi Ngoc Loan | NK | [Field] | [19 empty] | 16
S6 |  |  |  |  | Translator 3 |  |  | To be named | NK | [Field] | [19 empty] | 14
S7 |  |  |  |  | Translator 4 |  |  | To be named | NK | [Field] | [19 empty] | 12
S8 |  |  |  |  | Translator 5 |  |  | To be named | NK | [Field] | [19 empty] | 12
S9 |  |  |  |  | CAD Operator 1 |  |  | To be named | NK | [Field] | [19 empty] | 14
S10 |  |  |  |  | CAD Operator 2 |  |  | To be named | NK | [Field] | [19 empty] | 4
Supporting Group 2 (SPG2)
S11 |  |  |  |  | Bilingual Secretary 2 |  |  | Ngo Thi Quy Duyen | NK | [Field] | [19 empty] | 17
S12 |  |  |  |  | CAD Operator 3 |  |  | Van Ba Phi | NK | [Field] | [19 empty] | 14.5
S13 |  |  |  |  | CAD Operator 4 |  |  | To be named | NK | [Field] | [19 empty] | 12
S14 |  |  |  |  | CAD Operator 5 |  |  | To be named | NK | [Field] | [19 empty] | 12
S15 |  |  |  |  | CAD Operator 6 |  |  | To be named | NK | [Field] | [19 empty] | 12
Supporting Group 3 (SPG3)
S16 |  |  |  |  | Bilingual Secretary 3 |  |  | To be named | NK | [Field] | [19 empty] | 14
S17 |  |  |  |  | CAD Operator 7 |  |  | To be named | NK | [Field] | [19 empty] | 12
Supporting Group 4 (SPG4)
S18 |  |  |  |  | Bilingual Secretary 4 |  |  | To be named | NK | [Field] | [19 empty] | 8
S19 |  |  |  |  | CAD Operator 8 |  |  | To be named | NK | [Field] | [19 empty] | 8
Total | [9 empty] | [Field] | [19 empty] | 250
Work in Danang Main Office
Work in Hanoi Sub-office
B/D (4)
Procurement Assistance (10)
D/D (3)
B/D (5)
Procurement Assistance (10)
D/D (4)
B/D (7)
Procurement Assistance (6)
D/D (6 to 8)