# Letter of Submission

Project Location Map

Project Route Map

# Table of Contents

# Abbreviations

# Main Part

Part A	General	1

A.1 Project Features	1

A.1.1 Background	1

A.1.2 Recent Major Updates	2

A.1.3 Location	3

A.1.4 Objectives	3

A.1.5 Project Components	4

A.1.6 Safeguards	8

A.1.7 Project Cost	9

A.1.8 Funding Arrangement	9

A.1.9 Contract Packaging	10

A.1.10 Project Implementation Structure	11

A.1.11 Project Implementation Program	12

A.2 Outline of the Services	14

A.2.1 General	14

A.2.2 Objectives	14

A.2.3 Scope in TOR	14

A.2.4 Additional Scope to TOR	15

A.2.5 Work Items in the Services	15

A.2.6 Work Schedule	16

A.2.7 Reporting Schedule	19

A.2.8 Organization	25

A.2.9 Staffing	27

A.2.10 Terms of Payment	28

Part B	Project Management	33

B.1 Basic Policy	33

B.2 General Phasing in Project Management	33

Part C	Previous Studies Review and Establishing Detailed Engineering Design Framework	36

C.1 Review Previous Studies	36

C.2 Establish Detailed Engineering Design Framework	37

Part D	Detailed Engineering Design and Procurement Planning	39

D.1 Contract Packaging	39

D.1.1 Propose Contract Packaging	39

D.2 Surveys and Investigations	39

D.2.1 Data Collection	39

D.2.2 Conduct Topographic Survey	41

D.2.3 Conduct Hydrological Survey and Analysis	44

D.2.4 Inundation Analysis	46

D.2.5 Conduct Geotechnical and Geological Investigations	47

D.2.6 Conduct Material Source Survey	50

D.2.7 Conduct Relevant Facilities Survey	51

D.2.8 Conduct Additional Traffic Surveys	52

D.2.9 Conduct Independent Land Valuation Survey	53

D.2.10 Conduct Environmental and Social Surveys	53

D.3 Civil Engineering Design	54

D.4 O&M Plan and Design	59

D.5 ITS Plan and Design	61

D.6 Electrical Facilities Design	62

D.7 Public Utilities Relocation Plan	63

D.8 Safeguards	64

D.8.1 Assist in Updating EIA and EMP	64

D.8.2 Review and update Resettlement Action Plan (RAP)	64

D.9 Construction Planning	77

D.9.1 Prepare Construction Plan	77

D.10 Project Cost Estimate	78

D.10.1 Estimate Project Cost	78

D.11 Procurement Documents	79

D.11.1 Prepare Procurement Documents	79

D.12 Project Implementation Program	80

D.12.1 Prepare Project Implementation Program	80

Part E	Procurement Assistance	81

E.1 Assist in Tendering Procedures	81

Part F	Land Acquisition Staking	83

Part G	Technology Transfer	84

G.1 Provide Training to VEC, PMU85 and Relevant Organizations	84

G.2 Provide Training to the Key Local Professional Staff	85

# Appendix

Appendix	1	:	Terms of Reference (Appendix A in the Contract)

Appendix	2	:	List of Bridges (As of December 2011)

Appendix	3	:	List of Culverts (As of December 2011)

Appendix	4	:	List of Communes along the expressway

Appendix	5	:	List of Crossing of Electrical Lines

# Abbreviations

AIDS	:	Acquired Immune Deficiency Syndrome

AM	:	Ante Meridiem

AP	:	Affected Person

B/D	:	Basic Design

BL	:	Building

BOT	:	Build-Operate-Transfer

BP	:	Beginning Point

B/Q	:	Bill of Quantities

BR	:	Bridge

CARB	:	Compensation, Assistance and Resettlement Boards

CB	:	Culvert Box

CDM	:	Civil Design Management

CID	:	Civil Design Team

COD	:	Cost and Document Team

COR	:	Core Team

COS	:	Cost Estimate

CP	:	Culvert Pipe

CPC	:	City People’s Committee

CPCSR	:	Comprehensive Plan on Compensation, Support and Resettlement

C/S	:	Construction Supervision

CSC	:	Construction Supervision Consultant

CU	:	Triaxial Compression Test

Cv	:	Consolidation Test

DARD	:	Department of Agriculture and Rural Development

DC	:	Design Consultant

D/D	:	Detailed Engineering Design

# DE	:	Deep Excavation

DEG	:	Design Group

DMS	:	Detailed Measurement Survey

DOC	:	Document

DOFPP	:	Department of Fire Prevention and Protection

DOLA	:	Department of Land Administration

DONRE	:	Department of Natural Resources and Environment

DOT	:	Department of Transport

DOTP	:	Department of Traffic Office

DP	:	Displaced Person

DPC	:	District People’s Committee

DRC	:	District Resettlement Committee

DRD	:	Drainage Design

ED	:	Evaluation Department

EIA	:	Environmental Impact Assessment

EID	:	Electrical Facility and Intelligent Transport Systems Design

EMP	:	Environmental Management Plan

ENV	:	Environmental Team

EOO	:	Expressway Operation Office

EP	:	Ending Point

ER	:	Existing Road

ESCRD	:	Environmental and Social Considerations Review Division

ETC	:	Electric Toll Collection

EVN	:	Electricity of Vietnam

FIDIC	:	International Federation of Consulting Engineers

FO	:	Flyover

F/S	:	Feasibility Study

GOVN	:	Government of Vietnam

GPS	:	Global Positioning System

GTD	:	Geotechnical Design

GTS	:	Geotechnical Survey

HCMC	:	Ho Chi Minh City

HDS	:	Hydrological Survey

HE	:	High-embankment

HEC-RAS	:	Hydrologic Engineering Centers River Analysis System, US Army Corps of Engineer

HIDO	:	Highway Industry Development Organization, Japan

HIV	:	Human Immunodeficiency Virus

HVL	:	High-voltage Line

IBRD	:	International Bank for Reconstruction and Development

IC	:	Interchange

ICB	:	International Competitive Bidding

ICD	:	Interchange Design

ICR	:	Inception Report

ID	:	Identification

IDA	:	International Development Association

IMO	:	Independent Monitoring Organization

IOL	:	Inventory of Losses

I/P	:	Implementation Program

IRB	:	Interchange Rampway Bridge

IS	:	Intersection

ITS	:	Intelligent Transport Systems

JBIC	:	Japan Bank for International Cooperation

JEHDRA	:	Japan Expressway Holding and Debt Repayment Agency

JETRO	:	Japan External Trade Organization

JICA	:	Japan International Cooperation Agency

JV	:	Joint Venture

L/A	:	Loan Agreement

LOS	:	Level of Services

LRB	:	Large River Bridge

MBD	:	Major Bridges Design

M/D	:	Minutes of Discussion

MEX	:	Metropolitan Expressway Co., Ltd., Japan

MGT	:	Management Team

ML	:	Main Line

MLIT	:	Ministry of Land, Infrastructure, Transport and Tourism, Japan

MLS	:	Material Source Survey

MOF	:	Ministry of Finance

MOND	:	Ministry of National Defense

MONRE	:	Ministry of Natural Resources and Environment

MOPS	:	Ministry of Public Security

MOT	:	Ministry of Transport

MRB	:	Major River Bridge

MS	:	Milestone

MS	:	Microsoft

NE	:	Nippon Engineering Consultants Co., Ltd., Japan

NEE	:	Normal Embankment and Excavation

NEXCO	:	Nippon Expressway Company Limited, Japan

NH	:	National Highway

NK	:	Nippon Koei Co., Ltd., Japan

NTP	:	Notice to Proceed

OAM	:	Operation and Maintenance

OED	:	Operations Evaluation Department

O&M	:	Operation and Maintenance

OMI	:	Operation and Intelligent Transport Systems Team

OP	:	Overpass

ORB	:	Other River Bridge

ORSE	:	Organization for Road System Enhancement, Japan

PA	:	Parking Area

PAP	:	Project Affected People

PC	:	People’s Committee

PIARC	:	Permanent International Association of Road Congresses

PIS	:	Project Implementation Support for Vietnam Expressway Corporation

PKG	:	Package

PM	:	Prime Minister

PM	:	Post Meridiem

PMBOK	:	Project Management Body of Knowledge

PMU	:	Project Management Unit

PPC	:	Provincial People’s Committee

P/Q	:	Pre-qualification

PSMD	:	Project Site Management Department

PTC2	:	Power Transmission Company No. 2

PVD	:	Pavement Design

QACU	:	Quality Assurance and Compliance Unit

QA/QC	:	Quality Assurance and Quality Control

RAP	:	Resettlement Action Plan

RB	:	River Bridge

RC	:	Resettlement Committee

RCS	:	Replacement Cost Survey

RD	:	Roadway

RDD	:	Road Design

RES	:	Resettlement

RFP	:	Request for Proposals

RMP	:	Resettlement Monitoring Plan

RNIP	:	Road Network Improvement Program

ROW	:	Right of Way

RP	:	Resettlement Plan

RRD	:	Revetment and River Bed Protection Design

SA	:	Service Area

SAE	:	Social and Environmental

SB	:	Stream Bridge

SED	:	Section Design

SES	:	Socio-economic Survey

SG	:	Softground

SPG	:	Supporting Group

SPT	:	Standard Penetration Test

T/A	:	Technical Assistance

TB	:	Toll Barrier

TEC	:	Thai Engineering Consultants Co., Ltd., Thailand

TEDI	:	Transport Engineering Design Incorporated

TFD	:	Bridge Temporary Facility Design

TG	:	Toll Gate

TMC	:	Traffic Management Center

TN	:	Tunnel

TND	:	Tunnel Design

TOR	:	Terms of reference

TPO	:	Toll Plaza Office

TPS	:	Topographic Survey

TRG	:	Training Team

TRS	:	Traffic Survey

USD	:	United States Dollars

UU	:	Triaxial Compression Test

VAT	:	Value Added Tax

VEC	:	Vietnam Expressway Corporation

VD	:	Viaduct

VICS	:	Vehicle Information and Communication System

VIETTEL	:	Vietnam Military Electronic and Telecommunications Corporation

VND	:	Vietnamese Dong

VNPT	:	Vietnam Posts and Telecommunications Group

VNR	:	Vietnam National Railway

VST	:	Vane Shear Test

WB	:	The World Bank

WT	:	Waterway

# Main Part

General

Project Features

Background

The preparation of Pre-F/S for the Project under BOT scheme was approved by MOT in Decision No. 2654/QD-BGTVT dated September 11, 2000.  The Pre-F/S report was prepared by PMU85 and approved by the Prime Minister in his letter No. 493/CP-CN dated April 21, 2003.  Continually, the preparation of F/S was approved by MOT in Decision No. 134/QD-BGTVT dated January 14, 2004.  The F/S report was also prepared by PMU85 and submitted to MOT in his letter No. 514/BQL-KHDA2 dated May 11, 2005.  However, this BOT scheme Project did not materialize because of funding sources were not identified at that time.

Two (2) years later, the Project was approved as one (1) of the top priority projects in transport sector by GOVN in Decision No. 412/QD-TTg dated April 11, 2007.  For carrying forward the Project, GOVN requested JETRO to assist a further study expecting materialization of the Project by a JBIC (currently JICA) loan scheme in June 2007.  JETRO conducted the study and submitted the study report to MOT on April 28, 2008.

In parallel with the JETRO study, WB declared GOVN to be eligible for the IBRD loan in November, 2007 and the Project was identified as the top priority use for the loan.  After submission of the JETRO study report, WB undertook the identification missions in April and June, 2008 and confirmed necessity of updating the JETRO study to meet his requirements and decided to allocate the fund from on-going RNIP (IDA Credit No.: 3843-VN) to conduct the WB supplemental study.  The study report was prepared by PMU85 and submitted to MOT in his letter No. 551/BQl-KHDA2 dated June 13, 2009.

In response to the supplemental study, WB engaged an international consultant and undertook the WB appraisal study.  In the appraisal study, WB modified the alignment at three (3) sections by taking into consideration social and environmental issues.  Based on the modified alignment, TEDI updated the supplemental study and submitted as the draft F/S report to MOT in April, 2010.  The draft F/S report was also finalized by TEDI in accordance with the MOT appraisal report No. 6188/BGTVT-KHDT dated September 8, 2011 and submitted by VEC as the F/S report to MOT in September 2010.  The F/S report was approved by MOT in Decision No. 2656/QD-BGTVT dated September 10, 2010.

In parallel with the F/S approval, WB agreed to allocate the fund from RNIP for D/D and the Prime Minister allowed commencing the procurement of D/D consultant.  Through the procurement procedures, NK-NE-Chodai-TEC JV (the Consultant) was selected and signed the contract with PMU85 on November 15, 2011.  Subsequently, PMU85 issued NTP in his letter No. 1622/PMU85-PP2 dated November 18, 2011 and the consulting service was officially commenced from December 1, 2011.

Outline of the Project background is shown in Figure A.1.

Figure A.1   Project Chronicle

Recent Major Updates

Main Updates after Proposals Submission

The Consultant submitted the proposals for Consulting Services for Detailed Design for Danang - Quang Ngai Expressway Development Project (the Services) on June 1, 2010 based on the draft F/S report distributed by VEC/PMU85 in the procurement stage (see A.1.1).  Since that time, various documents for the Project have been issued and updated by the relevant organizations.

Major updates after the proposals submission are shown in Table A.1.

Table A.1   Major Updates after Proposals Submission

| No. | Items |  | Issued by | Subject (Summary) | Ref. No. | Date Issued |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 01 | F/S | Approval | MOT | F/S Approval | Decision No. 2656/QD-BGTVT | 10 | Sep., | 2010 |
| 02 |  |  | GOVN Office | Investment Approval and Assigning MOT for F/S Approval | Document No. 4684/VPCP-KTN | 7 | Jul., | 2010 |
| 03 |  | Appraisal | MOT | F/S Appraisal Report | Document No. 6188/BGTVT-KHDT | 8 | Sep., | 2010 |
| 04 |  | Submission | VEC | Submission of F/S Report | Letter No. 384/TTr-VEC | 7 | Sep., | 2010 |
| 05 |  |  |  |  | Letter No. 160/TTr-VEC | 30 | Jul., | 2010 |
| 06 | Safeguards | EIA | MONRE | Approval for Supplemental EIA | Decision No. 2046/QD-BTNMT | 29 | Oct., | 2010 |
| 07 |  | RAP | PM | Approval for RAP (Based on F/S Alignment) | Decision No. 442/TTg-KTN | 23 | Mar., | 2011 |
| 08 | Funding | JICA Loan | GOVN-JICA | L/A | ----- | 15 | Jun., | 2011 |
| 09 |  |  |  | M/D (L/A) | ----- | 17 | Jan., | 2011 |
| 10 |  |  |  | M/D (Appraisal Mission) | ----- | 21 | Oct., | 2010 |
| 11 |  | WB Loan | GOVN-WB | M/D (Appraisal Mission) | ----- | 21 | Apr., | 2011 |
| 12 |  | GOVN | MOT | Approval for Adjustment of Project Investment Structure | Decision No. 666/QD-BGTVT | 6 | Apr., | 2011 |
| 13 |  |  | GOVN Office | VEC’s Responsibilities (Borrowing/Paying Loan) | Document No. 4684/VPCP-KTN | 7 | Jul., | 2010 |
| 14 |  |  | MOF |  | Document No. 695/BTC-QLN | 13 | Aug., | 2010 |
| 15 | Procurement | JICA Portion | MOT | Approval for Procurement Plan (JICA Portion) | Decision No. 1688/QD-BGTVT | 28 | Jul., | 2011 |
| 16 |  | WB Portion | MOT | Approval for Procurement Plan (WB Portion) | Decision No. 1423/QD-BGTVT | 30 | Jun., | 2011 |
| 17 |  | GOVN | MOND | Executing Plan (Searching and De-mining Bombs) | Decision No. 1286/QD-BQP | 20 | Apr., | 2011 |
| 18 | Project Implementation Structure |  | MOT | Assigning PMU85 for Implementation Agency in D/D | Decision No. 2149/QD-BGTVT | 19 | Sep., | 2011 |
| 19 | Project Implementation Program |  | PMU85 | Commencement of Const. Works in 3rd Quarter, 2012 | Letter No. 1816/PMU85-PP2 | 22 | Sep., | 2011 |
| 20 | Request from Quang Nam PPC |  | Quang Nam | Agreement for Re-alignment/Request for Additional IC | Circular No. 346/TB0UBND | 13 | Sep., | 2011 |
| 21 | (Additional IC and Re-alignment) |  |  | Request for Additional IC and Re-alignment Study | Document No. 2107/UBND-KTN | 17 | Jun., | 2011 |
| 22 |  |  | MOT | F/S Approval (including No.23 and 24 below) | Decision No. 2656/QD-BGTVT | 10 | Sep., | 2010 |
| 23 |  |  |  | Notice (for No.24 below) | Notice No. 325 | 6 | Aug., | 2010 |
| 24 |  |  | Quang Nam | Comments on Additional IC and Re-alignment | Document No. 1732/UBND-KTN | 31 | May, | 2010 |

Issues carried over to D/D Stage

The MOT Appraisal Report, Document No. 6188/BGTVT-KHDT dated September 8, 2010 mentioned that MOT/VEC received the comments on the draft F/S report from relevant organizations and basically modified those items according to their opinions in the F/S report.  However, in Paragraph IV.7, it was also mentioned that some technical issues were unsolved in the F/S stage and those issues were carried over to the subsequent D/D stage.

Issues carried over to D/D stage are shown in Table A.2.

Table A.2   Issues carried over to D/D Stage

| No. | Items | Issues carried over to D/D Stage |
| --- | --- | --- |
| 01 | Alternative Route | Study and adjust the section passing Duc Bo Shooting field (KM070 – KM080) in Quang Nam Province according to Notice No. 325 dated August 6, 2010 issued by MOT |
| 02 | Inundation Analysis | Study more carefully and define exactly where to construct viaducts and drainage culverts to ensure the flood discharge |
| 03 | Requirement for River Bridges | Discuss and agree with localities on hydrological and navigational requirement for river bridges other than four (4) major river bridges which already agreed with the localities in the F/S stage |
| 04 | Clearance with HVL (500kV) | Discuss and agree with EVN on countermeasures for insufficient vertical clearance between the expressway and existing HVL (500kV) at two (2) locations (KM004+431 and KM065+959) |
| 05 | Additional Overpass | Discuss and agree with VNR on intersecting mode (at grade or grade separation) at the intersection between the expressway and existing North-South Railway at KM135+270 (finally, an overpass with 492 m length was approved in the MOT F/S Approval) |
| 06 | ITS | Check in term of technical approach and standards, appropriate investment cost and suitable with current conditions of Vietnam |

Source: MOT Appraisal Report, Document No. 6188/BGTVT-KHDT dated September 8, 2010

Location

The expressway is a part of the North-South Expressway located in parallel with the existing NH1A and North-South Railway and passing through Danang city, Quang Nam and Quang Ngai provinces in the central region.  The road starts at the intersection of the Danang Bypass and NH14B in Danang city and ends at the connecting point with the planned City Ring Road at existing NH1A in Quang Ngai province.  The major socio-economic developments along the expressway are Chu Lai Open Economic Zone in Quang Nam province and Dung Quat Industrial Zone in Quang Ngai province.  As for the cultural properties, Hoi An Ancient Town and My Son Sanctuary, registered as the world heritage (cultural heritage), are existed along the expressway.

Project location map is shown in Figure A.2.

Figure A.2   Project Location Map

Objectives

The main objectives of the Project are to enhance travel efficiency and safety by constructing an expressway from Danang to Quang Ngai, and contributing to economic growth in the central region.

Outline of the Project framework and operating effectiveness indicators established by WB and VEC are shown in Figure A.3 and Table A.3, respectively.

Figure A.3   Outline of Project Framework

Table A.3   Operating Effectiveness Indicators established by WB and VEC

| No. | Area/Sections | Quantitative Indicators |  | Baseline | Target |
| --- | --- | --- | --- | --- | --- |
| 01 | Between Danang and Quang Ngai | Travel time | 10 ton freight vehicles | 233 minutes | 20 % reduction |
| 02 |  |  | Passenger vehicles | 158 minutes | 20 % reduction |
| 03 |  | Coefficient of variation (travel time) | 10 ton freight vehicles | 0.19 | 10 % reduction |
| 04 |  |  | Passenger vehicles | 0.08 | 10 % reduction |
| 05 |  | Traffic accidents (no. of fatalities) |  | 185 nos./year | 10 % reduction |

Source:	M/D (WB Appraisal Mission) dated April 21, 2011

Note:	JICA also agreed to establish the indicators in line with WB in M/D (JICA Appraisal Mission) dated October 21, 2010

Project Components

Three Project Components

The Project consists of the following three (3) components;

Table A.4   Three Project Components

| No. | Component | Description |
| --- | --- | --- |
| 01 | Component A Civil Works | Construction of four-lane dual carriageway road (with capacity for eventual widening to six lanes) and 131 km in total length |
| 02 | Component B ITS (Intelligent Transport Systems) | Provision of traffic management and toll collection facilities |
| 03 | Component C Expressway Operation and Maintenance (O&M) | Planning an institution to operate and maintain the expressway and identifying facilities and equipment that it will need. |

Source:	TOR 1

It is currently expected that the Project will be implemented with financial support from the World Bank and the Japan International Cooperation Agency (JICA). Funds from these agencies would be used to finance separate sections of the Project.

Expressway Construction and O&M Provision

Main features of expressway construction and O&M provision indicated in the F/S are shown in Table A.5, and Project facilities plan is shown in Figure A.4, respectively.

As of the end-December 2011, based on our preliminary review, the followings are identified and to be updated from the F/S:

- Alignment of Expressway

- Typical Cross Sections

- Location of Bridges

- Type of Bridges

- Locations of Cross Structures

- Type of Cross Structures

- Location of My Son Interchange

- Type of Interchanges

Location of My Son Interchange was studied in accordance with PMU85 instruction, and the Consultant proposed new location in our letter No. DQEDD-PMU85-38-11 dated October 25, 2011.

Table A.5   Main Features of Expressway Construction and O&M Provision

| No. | Items | Main Features |  | Ref. in TOR |
| --- | --- | --- | --- | --- |
| 01 | Road Length | 139.52 km |  | Component A |
|  |  |  | By Road Class: Expressway section: 131.5 km, Linking road section: 8.02 km | (TOR 1(1)) |
|  |  |  | By Jurisdiction: Danang city: 8.0 km, Quang Nam province: 92.0 km, Quang Ngai province: 39.52 km |  |
|  |  |  | Beginning Point (BP): Intersection of the existing Danang bypass and NH14B in Danang city |  |
|  |  |  | Ending Point (EP): Connecting point with the planned city ring road at the existing NH1A (KM1063+700) in Quang Ngai province |  |
| 02 | Road Classification | Expressway: Type A, Class 120, Linking Road: Class III, Delta |  |  |
| 03 | Design Speed | Expressway: 120 km/hr (Tunnel section: 100 km/hr), Linking Road: 80 km/hr |  |  |
| 04 | Nos. of Lane | 4 lanes (Ultimate stage: Widened to 6 lanes (see Figure A.4)) |  |  |
| 05 | Road With | Expressway: Road and Bridge sections: 26.0 m, Tunnel section: 2@12.75 m=25.5 m, Linking Road: 12.0 m |  |  |
| 06 | Design Hydrological Frequency | Expressway: 1 %, Linking Road: 4 % |  |  |
| 07 | Bridge | 131 bridges (L=15,486.85 m)1) |  |  |
|  |  |  | Large River Bridge (LRB, L>100 m): 20 bridges (L=5,687.55 m)2), Other River Bridge (ORB, L<100 m): 10 bridges (L=603.85 m), |  |
|  |  |  | Stream Bridge (SB): 8 bridges (L=354.90 m), Canal Bridge (CB): 18 bridges (L=666.00 m), |  |
|  |  |  | Viaduct (VD): 21 bridges (L=3,073.45 m), Overpass (OP): 23 bridges (L=1,186.80 m)1), |  |
|  |  |  | Interchange Rampway Bridge (IRB): 12 bridges (L=1,662.30 m), Flyover (FO): 19 bridges (L=2,252.00 m) |  |
| 08 | Major River Bridge | 4 bridges (L=2,670.00 m) |  |  |
|  |  |  | Thu Bong River (KM017+662): Ky Lam Bridge (L=962.00 m), Ba Ren River (KM020+185): Chiem Son Bridge (L=410.00 m), |  |
|  |  |  | Tra Bong River (KM109+320): Tra Bong Bridge (L=452.00 m), Tra Khuc River (KM125+700): Tra Khuc Bridge (L=846.00 m) |  |
| 09 | Tunnel | 1 tunnel (KM022+900, L=2@540 m) |  |  |
| 10 | Culvert | 375 culverts |  |  |
|  |  |  | Culvert Box: 188 culvert boxes (106 roadway culverts and 82 waterway culverts), Culvert Pipe: 187 culvert pipes |  |
| 11 | Softground | Approximately 3.6 km |  |  |
| 12 | Interchange | 9 interchanges |  |  |
| 13 | Frontage Road | Approximately 59.7 km |  |  |
| 14 | Earth Works | Soil excavation: 10,000,000 m3, Rock excavation: 1,000,000 m3, Filling: 24,000,000m3 |  |  |
| 15 | Electrical Facilities | Power supply, road lighting, tunnel ventilation and safety facilities |  | Component B |
| 16 | ITS | Traffic management, toll collection3) and communication systems |  | (TOR 1(2)) |
| 17 | O&M Building | 26 locations (see Figure A.4) |  | Component C |
|  |  |  | Traffic Management Center (TMC): 1 location, Expressway Operation Office (EOO): 1 location, Toll Plaza Office (TPO): 9 locations, | (TOR 1(3)) |
|  |  |  | Toll Barrier (TB): 2 locations, Toll Gate (TG): 7 locations, Service Area (SA): 2 locations, Parking Area (PA): 4 locations |  |
| 18 | O&M Equipment | O&M vehicles, spare parts, maintenance equipment and consumables |  |  |

Source:	MOT F/S Approval, Decision No. 2656/QD-BGTVT dated September 10, 2010 (modified discrepancies with the F/S report by the Consultant)

Note:	1)	Including the additional overpass with 492 m at KM135+270 (see No.5, Table A.2)

2)	Including 4 major river bridges (see No.8)

3)	Including electric toll collection system in accordance with MOT Notice No.94/TB-BGTVT dated March 10, 2009

Source:	MOT F/S Approval, Decision No. 2656/QD-BGTVT dated September 10, 2010 (modified discrepancies with the F/S report by the Consultant)

Note:	1)	Confirmed with the F/S Consultant (not mentioned in the MOT F/S Approval, Decision No. 2656/QD-BGTVT dated September 10, 2010)

Figure A.4   Project Facilities Plan

Extent of the Consulting Services

The overall consulting services for the Project consists of Detailed Engineering Design (D/D), Construction Supervision (C/S) and Project implementation support for PMU85/VEC.  The consulting services in this contract (the Services) cover D/D only, without C/S and Project implementation support.

Main scope of overall consulting services is summarized in Table A.6. See Table A.9 for reference.

Table A.6   Main Scope of Overall Consulting Services

| No. | Items |  | Main Scope |
| --- | --- | --- | --- |
| 01 | Detailed Engineering Design (D/D) |  | - Previous studies review and establishing D/D framework |
|  |  |  | - D/D and procurement planning (incl. B/D of O&M/ITS package) |
|  |  |  | - Procurement assistance (civil work packages) |
| 02 | Construction Supervision (C/S) |  | - B/D and procurement documents review (O&M/ITS package) |
|  |  |  | - Procurement assistance (O&M/ITS package) |
|  |  |  | - D/D review (civil work packages) |
|  |  |  | - C/S (incl. internal social, environmental and resettlement monitoring) |
|  |  |  | - Assisting in establishment of an O&M unit (incl. capacity development) |
|  |  |  | - Assisting in defect liability inspections |
| 03 | Project Implementation | Integrated Project Review and | - D/D appraisal |
|  | Support for PMU85/VEC | Monitoring Services | - Traffic safety audit |
|  |  |  | - Construction quality inspection |
|  |  |  | - Social and environmental external monitoring |
|  |  |  | - Resettlement external monitoring |
|  |  |  | - Overall project monitoring and evaluation |
|  |  |  | - Expressway user information and HIV/AIDS campaign |
|  |  | Financial Audit | - Annual project financial external audit |
|  |  | Financial Capacity Development | - Financial capacity development for VEC |

Source:	Decision No. 1423/QD-BGTVT dated June 30, 2011, Decision No. 1688/QD-BGTVT dated July 28, 2011

M/D (JICA Appraisal Mission) dated October 21, 2010, M/D (WB Appraisal Mission) dated April 21, 2011

Establishment of an O&M Unit

The O&M framework of the expressway section will be proposed in the Service.  Based on the F/S report, the estimated financial return by operating the expressway is low in the early stage because of the forecasted traffic volume is small.  Therefore, O&M concessions are not attractive for private investors, and the expressway is expected to be operated by an O&M unit under VEC in the early stage.

Expected O&M framework for the expressway, at this moment, is shown in Figure A.5.

Note:	1)	Various administrative arrangements such as level of services and its inspection system, accounting and auditing systems, toll rate setting and subsidies

Figure A.5   Expected O&M Framework for Expressway

Safeguards

Social and Environmental Assessment

The original EIA report based on the JETRO study was prepared by PMU85, and approved by MONRE in Decision No. 2378/QD-BTNMT dated November 12, 2008.  The supplemental EIA report based on the F/S alignment was also prepared by PMU85 and approved by MONRE in Decision No. 2046/QD-BTNMT dated October 29, 2010.

Social and environmental assessment framework for the expressway is shown in Figure A.6.

Figure A.6   Social and Environmental Assessment Framework for the Expressway

Land Acquisition and Resettlement

RAP based on the F/S alignment was prepared by PMU85 and approved by the Prime Minister in Decision No. 442/TTg-KTN dated March 23, 2011.

Land acquisition area and no. of resettlement households for the expressway is shown in Table A.7, and CPCSR framework for the expressway is shown in Figure A.7.

Table A.7   Land Acquisition Area and Nos. of Resettlement Households for the Expressway

| No. | Item | Unit | Danang | Quang Nam | Quang Ngai | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 01 | Land Acquisition Area | sq.m | 506,014 (5%) | 6,425,285 (67%) | 2,658,838 (28%) | 9,590,137 (100%) |
| 02 | Resettlement Households | nos. | 85 (7%) | 771 (60%) | 430 (33%) | 1,286 (100%) |

Source:	Decision No. 442/TTg-KTN dated March 23, 2011

Figure A.7   CPCSR Framework for the Expressway

Project Cost

The total investment cost was approved by MOT in Decision No. 2656/QD-BGTVT dated September 10, 2010, and it amounts to 27,968 Bil.VND (equivalent to 1,472 Mil.USD).

Total investment cost is shown in Table A.8.

Table A.8   Total Investment Cost

| No. | Items | Foreign Loans | State Budget | Total1) |  |
| --- | --- | --- | --- | --- | --- |
|  |  | (Mil.USD) | (Bil.VND) | (Equiv. to Bil.VND) | (Equiv. to Mil.USD) |
| 01 | Construction Cost | 904 |  | 17,179 | 904 |
| 02 | Equipment Cost | 31 |  | 580 | 31 |
| 03 | Consulting Services Cost | 53 |  | 1,003 | 53 |
| 04 | Project Management Cost |  | 68 | 68 | 4 |
| 05 | Other Cost | 32 |  | 606 | 32 |
| 06 | Land Acquisition and Compensation Cost |  | 1,074 | 1,074 | 56 |
| 07 | Contingency | 200 | 114 | 3,927 | 206 |
| 08 | VAT |  | 1,943 | 1,943 | 102 |
| 09 | Loan Interest and Financial Fees2) | 84 |  | 1,588 | 84 |
| Total |  | 1,304 | 3,199 | 27,968 | 1,472 |

Source:	Decision No. 2656/QD-BGTVT dated September 10, 2010

Note:	1)	Exchange rate: 1USD = 19,000VND

2)	Interest during construction, front-end fees, commitment charge and service charges

Funding Arrangement

The investment cost is financed by JICA, WB and counterpart fund and it was approved by MOT in Decision No. 2656/QD-BGTVT dated September 10, 2010.  VEC is responsible for borrowing and re-paying the loans and it was decided by GOVN Office and MOF in Document No. 4684/VPCP-KTN dated July 7, 2010 and Document No. 695/BTC-QLN dated August 13, 2010.

JICA signed L/A on June 15, 2011 and finances the civil works section between Danang to Tam Ky, electrical works, O&M building works and O&M/ITS equipment procurement for the whole section, C/S, other cost, contingency and loan interest and financial fees for JICA portion.

WB finances the D/D cost for the whole section through on-going RNIP (IDA Credit No.: 3843-VN).  In addition, WB approved to provide a loan and two (2) credits by the Executive Directors on May 24, 2011 and finances the civil works section between Tam Ky and Quang Ngai, C/S, other cost, contingency and loan interest and financial fees for WB portion, and project implementation support for VEC.  Funding arrangement among WB, JICA and GOVN is shown in Table A.9.

Table A.9   Funding Demarcation among WB, JICA and GOVN

| No. | Item |  |  | Section | Funding Demarcation |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | JICA1) | WB1) | GOVN |
| 01 | Construction (Civil Works) |  |  | Danang to Tam Ky | ● |  |  |
|  |  |  |  | Tam Ky to Quang Ngai |  | ● |  |
| 02 | Electrical, ITS Facilities and O&M Building Works, and O&M Equipment Provision |  |  | Whole Section | ● |  |  |
| 03 | Consulting | D/D |  | Whole Section |  | ● |  |
|  | Services | C/S | Civil Works | Danang to Tam Ky | ● |  |  |
|  |  |  |  | Tam Ky to Quang Ngai |  | ● |  |
|  |  |  | Electrical/O&M/ITS Works and Equipment Provision | Whole Section | ● |  |  |
|  |  | Project Implementation | Integrated Project Review and Monitoring Services | Whole Section |  | ● |  |
|  |  | Support for VEC | Financial Audit | Whole Section |  | ● |  |
|  |  |  | Financial Capacity Development | Whole Section |  | ● |  |
| 04 | Project Management, Land Acquisition and Compensation, Contingency and VAT |  |  | Whole Section |  |  | ● |

Source:	Decision No. 2656/QD-BGTVT dated September 10, 2010

M/D (JICA Appraisal Mission) dated October 21, 2010, M/D (WB Appraisal Mission) dated April 21, 2011

Note:	1)	Including other cost, contingency and loan interest and financial fees in each portion

Contract Packaging

The procurement plan for JICA portion including construction contract packaging was approved by MOT in Decision No. 1688/QD-BGTVT dated July 28, 2011.  As for the WB portion, it was also approved by MOT in Decision No. 1423/QD-BGTVT dated June 30, 2011.

As of December 2011, the Consultant submitted our procurement plan with our letter No. DQEDD-PMU85-77-11 dated December 15, 2011 in accordance with several times of discussion with PMU85/VEC.

Re-defining the package boundaries based on the modified alignment (see D.3.1(4))

Dividing PKG3 into Ky Lam Bridge (PKG3A) and remaining section (PKG3B) (see A.1.11).

Propose separation of “Traffic Safety and Street Lighting” as PKG14.

Bing Proposed construction contract packaging is shown in Table A.10.

Table A.10   Proposed Construction Contract Packaging (December 15, 2011)

| Contract Packaging |  |  |  |  | Lenders |  |
| --- | --- | --- | --- | --- | --- | --- |
| Items | Jurisdiction | No. | Station1) | Length1) | JICA | WB |
| Civil Works | Danang | PKG1 | KM000+000 - KM008+000 | 8.00 km | ● |  |
|  | Quang Nam | PKG2 | KM008+000 - KM016+880 | 8.88 km | ● |  |
|  |  | PKG3a | KM016+880 - KM018+100 | 1.22 km | ● |  |
|  |  | PKG3b | KM018+100 - KM021+500 | 3.40 km | ● |  |
|  |  | PKG4 | KM021+500 - KM032+600 | 11.10 km | ● |  |
|  |  | PKG5 | KM032+600 - KM042+000 | 9.40 km | ● |  |
|  |  | PKG6 | KM042+000 - KM052+000 | 10.00 km | ● |  |
|  |  | PKG7 | KM052+000 - KM065+000 | 13.00 km | ● |  |
|  |  | PKGA1 | KM065+000 - KM081+150 | 16.15 km |  | ● |
|  |  | PKGA2 | KM081+150 - KM099+500 | 18.35 km |  | ● |
|  | Quang Ngai | PKGA3 | KM099+500 - KM110+100 | 10.60 km |  | ● |
|  |  | PKGA4 | KM110+100 - KM124+700 | 14.60 km |  | ● |
|  |  | PKGA5 | KM124+700 - KM131+500 | 6.80 km |  | ● |
|  | Total |  |  | 131.50 km |  |  |
| Electrical/O&M Building/ITS Works and Equipment Provision | All | PKG13 | KM000+000 - KM131+150 | 131.50 km | ● |  |
| Traffic Safety and Street Lighting | All | PKG14 | KM000+000 - KM131+150 | 131.50 km | ● |  |

Source: Consultant proposal by DQEDD-PMU85-11 dated December 15, 2011

Note:	1)	Based on the modified alignment in D.3.1 Work Item (4) (station and section length are not based on F/S alignment)

On the basis of the above proposed packaging, the contract amount of each package in the approved bidding plan is revised as shown in Table A.11.

Table A.11   Updated Contract Amount by Proposed Contract Package (December 15, 2011)

| Jurisdiction | Contract Packaging |  |  |  |  |  |  | Contract (Bill. VND) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | No. | Section |  |  | Length (m) |  |  | JICA |  | WB |  |
|  |  |  |  |  |  | Rate | Traffic/Lighting | Amount wo Traffic/Lighting | Unit Cost (/km) | Amount | Amount wo Traffic/Lighting |
| Danang | PKG1 | KM000+000 | - | KM008+000 | 8,000 | 5.75% | 36.44 | 1,354.16 | 169 |  |  |
| Quang Nam | PKG2 | KM008+000 |  | KM016+880 | 8,880 | 6.38% | 40.44 | 1,377.69 | 155 |  |  |
|  | PKG3A | KM016+880 |  | KM017+000 | 120 | 0.09% | 0.55 | 810.44 | 664 |  |  |
|  |  | KM017+000 |  | KM018+100 | 1,100 | 0.79% | 5.01 |  |  |  |  |
|  | PK3B | KM018+100 |  | KM021+500 | 3,400 | 2.44% | 15.49 | 733.07 | 216 |  |  |
|  | PKG4 | KM021+500 |  | KM022+000 | 500 | 0.36% | 2.28 | 1,332.48 | 120 |  |  |
|  |  | KM022+000 |  | KM032+000 | 10,000 | 7.18% | 45.54 |  |  |  |  |
|  |  | KM032+000 |  | KM032+600 | 600 | 0.43% | 2.73 |  |  |  |  |
|  | PKG5 | KM032+600 |  | KM042+000 | 9,400 | 6.75% | 42.81 | 1,160.76 | 123 |  |  |
|  | PKG6 | KM042+000 |  | KM052+000 | 10,000 | 7.18% | 45.54 | 1,209.56 | 121 |  |  |
|  | PKG7 | KM052+000 |  | KM065+000 | 13,000 | 9.34% | 59.21 | 1,602.59 | 123 |  |  |
|  | PKG A1 | KM65+000 |  | KM081+150 | 16,150 | 11.60% | 73.55 |  |  | 1,607.13 | 100 |
|  | PKG A2 | KM081+150 |  | KM081+500 | 350 | 0.25% | 1.59 |  |  | 1,699.04 | 93 |
|  |  | KM081+500 |  | KM099+500 | 18,000 | 12.93% | 81.98 |  |  |  |  |
| Quang Ngai | PKG A3 | KM099+500 |  | KM100+000 | 500 | 0.36% | 2.28 |  |  | 1,447.38 | 137 |
|  |  | KM100+000 |  | KM110+100 | 10,100 | 7.26% | 46.00 |  |  |  |  |
|  | PKG A4 | KM110+100 |  | KM111+000 | 900 | 0.65% | 4.10 |  |  | 1,724.17 | 118 |
|  |  | KM111+000 |  | KM124+700 | 13,700 | 9.84% | 62.40 |  |  |  |  |
|  | PKG A5 | KM124+700 |  | KM125+000 | 300 | 0.22% | 1.37 |  |  | 1,742.14 | 120.1 |
|  |  | KM125+000 |  | KM131+500 | 6,500 | 4.67% | 29.60 |  |  |  |  |
|  |  | KM131+500 |  | KM139+204 | 7,704 | 5.53% | 35.09 | (linking road) |  |  |  |
|  |  | Expressway Length |  |  | 131,500 | 100.00% |  |  |  |  |  |
|  |  | Linking Road Length |  |  | 7,704 |  |  |  |  |  |  |
| All | PKG13 | KM000+000 | - | KM131+500 | 131,500 |  |  | 580.00 | 4 |  |  |
| All | PKG14 | KM000+000 | - | KM131+500 | 131,500 |  |  | 634.00 | 5 |  |  |
| Total |  |  |  |  |  |  | 634 | 9,580.76 |  | 8,219.86 | 18,434.6 |

Source: Consultant proposal by DQEDD-PMU85-11 dated December 15, 2011

Project Implementation Structure

MOT designated VEC as the Project Owner in Decision No. 220/QD-BGTVT dated January 22, 2010 and also appointed PMU85 as the Project Implementation Agency for the D/D stage in Decision No. 2149/QD-BGTVT dated September 19, 2011.

As for the construction stage, MOT approved that PMU85 for JICA financed portion and PMU1 for WB financed portion are Project Implementation Agencies, by signing the principle contracts with VEC in Decision No. 2656/QD-BGTVT dated September 10, 2011.

Project implementation structure is shown in Figure A.8.

Note:	1)	Project Implementation Support for VEC (see Table A.6)

Figure A.8   Project Implementation Structure

Project Implementation Program

The Project Implementation Program (I/P) was agreed among JICA, WB and GOVN during the JICA Appraisal in October, 2010.  However, this program is delayed approximately 15 months. i.e. the commencement of the detailed design was intended August 10, 2010 in Clause 7.2 of Data Sheet of the RFP issued on February 12, 2010, and now this Service was commenced on December 1, 2012.

Main considerations in updating Project I/P are shown in Table A.12, and proposed Project I/P is shown in Figure A.9.

Table A.12   Main Considerations in Updating Project I/P

| No. | Items | Contents |
| --- | --- | --- |
| 01 | Commencement of Construction Works (1st Priority, within September 2012) | The realization for commencing construction works within September 2012 is required by the Minutes of Contract Negotiation for the Services dated October 15, 2011. Based on the Consultant’s study, Ky Lam Bridge was selected as the priority package by design and land acquisition ease; then, PKG3 was divided into Ky Lam Bridge (PKG3A) and remaining sections (PKG3B). |
| 02 | Construction Period (Civil Work Packages) | The construction period of all civil work packages were defined 36 months in the following Decisions: - MOT Decision No. 1688/QD-BGTVT dated July 28, 2011 (Procurement Plan, JICA Portion) - MOT Decision No. 1423/QD-BGTVT dated June 30, 2011 (Procurement Plan, WB Portion) Based on the Consultant’s preliminary estimate, the construction period for PKG1 (Softground Section), PKG3A (Ky Lam Bridge) and PKGA5 (incl. Tra Khuc Bridge) were extended to 42 months. |
| 03 | Completion of D/D of Three (3) Packages (2nd Priority, within 6th month) | Draft D/D of first three (3) packages is required to complete within 6th month by the Minutes of Contract Negotiation for the Services dated October 15, 2011. In consideration of land acquisition, design ease and fairness among provinces, PKG1 and PKGA4 were selected as the priority packages. |

Figure A.9   Updated Project Implementation Program

Outline of the Services

General

This Inception Report (IC/R) is for Consulting Services for Detailed Design for Danang - Quang Ngai Expressway Development Project (the Services) in accordance with the Consulting Services Contract (the Contract) between PMU85 and Joint Venture of Nippon Koei Co., Ltd. (NK), Nippon Engineering Co., Ltd. (NE), Chodai Co., Ltd. and Thai Engineering Consultant Co., Ltd. (TEC) (the Consultant) signed on November 15, 2011.

The Services is officially commenced on December 1, 2011 in accordance with Notice to Proceed (NTP) issued PMU85 letter No. 1622/PMU85-PP2 dated November 18, 2011 and the Consultant letter No. DQEDD-PMU85-52-11 dated November 18, 2011.

Objectives

The objectives of the Services are, as stipulated in the TOR of the Contract:

- To undertake the efficient and proper preparation of the detailed engineering design;

- To prepare an implementation program that can ensure delivery of the project in an efficient and timely manner infrastructure in accordance with the implementation program; and

- To promote technology transfer by employing suitably qualified Vietnamese professionals for the detailed design and implementation planning for the Project and by providing appropriate training for staff of the related agencies who will be at various times responsible for the Project.

Scope in TOR

Two Modes in the Consulting Services

The Services are carried out by two (2) modes as shown in Table A.13.

Table A.13   Mode of the Services

| No. | Mode | Contents |
| --- | --- | --- |
| 1 | Primary Tasks | Arrangement for managing the Services by the Consultant, who is fully responsible to VEC/PMU85, for |
|  |  | adequacy and quality of the end outputs of the Services assuring duly compliance of the Services |
|  |  | assuring duly compliance of the scope of the Services specified in the Contract. |
| 2 | Assistance Tasks | The Consultant provides technical advice and assistance in carrying out the works to be accomplished |
|  |  | by VEC/PMU85 through the Consultant’s professional ability; however, the Consultant is not responsible |
|  |  | for the end outputs. |

Contents of the Consulting Service Contract

The scope of service is stipulated in the Contract consists of the following contents as shown in Table A.14.

Table A.14   Contents of the Consulting Service Contract

| No. | Content | Issue Date |
| --- | --- | --- |
| 01 | Contract | 15 November 2011 |
| 02 | Minutes of Discussion Meeting for Contract Finalization. | 15 October 2011 |
| 03 | The second Minutes of Contract Negotiation. | 20 September 2011 |
| 04 | Minutes of Contract Negotiation. | 26 May 2011 |
| 05 | The General Conditions of Contract. | 15 November 2011 |
| 06 | The Special Conditions of Contract; |  |
| 07 | Appendix A: Description of the Services |  |
| 08 | Appendix B: Reporting Requirements |  |
| 09 | Appendix C: Key Personnel and Sub-consultants |  |
| 10 | Appendix D: Cost Estimates |  |
| 11 | Appendix E: Services and Facilities Provided by the Client |  |
| 12 | Appendix F: Form of Advanced Payment Guarantee |  |

TOR in the Contract

As shown in Table A.14, the Terms of Reference (TOR) is provided in Appendix A: Description of the Services of the contract.

The Consultant reviewed the TOR carefully and prepare our work plan to satisfy the requirements in the most efficient and effective manner as shown in this Inception Report.

Additional Scope to TOR

On the basis of the Consultant’s understanding of the Project, with natural and social conditions of the region, the following additional work items were proposed in our Technical Proposals, in order to implement the Project smoothly and successfully.

Those work items and necessary professional staff input were agreed with the Client and stipulated in the Contract.

Table A.15   Additional Scope to TOR

| No. | Category | Scope |
| --- | --- | --- |
| 01 | Inundation Analysis | The Consultant consulted with JICA to utilize the results of “Project for Building Disaster Resilient Societies in Central Region in Vietnam (DRSC)” for the expressway design, and it was agreed by JICA. Supported by JICA’s agreement, the Consultant will carry out the inundation analysis to assess flood inundation conditions along and around the expressway, and compare the inundation phenomena ”Before Project” and “After Project”. |
| 02 | Electrical Facilities Design | There are many electrical facilities that crossing the expressway and/or locating nearby. Those electrical facilities should be relocated and appropriate design should be provided. Not only that there are several electrical facilities to be provided as integral part of the expressway. The Consultant will carry out the detailed design of those electrical facilities. |
| 03 | Public Utilities Relocation Plan | Public utilities such as electrical lines, telecommunication lines, water supply pipes, drainage piles, should be carefully and timely relocated during the construction. The Consultant identifies all public utilities to be relocated in the project, in consultation with the local authorities, and prepare necessary drawings and place the cost in the cost estimate. |

Work Items in the Services

The Consultant established the work items for the Services in accordance to the requirement of “Item 3. Scope of Services” in Appendix A: Description of Services in the Contract, with the above additional, as shown in Table A.16.

The work items in Table A.16 are further break downed into appropriate scale of work units which are good for monitoring and control. Detailed work items and the work method of each item are described later in Parts B to F in this report.

Table A.16   Summary of Work Items

| Work Items |  |  |  | Clause No. in TOR |
| --- | --- | --- | --- | --- |
| Part B | Project Management |  |  | Additional Task |
|  | B.1 | Establish and control practical management system |  | Additional Task |
| Part C | Previous Studies Review and Establishing Detailed Engineering Design Framework |  |  | 3.1, 3.2 |
|  | C.1 | Review previous studies |  | 3.2(1) |
|  | C.2 | Establish detailed engineering design framework |  | 3.2(2) |
| Part D | Detailed Engineering Design and Procurement Planning |  |  | 3.3 |
|  | D.1 | Contract Packaging |  | 3.3.1 |
|  |  | D.1.1 | Propose contract packaging | 3.3.1 |
|  | D.2 | Surveys and Investigations |  | 3.3.2 |
|  |  | D.2.1 | Collect relevant data and documents | 3.3.2(1) |
|  |  | D.2.2 | Conduct topographic survey | 3.3.2(2)(i), 3.5 |
|  |  | D.2.3 | Conduct hydrological survey and analysis | 3.3.2(2)(ii) |
|  |  | D.2.4 | Inundation analysis | Additional Task |
|  |  | D.2.5 | Conduct geotechnical and geological investigations | 3.3.2(2)(iii) |
|  |  | D.2.6 | Conduct material source survey | 3.3.2(2)(iv) |
|  |  | D.2.7 | Conduct relevant facilities survey | 3.3.2(2)(v) |
|  |  | D.2.8 | Review traffic forecasting and conduct baseline surveys | 3.3.2(2)(vi) |
|  |  | D.2.9 | Conduct independent land valuation survey | 3.3.2(2)(vii) |
|  |  | D.2.10 | Conduct environmental and social surveys | 3.3.2(2)(viii) |
|  | D.3 | Civil Engineering Design |  | 3.3.3 |
|  |  | D.3.1 | Prepare basic design of civil structures | 3.3.3 |
|  |  | D.3.2 | Prepare detailed engineering design of civil structures | 3.3.3 |
|  | D.4 | O&M Plan and Design |  | 3.3.5 |
|  |  | D.4.1 | Prepare institutional and administrative arrangement plan | 3.3.5 |
|  |  | D.4.2 | Prepare O&M plan | 3.3.5 |
|  |  | D.4.3 | Prepare basic design of O&M buildings | 3.3.5 |
|  | D.5 | ITS Plan and Design |  | 3.3.4 |
|  |  | D.5.1 | Prepare ITS plan | 3.3.4(1) |
|  |  | D.5.2 | Prepare basic design of ITS facilities | 3.3.4(2) |
|  | D.6 | Electrical Facilities Design |  | Additional Task |
|  |  | D.6.1 | Prepare detailed engineering design of electrical facilities | Additional Task |
|  | D.7 | Public Utilities Relocation Plan |  | Additional Task |
|  |  | D.7.1 | Prepare relocation plan of public utilities | Additional Task |
|  | D.8 | Safeguards |  | 3.3.6, Annex A, Annex B |
|  |  | D.8.1 | Review and update EIA, EMDP and EMP | 3.3.6, Annex A |
|  |  | D.8.2 | Review and update RAP | 3.3.6, Annex B |
|  | D.9 | Construction Planning |  | 3.3.7 |
|  |  | D.9.1 | Prepare construction plan | 3.3.7 |
|  | D.10 | Project Cost Estimate |  | 3.3.8 |
|  |  | D.10.1 | Estimate Project cost | 3.3.8 |
|  | D.11 | Procurement Documents |  | 3.3.9 |
|  |  | D.11.1 | Prepare procurement documents | 3.3.9 |
|  | D.12 | Project Implementation Program |  | 3.3.10 |
|  |  | D.12.1 | Prepare Project I/P | 3.3.10 |
| Part E | Procurement Assistance |  |  | 3.4 |
|  | E.1 | Assist in tendering procedures |  | 3.4 |
| Part F | Land Acquisition Staking |  |  | 3.5 |
|  | F.1 | Stake land acquisition to handover to local authorities |  | 3.5 |
| Part G | Technology Transfer |  |  | 3.6 |
|  | G.1 | Provide training to VEC, PMU85 and relevant organizations |  | 3.6 |
|  | G.2 | Provide training to key local professional staff |  | 3.6 |

Work Schedule

Milestones in the Contract

Milestones are mentioned in the Contract as summarized in Table A.17.

The Consultant prepared the work schedule in order to satisfy the required milestones.

Table A.17   Milestones in the Contract (December 2011)

| No. | Milestone (MS) | Date/Deadline | Clause in Contract |
| --- | --- | --- | --- |
| 01 | Contract signing | November 15, 2011 | Contract |
| 02 | Issuance of Notice to Proceed | November 18, 2011 | PMU85 letter No. 1622/PMU85-PP2 dated November 18, 2011 |
| 03 | Commencement of Consulting services | December 1st, 2011 | Consultant letter No. DQEDD-PMU85-52-11 dated November 18, 2011. |
| 04 | Submission of draft design report for the first contract package | Late December 2011 | Item I.3.6 of Minutes of Discussion dated 15/10/2011 |
| 05 | Inception Report | December 31, 2011 | Item (1), Appendix B: Reporting Requirements |
| 06 | Inception report of Replacement Cost Survey | December 31, 2011 | Item IV, TOR of RCS, Annex B, TOR Item (9), Appendix B: Reporting Requirements |
| 07 | Submission of a brief report on the appropriateness of the proposed alignment | January 15, 2012 | Item 7, Annex A, TOR Item (8), Appendix B: Reporting Requirements |
| 08 | Review and Detailed Design Framework Report | January 31, 2012 | Item (2), Appendix B: Reporting Requirements |
| 09 | Completion of detailed design for the first contract package | February 15, 2012 | Item I.3.6 of Minutes of Discussion dated 15/10/2011 |
| 10 | Submission of updated draft EIA and EMP reports | April 15, 2012 | Item 7, Annex A, TOR Item (8), Appendix B: Reporting Requirements |
| 11 | Submission of overall implementation plan of the project | March 31, 2012 | Item B.2 of Minutes of Contract Negotiation dated 26/05/2011 |
| 12 | Submission of RCS reports | May 15, 2012 | Item IV, TOR of RCS, Annex B, TOR Item (9), Appendix B: Reporting Requirements |
| 13 | Submission of 3 sets of draft design report, prequalification and tender documents for the first three contract packages | May 31, 2012 | Appendix B: Reporting Requirements |
| 14 | Submission of updated draft final EIA and EMP reports | July 15, 2012 | Item 7, Annex A, TOR Item (8), Appendix B: Reporting Requirements |
| 15 | Completion of design works and preparation of bidding documents of the first 3 packages | August 31, 2012 | Item B.2 of Minutes of Contract Negotiation dated 26/05/2011 |
| 16 | Commencement of the first package | September 2012 | Item I.1 of Minutes of Discussion dated 15/10/2011 Item 3.3.1 of TOR |
| 17 | Submission of full sets of design reports, prequalification and tender documents for the whole project | November 30, 2012 | Appendix B: Reporting Requirements |
| 18 | Commencement of 2nd to 5th package | Every 2 month | Item I.1 of Minutes of Discussion dated 15/10/2011 |
| 19 | Commencement of 6th to last package | Every one month |  |

Priority Packages

Taking the above mentioned requirement of the milestones (MS) into consideration, the D/D work schedule is divided into the following three (3) priorities to meet the requirements in the Project I/P (see A.1.11).

1st Priority Package	:	Complete D/D not later than February 15, 2012 (MS09)

2nd Priority Packages	:	Complete D/D not later than May 31, 2012 (MS13)

Non-priority Packages	:	Complete D/D not later than November 30, 2012 (MS17)

General Work Schedule

The Services was officially commenced from December 1, 2011 although the topographic survey work items were commenced from July 15, 2011 in accordance with the Minutes of Contract Negotiation dated May 26, 2011.

Service period is 14 months and end in January 2013. The procurement assistance will be continued after that time as agreed in the Minutes of Discussion Meeting dated October 15, 2011.

General work schedule is shown in Figure A.10.

Figure A.10   General Work Schedule

Reporting Schedule

Reporting Structure

Considering the requirements in Appendix B: Reporting Requirement in the Contract, the Consultant established the following six (6) categories, as reporting structure in the Services as shown in Table A.18.

Table A.18   Reporting Structure

| No. | Sub No. | Category |
| --- | --- | --- |
| 01 |  | General Reports |
| 02 |  | Technical Reports |
|  | 01 | Survey Reports |
|  | 02 | Basic Design Reports (Civil) |
|  | 03 | Detailed Engineering Design Reports (Civil) |
|  | 04 | Electrical Design Reports |
|  | 05 | Public Utilities Relocation Plan Reports |
|  | 06 | ITS Plan and Design Reports |
|  | 07 | O&M Plan and Design Reports |
| 03 |  | Cost Estimate Reports |
|  | 01 | Method Statements |
|  | 02 | Quantity Reports |
|  | 03 | Cost Estimate Reports |
| 04 |  | Procurement Reports |
|  | 01 | Procurement Plan Reports |
|  | 02 | PQ Documents |
|  | 03 | Tender Documents |
| 05 |  | Safeguard Documents |
| 06 |  | Discussion Papers |

List of Reports (Tentative)

As of the end- December 2011, the following reports are identified as shown in Table A.19. The list of reports will be continuously updated.

Submission Schedule (Tentative)

Tentative submission schedule of each report is shown in Figure A.11.

Table A.19   List of Reports (Tentative)

| Category | No. | Report Title (Tentative) |
| --- | --- | --- |
| General Reports | 01 | Inception Report |
|  | 02 | Monthly Progress Reports |
|  | 03 | Interim Reports |
|  | 04 | Draft Project Completion Report |
|  | 05 | Project Completion Report |
|  | 06 | Review Reports |
|  | 07 | Detailed Engineering Design Framework |
|  | 08 | Contract Packaging |
|  | 09 | Project I/P |
|  | 10 | Technology Transfer Reports |
| Technical Reports | 11 | Relevant Data and Documents |
|  | 12 | Topographic Survey Reports |
|  | 13 | ROW Survey Reports |
|  | 14 | Hydrological/Inundation Analyses Reports |
|  | 15 | Geotechnical and Geological Investigations Report |
|  | 16 | Material Source Survey Report |
|  | 17 | Relevant Facilities Survey Report |
|  | 18 | Traffic Forecasting Review Report |
|  | 19 | Baseline Survey Reports (Additional Traffic Survey) |
|  | 20 | Independent Land Valuation Survey Reports |
|  | 21 | Environmental and Social Survey Report (Site Survey) |
|  | 22 | Working Design Reports |
|  | 23 | Basic Design Reports (Civil) |
|  | 24 | Working Design Reports |
|  | 25 | Detailed Engineering Design Reports (Civil) |
|  | 26 | Quantity Reports (Civil) |
|  | 27 | Road Safety Audit Report |
|  | 28 | Electrical/O&M/ITS Plan |
|  | 29 | Draft Basic Design Reports (Electrical/O&M/ITS) |
|  | 30 | Quantity Report (Electrical/O&M/ITS) |
|  | 31 | Public Utilities Relocation Plan |
| Cost Estimate Reports | 32 | Cost Estimate Conditions |
|  | 33 | Cost Estimate Reports |
| Procurement Reports | 34 | Procurement Plan |
|  | 35 | Pre-qualification Documents (by PKG) |
|  | 36 | Bidding Documents (by PKG) |
|  | 37 | P/Q Evaluation Reports (Civil, by PKG) |
|  | 38 | Bid Evaluation Reports (Civil, by PKG) |
|  | 39 | Draft Contract Documents (Civil, by PKG) |
| Safeguard Documents | 40 | Brief Report on Appropriateness of F/S Alignment |
|  | 41 | Updated Draft EIA and EMP |
|  | 42 | Draft Final Updated Draft EIA and EMP |
|  | 43 | Draft TOR (External Environmental Monitoring) |
|  | 44 | Inception Report (Resettlement Monitoring Plan) |
|  | 45 | CPCSR (by Province) |
|  | 46 | Draft TOR (External Resettlement Monitoring) |
|  | 47 | Internal Monitoring Reports (CPCSR) |
| Discussion Papers | 48 | Alternative Alignment Study Reports |
|  | 49 | Cross Structure Plan (by PKG) |
|  | 50 | Alternative Study Reports |

Figure A.11   Reports Submission Schedule (Tentative) (1/4)

Figure A.11   Reports Submission Schedule (Tentative) (2/4)

Figure A.11   Reports Submission Schedule (Tentative) (3/4)

Figure A.11   Reports Submission Schedule (Tentative) (4/4)

Organization

Joint Venture

The Consultant Team is Joint Venture (JV) of Nippon Koei Co., Ltd. (NK), Nippon Engineering Co., Ltd. (NE), Chodai Co., Ltd. and Thai Engineering Consultant Co., Ltd. (TEC), and jointly and severally responsible for the Services among the JV firms.

Consultant Team

The Consultant Team divides into six (6) teams and four (4) supporting teams as described below.

Organization structure of the Consultant Team is shown in Figure A.12.

Management Team (MGT)

The Management Team is responsible for managing the Services, and all communications in the Services are exchanged through the team.  In the team, the Consultant organizes core team which consists of the representative of each team and secures the consistent communication among the teams.

Civil Team (CVT)

The Civil Team, consisting of Road Design Team, Bridge Design Team and Survey Group, is responsible for survey, planning and designing the civil structures.

In addition, LACT (Local Authority Coordination Team) is a virtual team for coordination with all level of local authorities. The Consultant understood that it required considerable time until reaching agreement with the local people for road structure design, especially cross structures.

O&M and ITS Team

The O&M and ITS team is responsible for preparing the O&M and ITS plan, basic design of the O&M buildings and ITS facilities, and detailed engineering design of the electrical facilities including the preparation of the technical specifications in the bidding documents.

Cost and Procurement Team

The Cost and Procurement Team is responsible for preparing the construction plan, engineer’s cost estimate, procurement plan, PQ documents and bidding documents, and assisting the tendering procedures.

Environmental Team

The Environmental Team consists of Social and Environmental Team (SAE) and Resettlement Team (RES).

SAE works with the relevant organizations for review and update of EIA and EMP.

RES works with the relevant organizations for review and update of RAP, conducting both the land valuation and Replacement Cost Survey (RCS) and monitoring the progress of the land acquisition.

Training Team

The Training Team is responsible for identifying the training needs with VEC, PMU85 and relevant organizations, and preparing and coordinating the training materials in cooperation with the engineers/specialists of the respective fields assign in other teams.

Supporting Group

The Supporting Group assists to the Key Professional Staff in daily works.  The Group consists of four (4) teams, and those are allocated three (3) teams in Danang Main Office and one (1) in Hanoi Sub-office (see A.2.5(1)(d)).

Figure A.12   Organization Structure of the Consultant Team

Home Office Support

NK, the prime consultant of JV firms has the home office support system and utilizes the technical, managerial and operational support including the review and verification of design in the Services.

Conceptual image of NK’s home office support system is shown in Figure A.13

Figure A.13   Conceptual Image of NK’s Home Office Support System

Office Arrangement

PMU85 organized the Project Site Management Department (PSMD) in his Danang office, and Danang CPC, Quang Nam and Quang Ngai PPCs and the Project site are also located in/near Danang city.  Therefore, the Consultant set up the Main Office in Danang city.

On the other hand, the Consultant outsources the D/D of all interchanges and bridges (excluding Ky Lam Bridge, 1st Priority Package) to the Vietnamese sub-consultants in Hanoi city (see A.2.5(2)(a)).  For supervising the outsourcing works, the Consultant set up the Sub-office in Hanoi city.

Office arrangement for Consultant team is shown in Table A.20.

Table A.20   Office Arrangement for Consultant Team

| No. | Office | Period | Address | Tel | Fax |
| --- | --- | --- | --- | --- | --- |
| 1 | Danang Main Office | 14 months (Dec. 2011 to Jan. 2013) | Unit 2, 11th floor, PVFC Danang Building, Lot A2.1, April 30 Street, Hai Chau District, Danang City, Vietnam | +84-(0)511-3797961 | +84-(0)511-3797962 |
| 2 | Hanoi Sub-office | 8 months (Apr. 2011 to Nov. 2012) | To be established |  |  |

Staffing

Staffing and Task Assignment

The Consultant established the staffing and task assignment in consistent with the work schedule and reporting plan described in A.2.6 and A.2.7.

It is noted that the Consultant outsources the D/D of all interchanges and bridges (excluding Ky Lam Bridge, 1st Priority Package) to the Vietnamese sub-consultants in Hanoi city to minimize the personnel inputs and shorten the design period.

Staffing and task assignment matrix for key professional staff are shown in Table A.21.

Staffing Schedule

The Consultant takes into account the staffing for the key professional staff as follows:

Arrange the staff who worked with VEC/PMU85 in the past studies;

Arrange the staff who worked together with other team members in the past;

Replacement of Professional Staff

Because of the delay of the commencement of the Services, the Consultant replaced several positions in both international professional staff and Vietnamese professional staff provided that substitute personnel possesses equivalent or higher qualification to the previous ones.

The Consultant submitted his proposal of the replacement with supporting documents by his letter No. DQEDD-PMU85-72-11 dated December 09, 2011, and PMU85 approve most of replacement by his replacement by his letter No. 1834/PMU85-PP2 dated December 21, 2011.

Updated Assignment Schedule

Time schedule for key international professional staff, key local professional staff and supporting staff are shown in Tables A.22 to A.24, respectively.

Terms of Payment

Table A.25 summarizes the terms of payment stipulated in Clause 6.4 of the Special Conditions of Contract (SCC).

Table A.25   Teams of Payment

| No. | Amount | Requirements |
| --- | --- | --- |
| 1 | - Twenty (20) percent of the Contract Price - 92,667,705 JPY - 1,234,820 USD | - Submission of a bank guarantee for the same amount. |
|  | - Ten (10) percent of the contract price - 46,333,853 JPY - 617,410 USD | - Submission of Inception Report (ICR). |
|  | - Twenty Five (25) percent of the contract price - 115,834,632 JPY - 1,543,525 USD | - Submission of Interim Report, Basic Design Report (BDR) and Prequalification Documents. |
|  | - Twenty (20) percent of the contract price - 92,667,705 JPY - 1,234,820USD | - Submission of Monthly Progress Report No.9 - Detailed Design Reports and Bidding Documents of the first 3 packages. |
|  | - Fifteen (15) percent of the contract price - 69,500,779 JPY - 929,115 USD | - Approval of Detailed Design Reports and Bidding Documents of the remaining packages - Draft Final Project Completion Report and satisfactory completion of the following works: - Review and update EIA, EMP, EMDP, RAP; - Construction method and schedule; - Preparation of implementation program; - Study and design of ITS and toll collection system; - Cost Estimate; - Expressway operation and maintenance. |
|  | - Ten (10) percent of the contract price - 46,333,853 JPY - 926,115 USD | - Approval of Final Project Completion Report. |

# Table A.21   Staffing and Task Assignment Matrix for Key Professional Staff

# Table A.22   Time Schedule for Key International Professional Staff

Table A.23   Time Schedule for Key Local Professional Staff (1/2)

Table A.24   Time Schedule for Key Local Professional Staff (2/2)

Table A.25   Time Schedule for Supporting Staff

Project Management

Basic Policy

The Consultant established the practical Project management system by utilizing PMBOK and its construction extension and customized it to the characteristics of the Services.

This project management system consists of 13 management areas, and the integration management which is one of the management areas consisting of the processes and activities needed to identify, define, combine, unify and coordinate the various processes and activities within the management process groups, is useful for understanding of overall project management system.

In consideration of the large-scale and complex assignment, the Consultant prioritizes the communication, quality and schedule managements in the Services. Especially, it is understood that the communication management is the most important management area, and the Consultant pay our best efforts and attention to this for successful implementation of the Project.

Work diagram of project management based on integration management is shown in Figure B.1, and describes the methodology of work items subsequently.

# Note:	Not all process interactions and data flow among the inputs, work items and reports are shown in the figure

Figure B.1   Work Diagram of Project Management based on Integration Management

General Phasing in Project Management

As shown in Figure B.1, the project management consists of five (5) phases, i.e. Initiating, Planning, Executing, Monitoring/Controlling, and Closing.

As of the end-December 2011, it is transition period between planning and executing. This Inception Report (ICR) is a product of the result of our project management planning.

Define the Services

The consulting contract defines the required Serviced to be performed by the Consultant.

Prepare the Primary Services Scope Statement

The Consultant reconfirmed the requirements stipulated in the contract and defines the Service in this Inception Report (ICR).  The ICR will function as baseline of the project management of the consulting services for all stakeholders to develop a common understanding of the Service scope.

Prepare the Services Management Plan

In the ICR, the Consultant explains how the Services is executed, monitored and controlled with addressing the communication, quality and schedule managements.

Main contents of three (3) major management areas are shown in Table B.1.

Table B.1   Main Contents of Three (3) Major Management Areas

| No. | Management Areas | Main Items | Contents |
| --- | --- | --- | --- |
| 1 | Communication | Communication requirements | - Among the relevant organizations and inside the consultant team |
|  |  | Communication item | - Including format, contents, level of detail, frequency, conveyor and receiver |
|  |  | Medium and technologies | - Meetings, letters, reports, workshops, etc. |
|  |  | Escalation process | - Identifying time frames and channel for escalation of issues |
|  |  | Method for updating | - Required conditions and process for updating |
|  |  | Common terminology | - Definitions for minimizing communication errors |
| 2 | Quality | Quality metrics | - Operational definition for quality control item, process and measurement |
|  |  | Quality checklists | - Structured tool for verifying QA/QC performance |
|  |  | Process improvement | - Process boundaries, configuration and metrics, and performance targets |
|  |  | Quality baseline | - Records for quality objectives |
|  |  | Method for updating | - Required conditions and process for updating |
| 3 | Schedule | Activity definition | - Activity list and attributes, and milestone list |
|  |  | Baseline schedule | - Baseline for progress monitoring and reporting |
|  |  | Monitoring and reporting | - Method for monitoring and reporting including format, contents and frequency |
|  |  | Method for updating | - Required conditions and process for updating |

Kick-off Meeting

Based on the Inception Report, the Consultant holds the kick-off meeting with not only the Project executing agency but also other relevant organizations for publicizing, gaining the consensus and smooth implementation of the Services.

In the past, there were two (2) kick-off meetings:

On 15 July 2011: A Kick-off meeting for commencement of the topographic survey was carried out with reference to the Work Plan of Topographic Survey.

On 25 November 2011: A Kick-off meeting for the commencement of the detailed design was carried out with reference to draft Inception Report.

This ICR is submitted at the end of December 2011, meeting the requirement of the milestone MS05 in Table A.17.

Direct and Manage the Services Execution

The Consultant directs and manages the Services execution in accordance with the process of executing the Services defined in the ICR in order to achieve the requirements stipulated in the contract.  Information on the status of the management activities being performed to accomplish the Services is routinely collected, and the Consultant compiles and submits the status as the monthly progress report.

The Consultant already established internal weekly meeting for information share and tackling difficulties in execution of the Services. This communication tool is the baseline of direct and management of the Service execution.

Monitor and Control the Services

The Consultant monitors and controls the processes used to initiate, plan, execute and close the Services to meet the performance objectives defined in this ICR.  Status of the activity is also compiled and submitted as the monthly progress report.

In order to help the monitoring and control, the Consultant will develop the work schedule by scheduling software, Microsoft Project, and the task(s) running on the critical path will be intensively monitored and necessary reallocation of resources, manpower and/or equipment, will be efficiently and effectively carried out.

Control Integrated Change

The Consultant controls integrated change which is the process of reviewing all change requests and approving and controlling changes to deliverables and organizational process assets.  The approved changes are reflected to update the ICR.  Status in the activity is also compiled and submitted as the monthly progress report.

It is understood that there would be considerable amount of changes required when the Consultant hold discussion with the local authorities. In this regards, the change management is the most critical management area, and the Consultant pay the most care to maintain good communication among the stakeholders.

Close the Services

The Consultant finalizes all of the activities across the process groups to formally close the Services.  It is understand that there will be two (2) closure in the Services:

Closure 1: Completion of the detailed engineering design.

Closure 2: Completion of the procurement assistance.

Administrative closing procedure is prepared timely when the above two (2) services are near to the completion.  All of documents of the management activities are compiled and submitted as the Project completion report.

Previous Studies Review and Establishing Detailed Engineering Design Framework

Review Previous Studies

TOR Requirements

Requirements in the TOR is summarized as shown in Table C.1

Table C.1   TOR Requirements for Previous Studies Review

| No. | TOR Requirements | Check |
| --- | --- | --- |
| 1 | - The Consultant shall review the previous studies to acquaint themselves with the evolution of the Project and its current features, and to identify matters that may materially affect the work of the current contract. - Key issues will be identified for discussion and agreement with PMU85. - The review shall cover, among others, the following subjects: |  |
| 2 | - Review of horizontal and vertical alignment and proposed structures. |  |
|  | - Review site-specific social and environmental impacts identified in the Environmental Impact Assessment (EIA) prepared by PMU85 and the mitigation measures proposed in the associated Environmental Management Plan (EMP). |  |
|  | - Review construction phasing and management of traffic during construction. |  |
|  | - Review toll operation and control facilities, operation and maintenance facilities and services, service areas, parking areas, etc. |  |

Source:	TOR 3.2 (1)

Methodology

The Consultant reviews the previous studies, especially the F/S report and safeguard documents, to take cognizance of the current arrangements of the Project and extracts the key issues which materially affect to the Services for discussing and obtaining the agreement with VEC/PMU85 and relevant organizations.

Work diagram of previous studies review is shown in Figure C.1, and main contents of previous studies review are shown in Table C.2, respectively.

Figure C.1   Work Diagram of Previous Studies Review

Table C.2   Main Contents of Previous Studies Review

| No. | Category | Main Contents |
| --- | --- | --- |
| 1 | Civil | - Topography, geology and hydrology of the Project area |
|  |  | - Technical standards1), and design criteria and conditions |
|  |  | - Route alignment, geometric design and typical cross sections |
|  |  | - Preliminary design of civil structures |
|  |  | - Construction planning and preliminary Project cost estimates |
|  |  | - Environmental impacts and its mitigation measures and RAP |
| 2 | O&M/ITS | - Existing legal and administrative arrangements |
|  |  | - O&M/ITS standards and plan |
|  |  | - O&M unit establishment plan |
|  |  | - Tariff rate and toll collection system |
|  |  | - Electrical/O&M/ITS facilities and equipment plan |

Note:	1)	Applicable technical standards for the Project were approved by MOT in Decision No. 362/QD-BGTVT dated February 20, 2009

Work Progress to Date

As of the end-December 2011, the following progress is performed.

- Horizontal alignment: Submitted technical report for finalization of expressway alignment by our letter No. DQEDD-PMU85-85-11 dated December 21, 2011.

- Vertical alignment: Finished preliminary alignment considering the all crossing structures.

- Structures (1), Bridges: In progress

- Structure (2), Road Structures: Finished preliminary planning.

- EIA and EMP: In progress.

- Construction Phasing: In progress

- Traffic Management during Construction: Not started.

- Toll Operation and Control Facilities: Not started.

- Operation and Maintenance facilities and Services: Not started.

- Service Areas and Packing Areas: Not started.

Establish Detailed Engineering Design Framework

TOR Requirements

Requirements in the TOR is summarized as shown in Table C.3

Table C.3   TOR Requirements for Establish Detailed Engineering Design Framework

| No. | TOR Requirements | Check |
| --- | --- | --- |
| 1 | - Establish design criteria and design standards to be applied for the Project. |  |
|  | - Recommend and agree with PMU85 the format and content for the Bills of Quantities, cost estimates and prequalification and bidding documents. |  |
|  | - Recommend and agree with PMU85/VEC the time schedule for preparation of the detailed design, the Bills of Quantities, cost estimates, prequalification documents and bidding documents to allow the tendering of works and construction for each contract package to commence immediately after the completion of necessary design and documentation work and the gaining of necessary approvals. |  |

Source:	TOR 3.2 (2)

Methodology

The Consultant establishes the detailed engineering design framework which consists of the primary matters for execution of the Services based on C.1 and obtains the approval from VEC/PMU85 and relevant organizations.

Work diagram of detailed engineering framework is shown in Figure C.2, and main contents of the detailed engineering design framework are shown in Table C.4, respectively.

Figure C.2   Work Diagram of Detailed Engineering Design Framework

Table C.2   Main Contents of Detailed Engineering Design Framework

| No. | Item | Main Contents |
| --- | --- | --- |
| 1 | Detailed Engineering Design Framework | - Updated applicable technical standards for the Project |
|  |  | - Format and content of the B/Q items, cost estimate and procurement documents |
|  |  | - Updated work schedule of the Services |

Work Progress to Date

As of the end-December 2011, the following progress is performed.

- Design Standards: Updated list of technical standards was submitted by our letter No. DQEDD-PMU85-79-11 dated December 16, 2011.

- Design Criteria: In progress.

- Format and Contents of BOQ and Cost Estimate: In progress

- Format and Contents of PQ Documents: A draft PQ Documents for PKG3A was submitted by our letter No. DQEDD-PMU85-53-11 dated November 18, 2011.

- Format and Contents of Bidding Documents: Not started.

- Recommendation of Time Schedule of Detailed Design: In progress.

Detailed Engineering Design and Procurement Planning

Contract Packaging

Propose Contract Packaging

TOR Requirements

Requirements in the TOR are summarized as shown in Table D.1

Table D.1   TOR Requirements for Contract Packaging

| No. | TOR Requirements | Check |
| --- | --- | --- |
| 1 | - The Consultant shall identify a recommended packaging for the project and get agreement with the Client before commencing detailed design. Packaging shall satisfy the following conditions: |  |
| 2 | - Individual packages should be confined to a single province. |  |
|  | - Individual package shall be financed by only a single financier. |  |
|  | - The value of a package should generally be from about 70 million to 100 million USD, i.e. neither too big nor too small. |  |
|  | - During preparation of the detailed design, the Consultant shall study, initiate the solutions and design a contract package with reasonable scopes of works beforehand so that its construction can be commenced in September, 2012. |  |

Source:	TOR 3.3.2

Methodology

Work diagram of contract packaging is shown in Figure D.1,

Figure D.1   Work Diagram of Contract Packaging

Work Progress to Date

As described in A.1.9, the Consultant proposed the contract packaging plan as shown in Table A.11 and waiting further discussion.

In case further modification is requested by VEC/PMU85, the Consultant studies it taking into account the impact to the D/D works and overall project implementation, and update it timely.

Surveys and Investigations

Data Collection

TOR Requirements

Requirements in the TOR are summarized as shown in Table D.2.

Table D.2   TOR Requirements for Data Collection

| No. | Items | Main Contents |
| --- | --- | --- |
| 1 | General cost estimate | - Production costs related to local transportation activities - depreciation regulations related to traffic vehicles - haulage tables for transportation services - charges for travel, bridges and roads, and insurance - costs for traffic accidents - inflation and exchange rate in the previous years - local unit price for calculation of general cost estimate - consult unit prices of projects under implementation in the region - investigate sources of materials and energies for construction - cooperate with local governments to identify disposal areas for soil and waste materials ( including liquid waste) |
| 2 | Survey for construction material transportation |  |
| 3 | Investigate and collect planning data related to the project and work with relevant authorities | - Collect planning maps of highways, railways, waterways and maritime - plan of industrial and urban zones along the route - plan of systems of hydraulic works , irrigation, canals, dykes, and pumping stations, etc - plan of underground works and system of underground and overhead lines - Plan of water supply and drainage system - plan of electricity supply and lighting - plan of communication system and other relevant plans along the route, etc (the plans must be granted with official approval of relevant authorities) |
| 4 | Collect project documents and design document of the relevant projects |  |
| 5 | Work and agree in writing with relevant authorities of Danang city, Quang Nam and Quang Ngai provinces, 5th military zone under Ministry of Defense, EVN, VNPT, PMU of industrial zones and other relevant managing agencies about the following contents | - Alignments - alternative design of interchange - scale and location of toll plazas, control center, service stations - elevation of detailed plans of urban zones and industrial zones - location, span or width, and elevation of culvert and frontage road - navigational clearance, railway clearance - documents related to hydraulic works, irrigation, water sources and sewage system for urban zones, clearance of large canals and dykes - areas within military structures, military barracks - and the other relevant documents, etc |

Source:	TOR 3.3.2 (1)

Methodology

The Consultant collects the relevant data and documents for basis of execution of the Services.

Work diagram of relevant data and documents is shown in Figure D.2, and main contents of relevant data and documents should refer to Table D.2 above.

Figure D.2   Work Diagram of Relevant Data and Documents

Work Progress to Date

As of the end-December 2011, the following progress is performed.

- Data collection is not progressed well.

- Data collection should be started immediately with support by PMU85 and local authorities.

Conduct Topographic Survey

TOR Requirements

Please refer to Appendix 1: Terms of Reference (TOR).

Methodology

The Consultant conducts the topographic and ROW surveys for preparation of engineering design, quantity take-off and CPCSR.  In consideration of the huge survey volumes, the Consultant outsources the site survey works to Vietnamese sub-consultant(s) and supervises their performance by the Survey Engineer.  The selection of sub-consultant(s) and work plan including survey specifications were approved by VEC/PMU85.

In consideration of the rainy season, short-period and work procedure of basic design, the Consultant conducted the site survey works in accordance with the following priorities:

1st Priority	:	Control point survey and leveling network (whole section)

2nd Priority	:	Planimetric survey (thruway, sections for survey centerline study)

3rd Priority	:	Remaining surveys for basic design

Non-priority	:	Surveys for detailed engineering design

Work diagram of topographic survey is shown in Figure D.3, and work quantities for topographic survey are shown in Table D.3, respectively

Work Progress to Date

As of the end-December 2011, the following progress is performed.

- The Consultant submitted the revised work plan for the control point survey by our letter No. DQEDD-VEC-05-11 dated July 20, 2011. VEC approved the work plan by his letter No. 1391/VEC-KTCNMT dated August 3, 2011.

- The Consultant submitted the revised work plan for the topographic survey by our letter DQEDD-PMU85-48-11 dated November 14, 2011.

- All field works except the survey for rampways of the interchanges are completed, including some additional survey areas.

- Digital files of plan, profile and cross-section of the throughway were already handed over to the design team.

Reporting and drawings are being finalized and to be completed in January as the final products of the survey works..

Figure D.3   Work Diagram of Topographic Survey

Table D.3   Work Quantities for Topographic Survey

Source:	Estimated quantities by the Consultant (as of end of November, 2011)

Conduct Hydrological Survey and Analysis

TOR Requirements

Please refer to Appendix 1: Terms of Reference (TOR).

Methodology

“National Strategy for Natural Disasters Prevention, Response and Mitigation to 2020” and “Provincial Integrated Disaster Risk Management Plan to 2020” have stressed for building flood resistant roads and widening the openings of bridges and culverts along the roads and railways to facilitate drainage.  Therefore, width of bridges, viaducts and culverts in the expressway is required to design with enough openings that flood conditions in river and on floodplain is not alter from the existing situations.

The expressway passes through floodplains of large rivers; therefore, some sections have severe problems.  The Consultant conducts hydrological and inundation analyses performed as follows:

Identify the sections of the expressway where inundation occurs

Determine design high water level in river and on floodplain along the expressway

Check width of bridges and culverts in F/S are enough or not

Optimize the length of bridges and culverts for cost-effectiveness

Work diagram of hydrological survey and analysis is shown in Figure D.4, and describes the methodology of work items subsequently.

Figure D.4   Work Diagram of Hydrological Survey and Analysis

Site Investigation

The Consultant conducts site investigations to acquire the river locations, channels and crossing points with the expressway and updates the specifications for hydrological survey including the river profile and cross-section survey points in the topographic survey (D.2.2).

Hydrological Survey

The Consultant outsources the hydrological survey works to Vietnamese sub-consultant(s) and supervises their performance by the Senior Hydrologist.  The selection of sub-consultant(s) and work plan including survey specifications shall be approved by VEC/PMU85.

Work quantities for hydrological survey are shown in Table D.4.

Table D.4   Work Quantities for Hydrological Survey

| No. | Items | Locations and Quantities |
| --- | --- | --- |
| 1 | Historical Water Level | A group of highest one, frequent one, average one and lowest one along the thruway centerline at 1.0 km interval |
|  |  | where existing ground level is less than 25 m from mean sea level and at all planned positions of bridge and culvert. |
| 2 | Water Level | Thrice a day in November and December 2011 at 6:00, 12:00 and 18:00 hours at three (3) positions (one (1) position |
|  |  | at river center, two (2) positions near banks) in four (4) major river bridges. |
| 3 | Water Flow Velocity | Once during high flood in November and December 2011 at three (3) positions (one (1) position at river center, two |
|  |  | (2) positions near banks) in four (4) major river bridges. |

Source:	Estimated quantities by the Consultant (based on F/S)

Data Collection

The Consultant collects hydro-meteorological data which is necessary for hydrological analysis.  Those data can be obtained from Hydro-meteorological Data Center in Hanoi.

Hydro-meteorological data collection plan is shown in Table D.5.

Table D.5   Hydro-meteorological Data Collection Plan

| No. | Items | Stations and Periods |
| --- | --- | --- |
| 1 | Annual Maximum Daily Rainfall | Danang (1964 - 2010), Cau Lau (1977 - 2010), Tam Ky (1977 - 2010), Tra My (1979 - 2010), |
|  |  | Tra Bong (1976 - 2010), Quang Ngai (1964 - 2010), Gia Vuc (1981 - 2010) |
| 2 | Annual Maximum Rainfall | Danang (amounts of 5, 15, 30, 45 and 60 minutes duration during 1986 - 2010 or rainfall intensity duration |
|  |  | frequency (IDF) curve with equation and constants) |
| 3 | Meteorological Data | Danang (mean monthly air temperature, wind speed, evaporation and relative humidity during 2001 - 2010) |
| 4 | Annual Maximum River Discharge | Nong Son (Thu Bon River, 1977 - 2010), Thanh My (Vu Gia River, 1977 - 2010), |
|  | (with Catchment Areas) | Son Giang (Tra Khuc River, 1979 - 2010) |
| 5 | Annual Maximum and Minimum | Giao Thuy (Thu Bon River, 1976 - 2010), Ai Nghia (Vu Gia River, 1976 - 2010), |
|  | River Water Levels | Son Giang and Tra Khuc (Tra Khuc River, 1977 - 2010), Cam Le (Other River, 1976 - 2010) |
| 6 | Hourly Water Levels and Rainfalls | Hourly Water Level (7 days): Giao Thuy and Cau Lau (Thu Bong River), Ai Nghia (Vu Gia River), |
|  | (one (1) week, the highest in 2009) | Son Giang and Tra Khuc (Tra Khuc River), Cam Le (Other River) |
|  |  | Hourly Rainfall 7 days): Danang, Tra My, Tam Ky and Quang Ngai |

Source:	Estimated quantities by the Consultant (based on F/S)

Rainfall Analysis

The Consultant conducts frequency analysis of annual maximum daily rainfall of stations in the Project area performed to determine 1 % (linking road: 4 %), 5 % and 50 % exceeding probability rainfalls at the stations.  Most commonly used log normal distribution function is employed for the frequency analysis.  As for the coverage of river basin area by a particular rainfall station, it is determined by using Thiessen’s Polygon Method.  Basin rainfalls of 1 % (linking road: 4 %), 5 % and 50 % exceeding probability levels are computed based on the point rainfalls, and hourly distribution pattern of basin rainfall is designed for runoff analysis.

Runoff Analysis

The Consultant conducts runoff analysis by using empirical methods (specific discharge method or rational method) or lumped sub-basin model.  The information such as catchment area, rainfall amount and intensities, and sub-basin parameters is collected for runoff analysis.  The lumped sub-basin model is calibrated by observed flood levels in river and on floodplain during high flood in 2009.  The river flow of 1 % (linking road: 4 %), 5 % and 50 % exceeding probabilities is estimated for determining design high water levels in river and on floodplain.

River Flow Capacity Estimation

The Consultant checks river flow capacity by employing river flow simulation model.  In case of 1 % (linking road: 4 %) exceeding probability flow is within the flow capacity of river, the design high water level in the river is estimated by unsteady river flow simulation by using HEC-RAS.  In case of 1 % (linking road: 4 %) exceeding probability flow overflows from river bank, inundation analysis is adopted for determining the design high water level in river and on floodplain.

Work Progress to Date

As of the end-December 2011, the following progress is performed.

- The Consultant submitted the revised work plan by our letter No. DQEDD-PMU85-50-11 dated November 18, 2011.

- Regarding the out-sourced hydrological survey:

  - Historical Water Level Survey: Field work completed.

  - Water Level Survey: Complete the field survey on December 29, 2011.

  - Water Flow Velocity Survey: Field work completed.

- Data collection is completed.

- Rainfall analysis is almost completed.

- Runoff analysis is 50% completed.

- River flow capacity analysis is just started.

Inundation Analysis

TOR Requirements

This scope is proposed by the Consultant as additional scope, not included in the Appendix 1: Terms of Reference (TOR).

Methodology

The Consultant conducts inundation analysis with input of 1 % (linking road section: 4 %) and 5 % exceeding probabilities basin rainfalls.  The scenarios of inundation analysis are as follows:

1 % (linking road: 4 %) exceeding probability basin rainfall and existing physical conditions of basin

1 % (linking road: 4 %) and 5 % exceeding probability basin rainfall, existing physical conditions of basin, and planned designs (dimensions) and arrangements of thruway bridge, viaduct and culvert

Other scenarios as needed to determine the design high water level in river and on floodplain

The Consultant utilizes MIKE-11 and ArcGIS for inundation analysis and flood maps preparations.  The data used in flood management model developed by JICA’s Disaster Protection Study in Quang Nam and WB’s Flood Risk Management Plan Study in Quang Ngai.

Image of MIKE-11 and ArcGIS is shown in Figure D.5.

| MIKE-11 (Inundation Analysis) | ArcGIS (Mapping) |
| --- | --- |

Figure D.5   Image of MIKE-11 and ArcGIS

Work Progress to Date

As of the end-December 2011, the following progress is performed.

- The Consultant submitted the first work plan report by our lette No. DQEDD-PMU85-74-11 dated December 10, 2011.

- Two working teams are mobilized, one for Danang-Quang Nam section, the other is for Quang Ngai section.

- Both analyses will be completed in January 2012.

Figure D.6   Image of Inundation Analysis

Conduct Geotechnical and Geological Investigations

TOR Requirements

Please refer to Appendix 1: Terms of Reference (TOR).

Methodology

The Consultant conducts the geotechnical and geological investigations for engineering design.  In consideration of huge investigation volumes, the Consultant outsources the site investigation works to Vietnamese sub-consultant(s) and supervises their performance by the Soil/Geotechnical Engineer 2 and Geological Engineer (Tunnel).  The selection of sub-consultant(s) and work plan including investigation specifications shall be approved by VEC/PMU85.

The Consultant conducts the site investigation works in accordance with the following priorities:

1st Priority Investigations	:	PKG3a (1st Priority Package)

2nd Priority Investigations	:	PKG1 and PKGA4 (2nd Priority Packages)

3rd Priority Investigations	:	Other Civil Work Packages (Non-priority Packages)

Non-priority Investigations	:	PKG13 (O&M Package)

The structural plan including bridge plan may be modified from F/S in accordance with the results of several surveys and analyses, especially hydrological and inundation analyses (D.2.3).  Therefore, the commencement of geotechnical and geological investigations shall be taken into account the maturity of the structure plan for avoiding re-investigations.

Work diagram of geotechnical and geological investigations is shown in Figure D.7, and tentative work quantities for geotechnical and geological investigations are shown in Table D.6, respectively.

Figure D.7   Work Diagram of Geotechnical and Geological Investigations

Work Progress to Date

As of the end-December 2011, this work does not start yet.

Table D.6   Tentative Work Quantities for Geotechnical and Geological Investigations

# Source:	Estimated quantities by the Consultant (based on F/S-2010)

Conduct Material Source Survey

TOR Requirements

Requirements in the TOR are summarized as shown in Table D.7.

Table D.7   TOR Requirements for Material Source Survey

| No. | TOR Requirements | Check |
| --- | --- | --- |
| 1 | - This task must be ensured to collect all data of locations of material sources which meet the requirements of the Project, are practical and feasible during construction. - Back filling materials (borrow pits) and sand for soft ground treatment: |  |
| 2 | - identify exploitable soil and sand quarries; - work with local governments to gain agreement in writing ad then, map out them on plan at scale of 1/50,000. - Collect data related to capacity and quality of each quarry; - take testing sample to identify necessary parameters of back filling materials and others for soft ground treatment. |  |
| 3 | - Survey and evaluation of general situation, capacity and transportation length of the routes for exploitation and transportation to the construction site. |  |
| 4 | - For borrow pits and quarry sites which are exploited or being exploited, collect data related to their capacity and quality, exploitability, and transporting conditions to the construction site. - For new borrow pits and quarry sites, carry out procedures for survey and testing necessary characteristics of each material. |  |

Source:	TOR 3.3.2 (2).(iv)

Methodology

The Consultant conducts material source survey by outsourcing to Vietnamese sub-consultant(s) at locations identified with the local PCs to confirm quality and volume of borrow, sand and rock materials for detailed engineering design and construction planning.  The selection of sub-consultant(s) and work plan including survey specifications shall be approved by VEC/PMU85.

Work diagram of material source survey is shown in Figure D.8, and tentative work quantities for material source survey are shown in Table D.8, respectively.

Figure D.8   Work Diagram of Material Source Survey

Table D.8   Tentative Work Quantities for Material Source Survey

| No. | Item | Unit | Quantities | Remark |
| --- | --- | --- | --- | --- |
| A | Sampling and Laboratory Test |  |  |  |
| 1 | Borrow Material |  |  | 1 location/20 km*140 km = 8 locations |
| 1.1 | Undisturbed Sample Test | nos. | 24 | 3 samples/location*8 locations |
| 1.2 | Standard Compaction Test | nos. | 24 | 3 samples/location*8 locations |
| 1.3 | CBR Test | nos. | 24 | 3 samples/location*8 locations |
| 2 | Rock |  |  |  |
| 2.1 | Rock Sample Test | nos. | 15 | 3 samples/location*5 locations |
| 3 | Fine Sand |  |  |  |
| 3.1 | Sand Sample Test | nos. | 24 | 3 samples/location*8 locations |
| 3.2 | Standard Compaction Test | nos. | 24 | 3 samples/location*8 locations |
| 4 | Coarse Sand |  |  |  |
| 4.1 | Sand Sample Test | nos. | 6 | 3 samples/location*2 locations |

Work Progress to Date

As of the end-December 2011, this work does not start yet.

Conduct Relevant Facilities Survey

TOR Requirements

Requirements in the TOR are summarized as shown in Table D.9.

Table D.9   TOR Requirements for Relevant Facility Survey

| No. | TOR Requirements | Check |
| --- | --- | --- |
| 1 | - Survey current situations of traffic works in the area to evaluate usage capacity and level that shall be upgraded to construct service roads for construction of the expressway. |  |
| 2 | - Survey old bridges and culverts on the cross lines: - Identify location, survey profile, main cross-section, and elevation of components of existing works; |  |
| 3 | - review construction materials; - evaluate loading capacity of the works; - evaluate fault degrees, suitability and utilizing capacity. |  |
| 4 | - Survey current situations of irrigation works within study area. |  |
| 5 | - Survey underground structures, public works: - optical cables, underground cables, pipeline, oil and petrol pipeline, etc. |  |
| 6 | - Survey existing power supply in the route, and request for supplying capacity and starting points. - For transformer stations, request was made to identify their location, scale, capacity, specifications, and works which is supplied with power, etc. - Survey additional locations of transformer stations; - identify clearly locations of the station by coordinate and full description in maps including topographic, geologic and ground object data, and agreeing with the local governments in writing on these issues, etc. |  |
| 7 | - Survey cultural buildings, temples, pagodas, and relevant legal religious buildings. |  |

Source:	TOR 3.3.2 (2).(v)

Methodology

The Consultant conducts the relevant facilities survey in the Project area to identify the obstacles and cultural properties for extracting the design controls, and evaluates the level of capacity of existing roads and structures for construction planning.

Work diagram of relevant facilities survey is shown in Figure D.9, and main contents of relevant facilities survey is shown in Table D.10, respectively.

Figure D.9   Work Diagram of Relevant Facilities Survey

Table D.10   Main Contents of Relevant Facilities Survey

| No. | Items | Contents |
| --- | --- | --- |
| 1 | Design Controls | - Identify the location, capacity and specification of the obstacles in the Project area |
|  |  | - Identify the cultural buildings, temples, pagodas and relevant legal religious buildings |
| 2 | Construction Planning | - Evaluate current traffic conditions of the existing roads in the Project area |
|  |  | - Identify and evaluate loading capacity of bridges/culverts on potential construction roads |

Work Progress to Date

As of the end-December 2011, this work does not start yet.

Conduct Additional Traffic Surveys

TOR Requirements

Requirements in the TOR are summarized as shown in Table D.11.

Table D.11   TOR Requirements for Additional Traffic Surveys

| No. | TOR Requirements | Check |
| --- | --- | --- |
| 1 | - The Consultant shall review available traffic data on the existing road and conduct additional surveys as necessary to: |  |
| 2 | - Collect data needed for the detailed design of foundations, pavements, interchanges, and toll stations, etc; and |  |
| 3 | - Collect base line data that can be used for monitoring performance of the completed Project, where this data shall include the quantity and composition of traffic using the current national highway, total travel time and the variability of the travel time for, separately, cars and trucks, and the number and type of traffic accidents per annum along the current corridor. |  |
| 4 | - This data will be collected separately for at least the segments Danang to Tam Ky and Tam Ky to Quang Ngai. |  |

Source:	TOR 3.3.2 (2).(vi)

Methodology

The Consultant reviews the traffic demand forecasting in F/S to establish the requirements for the engineering design from the traffic aspects.  In addition, the Consultant reviews the traffic survey data above and other relevant studies around the Project area to collect the available baseline data for the performance indicators in the Project framework (A.1.4).

In case of the appropriate data is not identified, the Consultant conducts the additional traffic survey by outsourcing to the Vietnamese sub-consultant(s).  The selection of sub-consultant(s) and work plan including survey specifications shall be approved by VEC/PMU85.

Work diagram of traffic forecasting review and baseline surveys is shown in Figure D.10, and tentative work quantities for baseline survey is shown in Table D.12, respectively.

Figure D.10   Work Diagram of Traffic Forecasting Review and Baseline Surveys

Table D.12   Tentative Work Quantities for Baseline Survey

| No. | Surveys | Contents |  |
| --- | --- | --- | --- |
| 1 | Traffic Count | Day and Time | 1 weekday and 1 holiday, 24 hours in each day |
|  |  | Location | On the existing NH1A (2 segments Danang to Tam Ky and Tam Ky to Quang Ngai) |
|  |  | Survey Item | Traffic volume and composition on the both directions |
| 2 | Travel Time | Day and Time | 1 weekday and 1 holiday, peak traffic hour identified in the traffic count survey |
|  |  | Location | On the existing NH1A (2 segments Danang to Tam Ky and Tam Ky to Quang Ngai) |
|  |  | Survey Item | Travel time by each vehicle classification on the both directions |
| 3 | Traffic Accident | Period | Annual (the last 3 years) |
|  |  | Location | On the existing NH1A (2 segments Danang to Tam Ky and Tam Ky to Quang Ngai) |
|  |  | Survey Item | Nos. and type of traffic accident |

Work Progress to Date

As of the end-December 2011, the following progress is performed.

- Vietnamese Transport Economist was mobilized on December 12, 2011.

- Started the preparation of the work plan.

Conduct Independent Land Valuation Survey

TOR Requirements

Requirements in the TOR are summarized as shown in Table D.13.

Table D.13   TOR Requirements for Land Valuation Survey

| No. | TOR Requirements | Check |
| --- | --- | --- |
| 1 | - As part of the work on updating the Resettlement Action Plan (RAP) the consultant will engage as a sub-consultant a qualified Land Valuation Consultant (LVC). |  |
| 2 | - The LVC must be licensed by the Ministry of Finance to undertake land valuation in Viet Nam and be independent of all project stakeholders. |  |
| 3 | - As part of the updating work the LVC will undertake a survey to establish current market values for all types of land, by location and use, sufficient to confirm the budget under the updated RAP. |  |

Source:	TOR 3.3.2 (2).(vii)

Methodology

The Consultant conducts the independent land valuation survey by outsourcing to the qualified land valuation consultant who is licensed by MOF and independent of all Project stakeholders to confirm the current market prices of land by location and use in each commune in the Project area.  The selection of sub-consultant and work plan including survey specifications shall be approved by VEC/PMU85.

Work diagram of independent land valuation survey is shown in Figure D.11, and potential land valuation consultants in the Project area is shown in Table D.14, respectively.

Figure D.11   Work Diagram of Independent Land Valuation Survey

Table D.14   Potential Land Valuation Consultants in the Project Area

| No. | City/Province | Name of Consultant | Tel | Fax | e-mail |
| --- | --- | --- | --- | --- | --- |
| 1 | Danang | Danang Valuation & Financial Services Limited Company | 0511-3887628 | 0511-3887532 | divc@vnn.vn |
| 2 | Quang Nam | Quang Nam Financial & Price Consultancy Joint-stock Company | 0510-3811657 | --- | mylangbd@yahoo.com.vn |
| 3 | Quang Ngai | Central Information & Valuation of Cost Joint-stock Company | 055-3818348 | --- | --- |

Work Progress to Date

As of the end-December 2011, the following progress is performed.

- During October 2011, several candidate companies visited the Consultant office.

- Since then, evaluation of those candidates has been processed.

- Finally, the Consultant selected Joint Venture of Danang – Quang Nam – Quang Ngai Independent Price Evaluation Company, and informed the selection result to PMU85 by our letter No. DQEDD-PMU85-92-11 dated December 23, 2011.

Conduct Environmental and Social Surveys

TOR Requirements

Undertake surveys as necessary to update the EIA and EMP.

Methodology

The Consultant conducts the site surveys for updating the existing EIA and EMP to confirm the environmental and social conditions in the Project area in accordance with the JICA Guidelines for Environmental and Social Considerations and WB safeguard policies and, if necessary.

Work diagram of environmental and social surveys is shown in Figure D.12.

Figure D.12   Work Diagram of Environmental and Social Surveys

Work Progress to Date

As of the end-December 2011, the following progress is performed.

- Collected Decision of Ministry of natural Resources and Environment (MONRE) issued recently.

- Review EIA report.

- Study the expressway corridor for identification of the location where noise sensitive receptors are exists.

Civil Engineering Design

TOR Requirements

Please refer to Appendix 1: Terms of Reference (TOR).

Methodology

The Consultant divides the civil engineering design into the basic design (B/D) and detailed engineering design (D/D) stages to proceed the design works efficiently.  The numbers of structure are huge; therefore, the Consultant prepares and utilizes the standard designs to assure the design quality.

Work items and demarcation between B/D and D/D stages is shown in Table D.10.

Prepare Basic Design of Civil Structures

In the B/D stage, the Consultant establishes the fundamental conditions and obtains the approval from VEC/PMU85 and other relevant organizations to avoid the re-design in the D/D stage.

Main contents of B/D stage are summarized below:

Establish design criteria and conditions;

Define typical cross sections;

Define thruway geometric design;

Prepare general view of all thruway bridges;

Prepare thruway culverts, tunnel and interchanges plan.

Work diagram of basic design of civil structures is shown in Figure D.13.

Prepare Detailed Design of Civil Structures

In the D/D stage, the Consultant conducts the remaining plan and design works in accordance with the B/D and outsources all of bridges (excluding Ky Lam Bridge, 1st Priority Package) and interchanges design to Vietnamese sub-consultants who have abundant experiences and resources for minimize the personnel inputs and shorten the design period.

Work diagram of detailed design of civil structures is shown in Figure D.14, and main contents of road safety audit are shown in Table D.15, respectively.

Table D.15   Main Contents of the Road Safety Audit (PIARC Road Safety Manual 2004)

| No. | Classification | Category |  |  | Indicators |
| --- | --- | --- | --- | --- | --- |
| 1 | All Roads | Horizontal alignment |  |  | Curve radius, speed differentials, surface conditions, overturning, super-elevation, |
|  |  |  |  |  | road width, shoulders, roadside sight distance/forgiving road, passing in curve |
|  |  |  |  |  | warning signs and devices, combination of features |
| 2 |  | Vertical | Grade | Downhill | Generalities (stopping distance, brake temperature, compound grades, etc.), |
|  |  | alignment |  |  | location of road sign, drainage capacity and structure, brake check area, arrester beds |
|  |  |  |  | Uphill | Generalities (deceleration rate, speed reduction, etc.), climbing lanes, drainages |
|  |  |  | Curves |  | Generalities (sight distance, etc.), passing (pavement marking), drainages |
| 3 |  | Human factors (driver) |  |  | Strain, workload, perception, lane tracking, choice of speed, orientation, anticipation |
| 4 | Non-access | Sight distance | At grade intersections |  | Stopping, maneuvering, passing sight and decision sight distances, sight triangles |
|  | Control Roads |  | Two-way, two lane roads |  | Stopping, decision, passing and meeting sight distances |
| 5 |  | At grade intersections |  |  | Generalities (intersection type, access control, sight distance, |
|  |  |  |  |  | distance between intersections, conflict points at intersections, etc.) |

Note:	Sight distance and at grade intersection are astride the plural categories in the table

Work Progress to Date

As of the end-December 2011, the following progress is performed.

- The basic design work has been progressed well and the following reports were submitted for the discussion:

- <List of report submitted>

- The centerline of the alignment is finalized on December 19, 2011.

- Based on this alignment, road plan drawings are being prepared for “commune meeting” with indication of all cross structures.

- Updated list of bridges is shown in Appendix 2.

- Updated list of culverts is shown in Appendix 3.

- Updated list of communes along the expressway is shown in Appendix 4. It is identified that there are 58 borders of communes passing through 39 communies.

# Table D.15   Work Items and Demarcation between B/D and D/D Stages

Legend:	●(B/D), ●(D/D)

Code:	RD(Road), TN(Tunnel), BR(Bridge), RB(River Bridge), LRB(Large River Bridge), ORB(Other River Bridge), MRB(Major River Bridge), CB(Culvert Box), WT(Waterway), CP(Culvert Pipe), BL(Building), IRB(Interchange Rampway Bridge), FO(Flyover)

Note:	1) LRB(L>100 m), ORB(L<100 m), Other LRB (100 m<L<300 m)

2) 4 Bridges (Ky Lam Bridge (LRB08, KM017+662), Chiem Son Bridge (LRB09, KM020+185), Tra Bong Bridge (LRB19, KM109+320), Tra Khuc Bridge (LRB20, KM125+700))

3) Stream Bridge (SB), Canal Bridge (CB), Viaduct (VD), Overpass (OP)

4) Toll Barrier (TB) and Toll Plaza Office (TPO), Service Area (SA), Parking Area (PA), Traffic Management Center (TMC), Expressway Operation Office (EOO)

5) Toll Gate (TG) and Toll Plaza Office (TPO)

6) Civil Works Only

7) Plan and Profile and General View (Bridge)

Note:	1) Revision of thruway geometric design (vertical) and culvert and bridge plan in accordance with hydrological survey and analysis (D.2.3)

2) Thruway plan and profile and general view (thruway bridges)

Figure D.13   Work Diagram of Basic Design of Civil Structures

# Note:	Outsourcing work items are (20) structural design (bridge), (21) bridge temporary facility plan, (11) geometric design (interchange), (46) design drawings (D/D) (bridge and interchange only), (47) quantity taking-off (bridge and interchange only)

Figure D.14   Work Diagram of Detailed Design of Civil Structures

O&M Plan and Design

TOR Requirements

Please refer to Appendix 1: Terms of Reference (TOR).

Methodology

Prepare Institutional and Administrative Arrangement Plan

The Consultant confirms the existing legal and regulatory framework for expressway O&M in Vietnam and studies the necessary institutional and administrative arrangement plan for O&M of the expressway.  Based on the plan, the Consultant holds workshops with the relevant organizations and gains the consensus for work sequence, schedule and organizations in-charge of the arrangement works.

Work diagram of institutional and administrative arrangement plan is shown in Figure D.15, and main items for institutional and administrative arrangement plan are shown in Table D.16, respectively.

Figure D.15   Work Diagram of Institutional and Administrative Arrangement Plan

Table D.16   Main Items for Institutional and Administrative Arrangement Plan

| No. | Items | Contents |
| --- | --- | --- |
| 1 | Institutions | The necessary institutions shall be set up in order to clarify and delineate responsibilities among relevant |
|  |  | organizations involved in O&M. |
| 2 | Standards | O&M works on expressways mainly consists of traffic operation, road maintenance and toll collection. |
|  |  | The establishment of standards for each work is essential in the effective and efficient implementation of works. |
| 3 | Enforcement and Regulation | In order to properly implement expressway operation by the road administrator, administrative demarcation of |
|  |  | responsibilities for traffic enforcement and regulation between the administrator and concerned regular |
|  |  | authority shall be clarified. |

Prepare O&M Plan

The Consultant prepares the O&M plan for the Expressway in accordance with the existing legal and regulatory framework confirmed in D.4.1.  As for the items which are not existed and scheduled in the institutional and administrative arrangement plan in D.4.1, the Consultant establishes the assumptions based on overseas practices.

Work diagram of O&M plan is shown in Figure D.16, and describes the methodology of work items subsequently.

Figure D.16   Work Diagram of O&M Plan

Establish Basic Assumptions

The Consultant establishes basic assumptions for preparing O&M plan in accordance with the existing legal and regulatory framework confirmed in D.4.1.  As for the items which are not existed and scheduled in the institutional and administrative arrangement plan in D.4.1, the Consultant establishes the assumptions based on overseas practices.

Establish LOS

The Consultant establishes LOS by extracting the requirements in MOT Circular on Expressway O&M and utilizing overseas experiences for definition of O&M activity and frequency.

Possible performance indicators for LOS are shown in Table D.17.

Table D.17   Possible Performance Indicators for LOS

| No. | Category | Indicators |
| --- | --- | --- |
| 1 | Availability | Frequency of road closures, transaction time of traffic accidents, duration and work area of maintenance works |
| 2 | Mobility | Average covering speed, traffic density |
| 3 | Accessibility | Capacity of toll gates, transaction system and time of toll gates |
| 4 | Safety | Traffic safety facilities, lighting, enforcement of traffic regulation, traffic accident rate, visibility |
| 5 | Comfortability | Facilities and activity level of SAs/PAs |
| 6 | Emergency Response | Covering time of rescue cars arrival (ambulance and fire fighting cars) |
| 7 | Surface Conditions | Coarseness, roughness and pot holes of road surface |
| 8 | Traffic Information | Traffic congestion/delay, regulation and disaster |
| 9 | Environment Aspect | Noise, air pollution |

Define O&M Activity and Frequency

The Consultant defines the O&M activity and frequency in case of regular, traffic regulation and emergency to satisfy LOS established in (2) above in accordance with MOT Circular on Expressway O&M or by utilizing the overseas experiences.  The activity and frequency is taken into account stage-wised strengthening for ensuring LOS in the future traffic growth.

Prepare O&M Plan

The Consultant prepares the O&M plan based on (1) to (3) above.  As for the item related to ITS, the Consultant utilizes ITS Standards prepared by JICA T/A to define the basic requirements and system.  Based on this basic requirements and system, the Consultant prepares the functions and specifications for ITS facility and system configuration in D.5.1(3).

Main contents of O&M plan are shown in Table D.18.

Table D.18   Contents of O&M Plan

| No. | Item | Contents |
| --- | --- | --- |
| 1 | O&M Charter | Name, legal status, objectives, policies, responsibilities, targets, budgets, management, organization, staffing |
| 2 | Traffic Management | Traffic surveillance and control system, organization and staffing |
| 3 | Toll Collection | Location of toll plaza, numbers of toll barrier/gate, toll collection system, organization and staffing |
| 4 | SA/PA Services | Location of SAs/PAs, contents of the services, organization and staffing |
| 5 | Maintenance | Maintenance system (including road asset management), organization and staffing |
| 6 | Administration | Organization, personnel, reports and financial management system |
| 7 | O&M Buildings | Layout plan of toll plaza, O&M building and SAs/PAs |
| 8 | O&M Equipment | Procurement, management and maintenance plan of O&M equipment |

Prepare O&M Unit Establishment Plan

The Consultant prepares the O&M unit establishment plan including the training program in consideration of the required arrangements and enhancements extracted in (4) above.

Estimate O&M Cost

The Consultant estimates the O&M cost both of the Project implementation and operation stages based on (4) to (5) above.  However, the cost in the Project implementation stage is used for the reference, and the detailed cost is estimated in D.10.1.

Based on (1) to (6) above, the Consultant compiles the O&M plan and holds workshops with VEC/PMU85 and relevant organizations.

Prepare Basic Design of O&M Buildings

The Consultants prepares the basic design of O&M buildings based on the O&M plan in D.4.2.  The design covers all of facilities in toll plaza, O&M buildings and SA/PA except communications and electrical facilities which are designed in D.5.2 and D.6.1, respectively.

Work diagram of basic design of O&M buildings is shown in Figure D.17.

Figure D.17   Work Diagram of Basic Design of O&M Buildings

Work Progress to Date

As of the end-December 2011, this work does not start yet.

ITS Plan and Design

TOR Requirements

Please refer to Appendix 1: Terms of Reference (TOR).

Methodology

Prepare ITS Plan

Based on the ITS basic requirements and system in D.4.2(4), the Consultant prepares the ITS development plan which is composed of planning concept, stage development, location of facilities, equipment procurement and implementation plans.  Based on the development plan, the Consultant prepares the basic functions and specifications of ITS facility and system in accordance with ITS Standards prepared by JICA T/A.

Work diagram of ITS plan is shown in Figure D.18, and main contents of ITS basic requirements and system are shown in Table D.19, respectively.

Figure D.18   Work Diagram of ITS Plan

Table D.19   Main Contents of ITS Basic Requirements and System

| No. | Items | Contents |
| --- | --- | --- |
| 1 | Organization | Organization of maintenance, traffic management and toll collection |
| 2 | Traffic Control | Operation system for traffic control including emergency site management |
| 3 | Road Traffic Information (Collection) | Item, contents, frequencies, information flow and operation plan to be collected by ITS |
|  |  | (traffic volume, congestion and accident, over-weight, weathers, disaster, structural conditions) |
| 4 | Road Traffic Information (Provision) | Required road traffic information providing to road users and stakeholders |
| 5 | Toll Collection | Toll collection method and transaction flow |

Prepare Basic Design of ITS Facilities

The Consultant prepares the basic design of ITS facilities, communication system, toll collection facilities and system and obtains the approval from VEC/PNU85.

Work diagram of basic design of ITS facilities is shown in Figure D.19.

Figure D.19   Work Diagram of Basic Design of ITS Facilities

Work Progress to Date

As of the end-December 2011, this work does not start yet.

Electrical Facilities Design

TOR Requirements

This scope is proposed by the Consultant as additional scope, not included in the Appendix 1: Terms of Reference (TOR).

Methodology

Prepare Detailed Engineering Design of Electrical Facilities

The Consultant prepares the detailed engineering design of electrical facilities in relation with the basic design of civil structures (D.3.1), O&M buildings (D.4.3) and ITS facilities (D.5.2).  The works are included to coordinate and agree the power receiving plan with the power suppliers in the Project area.

Work diagram of detailed engineering design of electrical facilities is shown in Figure D.20, and electrical facilities plan in F/S is shown in Table D.20, respectively.

Figure D.20   Work Diagram of Electrical Facilities Design

Table D.20   Electrical Facilities Plan in F/S

| No. | Items | Facilities |
| --- | --- | --- |
| 1 | Power Supply | Power receiving points, receiving power voltages and capacities, and back-up power supply facilities |
| 2 | Road Lighting | Lighting source and output power, height, interval and location of lighting poles, and lighting calculation |
| 3 | Tunnel Ventilation and Safety | Reporting system, information system, fire-fighting facilities, and ventilation facilities, etc. |

Source:	Decision No. 2656/QD-BGTVT dated September 10, 2010

Work Progress to Date

As of the end-December 2011, this work does not start yet.

Public Utilities Relocation Plan

TOR Requirements

This scope is proposed by the Consultant as additional scope, not included in the Appendix 1: Terms of Reference (TOR).

Methodology

Prepare Relocation Plan of Public Utilities

The Consultant confirms the public utilities which are necessary to relocate by the implementation of the Project based on the topographic survey (D.2.2), relevant facilities survey (D.2.6) and basic design of civil structures (D.3.1).  The Consultant prepares and agrees the relocation plan and cost estimate in cooperation with the relevant agencies.

Work diagram of public utilities relocation plan is shown in Figure D.21, and probable public utilities to be relocated by the Project are shown in Table D.21, respectively.

Figure D.21   Work Diagram of Public Utilities Relocation Plan

Table D.21   Probable Public Utilities to be relocated by the Project

| No. | Public utilities | Owners |
| --- | --- | --- |
| 1 | Electrical Line | Power Transmission Company No.2 (PTC2) |
| 2 | Telecommunication Line | Vietnam Posts and Telecommunications Group (VNPT) or |
|  |  | Vietnam Military Electronic and Telecommunications Corporation (VIETTEL) |
| 3 | Water Supply Pipe | Water Supply Company in each City/Province |
| 4 | Sewerage Pipe | Transport Works Management Company or Drainage Company |
| 5 | Irrigation Canal | Department of Agriculture and Rural Development (DARD) |

Work Progress to Date

As of the end-December 2011, the following progress is performed.

- Vietnamese Electrical Engineer started to visit electrical companies in order to discuss the method of the relocation works.

- Identified crossing of the electrical lines are more than 200 places as shown in Appendix 5.

Safeguards

Assist in Updating EIA and EMP

TOR Requirements

Please refer to Appendix 1: Terms of Reference (TOR).

Methodology

The Consultant assists PMU85 in updating EIA and EMP.  The environmental assessment for the Project is required to satisfy not only the Vietnamese law/regulations but also JICA/WB safeguard policies.

The F/S alignment was finalized through the appraisal process to the draft F/S.  However, the used map of existing EIA is too small scale (1/50,000) and not suitable for confirmation of appropriateness of the road alignment.  Therefore, the Consultant reviews and confirms the appropriateness of the F/S alignment with the alternative study based on the adequate scale maps and design details.

In relation with the engineering design, the Consultant analyzes the environmental impacts by the Project and incorporates the environmental requirements to the engineering design.  Based on above, the Consultant develops the mitigation measures and updates the existing EIA and EMP including the preparation of draft TOR for external monitoring by the third party during the construction stage.

Work diagram of updating EIA and EMP is shown in Figure D.22.

Figure D.22   Work Diagram of Updating EIA and EMP

Work Progress to Date

Please refer to D.2.10 in the above.

Review and update Resettlement Action Plan (RAP)

Scope of Works

Scope of the works is stipulated in Appendix 1: Terms of Reference (TOR) of the Contract and cab be summarized as follows:.

- To prepare an updated the Comprehensive Plan on Compensation, Supports and Resettlement (CPCSR) in accordance with World Bank guidelines based on the Resettlement Plan prepared by PMU85 and the detailed designs. World Bank guidelines have been applied in this project including the Bank’s Resettlement Policy OP 4.12, includes safeguards to address and mitigate the economic, social, and environmental risks arising from involuntary resettlement; the OP 4.11 on Cultural Property and  the OP 4.10 on Indigenous Peoples.

- To carry out a social, poverty and gender analysis (social impact assessment) in accordance with the Work Bank guidelines and Viet Nam requirements.

- The above objectives also cover the impact of the project on ethnic minorities and vulnerable groups, socio-economic profiles and poverty reduction effects of affected communities.

Approach

The general flow of works is presented in Figure D.23.

Figure D.23   Work Diagram of Preparing and Enforcing CPCSR

Major Tasks and Methods

Summary of the main tasks harmony with stakeholders and the methods will be used to fulfill the tasks are presented in Table D.22.

Proposed major methods will be applied are described below.  These may be supplemented by Participatory Rapid Appraisal (PRA) methods.

Semi-structured interviews

Interviews to key persons will be conducted using semi-structured interviews based on a checklist of information need to be collected. Key informants and stakeholders will be selected from local leaders, residents or persons with special knowledge or experience about resettlement activities and implementation. They are should be chairman of People committee of affected communes/wards, leader of women unions, heads of affected hamlets/quarters and head of DCC of project-affected districts.

For key informants and stakeholders, semi-structured interviews will be carried out with a view of obtaining background information that can not be obtained from reports or surveys. Some of this information relates to the conditions vulnerable groups such as old and disabled, ethnic minorities etc., and includes program for training as well as other specific measures and services that may be provided, as part of the development of the project.

Besides interviewing the key persons, project affected persons also will be interviewed randomly about compensation, relocation and the satisfaction of APs. Persons belonging to vulnerable group also will be taken into account of these interviews.

Collecting secondary/available documents

For general background information on the affected communities, the reports and development plans of the respective districts and communes/wards will be acquired and studied. This also includes eventual specific information from line organizations at district and provincial levels, such as Department of Natural Resources (DONRE), Department of Agriculture and Rural development (DARD), Department of Industry (DOI), Department of Labor, Invalid and Social Affairs (DOLISA) etc.

The team members also will be responsible for collecting reports, data relating to resettlement issues from various sources such as job service offices, training centers, health stations, schools, pagodas, churches, etc.

# Table D.21   Major Works, Methods and Supports Needed from Related Agencies

| No | Works item | Purposes | Methods | Need support from PMU 85 | Need support from DCSCCs | Need support from other |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Review of existing reports and policies | Find out the GAPs between WB policies and Vietnamese policies | Gap analysis | Project documents as RAPs reports. EIA, EMP, maps | Social and Economic development Reports. | - |
| 2 | Collect secondary data and information | -Update progress of compensation, resettlement and livelihood activities -Finding livelihood options in project areas -Collect current decisions, legal documents relating to resettlement issues of the DQEP project. | Meeting with District Compensation Councils (DCCs) and PMU-85 Key informant interviews based on check lists of necessary information | -Arrange PMU-85’s Coordinators to cooperate with RES team -Introduce RES Team to DPC and DCSCC and local authorities | DPCs of affected Communes provide Social economic reports including the resettlement situation and updated process land acquisition report. | PCs of affected districts provide Social economic reports including the resettlement situation and updated process land acquisition report. |
| 3 | Consultation meetings | -Public meeting: (i) Inform affected persons (APs) of the progress of project; progress of compensation and resettlement program, and project’s policies; (ii) Affected persons express their request on resettlement and income restoration supports | Focus group discussion: separate consultation with different topics and groups of APs | PMU 85 assist to get permits from local authorities. Cooperate with Consultants for introducing the DQEP project to PAPs as well as Local authority | Official of DCSCCs take part the meetings and explain to affected people on regulations and policies related to compensation, supports and resettlement. | PC of affected districts to provide the permits to conduct the meetings |
|  |  | -Stakeholder meeting: To consult with participants on the draft RP | Technical support and inputs Prepare meeting notes as well as comments from participants | Leading the workshop and invitation letters to participants. |  |  |
| 4 | Replacement cost survey | Determine the replacement cost in the affected area to apply for the project | Involve with the external valuers | Leading meetings to approve survey’s results | DCSCCs to discuss/comments on the survey’s results |  |
| 5 | Detailed measurement surveys-DMS (conducted by DCSCCs) | -Obtain full database of APs and their loss assets to prepare land compensation award papers. -Assess incomes, identify productive activities, target groups and plan for income restoration -evaluation relocation options and social development program for vulnerable groups | Supervising DMS Conduct supplement interview using household Questionnaire | Supervisor to the DMS process and Data. Support to RES team receive database of APs. | DCSCCs to provide the full database of APs and their loss assets as soon as possible. | DD consultants to provide detail maps of ROW and underpass, overpass, interchanges |
| 6 | Supplement social survey | -Identify and update the economic and social conditions of affected persons, disaggregated by gender, ethnicity, and type of impact (i.e. loss of residential land and house, loss of agricultural land, loss of income from business or employment, etc.) -conduct quick evaluation to APs groups which are not consider in the list of APs comment by DPC, or PPC. -Identify income restoration options and severely affected groups | -Collect annual social economic reports of Commune People Committees -Interview using questionnaire -Observations | PMU 85 assist to get permits from local authorities | DCSCCs to provide the full list of APs . DPC of affected Commune to provide the permits RES team to conduct the surveys as necessary. | PC of affected districts to provide the permits to conduct the surveys |
| 7 | Resettlement site survey | Carry out feasibility study of the final sites identified; confirm available resources and facilities and identify requirements to improve replacement sites. | Meeting with relating agencies, design and construction companies. Interview key informants based on a check list Observations | PMU 85 assist to get permits from local authorities | DCCs to provide information of resettlement sites, including maps | PC of host districts to provide the permits to conduct the surveys |
| 8 | Prepare the draft updated resettlement plans | Integrating and analyzing data, information, results of field studies to prepare the draft updated RP, including a livelihood restoration program | Desk study | Provide advices on how to narrow the gaps with WB’s requirements | Provide solutions on how to narrow the gaps with WB’s requirements |  |
| 9 | Finalize the Updated RP | To complete the Updated Resettlement plan according to suggestions recorded at the stakeholder meeting | Desk study | PMU 85: to provide consultations on how to deal with WB’s requirements |  |  |

Structured direct observations

Another PRA tool will be used is a structured direct observation. Field observations on status of resettlement implementation, plus individual or group interviews for cross-checking purposes will be conducted every time the team going to the field. In-depth case studies of APs and host populations from various social classes will be carried out to assess impact of resettlement.

Consultation meetings

The team will assist the affected districts in organizing the public consultation meetings. The public consultation meetings shall be organized when the draft updated RP has been finished. The main technique to be used in the consultation meetings is focus group discussion. Specific topics such as land compensation payments, services at resettlement sites, income restoration, and gender issues will be discussed in open-ended group sessions. These group will be divided according to their categories, which will be revealed thank to social survey.

Stakeholder Meetings:

Stakeholder meeting will be held with provincial, district and commune leaders and representatives of their key departments.

Survey using questionnaire

The DMS is carried out by DCCs, acting on the request of the project management in order to identify extent and effects of land loss, assess entitlements and to prepare land compensation award papers. It is based on project planning documents, land-use maps and land records. The DMS only includes persons with title for compensation.

Besides, resettlement consultants conduct a supplement survey for severely affected HHs and 126 HHs identified recently as affected HHs. This survey  use household questionnaire that covers all APs irrespective of entitlement or ownership. It provides a complete inventory of all APs and their assets. It will be used to assess incomes, identify productive activities, and plan for income restoration, to develop relocation options and social preparation phase for vulnerable groups. The survey questionnaires will be briefed fully on the requirements of the survey and policy needs, including eligibility and entitlement categories, if they have already been defined prior to the survey. The core team for the survey will be interdisciplinary, comprising a range of skills (for example, ecological, legal, economic, socio-cultural, environmental, land use, planning, regional and settlement).

Resettlement Team and Staff Assignments

Responsibility Assignment

Resettlement consultants (RCs) team composition and tasks assigned are presented in Table D.22

Table D.22   Responsibility Assignment in Resettlement Team

| No. | Name | Position | Task assigned |
| --- | --- | --- | --- |
| 1 | Vu Ngoc Long, PhD | International Resettlement Specialist | - Responsible for overall resettlement activities and reporting works. - To build plan and coordinate all activities of the project in order to complete the planned tasks successfully. - To ensure the progress of the project, evaluate quality of resettlement activities. - To prepare the draft URP and finalize it after getting feedbacks |
| 2 | Nguyen Manh Ha, Msc | Senior Resettlement specialist | - Detailed Measurement Survey - Replacement cost survey (with external valuers) - Income restoration program - Review and update policies, grievance mechanism, institutional arrangements and other sections of the URP - Conduct consultation workshop |
| 3 | Lam Dinh Uy | Social and resettlement specialist | - Collect secondary data and information - Detailed Measurement Survey - Review the SES baseline, analysis and carry out supplementary work - Review and finalize the relocation strategy, including the Resettlement site survey - Conduct consultation workshop |
| 4 | Tran Van Binh, PhD | Cultural and Archaeological specialist | - Review the impacts on sites having archaeological, paleontological, historical, religious and unique natural values. Propose the mitigation measures to avoid the elimination - Review the impacts on indigenous peoples, and to prepare an lndigenous Peoples Plan that will ensure these people to receive social and economic benefits that are culturally appropriate and gender and "inter-generationally" inclusive. |

Working Steps and Implementation Arrangement

The working steps and the implementation arrangement is shown in Figure D.24

* Possible issues are: (i) Differences between replacement cost and PPC’s cost; (ii) For the priority package, project has to make compensation payment before WB’s approvals to ensure the progress of civil construction works; (iii) Livelihood measures for severely affected households.

Figure D.24   Working Steps and Implementation Arrangement

Division of Updated Resettlement Plan (URPs) Reports

To ensure the project’s progress, Updated RPs will be prepared on district basic because all resettlement and land acquisition activities are conducted at district level by the District Compensation Councils. Therefore, all data and information (especially the DMS data) will be collected district by district. One URP will cover one or more district and therefore cover several packages. For the priority package, it should be included in a URP which covers one district only. Division of URPs is proposed as shown in Table D.23

Table D.23   Division of Updated Resettlement Plan (URPs) Reports

| Locality | Contract Packaging |  |  | District and commune | Remarks | Updated RP |
| --- | --- | --- | --- | --- | --- | --- |
|  | No. | Section | Length (m) |  |  |  |
| Danang | PKG1 | KM000+000 - KM008+000 | 8,000 | Hoa Nhon, Hoa Phong, Hoa Tien Comm (Hoa Vang Dist) | Unchanged | URP 1 |
|  | PKG2 | KM008+000 - KM016+880 | 8,880 | Dien Tien, Dien Tho Comm. (Dien Ban Dist.) | Km17+00 is on the approach road of Ky Lam bridge | URP 2 (Dien Ban District) |
|  | PKG3A | KM016+880 - Km18+100 | 1,220 | Dien Tho, Dien Quang Comm.(Dien Ban Dist.) | Package of Ky Lam bridge |  |
|  | PKG3B | KM018+100 - KM021+500 | 3,400 | Dien Quang, Duy Trinh Comm. (Duy Xuyen Dist.) | To avoid large steep at Km22+00 | URP 3 (Duy Xuyen, Que Son districts) |
|  | PKG4 | KM021+500 - KM032+600 | 11,100 | Duy Trinh, Duy Son, Duy Trung Comm.(Duy Xuyen Dist.); Que Xuan Comm. (Que Son Dist.) | To avoid large steep and deep excavation at Km32+00 |  |
|  | PKG5 | KM032+600 - KM042+000 | 9,400 | Que Xuan, Phu Tho Comm. (Que Son Dist.); Binh Quy Comm. (Thang Binh Dist.) | Unchanged |  |
|  |  |  |  |  |  | URP 4 (Thang Binh, Phu Ninh and Nui Thanh Districts) |
| Quang Nam | PKG6 | KM042+000 - KM052+000 | 10,000 | Binh Quy, Binh Chanh, Binh Que Comm. (Thang Binh Dist.) | Unchanged |  |
|  | PKG7 | KM052+000 - KM065+000 | 13,000 | Binh Que Comm. (Thang Binh Dist.); Tam Thanh, Tam Phuoc, Tam Dan, Tam Thai Comm. (Phu Ninh Dist.) | Unchanged |  |
|  | PKG A1 | KM065+000 - KM081+150 | 16,150 | Tam Thai, Tam Dai, (Phu Ninh Dist); Tam Ngoc (Tam Ky City) Tam Xuan, Tam Anh Comm. (Nui Thanh Dist.) | Km81+500 is at the location of overpass culvert and nearby the approach road of a bridge L=55m |  |
|  | PKG A2 | KM081+150 - KM099+500 | 18,350 | Tam Anh, Tam My, Tam Nghia Comm. (Nui Thanh Dist.) | Station KM099+500 is the boundary between QN-QNg |  |
| Quang Ngai | PKG A3 | KM099+500 - KM110+100 | 10,600 | Binh Nguyen, Binh Trung, Binh Long Comm. (Binh Son Dist.) | To avoid deep excavation at Km111+00 and high embankment nearby | URP 5 (Binh Son Dist.) |
|  | PKG A4 | KM110+100 - KM124+700 | 14,600 | Binh Long Comm. (Binh Son Dist); Tinh Tho, Tinh Ha Comm. (Son Tinh Dist.) | Km124+500 is on the approach road of Tra Khuc bridge |  |
|  |  |  |  |  |  | URP 6 (Son Tinh, Tu Nghia and Quang Ngai City) |
|  | PKG A5 | KM124+700 - KM131+150 | 6,450 | Tinh Ha Comm. (Son Tinh Dist.); Nghia Ky, Nghia Dien Comm. (Tu Nghia Dist.); Quang Phu Ward (Quang Ngai City) |  |  |

Work Schedule

Overall

Based on the division of URPs above, the overall work schedule of the update resettlement plan is proposed as shown in D.25.

Figure D.25   Overall Work Schedule for Update Resettlement Plan

Priority Section

The URP 2 covering Dien Ban district, Quang Nam province, include the priority package PKG3A, will be finished in the end of July 2012. This will give sufficient time to implement the URP, ensure that cleared land will be available for commencing the construction of the package 3A in September 2012.

The detailed work schedule of the URP 2 is shown in Table D.24.

Table D.24   Detail Work Schedule for Updated RP No 02 – Dien Ban district, Quang Nam Province.

| No. | Activities | Person in charge | Proposed timing |  | PMU 85 supports |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Start | Finish |  |
| 1 | Review of existing reports and policies Detail working plan. | Long, Ha, Uy, Binh | 1/12/2011 | 30/12/2011 | Project documents |
| 2 | Collect secondary data and updated Social economic situation of PAPs in 03 communes, Dien Ban district , Quang Nam pro. | Long, Ha, Binh, Uy | 06/12/2011 | 15/1/2012 | -Arrangement meeting with DPC, DCSCC and introduce RES Team. - Introduction Letter to Local authority and Departments -Indicate coordinator-PMU85. |
| 2.1 | Meeting with relevant stakeholders, DARD, DONRE, Provincial Departments, NGOs. PRC, | Long, Uy |  |  |  |
| 2.2 | Meeting with local authority: CPC | Binh, Uy, Ha |  |  |  |
| 2.3 | Meeting with MASS Organization | Binh, Uy |  |  |  |
| 3 | Detailed measurement surveys (DMS) (1059 HH) | Ha, Binh | 05/2/2012 | 30/3/2012 | Prepare contract with DCSCCs to provide the full database of APs and their loss assets. |
| 3.1 | - Dien Tien commune (131HH) |  |  |  |  |
| 3.2 | - Dien Tho commune (887HH) |  |  |  |  |
| 3.3 | - Dien Quang Commune (40HH)? |  |  |  |  |
| 4 | Replacement cost survey | Long, Uy | 15/12/2011 | 05/2/2012 |  |
|  | Selection the external land valuers Company and Prepare the contracts |  | 12/12/2011 |  | Comment and approve the External Land Valuers |
| 5 | Supplement social survey |  |  |  | Introduce RES Team to DCP, CPC, for cooperation working in the field. |
| 5.1 | Study on updated the situation of project sites | Ha, Binh | 06/12/2011 | 30/12/2011 |  |
| 5.2 | The second detail Supplement Social Survey for 126 HH in Dien Quang commune and other Vulnerable groups. | Uy | 06/12/2011 | 30/12/2011 |  |
| 6 | Resettlement site survey: 04 sites | Long, Ha, Uy, Binh | 01/3/2012 | 30/3/3012 | -Introduce RES Team to DCSCCs, to Provincial Resettlement Committee. |
| 6.1 | - Thai Son site , Dien Tien commune |  |  |  |  |
| 6.2 | - Dong Hoa site , Dien tho Commune |  |  |  |  |
| 6.3 | - Ky Lam site , Dien tho commune |  |  |  |  |
| 6.4 | - Phong thu 01, Dien tho, Dien Quang commune |  |  |  |  |
| 7 | Survey for Income Restoration Programme (IRP) | Binh | 06/12/2011 | 06/2/2012 | -Introduce RES Team to MASS organizations, CPC, DCSCCs, and departments. |
| 7.1 | - Dien Tien commune |  |  |  |  |
| 7.2 | - Dien Tho commune |  |  |  |  |
| 7.3 | - Dien Quang Commune |  |  |  |  |
| 8 | Community Meetings | Long |  |  |  |
| 8.1 | Consultation meetings for SIA and EIA | Long, Uy , Ha | 02/1/2012 | 14/1/2012 | Co-Chair the meeting together DPC, CPC. Coordinate with EIA consultant to present project design and EIA reports as well EMP. |
| 8.1.1 | Dien Tien commune |  | 09/1/2012 |  |  |
| 8.1.2 | Dien Tho commune |  | 10/1/2012 |  |  |
| 8.1.3 | Dien Quang Commune |  | 11/1/2012 |  |  |
| 8.2 | Consultation meetings for IRP | Long, Binh | 01/3/2012 | 15/3/2012 | Co-Chair the meeting together CPC. |
| 8.2.1 | Dien Tien commune |  | 8/3/2012 |  |  |
| 8.2.2 | Dien Tho commune |  | 9/3/2012 |  |  |
| 8.2.3 | Dien Quang Commune |  | 10/3/2012 |  |  |
| 8.3 | Consultation meeting for Resettlement sites | Long, Ha, Uy | 15/4/2012 | 30/4/2012 | Co-Chair the meeting together DPC, CPC. Coordinate with DCSCC to present resettlement sites as well as moving planning. |
| 8.3.1 | - Thai Son site , Dien Tien commune |  | 20/4/2012 |  |  |
| 8.3.2 | - Dong Hoa site , Dien tho Commune |  | 21/4/2012 |  |  |
| 8.3.3 | - Ky Lam site , Dien tho commune |  | 22/4/2012 |  |  |
| 8.3.4 | - Phong thu 01, Dien tho, Dien Quang commune |  | 23/4/2012 |  |  |
| 9 | Prepare the draft URP 02 – Dien Ban district | Long , Uy | 01/5/2012 | 30/5/2012 |  |
| 9.1 | Consultation meeting for draft URPs | Long, Uy, Ha, Binh | 15/5/2012 |  | Co-Chair the meeting together DPC, CPC. |
| 9.2 | Discloser URPs | Long, Uy | 20/5/2012 |  |  |
| 10 | Finalize the final draft Updated RP | Long, Uy | 30/6/2012 |  |  |

Land Acquisition Impact as of December 2011

As of December 2011, land acquisition impact is estimated as shown in Table D.25.

Table D.25   Land Acquisition Impact as of December 2011

| Items | Unit | Danang | Quang Nam | Quang Ngai | Total |
| --- | --- | --- | --- | --- | --- |
| PAPs | HH | 424 | 4.486 | 1,896 | 6,898 |
| Affected Districts |  | 1 | 7 | 4 | 12 |
| Affected Communes |  | 3 | 24 | 11 | 38 |
| Resident land | HH | 62 | 878 | 648 | 1,588 |
|  | m2 | 38,498 | 347,138 | 340,749 | 726,385 |
| Agricultural land | HH | 295 | 2473 | 1,369 | 4,137 |
|  | m2 | 370,374 | 2,686,623 | 1,281,653 | 4,338,650 |
| Public land | m2 | 88,067 | 1,923,858 | 908,021 | 2,919,946 |
| Forest land | m2 | 9,075 | 1,700,726 | 128,415 | 1,838,216 |
| Houses | HH | 59 | 763 | 589 | 1,411 |
|  | m2 | ? | 37,594 | 26,059 | 63,653? |
| Resettle | HH | 85 | 771 | 430 | 1,286 |
| Affected Gov. offices |  |  | 2 | 2 | 4 |

Work Progress to Date

The Consultant submitted the work plan of updating resettlement plan, and it was approved by PMU85. Accordingly, the Consultant is preparing the first consultation meeting in Dien Ban District in Quang Nam Province.

Construction Planning

Prepare Construction Plan

TOR Requirements

Requirements in the TOR are summarized as shown in Table D.26.

Table D.26   TOR Requirements for Construction Method and Schedule

| No. | TOR Requirements | Check |
| --- | --- | --- |
| 1 | - The Consultant shall carry out the study of construction execution and propose the most suitable and practical construction method and schedule of the Project. |  |

Source:	TOR 3.3.7.

Methodology

The Consultant prepares the construction methods, schedule, temporary facilities and procurement plan of labors, materials and construction machines to estimate the proper Project cost. Especially, the volume of borrow materials are huge; therefore, the Consultant prepares the mass curve to estimate the proper hauling cost.

Work diagram of construction planning is shown in Figure D.26, and image of construction scheduling and mass curve is shown in Figure D.27, respectively.

Figure D.26   Image of Construction Scheduling and Mass Curve

| Construction Scheduling (MS Project) | Mass Curve |
| --- | --- |

Figure D.27   Image of Construction Scheduling and Mass Curve

Work Progress to Date

As of the end-December 2011, the following progress is performed.

- Temporary construction roads were identified for whole section.

- Necessary topographic survey areas are identified.

- Rough estimate of the construction cost was carried out.

Project Cost Estimate

Estimate Project Cost

TOR Requirements

Requirements in the TOR is summarized as shown in Table D.27.

Table D.27   TOR Requirements for Cost Estimate

| No. | TOR Requirements | Check |
| --- | --- | --- |
| 1 | - The Consultant shall prepare the detailed cost estimate for the construction of the Project, including: |  |
| 2 | - Bills of Quantities for the construction works of every contract package and the whole project. |  |
|  | - The cost estimate for every contract package based on a detailed unit price analysis. |  |
|  | - Prepare the total cost estimate for every contract package and the whole project based on the Bills of Quantities and taking account of project management and other costs, and showing a breakdown of foreign and local currency portions. |  |
|  | - Prepare annual financing schedules for every contract package and the whole project based on the construction schedule and showing total costs and a breakdown of foreign and local currently portions. |  |

Source:	TOR 3.3.8

Methodology

The Consultant estimates the Project cost and annual fund requirements by contract packages in relation with the construction plan (D.9.1).  The cost estimate conditions are severely affected to the outputs; therefore, the Consultant proposes those conditions in advance and obtains the approval from VEC/PMU85 and other relevant organizations.

Work diagram of Project cost estimate is shown in Figure D.28, and main contents of cost estimate conditions are shown in Table D.28, respectively.

Figure D.28   Work Diagram of Project Cost Estimate

Table D.28   Main Contents of Cost Estimate Conditions

| No. | Item | Contents |
| --- | --- | --- |
| 1 | Time of Cost Estimate | Time applied in the cost estimate (quarter) |
| 2 | Currency | Foreign currency applied in the cost estimate |
| 3 | Exchange Rate | Exchange rate for the foreign currency applied in the cost estimate |
| 4 | Classification Condition of Currency | Classification conditions of foreign and local currencies applied in the cost estimate |
| 5 | Tax Exemption | Items of the tax exemption applied in the cost estimate |
| 6 | Cost Estimate Standards | Cost estimate standards applied in the cost estimate |
|  |  | (productivity, and unit cost of materials, labors, construction machine operation and hauling ) |
| 7 | Price Fluctuation Rate | Price fluctuation rate of the foreign and local currencies applied in the cost estimate |
| 8 | Physical Contingency Rate | Physical contingency rate applied in the cost estimate |

Work Progress to Date

As of the end-December 2011, the following progress is performed.

- The Consultant reviewed the cost estimate in the F/S.

- The Consultant proposed revision of procurement plan as shown in Table A.11.

Procurement Documents

Prepare Procurement Documents

TOR Requirements

Requirements in the TOR are summarized as shown in Table D.29.

Table D.29   TOR Requirements for Preparation of Procurement Documents

| No. | TOR Requirements | Check |
| --- | --- | --- |
| 1 | - For sections of the Project to be funded with assistance from the World Bank, the Consultant shall prepare procurement documents in accordance with the World Bank's Procurement Guidelines, Standard Pre-Qualification Documents and Standard Bidding Documents for Procurement of Works. - For sections to be funded with assistance from the Government of Japan, the documents will be prepared in accordance with the most recent version of the Handbook for Procurement under ODA Loans. - These standard documents will be provided to the Consultant. |  |
|  | - The procurement documents to be prepared by the Consultant will include those needed for pre-qualification, bidding and contracting each contract package. - The documents shall be prepared and completed in a timely manner so that prequalification of packages for which design has been completed and approvals gained can be undertaken in parallel with detailed design for other packages and the bidding can be started immediately after completing the detailed design for the concerned contract package. |  |
|  | - Pre-qualification, bidding and contract documents shall be in English. - The documents shall be translated into Vietnamese by the Consultant and submitted to VEC for approval. - Where there is discrepancy between the English and Vietnamese versions, the English version will prevail. |  |

Source:	TOR 3.3.9

Methodology

The Consultant prepares the procurement plan, P/Q and bidding documents including those evaluation criteria in accordance with the current WB/JICA procurement guidelines and standard forms.

The conditions of contract in the bidding documents are applied the appropriate series of FIDIC, and the technical specifications including EMP with supervision of engineers/specialists in every technical field for ensuring the quality.

Work diagram of procurement documents preparation is shown in Figure D.29.

Figure D.29   Work Diagram of Procurement Documents Preparation

Work Progress to Date

As of the end-December 2011, the following progress is performed.

- The Consultant submitted the revised procurement plan on December 15,2011.

- The Consultant submitted the first draft of the pre-qualification documents of PKG3A: Ky Lam Bridge.

Project Implementation Program

Prepare Project Implementation Program

TOR Requirements

Requirements in the TOR are summarized as shown in Table D.30.

Table D.30   TOR Requirements for Preparation of Implementation Program

| No. | TOR Requirements | Check |
| --- | --- | --- |
| 1 | - The Consultant shall prepare the implementation program in accordance with the final scope of works. |  |

Source:	TOR 3.3.10

Methodology

The current Project I/P is shown in Figure A.9.

During the Services, the Consultant studies the construction period in each contract package and updates the Project I/P in accordance with the results of construction planning (D.9), if required.

Work diagram of Project implementation program is shown in Figure D.27.

Figure D.27   Work Diagram of Project Implementation Program

Work Progress to Date

As of the end-December 2011, the following progress is performed.

- The Consultant updated the Project I/P and proposing in the revised procurement plan submitted on December 15, 2011.

- As requested in Appendix B, the overall I/P will be submitted within four (4) months from the commencement date of the Services.

Procurement Assistance

Assist in Tendering Procedures

TOR Requirements

Requirements in the TOR are summarized as shown in Table E.1.

Table E.1   TOR Requirements for Procurement Assistance

| No. | TOR Requirements | Check |
| --- | --- | --- |
| 1 | - The Consultant shall provide necessary technical assistance to PMU85/VEC in all aspects of the procurement process in accordance with the procurement regulations of GOVN and World Bank guidelines. - The technical assistance shall include, but not limited to, the following: |  |
| 2 | - Preparation of the Procurement Plan covering all major work contracts. |  |
| 3 | - Preparation of pre-qualification and bidding documents for each contract package. |  |
| 4 | - Providing necessary assistance on invitation of pre-qualification, evaluation of pre-qualification applications and preparation of pre-qualification evaluation reports for submission for review by concerned agencies including PMU85, VEC, MOT and the World Bank. |  |
| 5 | - Providing necessary assistance on invitation for bids, bid opening, pre-bid conference, pre-bid site visits for the pre-qualified interested bidders, preparation of clarification answers and addendum to bidding documents, evaluation of bids, preparation of bid evaluation report in accordance with the World Bank’s standard bid evaluation form and the MOT’s form for submission for review by concerned agencies including PMU85, VEC, MOT and the World Bank. |  |
| 6 | - Assist PMU85/VEC in contract negotiation, preparation and finalization of contracts submission for review by concerned agencies including VEC, MOT and the World Bank. |  |

Source:	TOR 3.4

Methodology

The Consultant assists VEC/PMU85 in tendering procedures of all civil contract packages in accordance with the JICA/WB procurement guidelines.  In the assistance, the Consultant conducts the independent P/Q and bid evaluations to advise VEC/PMU85 on issues related to contract negotiations.

Work diagram of procurement assistance is shown in Figure E.1.

Work Progress to Date

Please refer to D.11.

Figure E.1   Work Diagram of Procurement Assistance

Land Acquisition Staking

TOR Requirements

Requirements in the TOR are summarized as shown in Table F.1.

Table E.1   TOR Requirements for Procurement Assistance

| No. | TOR Requirements | Check |
| --- | --- | --- |
| 1 | - The Consultant shall stake land acquisition to hand over to local authorities who undertake compensation for land acquisition and resettlement. |  |

Source:	TOR 3.5

Methodology

General work flow of the land acquisition staking is as follows as shown in Figure F.1.

Figure F.1   Work Diagram of Land Acquisition Staking

Prepare ROW Drawings

The Consultant prepares ROW (Right-Of-Way) drawings on the basis of the civil engineering design, commune by commune.

Confirm with Local Authorities

The Consultant confirms the ROW drawings with the local authorities. Updating the RAP should be carried out with the discussion.

The drawings shall be finalized after agreement with relative authorities.

Land Acquisition Staking

The Consultant stakes the land acquisition boundaries. This work will be out-sources in order to carry out in efficient and effective manner.

Work Progress to Date

As of the end-December 2011, the following progress is performed.

- The Consultant identified the extent of all communes as shown in Appendix 4.

- The Consultant provided some draft ROW drawings to our resettlement team for consultation meeting, especially for the priority package of PKG3A: Ky Lam Bridge.

Technology Transfer

Provide Training to VEC, PMU85 and Relevant Organizations

TOR Requirements

Requirements in the TOR is summarized as shown in Table G.1

Table G.1   TOR Requirements for Technology Transfer

| No. | TOR Requirements | Check |
| --- | --- | --- |
| 1 | - The Consultant shall undertake training and technology transfer for PMU85, VEC, local consultant and relevant authorities. |  |

Source:	TOR 3.6

Methodology

The Consultant provides the appropriate technology transfer to VEC, PMU85 and relevant organizations for enhancing the necessary knowledge and capacity to ensure the smooth execution of the Project and sustainable development of the expressway network in Vietnam.

The objectives of the training are that VEC, PMU85 and relevant organizations acquire the knowledge and capacity which are necessary to manage and control the Project smoothly and to make decisions with sufficient technical backgrounds for the important issues and peculiar matters of expressway in the Project.  Based on the knowledge and capacity acquired by the training program, VEC, PMU85 and relevant organizations are able to manage and control the expressway development projects by themselves.

The Consultant assigns the key professional staff as the Training Specialists and identifies the training needs with VEC, PMU85 and relevant organizations in the beginning of the Services.  Based on the needs above, the Consultant prepares the training plan which consists of the training themes, program, trainees and implementation schedule.  The training schedule is taken into account the work schedule of the Services to provide the workshops at appropriate timing in advance of the execution of the Services.

In corporation with each engineer/specialist in the respective fields, the training specialists prepare the appropriate training materials and hold the workshops to VEC, PMU85 and relevant organizations.

Tentative training themes are as follows:

Project management of all project phases (PMBOK);

Safeguards (WB/JICA safeguards policy);

Expressway road safety and auditing system (PIARC road safety manual);

Expressway administration, O&M, ITS and ETC systems (including overseas study tour).

Work program of technology transfer to VEC, PMU85 and relevant organizations is shown in Figure G.1, and tentative training program of the overseas study tour is shown in Table G.2, respectively.

In case, VEC/PMU85 agree to carry out the program, the Consultant arrange necessary procedures timely.

Figure G.1   Work Diagram of Technology Transfer to VEC, PMU85 and Relevant Organizations

Table G.2   Training Program of Overseas Study Tour (Tentative)

| Day | Time | Program | Contents | Stay at |
| --- | --- | --- | --- | --- |
| 1 | Night | Move to Narita | - Move from Hanoi to Narita by airplane | Flying overnight |
| 2 | AM | Move to Tokyo | - Move from Narita to Tokyo by car | Tokyo |
|  | PM | Visit to MLIT | - Introduce expressway administrative policy |  |
| 3 | AM | Visit to JEHDRA | - Introduce expressway business and implementation scheme | Tokyo |
|  |  | Visit to ORSE | - Introduce ETC technology and standardized system |  |
|  | PM | Visit to HIDO | - Introduce advanced ITS technology |  |
|  |  | Visit to VICS center | - Introduce traffic information and VICS system |  |
| 4 | AM | Visit to MEX | - Introduce traffic management and O&M system for intra-urban expressway | Tokyo |
|  | PM | Visit to NEXCO | - Introduce traffic management and O&M system for inter-urban expressway |  |
| 5 | AM | Move to Narita | - Move from Tokyo to Narita by car | Hanoi |
|  |  | Move to Hanoi | - Move to Narita to Hanoi by airplane |  |

Work Progress to Date

As of the end-December 2011, this work does not start yet.

Provide Training to the Key Local Professional Staff

TOR Requirements

Requirements in the TOR are summarized as shown in Table G.1 above.

Methodology

During the Services, the Consultant provides person-to-person technology transfer to key local professional staff by co-working style in the respective fields.  It is expected that the key local professional staff are acquired day-to-day knowledge and skills necessary for the execution of the Services.

Work diagram of technology transfer to key local professional staff is shown in Figure G.2.

Figure G.2   Work Diagram of Technology Transfer to Key Local Professional Staff

Work Progress to Date

As of the end-December 2011, the following progress is performed.

- The Consultant starts the training to the key local professional from the commencement of the topographic survey on July 15, 2011, day-to-day basis, person-to-person basis.

- Especially, the Consultant is paying much attention in providing communication management in the project management, i.e. participation to the general meeting, issuance of Inter-Office-Memo.