## Fig.A.1
2000
Approved the preparation of BOT Pre-F/S
Approved BOT Pre-F/S
Approved the preparation of BOT F/S
Prerpared BOT F/S
Approved as one of the top priority projects
Updated the JETRO study
Undertook the preparation mission
Declared eligibility for IBRD loan
Year
GOVN
JETRO
Not materialized as the BOT scheme Project
Undertook the identification missions
Prepared the study report
Received the JETRO study report
WB
Adopted the study
Allowed advance procurement
Proceeded the procurement process
BOT scheme
2003
2004
2005
2007
2008
2009
JETRO Study
WB Study
Finalized/submit as the F/S
TEDI F/S
2010
2011
Contracted/Issued NTP

## Fig.A.2
My Son
Danang City
BP
Hoi An
Hanoi/East-West Corridor
HCMC
Source: Dung Quat Economic Zone Authority
Dung Quat Economic Zone
Source: Chu Lai Open Economic Zone Authority
Chu Lai Open Economic Zone
North-South Expressway
Project Road
Quang Tri - Da Nang (Plan)
Quang Ngai - Quy Nhon (Plan)
Other Classified Road
Da Nang Bypass
National Highway
Provincial Road
Others
Provincial Border
North-South Railway
World Heritage
EP
LEGEND
Quang Ngai
N
14
14B
1A
14E
Tam Ky
Project Road (L=139.5 km)

## Fig.A.3
Goals
Purpose
Project Design (Summary)
External Conditions (Important Assumptions/Risks)
- Expressway construction and O&M equipment provision (see A.1.4(1))
- Expressway facilities and equipment
- Expressway O&M system and trained staffs
- Improve transport linkages in the central region
- Grow economies in the central region
- Accelerate development investments in the central region
- Provide appropriate O&M services by the established unit
- Obtain cooperation from inhabitants in the Project area
- Consulting services (see A.1.4(2))
- Project management by VEC/PMU85 (see A.1.10)
Pre-conditions
- Establishment of an O&M unit (see A.1.4(3))
- Land acquisition and resettlement (see A.1.5(2))
- Obtain agreement from inhabitants in the Project area
- Social and environmental assessment (see A.1.5(1))
Outputs
Activities

## Fig.A.4
1A
Danang
Hanoi/
HCMC
Dung Quat
East-West Corridor
Tuy Loan IC
My Son IC
Ha Lam IC
Tam Ky IC
Chu Lai IC
Dung Quat IC
Binh Son IC
Quang Ngai North IC
Quang Ngai IC
KM000+000
KM020+805
KM040+776
KM064+200
KM083+800
KM102+255
KM112+615
KM123+915
KM130+750
20.805 km
19.971 km
23.424 km
19.600 km
18.455 km
10.360 km
11.300 km
6.835 km
KM000+000
KM008+000
KM100+000
KM139+500
Expressway, L=131.5 km
Quang Ngai, L=39.5 km
Quang Nam, L=92.0 km
Danang, L=8.0 km
KM000+000
KM131+500
North-South Expressway
Danang - Quang Ngai
Quang Tri-Danang (Plan)
Quang Ngai-Quy Nhon (Plan)
Other Classified Road
Danang Bypass
National Highway
Provincial/District/City Roads
Provincial/District/City Road (Plan)
Railway
North-South Railway
LEGEND
Project Facilities
Thruway (Expressway)
Linking Road (New Construction)
Interchange (IC)
Viaduct
Major River Bridge
Tunnel
Traffic Management Center (TMC)
Expressway Operation Office (EOO)
Service Area (SA)
Parking Area (PA)
Toll Barrier (TB)
Toll Gate (TG)
Toll Plaza Office (TPO)
14B
PA, KM029+130
SA, KM069+600
TMC, KM000+950
Tuy Loan TPO
My Son
Ha Lam TPO
Tam Ky TPO
Chu Lai TPO
Dung Quat TPO
TB, KM129+800
14E
TPO
Quang Ngai TPO
TN01, KM022+900, L=2@540 m
Chiem Son Bridge (LRB09), KM020+185, L=410.00 m
VD02, KM010+271, L=90.20 m
Ky Lam Bridge (LRB08), KM017+662, L=962.00 m
VD07, KM018+319, L=86.20 m
VD08, KM018+612, L=62.15 m
VD09, KM018+831, L=86.20 m
Tra Bong Bridge (LRB19), KM109+320, L=452.00 m
VD17, KM110+120, L=492.00 m
VD20, KM128+180, L=292.00 m
VD19, KM127+200, L=652.00 m
Tra Khuc Bridge (LRB20), KM125+700, L=846.00 m
BP
EP
Length between ICs
Length by City/Province
Total Length
TB, KM004+750
District
District
Chu Lai
Road
Road
Industrial
Dung Quat
Industrial
Tra Bong-
Road
Provincial
Road
Provincial
Quang Ngai
City Ring Road
610
616
Road
623
Road
625
Quang Ngai
City
Road
Binh Long
EOO, KM064+750
PA, KM098+800
Binh Son
VD03, KM011+904, L=150.25 m
VD04, KM013+210, L=138.30 m
VD05, KM014+873, L=117.20 m
VD06, KM015+171, L=117.20 m
VD10, KM019+350, L=47.10 m
VD11, KM021+900, L=47.10 m
VD13, KM027+900, L=26.10 m
VD14, KM032+440, L=26.10 m
VD15, KM034+120, L=70.15 m
VD16, KM105+328, L=36.00 m
VD18, KM124+400, L=412.00 m
VD12, KM027+000, L=34.10 m
L=42.00 m
Thruway (Embankment Section, Initial Stage&Ultimate Stage)
Thruway (Cutting Section, Initial Stage&Ultimate Stage)
Thruway (Bridge Section, Initial Stage&Ultimate Stage)
Thruway (Tunnel Section, Initial Stage&Ultimate Stage)
Linking Road (Embankment Section, Initial Stage)
Linking Road (Bridge Section, Initial Stage)
Culvert
Frontage Road
TPO
North TPO
Quang Ngai
-KM000+120, L=49.10 m
VD01 (Widening),
VD21, KM134+726
KM139+500
Linking Road L=8.0 km

## Fig.A.5
Lender
Operator
User
CPC/PPCs
Ministries
MOT
MOF
VEC
MONRE
MOPS
DOFPPs
Road user
DONREs
DOLAs
DOTPs
DOTs
WB/JICA
Repay loans
Pay taxes
Repay loans
Provide services/
pay toll
Transfer
taxes
Report environ. conditions/
instruct correction
Lease ROW/
pay lease fee
Provide facilities and equip./
provide emergency services
Provide facilities
and equipment/
control traffic
violators
See Note 1)
Note 1):
(O&M unit)
Various administrative arrangements such as level of services and its inspection system, accounting and auditing systems,
toll rate setting and subsidies

## Fig.A.6
Stage
WB/JICA
VEC/PMU85
D/D
Contractors
Consultants
DONREs
MONRE
Construction
Operation
- Supervise and advise to task team (WB: QACU/Safeguard team in regional office, JICA: ESCRD)
- Concur updated EIA
- Approve updated EIA
- Evaluate the Project (WB: OED, JICA: ED)
- Implement EMP
- Assist in updating EIA
- Supervise EMP implementating
- Review and comment to monitoring
- Update EIA
- Monitor (third party)
- Manage EMP implementating
- Assist in monitoring (2 years)
- Evaluate the Project (2 years later)
- Monitor (O&M unit under VEC)
- Review and comment to monitoring
- Conduct interim review (1-2 times/year)
- Review and comment to monitoring
- Review and comment to monitoring (2 years)
Entrust/Report
Internal
External Monitoring
Monitoring

## Fig.A.7
Stage
WB/JICA
VEC/PMU85
Consultants
CPC/PPCs
MOT
D/D
Construction
Operation
- Assist in CPCSR and monitoring activities
- Approve CPCSR and supervise enforcing
- Prepare RMP and monitor enforcing
- Review and comment to monitoring
- Monitor (third party)
- Review and comment to monitoring
DPCs
- Prepare and enforce CPCSR (CARBs)
Entrust/Report
- Supervise and advise to task team (WB: QACU/Safeguard team in regional office, JICA: ESCRD)
- Evaluate the Project
- Conduct interim review (1-2 times/year)
- Assist in conducting survey and preparing support plan
- Conduct post-resettlement survey (third party)
(WB: OED, JICA: ED)
- Manage survey and notify to conduct support plan
Entrust/Report
- Instruct to conduct support plan to PAPs
- Review and comment to surveying and planning
- Review and comment to surveying and planning
- Conduct interim review (1-2 times/year)
- Conduct support plan to PAPs (CARBs)
- Concur CPCSR
External Monitoring
Internal
Monitoring
- Prepare support plan to PAPs (third party)
- Concur survey and support plans to PAPs
- Deliberate and supervise CPCSR (DRCs)

## Fig.A.8
The World Bank (WB)
Japan International Cooperation Agency (JICA)
Government of Vietnam (GOVN)
Quang Nam PPC
O&M Unit (to be established)
Ministry of Transport (MOT)
Danang CPC
Funding Agency
Consultant/Contractor
Other Stakeholders
Quang Ngai PPC
C/S Consultant
JICA Section
D/D Consultant (This Consulting Services)
C/S Consultant
WB Section
Funding Agency
Project Implementing Agency
Project Management Unit No. 85 (PMU85)
Project Owner
Contractors
Contractors
WB Section
Project Management Unit No. 1 (PMU1)
D/D and JICA Section
Vietnam Expressway Corporation (VEC)
D/D

## Fig.A.9
No. | Activities |  |  | Months | 2010 | 2011 | 2012 | 2013 | 2014 | 2015
1 | Common |  |  | - |  |  | Opening of the Project Road
11 |  | Loan Sign/Effectiveness | WB | -
12 |  |  | JICA | -
2 | GOVN Packages (PKG02, PKG09, PKG14) |  |  | 28
21 |  | Approval of the GOVN Packages | by GOVN, MONRE, WB | -
22 |  | Detailed Engineering Design | Detailed Engineering Design | 3
23 |  |  | Procurement Assistance (Contractors) | 1
24 |  | Land Acquisition and Resettlement |  | 4
25 |  | Procurement | C/S Consultant (Single Source Selection) | 1
26 |  |  | Contractors (Single Source Selection) | 1
27 |  | Construction Supervision |  | 24
28 |  | Construction Works | Civil Works | 24
3 | WB Packages (PKG08, PKG10-PKG13, PKG15-PKG16) |  |  | 56
31 |  | Detailed Engineering Design | Detailed Engineering Design | 12
32 |  | Land Acquisition and Resettlement |  | 10
33 |  | Procurement | C/S Consultant (International Competitive Bidding) | 5
34 |  |  | Contractors (International Competitive Bidding) | 5
35 |  | Construction Supervision |  | 44
36 |  | Construction Works | Civil Works | 44
4 | JICA Packages (PKG01, PKG03-PKG07, PKG17-PKG18) |  |  | 58
41 |  | Detailed Engineering Design | Detailed Engineering Design | 12
42 |  | Land Acquisition and Resettlement |  | 10
43 |  | Procurement | C/S Consultant (International Competitive Bidding) | 5
44 |  |  | Contractors (International Competitive Bidding) | 5
45 |  | Construction Supervision |  | 46
46 |  | Construction Works | Civil Works | 44
47 |  |  | Electrical Facilities and ITS/O&M Building Works | 33
48 |  |  | O&M Equipment Procurement | 28

## Fig.A.10
[5 empty] | Calender Year |  |  |  | 2011 | [5 empty] | 2012
[5 empty] | Calender Month |  |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
[5 empty] | Cumulative Month |  |  |  | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Basic Design/Detailed Engineering Design and Procurement Planning
Part B Project Management | [7 empty] | 14 months
|  | B.1 |  | Establish and control practical project management system |  |  |  | 14 months
Part C Previous Studies Review and Establishing Detailed Engineering Design Framework | [7 empty] | 2 months
|  | C.1 |  | Review previous studies |  |  |  | 2 months
|  | C.2 |  | Establish detailed engineering design framework |  |  |  | 1 months
Part D Detailed Engineering Design and Procurement Planning | [7 empty] | 14 motnhs
| D.1 |  |  | Contract Packaging |  |  |  | 1 months
|  | D.1.1 |  | Propose contract packaging |  |  |  | 1 months
| D.2 |  |  | Surveys and Investigations |  |  |  | 9.5 months
|  | D.2.1 |  | Collect relevant data and documents |  |  |  | 1 months
|  | D.2.2 |  | Conduct topographic survey |  |  |  | 7.5 months
|  |  |  | - Control point survey |  |  |  | 1.5 months
|  |  |  | - Priority sections (planimetric survey only) |  |  |  | 0.5 months
|  |  |  | - River bridge sections (all survey items) |  |  |  | 1.5 months
|  |  |  | - Other surveys |  |  |  | 4 months
|  |  |  | - ROW survey |  |  |  | 1 months
|  | D.2.3 |  | Conduct hydrological survey and analysis |  |  |  | 3 months
|  |  |  | - Flood record survey |  |  |  | 1 months
|  |  |  | - Hydrological and inundation analyses |  |  |  | 3 months
|  | D.2.4 |  | Conduct geotechnical and geological investigations |  |  |  | 5 months
|  | D.2.5 |  | Conduct material source survey |  |  |  | 2 months
|  | D.2.6 |  | Conduct relevant facilities survey |  |  |  | 3 months
|  | D.2.7 |  | Review traffic forecasting and conduct baseline surveys |  |  |  | 3 months
|  | D.2.8 |  | Conduct independent land valuation survey |  |  |  | 2 months
|  | D.2.9 |  | Conduct environmental and social surveys |  |  |  | 8 months
| D.3 |  |  | Civil Engineering Design |  |  |  | 15 months
|  | D.3.1 |  | Prepare basic design of civil structures |  |  |  | 5 months
|  |  |  | - Horizontal alignment study (all thruway bridges) |  |  |  | 0.5 months
|  |  |  | - Site survey |  |  |  | 0.5 months
|  |  |  | - Horizontal Alignment study (whole thruway) |  |  |  | 1 months
|  |  |  | - Other basic design works |  |  |  | 4 months
|  | D.3.2 |  | Prepare detailed engineering design of civil structures |  |  |  | 10 months
|  |  |  | - Detailed engineering design (3 prioritized contract packages) |  |  |  | 5 months
|  |  |  | - Detailed engineering design (other contract packages) |  |  |  | 8 months
|  |  |  | - Appraisal |  |  |  | 5 months
| D.4 |  |  | O&M Plan and Design |  |  |  | 7 months
|  | D.4.1 |  | Prepare institutional and administrative arrangement plan |  |  |  | 2 months
|  | D.4.2 |  | Prepare O&M plan |  |  |  | 3 months
|  | D.4.3 |  | Prepare basic design of O&M buildings |  |  |  | 3 months
| D.5 |  |  | ITS Plan and Design |  |  |  | 5 months
|  | D.5.1 |  | Prepare ITS plan |  |  |  | 2 months
|  | D.5.2 |  | Prepare basic design of ITS facilities |  |  |  | 3 months
| D.6 |  |  | Electrical Facilities Design |  |  |  | 5 months
|  | D.6.1 |  | Prepare detailed engineering design of electrical facilities |  |  |  | 5 months
| D.7 |  |  | Public Utilities Relocation Plan |  |  |  | 2 months
|  | D.7.1 |  | Prepare relocation plan of public utilities |  |  |  | 2 months
| D.8 |  |  | Safeguards |  |  |  | 14 months
|  | D.8.1 |  | Assist in updating EIA and EMP |  |  |  | 8 months
|  | D.8.2 |  | Assist in preparing and enforcing CPCSR |  |  |  | 14 months
| D.9 |  |  | Construction Planning |  |  |  | 7 months
|  | D.9.1 |  | Prepare construction plan |  |  |  | 7 months
| D.10 |  |  | Project Cost Estimate |  |  |  | 11 months
|  | D.10.1 |  | Estimate Project cost |  |  |  | 11 months
| D.11 |  |  | Procurement Documents |  |  |  | 12 months
|  | D.11.1 |  | Prepare procurement documents |  |  |  | 12 months
| D.12 |  |  | Project Implementation Program |  |  |  | 1 months
|  | D.12.1 |  | Prepare Project I/P |  |  |  | 1 months
E Technology Transfer | [7 empty] | 14 months
|  | E.1 |  | Provide training to VEC/PMU85 |  |  |  | 4 months
|  | E.2 |  | Provide training to the key local professional staff |  |  |  | 14 months
: Rainy season
[5 empty] | Calender Year |  |  |  | 2011 | [5 empty] | 2012
[5 empty] | Calender Month |  |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
[5 empty] | Cumulative Month |  |  |  | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Basic Design/Detailed Engineering Design and Procurement Planning
Reports/ |  |  | Inception Report |  |  | 30 copies | (English: 15, Vietnamese: 15)
Documents |  |  | Previous Studies Review Report |  |  | 60 copies | (English: 15, Vietnamese: 15)*2
|  |  | Detailed Engineering Design Framework |  |  | 30 copies | (English: 15, Vietnamese: 15)
|  |  | Monthly Progress Report |  |  | 420 copies | (English: 15, Vietnamese: 15)*14
|  |  | Brief Report on Appropriateness of the F/S Alignment |  |  | 30 copies | (English: 15, Vietnamese: 15)
|  |  | Updated draft EIA and EMP |  |  | 30 copies | (English: 15, Vietnamese: 15)
|  |  | Draft Final Updated EIA and EMP |  |  | 30 copies | (English: 15, Vietnamese: 15)
|  |  | Comprehensive Plan on Compensation, Support and Resettlement |  |  | 90 copies | (English: 15, Vietnamese: 15)*3
|  |  | Basic Design Report (Civil, Draft Design Report) |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Design Report |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Pre-qualification Document |  |  | 96 copies | (English: 03, Vietnamese: 03)*16
|  |  | Bidding Documents |  |  | 96 copies | (English: 03, Vietnamese: 03)*16
|  |  | Road Safety Audit Report |  |  | 30 copies | (English: 15, Vietnamese: 15)
|  |  | Draft Final Project Completion Report |  |  | 30 copies | (English: 15, Vietnamese: 15)
|  |  | Project Completion Report |  |  | 30 copies | (English: 15, Vietnamese: 15)
Technical |  |  | Contract Packaging |  |  | 6 copies | (English: 03, Vietnamese: 03)
Reports |  |  | Relevant Data and Documents |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Topographic Survey Report |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | ROW Survey Report |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Flood Record Survey Report |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Hydrological Survey and Analysis Report |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Geotechnical Investigation Report |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Geological Profile Map (Tunnel Section) |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Material Source Survey Report |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Relevant Facilities Survey Report (Design Controls) |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Traffic Forecasting Review Report |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Baseline Survey Report (Additional Traffic Survey) |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Independent Land Valuation Survey Report |  |  | 12 copies | (English: 06, Vietnamese: 06)
|  |  | Environmental and Social Survey Report (Site Investigation) |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Design Criteria and Conditions (Civil Engineering Design) |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Standard Design (Culvert Works) |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Standard Design (Bridge Works) |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Standard Design (Revetment and River Bank Protection Works) |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Standard Design (Road Accessory) |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Standard Design (Pavement Works) |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Standard Design (Slope Protection Works) |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Standard Design (Softgound Treatment) |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Standard Design (Drainage Works) |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Standard Design (Bridge Temporary Facility Works) |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Alignment Study Report |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Comparative Study Report (Major Bridges) |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Comparative Study Report (Interchanges) |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Working Design Reports |  |  | 96 copies | (English: 03, Vietnamese: 03)*16
|  |  | Quantity Reports |  |  | 96 copies | (English: 03, Vietnamese: 03)*16
|  |  | Institutional and Administrative Arrangement Plan |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | O&M Plan |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | ITS Plan |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Public Utilities Relocation Plan |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Draft TOR (External Environmental Monitoring) |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Resettlement Monitoring Plan (Inception Report) |  |  | 12 copies | (English: 06, Vietnamese: 06)
|  |  | Draft TOR (External Resettlement Monitoring) |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Construction Plan |  |  | 90 copies | (English: 03, Vietnamese: 03)*15
|  |  | Cost Estimate Conditions |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Cost Estimate Report |  |  | 96 copies | (English: 03, Vietnamese: 03)*16
|  |  | Procurement Plan |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Training Plan |  |  | 6 copies | (English: 03, Vietnamese: 03)
|  |  | Training Materials |  |  | 24 copies | (English: 03, Vietnamese: 03)*4
Basic Design (4)
Detailed Engineering Design and Procurement Planning (10)
For B/D (4.5)
For D/D (5)
B/D (5)
D/D (10)
Plan (4)
B/D (3)
B/D (3)
Plan (2)
D/D (5)
Basic Design (4)
Detailed Engineering Design and Procurement Planning (10)
(O&M and ITS)
(Each province)
(3 prioritized contract packages)
(Other contract packages)
(3 prioritized contract packages)
(Other contract packages)
(3 prioritized contract packages)
(Other contract packages)
(3 prioritized contract packages)
(Other contract packages)
(3 prioritized contract packages)
(Other contract packages)
(PM. safeguards)
(Road safety)
(Expressway administration, O&M, ITS and ETC systems)

## Fig.A.11
LEGEND
| : | Project Owner
| : | Project Implementing Agency
| : | Home Office Support
| : | Consultant Team
Nippon Koei Co., Ltd. Head Office
Home Office Support
Consultant Team
Key Professional Staff
Project Management Unit No.85
(PMU85)
Executing Agency
Management
Project Manager/Team Leader
Co-Project Manager
Civil Design Team (CID)
Design Group (DEG)
Section Design (SED)
Road Design 1 (RDD1, PKG1-7, L=65.0 km)
Interchange Design (ICD)
Major Bridges Design (MBD)
Tunnel Design (TND)
Geotechnical Design (GTD)
Drainage Design (DRD)
Revetment and River Bed Protection Design (RRD)
Pavement Design (PVD)
Survey Group (SUG)
O&M and ITS Team (OMI)
Topographic Survey (TPS)
Core Team (COR)
Team (MGT)
Civil Design Management (CDM)
Road Design 2 (RDD2, PKGA1-A5, L=74.5 km)
Material Sources Survey (MLS)
Geotechnical Survey (GTS)
Hydrological Survey (HDS)
Traffic Survey (TRS)
Supporting Staff
Supporting Group 1 (SPG1)
Supporting Group 2 (SPG2)
Supporting Group 3 (SPG3)
Note: COR consists of representatives of each team
O&M (OAM)
Electrical Facility and ITS Design (EID)
Environmental Team (ENV)
Cost and Document Team (COD)
Cost Estimate (COS)
Document (DOC)
Social and Environmental (SAE)
Resettlement (RES)
Supporting Group 4 (SPG4)
Bridge Temporary Facility Design (TFD)
Training Team (TRG)
Vietnam Expressway Corporation
(VEC)
Owner
SPG1
SPG2
SPG3
SPG1
SPG4
SPG4

## Fig.A.12
Consultant Team
Project Manager/Team Leader, Ichizuru ISHIMOTO
Management Team (MGT)
Civil Design Team (CID)
O&M and ITS Team (OMI)
Cost and Document Team (COD)
NK Representative Office in Hanoi
Chief Representative, Masanobu SAKAMOTO
Report/Coordination
WB Representative Office in Hanoi
(1) Technical Support
(2) Managerial Support
(3) Operational Support
Overseas Consulting Administraion
Domestic Consulting Administraion
Systems Engineering Department
Technology/Knowledge
Technology Management Administraion
Advanced Technology
Total Quality Control under ISO 9001/14001
NK Head Office in Tokyo
Environmental Team (ENV)
Training Team (TRG)
Chief Engineers' Group
Transportation Engineering Department
Logistic & Operations Department
Research & Development Center

## Fig.B.1
(3) Prepare the Services management plan
(1) Define the Services
(2) Prepare the primary Services scope statement
- Scope management
- Schedule managament
- Cost managament
- Quality managament
- Staffing managament
- Communication managament
- Procurement managament
(4) Kick-off meetings
(8) Close the Services
- Environmental factors of the Firms
- Organizational process assets (see A.2.4(1)(c))
*) Inception report
*) Monthly progress reports
- Proposals and contract of the Services
(5) Direct and manage the Services execution
(6) Monitor and control the Services
(7) Control integrated changes
Update
scope statement
Administrative
closure procedure
Process Groups
Initiating
Planning
Executing
Monitoring/
Controlling
Closing
Inputs
Work Items
Reports
the Services
Feedback to
process assets
the organizational
Update
management plan
the Services
- Integration management
- Risk managament
*) Several reports/documents
- Safety management
- Environmental management
- Financial management
- Claim management
(see A.2.3)
Construction
Extension
*) D/F project completion report
*) Project completion report

## Fig.C.1
(1) Review previous studies (civil)
(2) Review previous studies (O&M and ITS)
*) Previous studies review report (civil)
- Previous study reports
Inputs
Work Items
Reports
- Related Decisions and documents for the Project
- EIA and RAP
*) Previous studies review report (O&M and ITS)

## Fig.C.2
(1) Establish detailed engineering design framework
*) Detailed engineering design framework
*) Previous studies review report (civil)
Inputs
Work Items
Reports
*) Inception report

## Fig.D.1
- Current F/S
(1) Propose contract packaging
*) Contract packaging
Inputs
Work Items
Reports
- Related Decisions and documents for the Project

## Fig.D.2
- Current F/S
(1) Collect relevant data and documents
*) Relevant data and Documents
Inputs
Work Items
Reports
- EIA and RAP

## Fiｇ.D.3
Inputs
Work Item
Reports
Interchange1)
Others
- Previous studies review (C.1(1))
Thruway
Note 1): Include the toll plaza and buildings in IC
Note 2): Include receiving the entry permission letter from the PCs
(1) P/Q, contract negotiation and signing of sub-contractors
*) P/Q (topographic, sub-contractor)
(2) Work Plan 1 (1st Priority)
*) Work Plan 1 (Topographic, 1st Priority)
(3) Kick-off meeting2)
(5) 1st Priority Survey (Item A: Control point and leveling network)
(4) Mobilization (ItemD: Mobilization and temporary campyard)
(6) Work Plan 2 (2nd Priority)
*) Work Plan 2 (Topographic, 2nd Priority)
- Study bridge horizontal alignment (D.3.1(*))
(7) 2nd Priority Survey (Item 3.1: Planimetric (Main Line))
- Study survey centerline (D.3.1(*))
*) Work Plan 3 (Topographic, 3rd Priority)
(8) Work Plan 3 (3rd Priority)
(9) 3rd Priority Survey 1 (Item 5,12: Bridge (River Bridge only))
(10) 3rd Priority Survey 2
- Item 03: Main Line (excl. (7) and Item 3.3: Cross-section)
- Item 04: Tunnel
- Item 05: Bridge (excl. Flyover)
- Item 11: Main Line (excl. Item 11.3: Cross-section)
- Item 12: Bridge (excl. (9))
*) Basic Design Report
(12) Non-priority Survey
- Item 03: Main Line (Item 3.3: Cross-section)
- Item 06: Culvert Box (excl. (13))
- Item 07: Culvert Pipe (excl. (13))
- Item 13: Culvert Box
- Item 14: Culvert Pipe
- Item 11: Main Line (Item 11.3: Cross-section)
(11) Work Plan 4 (Non-priority)
(13) Non-priority Survey
- Item 06: Culvert Box (excl. (12))
- Item 07: Culvert Pipe (excl. (12))
- Item 09: Interchange
(14) Non-priority Survey
- Item 08: Canal (Re-alignment)
- Item 10: Building
- Item 15: Intersection (NH1A)
(15) Work Plan 5 (ROW Survey)
(16) ROW Survey (Provisional Sum)
*) Topographic Survey Report
*) Work Plan 4 (Topographic, 4th Priority)
*) Work Plan 5 (ROW Survey)
*) ROW Survey Report
*) Public Utilities Relocation Plan
後日検討
- Site Investigation (D.2.3(1))

## Fig.D.4
Inputs
Work Item
Reports
(1) Site Investigation
(9) Inundation analysis
(10) Cost-benefit analysis
- Previous Studies Review (C.1)
- Existing flood map
- Profile (Offshore) (Item 5.5, D.2.2)
*) Hydrological Survey and Analysis Report
(6) Rainfall Analysis
Update River Profile and
(5) Data Collection
(2) P/Q, Contract Negotiation and
*) P/Q (Hydrological Survey)
Signing with Sub-contractors
(4) Hydrological Survey
*) Hydrological Survey Report
(7) Runoff Analysis
(8) River Flow Capacity Estimation
Cross-section Survey Points
- River Cross-section (Item 5.8, D.2.2)
- River Profile (Item 5.7, D.2.2)
(3) Work Plan (Hydrological Survey)
*) Work Plan (Hydrological Survey)

## Fig.D.6
Inputs
Work Item
Reports
(3) P/Q, contract negotiation and signing of sub-contractors
(1) Site Investigation
(2) Work Plan 1
(4) Kick-off Meeting1)
(5) Geotechnical and Geological Investigations
*) P/Q (Geotechnical, sub-contractor)
*) Work Plan (Geotechnical)
*) Geological Profile Map (Tunnel Section)
*) Geotechnical Investigation Report
Note 1): Include receiving the entry permission letter from the PCs
- Previous studies review (C.1(1))
- D/D Framework (C.1(2))
- Basic Design of Civil Structures (D.3.1)
- Detailed Engineering Design of Civil Structures (D.3.2)
- O&M Plan (D.4.2)

## Fig.D.7
Inputs
Work Item
Reports
(3) P/Q, contract negotiation and signing of sub-contractors
(1) Site Investigation with Local PCs
(2) Work Plan
(4) Kick-off Meeting1)
(5) Material Source Survey
*) P/Q (Material, sub-contractor)
*) Work Plan (Material)
*) Material Source Survey Report
- Previous studies review (C.1(1))

## Fig.D.11 (2)
Inputs
Work Item
Reports
(1) Site Survey Plan
(2) Environmental and Social Surveys (Site Survey)
*) Environmental and Social Survey Report (Site Survey)
- Previous studies review (C.1(1))

## Fig.D.8
Inputs
Work Item
Reports
(1) Meeting with Local PCs
(2) Site Survey
*) Relevant Facilities Survey Report (Design Controls)
- Previous studies review (C.1(1))
- Relevant Data and Documents (D.2.1)

## Fig.D.10
Inputs
Work Item
Reports
- Previous studies review (C.1(1))
(2) P/Q, contract negotiation and signing of sub-contractors
(1) Work Plan
(3) Kick-off Meeting1)
(4) Independent Land Valuation Survey Report
*) P/Q (Independent Land Valuation Survey, sub-contractor)
*) Work Plan (Independent Land Valuation Survey)
*) Independent Land Valuation Survey Report

## Fig.D.11
Inputs
Work Item
Reports
(1) Site Survey Plan
(2) Environmental and Social Surveys (Site Survey)
*) Environmental and Social Survey Report (Site Survey)
- Previous studies review (C.1(1))

## Fig.D.12
Inputs
Work Item
Reports
(1)
**) Design Criteria and Conditions (Civil 1)
- Previous Studies Review (C.1(1))
- Detailed Engineering Design Framework (C.1(2))
Civil Design Management (CDM)
Design Group (DEG)
Section Design (SED)
Other Teams (ICD, MBD, TND, RRD)
(4)
(5)
- Planimetric Survey (D.2.2, Items 3.1/5.2-3, 2nd Priority)
- Planimetric Survey (D.2.2, Items 3.1/4.1/5.2-3/11.1, 3rd Priority)
**) Alternative Alignment Study Reports
**) Geometric Design Report (Thruway, Horizontal)
(50)
**) Basic Design Report (Civil, Draft Design Report)
(46) Design Drawings (B/D)2)
1) Rivision of Thruway Geometric Design and Culvert and Bridge Plan in accordance with Hydrological Survey and Analysis (D.2.3)
Note:
(8)
(9)
- Profile Survey (D.2.2, Items 3.2/5.4-5/11.2, 3rd Priority)
- Cross-section Survey (D.2.2, Items 3.3/5.6/11.3, 3rd Priority)
(6)
(13)
(14)
(16)
(10)
(11)
(23)
(24)
(25)
(20)
(21)
(22)
Geometric Design (Thruway, Horizontal)
Alternative Alignment Study
Design Criteria and Conditions (Civil 1)
Crossing Plan ( for Roadway/Waterway/HVL)
Frontage Road Plan
Geometric Design (Thruway, Vertical)
**) Crossing Plan (for Roadway/Waterway/HVL)
**) Frontage Road Plan
Bridge Plan (Thruway Bridges)
Standard Design (Bridge Works)
Comparative Study (Major River Bridges)
Tunnel Portal Location Plan
**) Geometric Design Report (Thruway, Vertical)
**) Tunnel Plan
**) Comparative Study Report (Major River Bridges)
**) Bridge Plan (Thruway Bridges)
**) Alternative Study Report (Interchange Location)
Tunnel Cross Section
Alternative Study (Interchange Location)
- Hydrological Survey and
- Engineering Geological Survey
TND
TND
MBD
- River Profile Survey (D.2.2, Items 5.7/12.7, 3rd Priority)
- River Cross-section Survey (D.2.2, Items 5.8/12.8, 3rd Priority)
(D.2.4, Items 3/11 Bridge (BR))
ICD
ICD
**) Comparative Study Report (Interchange Type)
**) Interchange Plan (Based on Satellite Photo)
Comparative Study (Interchange Type)
Interchange Plan (Based on Satellite Photo)
Scoring Analysis
Stndard Design
RRD
Revetment/River Protection Plan
**) Revetment/River Bed Protection Design Report
(Rivetment/River Protection Works)
Analysis (D.2.3)
(41)
Culvert Plan
**) Culvert Plan (Thruway)
(27) Revision (B/D)1)
2) Thruway Plan and Profile, Typical Cross Sections and General View (Thruway Bridges)
SED/MBD
SED/MBD
Basic Design Report (Civil, Draft Design Report)
**) Standard Design (Bridge Works)
(3)
Typical Cross Sections
**) Typical Cross Sections
- Relevant Facilities Survey (D.2.6)

## Fig.D.13
(2)
Inputs
Work Item
Reports
Civil Design Management (CDM)
Design Group (DEG)
SED, ICD, MBD, TND, TFD
GTD, DRD, PVD
GTD/DRD/TFD/PVD
**) Design Criteria and Conditions (Civil 2, Others)
- Previous Studies Review Report (Civil)
- Detailed Engineering Design Framework
- Basic Design Report (Civil, Draft Design Report)
(47) Design Drawings (D/D)
SED/ICD/MBD/TND/GTD/DRD/TFD/PVD
(49) Quantity Taking-off
**) Quantity Reports
SED/ICD/MBD/TND/GTD/DRD/TFD/PVD
(51)
Working Design Reports
(52)
Design Report
**) Working Reports
**) Design Report
(38)
(40)
(39)
Drainage Analysis
Stndard Design (Drainage Works)
DRD
Drainage Plan
**) Drainage Design Report
(36)
(37)
Standard Design (Pavement Works)
Pavement Plan
PVD
**) Pavement Design Report
(28)
(29)
(30)
Slope Stability Analysis
Standard Design (Slope Protection Works)
GTD
Slope Protection Plan
**) Slope Protection Design Report
(33)
(34)
(35)
Consolidation/Stability Analysis
Standard Design (Softground Treatment)
GTD
Softground Treatment Plan
**) Softground Treatment Design Report
(19)
Bridge Temporary Facility Plan
MBD/TFD
(18)
Standard Design
TFD
(17)
SED/MBD
(7)
Geometric Design (Others)
(15)
Bridge Plan (Other Bridges)
(12)
Tunnel Supporting Plan
(26)
Geometric Design (Interchange)
Structural Design (Bridge)
(Bridge Temporary Facility Works)
Design Criteria and Conditions (Civil 2, Others)
**) Hydrological Survey and Analysis (D.2.3, for (38))
**) Material Source Survey (D.2.5, for (36))
**) Traffic Forecasting Review and Baseline Survey (D.2.7, for (36)/(37))
**) Engineering Geological Survey (D.2.4, Items 7/8, for (28))
**) Engineering Geological Survey (D.2.4, Items 3/5/6, for (33))
**) Engineering Geological Survey (D.2.4, Item 2, for (12))
TND
SED
ICD
(42)
Culvert Plan (Others)
SED
**) Planimetric Survey (D.2.2, Items 5.2/9.3, for (7)/(15)/(26))
**) Profile Survey (D.2.2, Items 5.4/9.4, for (7)/(15)/(26))
**) Cross-section Survey (D.2.2, Items 5.6/9.5, for (7)/(15)/(26))
(43)
Standard Design (Culvert Works)
(31)
Retaining Wall Plan
(32)
Standard Design (Retaining Wall)
SED
(45)
Road Accessory Plan
(44)
Standard Design (Road Accessory)
SED
**) Geometric Design Report (others), by (7)
**) Bridge Plan (Other Bridges), by (15)
**) Bridge Temporary Facility Design Report, by (18)/(19)
**) Retaining Wall Design Report, by (31)/(32)
**) Culvert Plan (Others), by (42)
**) Standard Design (Culvert Works), by (43)
**) Road Accessory Design Report, by (44)/(45)
(48)
Road Safety Audit
**) Road Safety Audit Report
**) Profile Survey (D.2.2, Items 6.1-2/7.1/13.1-2/14.1)
**) Cross-section Survey (D.2.2, Items 6.3/7.3)
Outsourcing Work Items: (17) Structural Design (Bridge), (19) Bridge Temporary Facility Plan, (26) Geometric Design (Interchange), (47) Design Drawings (D/D) (Bridge and Interchange Only), (49) Quantity Taking-off (Bridge and Interchange Only)

## Fig.D.xx1
Inputs
Work Item
Reports
(1) Prepare Design Criteria and Conditions
- Previous studies review (C.1(1))
(2) Prepare Electrical Facilities Plan
(3) Loading Analysis
(4) Prepare design drawings
*) Electrical Facilities Plan
*) Working Design Report
*) Design Criteria and Conditions (Electrical)
- Detailed Engineering Design Framework (C.1(2))
- Basic Design of Civil Structures (D.3.1)
- O&M Plan (D.4.2)
- ITS Plan (D.5.1)
(5) Quantity Taking-off

## Fig.D.xx2
Inputs
Work Item
Reports
(1) Confirm Existing Public Utilities
- Previous studies review (C.1(1))
(2) Prepare Relocation Plan with Relevant Agencies
**) Public Utilities Relocation Plan
- Topographic Survey (D.2.2)
- Relevant Facilities Survey (D.2.6)
- Basic Design of Civil Structures (D.3.1)

## Fig.D.xx3
Inputs
Work Item
Reports
(1) Prepare Construction Methods
- Previous Studies Review (C.1)
(4) Prepare Construction Schedule
- Detailed Engineering Design Framework (C.2)
- Contract Packaging (D.1.1)
- Surveys and Investigations
**) Construction Plan
(3) Prepare Procurement Plan
(2) Prepare Temporary Facility Plan
(D.2.1, D.2.3, D.2.5-7, D.2.9)
- Civil Engineering Design (D.3)
- Basic Design of O&M Buildings (D.4.3)
- Basic Design of ITS Facilities (D.5.2)
- Detailed Design of Electrical Facilities (D.6.1)
- EIA and EMP (D.8.1)

## Fig.D.xx3 (2)
Inputs
Work Item
Reports
(1) Comparative Study of the F/S Alignment
- Previous Studies Review (C.1)
(4) Prepare draft TOR for External Monitoring
**) Draft TOR (External Environmental Monitoring)
(3) Update the Updated Draft EIA and EMP
(2) Update the existing EIA and EMP
**) Brief Report on Appropriateness of the F/S Alignment
- Alternative Alignment Study (D.3.1(4))
**) Updated Draft EIA and EMP
**) Draft Final Updated Draft EIA and EMP
- Environmental and Social Surveys (D.2.9)
- Basic Design of Civil Structures (D.3.1)
- Material Source Survey (D.2.5)
- Detailed Design of Civil Structures (D.3.2)
- Construction Planning (D.9)

## Fig.D.xx3 (3)
Inputs
Work Item
Reports
(1) Prepare Resettlement Monitoring Plan
- Previous Studies Review (C.1)
(6) Internal Monitoring (CPCSR)
**) Resettlement Monitoring Plan (Inception Report)
- ROW Survey (D.2.2(16))
**) Internal Monitoring Report (CPCSR)
- Environmental and Social Surveys (D.2.9)
- Independent Land Valuation Survey (D.2.8)
(3) Assist in establishing Land Acquisition and Compensation Policy
(4) Assist in finalizing CPCSR
**) Comprehensive Plan on Compensation,
Support and Resettlement
(5) Assist in preparing draft TOR (External Resettlement Monitoring)
**) Draft TOR (External Resettlement Monitoring)
(2) Assist in updating Census of PAPs

## Fig.D.xx4
Inputs
Work Item
Reports
(1) Establish Cost Estimate Conditions
- Previous Studies Review (C.1)
(3) Inputs Quantities
- Detailed Engineering Design Framework (C.2)
**) Cost Estimate Reports
(2) Analyze General Unit Cost
- Civil Engineering Design (D.3)
- Basic Design of O&M Buildings (D.4.3)
- Basic Design of ITS Facilities (D.5.2)
- Detailed Design of Electrical Facilities (D.6.1)
- EIA and EMP (D.8.1)
(4) Estimate Project Cost
**) Cost Estimate Conditions
- Material Source Survey (D.2.5)
- Construction Plan (D.9.1)

## Fig.D.xx5
Inputs
Work Item
Reports
(1) Prepare Procurement Plan
(3) Prepare Bidding Documents
- Detailed Engineering Design Framework (C.2)
**) Bidding Documents
(2) Prepare Pre-qualification Documents
- Civil Engineering Design (D.3)
- Basic Design of O&M Buildings (D.4.3)
- Basic Design of ITS Facilities (D.5.2)
- Detailed Design of Electrical Facilities (D.6.1)
- EIA and EMP (D.8.1)
**) Procurement Plan
- Material Source Survey (D.2.5)
- Construction Plan (D.9.1)
**) Pre-qualification Documents
- Project I/P (D.12.1)
- Contract Packages (D.1.1)

## Fig.D.xx6
- Inception Report (A.1.10)
1) Confirm and Update the Current Project I/P
*) Project I/P
Inputs
Work Items
Reports
- Correct Relevant Data and Documents (D.2.1)

## Fig.E.1
Inputs
Work Item
Reports
1) Assist in announcing the P/Q invitations
**) P/Q evaluation reports
2) Assist in evaluating the P/Q applications
- Review and approve the P/Q documents by MOT
- Submit the P/Q applications by the applicants
3) Assist in notifying the P/Q evaluation results
- Review and approve the P/Q evaluation reports by MOT
- Review and concur the P/Q evaluation reports by WB/JICA
4) Assist in issuing the bidding documents
5) Assist in opening the pre-bid conference and site visits
6) Assist in issuing the clarification answers and addendum
- Inquiries by the bidders
8) Assist in opening the bids
9) Assist in evaluating the bids
**) Bid evaluation reports
- Review and approve the bid evaluation results by MOT
- Review and concur the bid evaluation results by WB/JICA
10) Assist in notifying the bid evaluation results
7) Assist in inviting for the bids
11) Assist in contract negotiations
**) Draft contract documents
12) Assist in preparing the contract documents
- Contract signing
- Review and approve the contract documents by MOT
- Review and concur the contract documents by WB/JICA
- Review and concur the P/Q documents by the WB/JICA
- Review and approve the bidding documents by MOT
- Review and concur the bidding documents by WB/JICA

## Fig.F.1
- Organizational Process Assets (A.2.4(1)(c)
1) Identify training needs with VEC/PMU85
*) Training plan
Inputs
Work Items
Reports
2) Prepare training plan
3) Prepare training materials
*) Training materials
4) Conduct workshops and overseas study tour
- Inception Report

## Fig.F.2
- Organizational Process Assets (A.2.4(1)(c)
Inputs
Work Items
Reports
1) Provide person-to-person technology transfer

## Tab.A.9
Tasks |  |  |  | MGT |  | CID | [43 empty] | OMI | [17 empty] | COD | [5 empty] | ENV | [6 empty] | TRG
[6 empty] | CDM | [5 empty] | DEG | [25 empty] | SUG | [11 empty] | OAM | [9 empty] | EID | [7 empty] | COS |  |  | DOC |  |  | SAE |  |  | RES
[12 empty] | SED | [9 empty] | ICD |  | MBD |  | TND |  | GTD |  |  |  | DRD |  | RRD |  | TFD | PVD/ |  | TPS |  | GTS |  |  |  | HDS |  |  |  | TRS
[12 empty] | RDD1 |  |  |  |  | RDD2 | [19 empty] | MLS
|  |  |  | Project Manager/Team Leader | Co-Project Manager | Senior Highway Engineer | Road Safety Audit Specialist | Senior Bridge Engineer | Highway Engineer 1-2 | Road Safety Audit Specialist | Bridge/Structural Engineer 1-2 | Highway Engineer 1 | Bridge/Structural Engineer 1 | Bridge/Structural Engineer 2 | Highway Engineer 3-4 | Bridge/Structural Engineer 3-4 | Highway Engineer 2 | Bridge/Structural Engineer 3 | Bridge/Structural Engineer 4 | Highway Engineer 5-6 | Bridge/Structural Engineer 5-6 | Senior Interchange Specialist | Interchange Specialist | Bridge/Structural Engineer 5 | Bridge/Structural Engineer 7 | Tunnel Engineer | Tunnel Engineer | Soil/Geotechnical Engineer 1 (Slope) | Soft Ground Treatment Specialist | Soil/Geotechnical Engineer 1 (Slope) | Soft Ground Treatment Specialist | Drainage Engineer | Drainage Engineer 1-2 | River Engineer | River Engineer | Bridge/Structural Engineer 6 | Pavement/Material Engineer | Pavement/material Engineer 1-2 | Survey Engineer | Senior Surveyor 1-3 | Soil/Geotechnical Engineer 2 | Geological Engineer (Tunnel) | Soil/Geotechnical Engineer 2-4 | Geological Engineer (Tunnel) | Senior Hydrologist | Inundation Analyst | Hydraulic Engineer 1-2 | Inundation Analyst | Transport Economist | Operating & Maintenance Specialist | Expressway Management Unit Specialist | Traffic Management Specialist | Asset Management Specialist | Architect | Operating & Maintenance Specialist | Expressway Management Unit Specialist | Traffic Management Specialist | Asset Management Specialist | Architect 1-2 | ITS Specialist | Communication System Engineer | Senior Electrical Engineer | Toll Collection System Specialist | ITS Specialist | Communication System Engineer | Electrical Engineer 1-2 | Toll Collection System Specialist | Construction Planner/Cost Estimator | Cost Estimator 1 | Cost Estimator 2-3 | Senior Procurement/Contract Specialist | Procurement/Contract Specialist 1 | Procurement/Contract Specialist 2 | Social and Environmental Specialist | Senior Environmental Specialist | Environmental Specialist | Resettlement Specialist | Senior Resettlement Specialist | Social and Resettlement Specialist | Cultural and Archaeological Specialist | Training Specialist | Training Specialist
|  |  |  | I1 | L1 | I2 | I3 | I4 | L2-L3 | L4 | L5-L6 | I5 | I6 | I7 | L7-L8 | L9-L10 | I8 | I9 | I10 | L11-L12 | L13-L14 | I11 | L15 | I12 | L16 | I13 | L17 | I14 | I15 | L18 | L19 | I16 | L20-L21 | I17 | L22 | I18 | I19 | L23-L24 | I20 | L25-L27 | I21 | I22 | L28-L30 | L31 | I23 | I24 | L32-L33 | L34 | L35 | I25 | I26 | I27 | I28 | I29 | L36 | L37 | L38 | L39 | L40-L41 | I30 | I31 | I32 | I33 | L42 | L43 | L44-L45 | L46 | I34 | L47 | L48-L49 | I35 | L50 | L51 | I36 | L52 | L53 | I37 | L54 | L55 | L56 | I38 | L57
Part B Project Management
|  | B.1 | Establish and control practical project management system | ● | ●
Part C Previous Studies Review and Establishing Detailed Engineering Design Framework
|  | C.1 | Review previous studies | ◎ | ◎ | ● |  | ● | ● |  | ● | [27 empty] | ● | ● |  |  |  |  | ● | ● | ● | ● | ● | ● | ● |  |  |  | ● | ● | [11 empty] | ● | ● |  |  |  |  | ● | ● | ● | ● | ● | ● | ●
|  | C.2 | Establish detailed engineering design framework | ● | ● | ● |  | ● | ● |  | ● | [56 empty] | ● | ● |  | ● | ●
Part D Detailed Engineering Design and Procurement Planning
| D.1 |  | Contract Packaging
|  | D.1.1 | Propose contract packaging | ● | ● | [62 empty] | ● | ● |  | ● | ●
| D.2 |  | Surveys and Investigations
|  | D.2.1 | Collect relevant data and documents | ◎ | ◎ | ● |  |  | ● | [58 empty] | ● | ● |  | ● | ●
|  | D.2.2 | Conduct topographic survey | ◎ | ◎ | [33 empty] | ● | ●
|  | D.2.3 | Conduct hydrological survey and analysis | ◎ | ◎ | [39 empty] | ● | ● | ● | ●
|  | D.2.4 | Conduct geotechnical and geological investigations | ◎ | ◎ | [20 empty] | ● | ● | [13 empty] | ● | ● | ● | ●
|  | D.2.5 | Conduct material source survey | ◎ | ◎ | [31 empty] | ● | ● |  |  | ● |  | ●
|  | D.2.6 | Conduct relevant facilities survey | ◎ | ◎ | ● |  | ● | ● |  | ● | ● |  |  | ● |  | ● |  |  | ● | [24 empty] | ● |  | ● |  | ● | [18 empty] | ● | [5 empty] | ● | ● | ●
|  | D.2.7 | Review traffic forecasting and conduct baseline surveys | ◎ | ◎ | ● | [42 empty] | ●
|  | D.2.8 | Conduct independent land valuation survey | ◎ | ◎ | [71 empty] | ● | ● | ●
|  | D.2.9 | Conduct environmental and social surveys | ◎ | ◎ | [68 empty] | ● | ● | ●
| D.3 |  | Civil Engineering Design
|  | D.3.1 | Prepare basic design of civil structures | ◎ | ◎ | ● |  | ● | ● |  | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | [6 empty] | ● | ●
|  | D.3.2 | Prepare detailed engineering design of civil structures | ◎ | ◎ | ● | ● | ● | ● | ● | ● | ● | ● |  | ● |  | ● | ● |  | ● |  | ● |  | ● |  | ● | ● | ● | ● | ● | ● | ● | ● |  |  | ● | ● | ●
| D.4 |  | O&M Plan and Design
|  | D.4.1 | Prepare institutional and administrative arrangement plan | ◎ | ◎ | [44 empty] | ● | ● |  |  |  | ● | ●
|  | D.4.2 | Prepare O&M plan | ◎ | ◎ | [44 empty] | ● | ● | ● | ● |  | ● | ● | ● | ●
|  | D.4.3 | Prepare basic design of O&M buildings | ◎ | ◎ | [48 empty] | ● |  |  |  |  | ●
| D.5 |  | ITS Plan and Design
|  | D.5.1 | Prepare ITS plan | ◎ | ◎ | [54 empty] | ● |  |  | ● | ● |  |  | ●
|  | D.5.2 | Prepare basic design of ITS facilities | ◎ | ◎ | [54 empty] | ● | ● |  | ● | ● | ● |  | ●
| D.6 |  | Electrical Facilities Design
|  | D.6.1 | Prepare detailed engineering design of electrical facilities | ◎ | ◎ | [56 empty] | ● |  |  |  | ●
| D.7 |  | Public Utilities Relocation Plan
|  | D.7.1 | Prepare relocation plan of public utilities | ◎ | ◎ | ● |  |  | ● | [52 empty] | ● |  |  |  | ●
| D.8 |  | Safeguards
|  | D.8.1 | Assist in updating EIA and EMP | ◎ | ◎ | [68 empty] | ● | ● | ●
|  | D.8.2 | Assist in preparing and enforcing CPCSR | ◎ | ◎ | [71 empty] | ● | ● | ● | ●
| D.9 |  | Construction Planning
|  | D.9.1 | Prepare construction plan | ◎ | ◎ |  |  | ● | [27 empty] | ● | [31 empty] | ●
| D.10 |  | Project Cost Estimate
|  | D.10.1 | Estimate Project cost | ◎ | ◎ | [62 empty] | ● | ● | ●
| D.11 |  | Procurement Documents
|  | D.11.1 | Prepare procurement documents | ◎ | ◎ | ● |  | ● | ● |  | ● | [42 empty] | ● |  |  |  |  | ● | ● | ● | ● | ● | ● | ● | ● | ● |  |  |  | ● | ● | ● | ● | ● | ●
| D.12 |  | Project Implementation Program
|  | D.12.1 | Prepare Project I/P | ● | ● | [62 empty] | ● | ● |  | ● | ●
Part E Technology Transfer
|  | E.1 | Provide training to VEC/PMU85 | ● | ● |  | ● |  |  | ● | [39 empty] | ● |  |  |  |  | ● |  |  |  |  | ● |  |  |  | ● | [9 empty] | ● | ● |  | ● | ● |  |  | ● | ●
|  | E.2 | Provide training to the key local professional staff | ● |  | ● | ● | ● |  |  |  | ● | ● | ● |  |  | ● | ● | ● |  |  | ● |  | ● |  | ● |  | ● | ● |  |  | ● |  | ● |  | ● | ● |  | ● |  | ● | ● |  |  | ● | ● |  |  |  | ● | ● | ● | ● | ● | [5 empty] | ● | ● | ● | ● |  |  |  |  | ● |  |  | ● |  |  | ● |  |  | ● |  |  |  | ●
◎: Management and Guidance ●: In-charge Red: Accountability for the Services Blue: Responsibility for the Team

## Tab.A.10
| Calender | [5 empty] | Calender Year |  |  |  |  | 2011 | [5 empty] | 2012 | [9 empty] | Duration | Proposal |  |  |  | Updated
[7 empty] | Calender Month |  |  |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
[7 empty] | Cumulative Month |  |  |  |  | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| Basic Design/Detailed Engineering Design and Procurement Planning | [26 empty] | 14
No |  |  |  | TOR | Position |  |  | Name |  | Firm | Home/ | 2011 | [5 empty] | 2012 | [9 empty] | Staff- | NK | NE | CD | TEC | NK | NE | CD | TEC
|  |  |  | 5.1 | [6 empty] | Field | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Months
[12 empty] | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Management Team (MGT)
I1 |  |  |  | 1 |  | Project Manager/Team Leader |  |  | Ichizuru Ishimoto | NK | [Field] | [16 empty] | 14.5 | NK: 14; NK: 14.5
Civil Design Team (CID)
Civil Design Management (CDM)
I2 |  |  |  | 2 |  | Senior Highway Engineer |  |  | Akira Magario | NK | [Field] | [16 empty] | 14 | NK: 13; NK: 14
I3 |  |  |  | 21 |  | Road Safety Audit Specialist |  |  | Takehiko Tsuji | NK | [Field] | [16 empty] | 3 | NK: 3; NK: 3
I4 |  |  |  | 5 |  | Senior Bridge Engineer |  |  | Yoshinori Abe | Chodai | [Field] | [16 empty] | 13 | CD: 13; CD: 13
Section Design (SED)
Road Design 1 (RDD1, PKG01-06, JICA Section)
I5 |  |  |  | 3 |  | Highway Engineer 1 |  |  | Koji Nakai | NK | [Field] | [16 empty] | 12.5 | NK: 12; NK: 12.5
I6 |  |  |  | 6 |  | Bridge/Structural Engineer 1 |  |  | Tetsuya Maeda | NK | [Field] | [16 empty] | 13 | NK: 12; NK: 13
I7 |  |  |  | 6 |  | Bridge/Structural Engineer 2 |  |  | Yoshiaki Nakakubo | Chodai | [Field] | [16 empty] | 4 | CD: 4; CD: 4
Road Design 2 (RDD2, PKG07-14, WB Section)
I8 |  |  |  | 3 |  | Highway Engineer 2 |  |  | Decha Sa-ngaunprasith | TEC | [Field] | [16 empty] | 12 | TEC: 12; TEC: 12
I9 |  |  |  | 6 |  | Bridge/Structural Engineer 3 |  |  | Hiroo Jin | NE | [Field] | [16 empty] | 12 | NE: 12; NE: 12
I10 |  |  |  | 6 |  | Bridge/Structural Engineer 4 |  |  | Yuichi Sano | NK | [Field] | [16 empty] | 4 | NK: 4; NK: 4
Interchange Design (ICD)
I11 |  |  |  | 4 |  | Senior Interchange Specialist |  |  | Chanchai Techashongs | TEC | [Field] | [16 empty] | 7 | TEC: 7; TEC: 7
Major Bridges Design (MBD)
I12 |  |  |  | 6 |  | Bridge/Structural Engineer 5 |  |  | Hiroyuki Yokoyama | Chodai | [Field] | [16 empty] | 11 | CD: 11; CD: 11
Tunnel Design (TND)
I13 |  |  |  | 11 |  | Tunnel Engineer |  |  | Wako Noto | NK | [Field] | [16 empty] | 4 | NK: 4; NK: 4
Geotechnical Design (GTD)
I14 |  |  |  | 7 |  | Soil/Geotechnical Engineer 1 (Slope) |  |  | Manoon Arayasiri | TEC | [Field] | [16 empty] | 2 | TEC: 2; TEC: 2
I15 |  |  |  | 8 |  | Soft Ground Treatment Specialist |  |  | Suvichai Methpreechakul | TEC | [Field] | [16 empty] | 3 | TEC: 3; TEC: 3
Drainage Design(DRD)
I16 |  |  |  | 23 |  | Drainage Engineer |  |  | Suntichai Horpaopan | TEC | [Field] | [16 empty] | 7 | TEC: 7; TEC: 7
Revetment and River Bed Protection Design (RRD)
I17 |  |  |  | 23 |  | River Engineer |  |  | Arristeo B. Rabajante | NK | [Field] | [16 empty] | 2 | NK: 2; NK: 2
Bridge Temporary Facility Design (TFD)
I18 |  |  |  | 6 |  | Bridge/Structural Engineer 6 |  |  | Akira Yanagisawa | Chodai | [Field] | [16 empty] | 7 | CD: 7; CD: 7
Pavement Design (PVD)/Material Sources Survey (MLS)
I19 |  |  |  | 9 |  | Pavement/Material Engineer |  |  | Bundit Kitsuwannarut | TEC | [Field] | [16 empty] | 4 | TEC: 4; TEC: 4
Topographic Survey (TPS)
I20 |  |  |  | 22 |  | Survey Engineer |  |  | Kazuhiro Ishizuka | NK | [Field] | [16 empty] | 6 | NK: 6; NK: 6
Geotechnical Survey (GTS)
I21 |  |  |  | 7 |  | Soil/Geotechnical Engineer 2 |  |  | Jirarote Piyapornpong | TEC | [Field] | [16 empty] | 5 | TEC: 5; TEC: 5
I22 |  |  |  | 23 |  | Geological Engineer (Tunnel) |  |  | Seichiro Kanai | NK | [Field] | [16 empty] | 2 | NK: 2; NK: 2
Hydrological Survey (HDS)
I23 |  |  |  | 10 |  | Senior Hydrologist |  |  | Khadananda Lamsal | NK | [Field] | [16 empty] | 3 | NK: 3; NK: 3
I24 |  |  |  | 23 |  | Inundation Analyst |  |  | Silver Yance | NK | [Field] | [16 empty] | 3 | NK: 3; NK: 3
O&M and ITS Team (OMI)
O&M (OAM)
I25 |  |  |  | 18 |  | Operating&Maintenance Specialist |  |  | Shigeki Takahashi | NK | [Field] | [16 empty] | 4 | NK: 4; NK: 4
I26 |  |  |  | 19 |  | Expressway Management Unit Specialist |  |  | Yuichi Tsujimoto | NK | [Field] | [16 empty] | 2 | NK: 2; NK: 2
I27 |  |  |  | 23 |  | Traffic Management Specialist |  |  | Hisanori Tomitaka | NK | [Field] | [16 empty] | 2 | NK: 2; NK: 2
I28 |  |  |  | 23 |  | Asset Management Specialist |  |  | Kyoichi Takeuchi | NK | [Field] | [16 empty] | 2 | NK: 2; NK: 2
I29 |  |  |  | 23 |  | Architect |  |  | Yoshinori Yamazaki | NK | [Field] | [16 empty] | 3 | NK: 3; NK: 3
Electrical Facility and ITS Design (EID)
I30 |  |  |  | 15 |  | ITS Specialist |  |  | Koichi Nishimura | NK | [Field] | [16 empty] | 5 | NK: 5; NK: 5
I31 |  |  |  | 16 |  | Communication System Engineer |  |  | Masahiro Sakagami | NK | [Field] | [16 empty] | 3 | NK: 3; NK: 3
I32 |  |  |  | 12 |  | Senior Electrical Engineer |  |  | Eiji Matsuda | NK | [Field] | [16 empty] | 7 | NK: 7; NK: 7
I33 |  |  |  | 17 |  | Toll Collection System Specialist |  |  | Masashi Iwamoto | NK | [Field] | [16 empty] | 4 | NK: 4; NK: 4
Cost and Document (COD)
Cost Estimate (COS)
I34 |  |  |  | 23 |  | Construction Planner/Cost Estimator |  |  | Masayuki Iwashita | NK | [Field] | [16 empty] | 11 | NK: 11; NK: 11
Document (DOC)
I35 |  |  |  | 14 |  | Senior Procurement/Contract Specialist |  |  | Anothai Boonthikul | TEC | [Field] | [16 empty] | 12 | TEC: 12; TEC: 12
Environmental (ENV)
Social and Environmental (SAE)
I36 |  |  |  | 13 |  | Social and Environmental Specialist |  |  | Yasuhira Minami | NK | [Field] | [16 empty] | 4 | NK: 5; NK: 4
Resettlement (RES)
I37 |  |  |  | 13 |  | Resettlement Specialist |  |  | Vu Ngoc Long | NK | [Field] | [16 empty] | 8 | NK: 10; NK: 8
Training (TRG)
I38 |  |  |  | 20 |  | Training Specialist |  |  | Noppong Unhabhokha | TEC | [Field] | [16 empty] | 4 | TEC: 4; TEC: 4
Total | [10 empty] | [Field] | [16 empty] | 239 | 136 | 12 | 35 | 56 | 136 | 12 | 35 | 56
|  | : | Work in Danang office | [25 empty] | NK: 239; NK: 239
|  | : | Work in Hanoi office
Detailed Engineering Design and Procurement Planning (10)
Basic Design (4)

## Tab.A.11
| Calender |  |  |  |  | Calender Year |  |  |  |  | 2011 | [5 empty] | 2012 | [9 empty] | Duration | Proposal | Updated
[6 empty] | Calender Month |  |  |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
[6 empty] | Cumulative Month |  |  |  |  | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| Basic Design/Detailed Engineering Design and Procurement Planning | [25 empty] | 14
No |  |  | TOR | Position |  |  | Name |  | Firm | Home/ | 2011 | [5 empty] | 2012 | [9 empty] | Staff-
|  |  | 5.2 | [6 empty] | Field | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Months
[11 empty] | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Management Team (MGT)
L1 |  |  | 1 |  | Co-Project Manager |  |  | Le Kim An | NK | [Field] | [16 empty] | 14.5 | 14 | 14.5
Civil Design Team (CID)
Civil Design Management (CDM)
L2 |  |  | 2 |  | Highway Engineer 1 (Geometric) |  |  | Tran Dinh Van | NK | [Field] | [16 empty] | 13 | 13 | 13
L3 |  |  | 2 |  | Highway Engineer 2 (Road Structure) |  |  | Phan Dang Viet Anh | NK | [Field] | [16 empty] | 13 | 13 | 13
L4 |  |  | 22 |  | Road Safety Audit Specialist |  |  | Tran Quang Huy | NK | [Field] | [16 empty] | 3 | 3 | 3
L5 |  |  | 3 |  | Bridge/Structural Engineer 1 (Superstructure) |  |  | Le Toan Thang | NK | [Field] | [16 empty] | 13 | 13 | 13
L6 |  |  | 3 |  | Bridge/Structural Engineer 2 (Substructure/Foundation) |  |  | Dao Ngoc Vinh | NK | [Field] | [16 empty] | 13 | 13 | 13
Section Design (SED)
Road Design 1 (RDD1, PKG01-06, JICA Section)
L7 |  |  | 2 |  | Highway Engineer 3 (Geometric) |  |  | Le Thi Thanh Thuy | NK | [Field] | [16 empty] | 12 | 12 | 12
L8 |  |  | 2 |  | Highway Engineer 4 (Road Structure) |  |  | Vu Gia Hung | NK | [Field] | [16 empty] | 12 | 12 | 12
L9 |  |  | 3 |  | Bridge/Structural Engineer 3 |  |  | Do Hong Phuc | NK | [Field] | [6 empty] | (Outsource D/D to sub-consultants) | [9 empty] | 4 | 4 | 4
L10 |  |  | 3 |  | Bridge/Structural Engineer 4 |  |  | Pham Anh Kiet | NK | [Field] | [6 empty] | (Outsource D/D to sub-consultants) | [9 empty] | 4 | 4 | 4
Road Design 2 (RDD2, PKG07-14, WB Section)
L11 |  |  | 2 |  | Highway Engineer 5 (Geometric) |  |  | Nguyen Dinh Trung | NK | [Field] | [16 empty] | 12 | 12 | 12
L12 |  |  | 2 |  | Highway Engineer 6 (Road Structure) |  |  | Dao Manh Son | NK | [Field] | [16 empty] | 12 | 12 | 12
L13 |  |  | 3 |  | Bridge/Structural Engineer 5 |  |  | Le Kien Cuong | NK | [Field] | [6 empty] | (Outsource D/D to sub-consultants) | [9 empty] | 4 | 4 | 4
L14 |  |  | 3 |  | Bridge/Structural Engineer 6 |  |  | Tran Anh Tuan | NK | [Field] | [6 empty] | (Outsource D/D to sub-consultants) | [9 empty] | 4 | 4 | 4
Interchange Design (ICD)
L15 |  |  | 22 |  | Interchange Specialist |  |  | Le Thanh Hung | NK | [Field] | [6 empty] | (Outsource D/D to sub-consultants) | [9 empty] | 2 | 2 | 2
Major Bridges Design (MBD)
L16 |  |  | 3 |  | Bridge/Structural Engineer 7 |  |  | Pham Ngoc Tuan | NK | [Field] | [6 empty] | (Outsource D/D to sub-consultants) | [9 empty] | 3 | 3 | 3
Tunnel Design (TND)
L17 |  |  | 22 |  | Tunnel Engineer |  |  | Tran Phong Nha | NK | [Field] | [16 empty] | 4 | 4 | 4
Geotechnical Design (GTD)
L18 |  |  | 4 |  | Soil/Geotechnical Engineer 1 (Slope) |  |  | Quach Thi Thu | NK | [Field] | [16 empty] | 2 | 2 | 2
L19 |  |  | 22 |  | Soft Ground Treatment Specialist |  |  | Trinh Viet Linh | NK | [Field] | [16 empty] | 3 | 3 | 3
Drainage Design (DRD)
L20 |  |  | 22 |  | Drainage Engineer 1 |  |  | Nguyen Minh Ngoc | NK | [Field] | [16 empty] | 7 | 7 | 7
L21 |  |  | 22 |  | Drainage Engineer 2 |  |  | Nguyen Phuc Hoa | NK | [Field] | [16 empty] | 6 | 6 | 6
Revetment and River Bed Protection Design (RRD)
L22 |  |  | 22 |  | River Engineer |  |  | Nguyen Son | NK | [Field] | [16 empty] | 2 | 2 | 2
Pavement Design (PVD)/Material Sources Survey (MLS)
L23 |  |  | 5 |  | Pavement/Material Engineer 1 |  |  | Tran Trong Nghia | NK | [Field] | [16 empty] | 4 | 4 | 4
L24 |  |  | 5 |  | Pavement/Material Engineer 2 |  |  | Nguyen Viet Hai | NK | [Field] | [16 empty] | 4 | 4 | 4
Topographic Survey (TPS)
L25 |  |  | 8 |  | Senior Surveyor 1 |  |  | Vo Thanh Binh | NK | [Field] | [16 empty] | 7.5 | 6 | 7.5
L26 |  |  | 8 |  | Senior Surveyor 2 |  |  | Le Van Thu | NK | [Field] | [16 empty] | 6 | 5 | 6
L27 |  |  | 8 |  | Senior Surveyor 3 |  |  | Nguyen Anh Tuan | NK | [Field] | [16 empty] | 4 | 5 | 4
Geotechnical Survey (GTS)
L28 |  |  | 4 |  | Soil/Geotechnical Engineer 2 |  |  | Nguyen Doan Tinh | NK | [Field] | [16 empty] | 5 | 5 | 5
L29 |  |  | 4 |  | Soil/Geotechnical Engineer 3 |  |  | Nguyen Manh Tuan | NK | [Field] | [16 empty] | 4 | 4 | 4
L30 |  |  | 4 |  | Soil/Geotechnical Engineer 4 |  |  | Trinh Minh Khiem | NK | [Field] | [16 empty] | 4 | 4 | 4
L31 |  |  | 22 |  | Geological Engineer (Tunnel) |  |  | Tran Ngoc Nhan | NK | [Field] | [16 empty] | 2 | 2 | 2
Hydrological Survey (HDS)
L32 |  |  | 7 |  | Hydraulic Engineer 1 |  |  | Ngo The Hung | NK | [Field] | [16 empty] | 3 | 3 | 3
L33 |  |  | 7 |  | Hydraulic Engineer 2 |  |  | Pham Huu Nhu | NK | [Field] | [16 empty] | 3 | 3 | 3
L34 |  |  | 22 |  | Inundation Analyst |  |  | Nguyen Huy Phuong | NK | [Field] | [16 empty] | 3 | 3 | 3
Traffic Survey (TRS)
L35 |  |  | 14 |  | Transport Economist |  |  | Vo Hoang Anh | NK | [Field] | [16 empty] | 3 | 3 | 3
O&M and ITS Team (OMI)
O&M (OAM)
L36 |  |  | 18 |  | Operating & Maintenance Specialist |  |  | Ha Quoc Hieu | NK | [Field] | [16 empty] | 4 | 4 | 4
L37 |  |  | 19 |  | Expressway Management Unit Specialist |  |  | Le Tung Lam | NK | [Field] | [16 empty] | 2 | 2 | 2
L38 |  |  | 22 |  | Traffic Management Specialist |  |  | Phan Minh Tuan | NK | [Field] | [16 empty] | 3 | 3 | 3
L39 |  |  | 22 |  | Asset Management Specialist |  |  | Trinh Ngoc Hai Thang | NK | [Field] | [16 empty] | 2 | 2 | 2
L40 |  |  | 15 |  | Architect 1 |  |  | Pham Quang Minh | NK | [Field] | [16 empty] | 3 | 3 | 3
L41 |  |  | 15 |  | Architect 2 |  |  | Ngo Vu Quang Khoa | NK | [Field] | [16 empty] | 3 | 3 | 3
Electrical Facility and ITS Design (EID)
L42 |  |  | 17 |  | ITS Specialist |  |  | Nguyen Huu Tinh | NK | [Field] | [16 empty] | 5 | 5 | 5
L43 |  |  | 17 |  | Communication System Engineer |  |  | To Minh Tri | NK | [Field] | [16 empty] | 3 | 3 | 3
L44 |  |  | 13 |  | Electrical Engineer 1 |  |  | Trinh Dinh Khiem | NK | [Field] | [16 empty] | 7 | 7 | 7
L45 |  |  | 13 |  | Electrical Engineer 2 |  |  | Vo Hong | NK | [Field] | [16 empty] | 5 | 5 | 5
L46 |  |  | 22 |  | Toll Collection System Specialist |  |  | Bui Phu Huy | NK | [Field] | [16 empty] | 4 | 4 | 4
Cost and Document Team (COD)
Cost Estimate (COS)
L47 |  |  | 16 |  | Cost Estimator 1 (Civil Work Packages) |  |  | Nguyen Thi Bich Thuy | NK | [Field] | [16 empty] | 11 | 11 | 11
L48 |  |  | 16 |  | Cost Estimator 2 (Civil Work Packages) |  |  | Phan Thi Thuy Trinh | NK | [Field] | [16 empty] | 7 | 8 | 7
L49 |  |  | 16 |  | Cost Estimator 3 (Other Packages) |  |  | Nguyen Thi Sinh | NK | [Field] | [16 empty] | 3 | 2 | 3
Document (DOC)
L50 |  |  | 6 |  | Procurement/Contract Specialist 1 |  |  | Nguyen The Truong | NK | [Field] | [16 empty] | 12 | 12 | 12
L51 |  |  | 6 |  | Procurement/Contract Specialist 2 |  |  | Ha Ngoc Anh Minh | NK | [Field] | [16 empty] | 6 | 8 | 6
Environmental Team (ENV)
Social and Environmental (SAE)
L52 |  |  | 9 |  | Senior Environmental Specialist |  |  | Pham Van Xuan | NK | [Field] | [16 empty] | 8 | 8 | 8
L53 |  |  | 21 |  | Environmental Specialist |  |  | Pham The Giang | NK | [Field] | [16 empty] | 8 | 8 | 8
Resettlement (RES)
L54 |  |  | 10 |  | Senior Resettlement Specialist |  |  | To be named | NK | [Field] | [16 empty] | 14 | 14 | 14
L55 |  |  | 11 |  | Social and Resettlement Specialist |  |  | Ho Thi Thu Thuy | NK | [Field] | [16 empty] | 14 | 14 | 14
L56 |  |  | 12 |  | Cultural and Archaeological Specialist |  |  | Le Duy Son | NK | [Field] | [16 empty] | 14 | 14 | 14
Training (TRG)
L57 |  |  | 20 |  | Training Specialist |  |  | To be named | NK | [Field] | [16 empty] | 4 | 4 | 4
Total | [9 empty] | [Field] | [16 empty] | 357 | 357 | 357
|  | : | Work in Danang office
|  | : | Work in Hanoi office
Detailed Engineering Design and Procurement Planning (10)
Basic Design (4)

## Tab.A.12
| Calender |  |  |  |  | Calender Year |  |  |  |  | 2011 | [5 empty] | 2012 | [9 empty] | Duration | Proposal | Updated
[6 empty] | Calender Month |  |  |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
[6 empty] | Cumulative Month |  |  |  |  | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| Basic Design/Detailed Engineering Design and Procurement Planning | [25 empty] | 14
No |  |  | TOR | Position |  |  | Name |  | Firm | Home/ | 2011 | [5 empty] | 2012 | [9 empty] | Staff-
|  |  | 5.2 | [6 empty] | Field | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Months
[11 empty] | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Supporting Group 1 (SPG1)
S1 |  |  |  |  | Office Manager |  |  | To be named | NK | [Field] | [16 empty] | 15.5 | 14 | 15.5
S2 |  |  |  |  | Bilingual Secretary 1 |  |  | To be named | NK | [Field] | [16 empty] | 14 | 14 | 14
S3 |  |  |  |  | Accountant |  |  | To be named | NK | [Field] | [16 empty] | 14 | 14 | 14
S4 |  |  |  |  | Translator 1 |  |  | To be named | NK | [Field] | [16 empty] | 15.5 | 14 | 15.5
S5 |  |  |  |  | Translator 2 |  |  | To be named | NK | [Field] | [16 empty] | 12 | 12 | 12
S6 |  |  |  |  | Translator 3 |  |  | To be named | NK | [Field] | [16 empty] | 12 | 12 | 12
S7 |  |  |  |  | Translator 4 |  |  | To be named | NK | [Field] | [16 empty] | 12 | 12 | 12
S8 |  |  |  |  | Translator 5 |  |  | To be named | NK | [Field] | [16 empty] | 12 | 12 | 12
S9 |  |  |  |  | CAD Operator 1 |  |  | To be named | NK | [Field] | [16 empty] | 14 | 14 | 14
S10 |  |  |  |  | CAD Operator 2 |  |  | To be named | NK | [Field] | [16 empty] | 4 | 4 | 4
S11 |  |  |  |  | Guard 1 |  |  | To be named | NK | [Field] | [16 empty] | 14 | 14 | 14
S12 |  |  |  |  | Guard 2 |  |  | To be named | NK | [Field] | [16 empty] | 14 | 14 | 14
Supporting Group 2 (SPG2)
S13 |  |  |  |  | Bilingual Secretary 2 |  |  | To be named | NK | [Field] | [16 empty] | 12 | 12 | 12
S14 |  |  |  |  | CAD Operator 3 |  |  | To be named | NK | [Field] | [16 empty] | 12 | 12 | 12
S15 |  |  |  |  | CAD Operator 4 |  |  | To be named | NK | [Field] | [16 empty] | 11 | 12 | 11
S16 |  |  |  |  | CAD Operator 5 |  |  | To be named | NK | [Field] | [16 empty] | 11 | 12 | 11
S17 |  |  |  |  | CAD Operator 6 |  |  | To be named | NK | [Field] | [16 empty] | 11 | 12 | 11
Supporting Group 3 (SPG3)
S18 |  |  |  |  | Bilingual Secretary 3 |  |  | To be named | NK | [Field] | [16 empty] | 12 | 12 | 12
S19 |  |  |  |  | CAD Operator 7 |  |  | To be named | NK | [Field] | [16 empty] | 12 | 12 | 12
Supporting Group 4 (SPG4)
S20 |  |  |  |  | Bilingual Secretary 4 |  |  | To be named | NK | [Field] | [16 empty] | 8 | 8 | 8
S21 |  |  |  |  | CAD Operator 8 |  |  | To be named | NK | [Field] | [16 empty] | 8 | 8 | 8
Total | [9 empty] | [Field] | [16 empty] | 250 | 250 | 250
|  | : | Work in Danang office
|  | : | Work in Hanoi office
Detailed Engineering Design and Procurement Planning (10)
Basic Design (4)

## Tab.D.2
No. | Item |  | Specifications |  | Unit | Qty | Remarks
A |  | Control Point and Leveling Network
1 |  | Primary Control Point (GPS)
1.1 |  | Primary Control Point (GPS) | Class IV, VN2000 |  | (nos.) | 49
1.2 |  | Primary Leveling Network (GPS Network) |  |  | (km) | 210
2 |  | Secondary Control Point
2.1 |  | Secondary Control Point | Class II |  | (nos.) | 500
2.2 |  | Secondary Leveling Network |  |  | (km) | 170
B |  | Expressway |  |  |  | 0
3 |  | Main Line (ML, Road Section) |  |  |  | 0
3.1 |  | Planimetric | 1/1,000 |  | (ha) | 1563.7033
3.2 |  | Profile | 1/1,000; 1/100 |  | (km) | 111.6931
3.3 |  | Cross-section | 1/200 |  | (km) | 812.763
4 |  | Tunnel (TN) |  |  |  | 0
4.1 |  | Planimetric | 1/500 |  | (ha) | 1.02
5 |  | Bridge (BR) |  |  |  | 0
5.1 |  | Secondary Control Point | Class II |  | (nos.) | 314
5.2 |  | Planimetric (On Shore) | 1/500 |  | (ha) | 320.0843
5.3 |  | Planimetric (Off Shore) | 1/500 |  | (ha) | 101.3222
5.4 |  | Profile (On Shore) | 1/500 |  | (km) | 25.678
5.5 |  | Profile (Off Shore) | 1/500 |  | (km) | 7.2373
5.6 |  | Cross-section (Approach Road) | 1/200 |  | (km) | 112.875
5.7 |  | River Profile | 1/1,000; 1/100 |  | (km) | 39.2
5.8 |  | River Cross-section | 1/200 |  | (km) | 23.8079
6 |  | Culvert Box (CB) |  |  |  | 0
6.1 |  | Profile | 1/500 |  | (km) | 42.4
6.2 |  | Profile | 1/200 |  | (km) | 5.8
6.3 |  | Cross-section | 1/200 |  | (km) | 128.4
7 |  | Culvert Pipe (CP) |  |  |  | 0
7.1 |  | Profile | 1/200 |  | (km) | 1.8
8 |  | Canal (Re-alignment) |  |  |  | 0
8.1 |  | Profile | 1/500 |  | (km) | 3.904
8.2 |  | Cross-section | 1/200 |  | (km) | 7.84
9 |  | Interchange (IC) |  |  |  | 0
9.1 |  | Secondary Control Point | Class II |  | (nos.) | 72
9.2 |  | Secondary Leveling Network |  |  | (km) | 18
9.3 |  | Planimetric | 1/500 |  | (ha) | 276
9.4 |  | Profile (Rampway) | 1/1,000; 1/100 |  | (km) | 19.4
9.5 |  | Cross-section (Rampway) | 1/200 |  | (km) | 101.955
10 |  | Building (BL) |  |  |  | 0
10.1 |  | Planimetric | 1/500 |  | (ha) | 20.46
C |  | Linking Road |  |  |  | 0
11 |  | Main Line (ML, Road Section) |  |  |  | 0
11.1 |  | Planimetric | 1/1,000 |  | (ha) | 79.25
11.2 |  | Profile | 1/1,000; 1/100 |  | (km) | 7.925
11.3 |  | Cross-section | 1/200 |  | (km) | 24.822
12 |  | Bridge (BR) |  |  |  | 0
12.1 |  | Secondary Control Point | Class II |  | (nos.) | 6
12.2 |  | Planimetric (On Shore) | 1/500 |  | (ha) | 2.22
12.3 |  | Planimetric (Off Shore) | 1/500 |  | (ha) | 0.75
12.4 |  | Profile (On Shore) | 1/500 |  | (km) | 0.222
12.5 |  | Profile (Off Shore) | 1/500 |  | (km) | 0.075
12.6 |  | Cross-section (Approach Road) | 1/200 |  | (km) | 0.567
12.7 |  | River Profile | 1/1,000; 1/100 |  | (km) | 0.2
12.8 |  | River Cross-section | 1/200 |  | (km) | 0.15
13 |  | Culvert Box (CB) |  |  |  | 0
13.1 |  | Profile | 1/500 |  | (km) | 0
13.2 |  | Profile | 1/200 |  | (km) | 2.4
13.3 |  | Cross-section | 1/200 |  | (km) | 0
14 |  | Culvert Pipe (CP) |  |  |  | 0
14.1 |  | Profile | 1/200 |  | (km) | 0
15 |  | Intersection (IS, NH1A) |  |  |  | 0
15.1 |  | Planimetric | 1/500 |  | (ha) | 42
15.2 |  | Profile | 1/1,000; 1/100 |  | (km) | 4.4
15.3 |  | Cross-section | 1/200 |  | (km) | 12.6
D |  | Mobilization and Temporary Camp Yard | 2% | of A+B+C
E |  | Reporting | 2% | of A+B+C

## Tab.D.7
No. | Item |  | Soil Class |  | Unit | Qty | Remarks
A |  | Expressway
1 |  | Main Line (ML, Normal Embankment and Excavation Sections (NEE))
1.1 |  | Mechanical Boring |  | I-III (100%) | (l.m.)
1.2 |  | Sampling |  |  | (nos.)
1.3 |  | Undisturbed Sample Test |  |  | (nos.)
1.4 |  | Disturbed Sample Test |  |  | (nos.)
2 |  | Tunnel (TN)
2.1 |  | Mechanical Boring (Vertical) |  | I-III (50%), IV-VI (50%) | (l.m.)
2.2 |  | Mechanical Boring (Horizontal) |  | I-III (50%), IV-VI (50%) | (l.m.)
2.3 |  | Sampling |  |  | (nos.)
2.4 |  | Standard Penetration Test (SPT) |  |  | (points)
2.5 |  | Disturbed Sample Test |  |  | (nos.)
2.6 |  | Unconfined Compression Test |  |  | (nos.)
2.7 |  | Profile Survey |  |  | (l.m.)
2.8 |  | Seismic Measurement |  |  | (l.m.)
3 |  | Bridge (BR)
3.1 |  | Mechanical Boring (On Shore) |  | I-III (50%), IV-VI (50%) | (l.m.)
3.2 |  | Mechanical Boring (Off Shore) |  | I-III (70%), IV-VI (30%) | (l.m.)
3.3 |  | Sampling |  |  | (nos.)
3.4 |  | Standard Penetration Test (SPT) |  |  | (points)
3.5 |  | Floating Equipment |  |  | (nos.)
3.6 |  | Vane Shear Test (VST) |  |  | (nos.)
3.7 |  | Undisturbed Sample Test |  |  | (nos.)
3.8 |  | Disturbed Sample Test |  |  | (nos.)
3.9 |  | Unconfined Compression Test |  |  | (nos.)
3.10 |  | Consolidation Test (Cv) |  |  | (nos.)
3.11 |  | Triaxial Compression Test (UU) |  |  | (nos.)
3.12 |  | Triaxial Compression Test (CU) |  |  | (nos.)
4 |  | Culvert Box (CB)
4.1 |  | Mechanical Boring (On Shore) |  | I-III (100%) | (l.m.)
4.2 |  | Sampling |  |  | (nos.)
4.3 |  | Standard Penetration Test (SPT) |  |  | (points)
4.4 |  | Vane Shear Test (VST) |  |  | (nos.)
4.5 |  | Undisturbed Sample Test |  |  | (nos.)
4.6 |  | Disturbed Sample Test |  |  | (nos.)
4.7 |  | Unconfined Compression Test |  |  | (nos.)
4.8 |  | Consolidation Test (Cv) |  |  | (nos.)
4.9 |  | Triaxial Compression Test (UU) |  |  | (nos.)
4.1 |  | Triaxial Compression Test (CU) |  |  | (nos.)
5 |  | Interchange (IC)
5.1 |  | Mechanical Boring |  | I-III (100%) | (l.m.)
5.2 |  | Sampling |  |  | (nos.)
5.3 |  | Standard Penetration Test (SPT) |  |  | (points)
5.4 |  | Undisturbed Sample Test |  |  | (nos.)
5.5 |  | Disturbed Sample Test |  |  | (nos.)
6 |  | Building (BL)
6.1 |  | Mechanical Boring |  | I-III (100%) | (l.m.)
6.2 |  | Sampling |  |  | (nos.)
6.3 |  | Standard Penetration Test (SPT) |  |  | (points)
6.4 |  | Vane Shear Test (VST) |  |  | (nos.)
6.5 |  | Undisturbed Sample Test |  |  | (nos.)
6.6 |  | Disturbed Sample Test |  |  | (nos.)
6.7 |  | Consolidation Test (Cv) |  |  | (nos.)
6.8 |  | Triaxial Compression Test (UU) |  |  | (nos.)
6.9 |  | Triaxial Compression Test (CU) |  |  | (nos.)
7 |  | Main Line (ML, Softground Section (SG))
7.1 |  | Mechanical Boring |  | I-III (100%) | (l.m.)
7.2 |  | Sampling |  |  | (nos.)
7.3 |  | Standard Penetration Test (SPT) |  |  | (points)
7.4 |  | Vane Shear Test (VST) |  |  | (nos.)
7.5 |  | Undisturbed Sample Test |  |  | (nos.)
7.6 |  | Disturbed Sample Test |  |  | (nos.)
7.7 |  | Consolidation Test (Cv) |  |  | (nos.)
7.8 |  | Triaxial Compression Test (UU) |  |  | (nos.)
7.9 |  | Triaxial Compression Test (CU) |  |  | (nos.)
8 |  | Main Line (ML, Deep Excavation Section (DE))
8.1 |  | Mechanical Boring |  | I-III (50%), IV-VI (50%) | (l.m.)
8.2 |  | Sampling |  |  | (nos.)
8.3 |  | Disturbed Sample Test |  |  | (nos.)
9 |  | Existing Road (ER)
9.1 |  | Belkenman Test |  |  | (nos.)
B |  | Linking Road
10 |  | Main Line (ML, Normal Embankment and Excavation Sections (NEE))
10.1 |  | Mechanical Boring |  | I-III (100%) | (l.m.)
10.2 |  | Sampling |  |  | (nos.)
10.3 |  | Undisturbed Sample Test |  |  | (nos.)
10.4 |  | Disturbed Sample Test |  |  | (nos.)
11 |  | Bridge (BR)
11.1 |  | Mechanical Boring (On Shore) |  | I-III (50%), IV-VI (50%) | (l.m.)
11.2 |  | Mechanical Boring (Off Shore) |  | I-III (70%), IV-VI (30%) | (l.m.)
11.3 |  | Sampling |  |  | (nos.)
11.4 |  | Standard Penetration Test (SPT) |  |  | (points)
11.5 |  | Floating Equipment |  |  | (nos.)
11.6 |  | Vane Shear Test (VST) |  |  | (nos.)
11.7 |  | Undisturbed Sample Test |  |  | (nos.)
11.8 |  | Disturbed Sample Test |  |  | (nos.)
11.9 |  | Unconfined Compression Test |  |  | (nos.)
11.1 |  | Consolidation Test (Cv) |  |  | (nos.)
11.11 |  | Triaxial Compression Test (UU) |  |  | (nos.)
11.12 |  | Triaxial Compression Test (CU) |  |  | (nos.)
12 |  | Culvert Box (CB)
12.1 |  | Mechanical Boring (On Shore) |  | I-III (100%) | (l.m.)
12.2 |  | Sampling |  |  | (nos.)
12.3 |  | Standard Penetration Test (SPT) |  |  | (points)
12.4 |  | Vane Shear Test (VST) |  |  | (nos.)
12.5 |  | Undisturbed Sample Test |  |  | (nos.)
12.6 |  | Disturbed Sample Test |  |  | (nos.)
12.7 |  | Unconfined Compression Test |  |  | (nos.)
12.8 |  | Consolidation Test (Cv) |  |  | (nos.)
12.9 |  | Triaxial Compression Test (UU) |  |  | (nos.)
12.1 |  | Triaxial Compression Test (CU) |  |  | (nos.)
13 |  | Existing Road (ER)
13.1 |  | Belkenman Test |  |  | (nos.)
C |  | Mobilization and Temporary Camp Yard
D |  | Reporting

## Tab.D.12
Category | [6 empty] | Work Item |  |  | Reports |  |  | Team In-charge | Facilities
[7 empty] | No. | Item |  | No. | Reports/Technical Reports |  |  | Expressway | [18 empty] | Linking Road
[14 empty] | Main Line | [9 empty] | Interchange |  |  |  |  | Crossing Road |  | Frontage Road |  | Main Line |  |  |  |  | Intersection
[14 empty] | RD | TN | BR |  |  |  | CB |  | CP | BL4) | RD | BR | CB | CP | BL5) | RD | BR | RD | CP | RD | BR |  | CB | CP | RD
[16 empty] | RB |  |  | Others3) | RD | WT |  |  |  | IRB | WT |  |  |  | FO |  |  |  | RB | Others3) | WT
[16 empty] | LRB1) |  | ORB1) | [15 empty] | ORB
[16 empty] | MRB1)2) | Others1)
1 | Design Criteria and Conditions | [5 empty] | (1) |  | Design Criteria and Conditions (Civil 1) | **) |  | Design Criteria and Conditions (Civil 1) | CDM | ● | ● | ● | ● | ● | ● | ● | ● | ● |  | ● | ● | ● | ● |  | ● | ● | ● | ● | ● | ● | ● | ● | ● | ●
[7 empty] | (2) |  | Design Criteria and Conditions (Civil 2, Others) | **) |  | Design Criteria and Conditions (Civil 2, Others) | GTD/DRD/TFD/PVD | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● |  |  | ● | ● | ● | ● |  | ● | ● | ● |  |  | ●
2 | Typical Cross Sections | [5 empty] | (3) |  | Typical Cross Sections | **) |  | Typical Cross Sections | CDM | ● | ● | ● | ● | ● | ● |  |  |  |  | ● | ● |  |  |  | ● | ● | ● |  | ● | ● | ● |  |  | ●
3 | Road |  |  |  | 3.1 | Alignment/Geometric | (4) |  | Alternative Alignment Study | **) |  | Alternative Alignment Study Reports | CDM | ● | ● |  | ● | ● | ●
[7 empty] | (5) |  | Geometric Design (Thruway, Horizontal) | **) |  | Geometric Design Report (Thruway, Horizontal) | CDM | ● | ● | ● | ● | ● | ● | [13 empty] | ● | ● | ●
[7 empty] | (6) |  | Geometric Design (Thruway, Vertical) | **) |  | Geometric Design Report (Thruway, Vertical) | CDM | ● | ● | ● | ● | ● | ● | [13 empty] | ● | ● | ●
[7 empty] | (7) |  | Geometric Design (Others) | **) |  | Geometric Design Report (Others) | SED | [15 empty] | ● | ● | ●
[5 empty] | 3.2 | Crossing Conditions | (8) |  | Crossing Plan (for Roadway/Waterway/Canal/HVL) | **) |  | Crossing Plan (for Roadway/Waterway/HVL) | CDM |  |  | ● | ● | ● | ● | ● | ● | ● | [6 empty] | ● | ● |  |  |  | ● | ● | ● | ● | ●
[5 empty] | 3.3 | Frontage Road | (9) |  | Frontage Road Plan | **) |  | Frontage Road Plan | CDM | [17 empty] | ●
4 | Tunnel | [5 empty] | (10) |  | Tunnel Portal Location Plan | **) |  | Tunnel Plan | TND |  | ●
[7 empty] | (11) |  | Tunnel Cross Section |  |  |  | TND |  | ●
[7 empty] | (12) |  | Tunnel Surporting Design |  |  |  | TND |  | ●
5 | Bridge |  |  |  | 5.1 | Bridge Structure | (13) |  | Comparative Study (Major River Bridges) | **) |  | Comparative Study Report (Major River Bridges) | MBD |  |  | ●
[7 empty] | (14) |  | Bridge Plan (Thruway Bridges) | **) |  | Bridge Plan (Thruway Bridges) | CDM |  |  | ● | ● | ● | ● | [14 empty] | ● | ●
[7 empty] | (15) |  | Bridge Plan (Other Bridges) | **) |  | Bridge Plan (Other Bridges) | CDM | [11 empty] | ● |  |  |  |  | ●
[7 empty] | (16) |  | Standard Design (Bridge Works) | **) |  | Standard Design (Bridge Works) | CDM |  |  |  | ● | ● | ● | [5 empty] | ● |  |  |  |  | ● |  |  |  | ● | ●
[7 empty] | (17) |  | Structural Design (Bridge) |  |  |  | SED/MBD |  |  | ● | ● | ● | ● | [5 empty] | ● |  |  |  |  | ● |  |  |  | ● | ●
[5 empty] | 5.2 | Temporary Facility | (18) |  | Bridge Temporary Facility Plan | **) |  | Bridge Temporary Facility Design Report | MBD/TFD |  |  | ● | ● | ● | ● | [5 empty] | ● |  |  |  |  | ● |  |  |  | ● | ●
[7 empty] | (19) |  | Standard Design (Bridge Temporary Facility Works) |  |  |  | MBD/TFD |  |  | ● | ● | ● | ● | [5 empty] | ● |  |  |  |  | ● |  |  |  | ● | ●
[5 empty] | 5.3 | River Bed/ | (20) |  | Scoring Analysis | **) |  | Revetment/River Bed Protection Design Report | RRD |  |  | ● | ● | ● | [15 empty] | ●
[6 empty] | Bank Protection | (21) |  | Standard Design (Revetment/River Bed Protection Works) |  |  |  | RRD |  |  | ● | ● | ● | [15 empty] | ●
[7 empty] | (22) |  | Revetment/River Bed Protection Plan |  |  |  | RRD |  |  | ● | ● | ● | [15 empty] | ●
6 | Interchange | [5 empty] | (23) |  | Alternative Study (Interchange Location) | **) |  | Alternative Study Report (Interchange Location) | CDM | [10 empty] | ●
[7 empty] | (24) |  | Comparative Study (Interchange Type) | **) |  | Comparative Study Report (Interchange Type) | ICD | [10 empty] | ●
[7 empty] | (25) |  | Interchange Plan (Based on Satellite Photo) | **) |  | Interchange Plan (Based on Satellite Photo) | ICD | [10 empty] | ●
[7 empty] | (26) |  | Geometric Design (Interchange) |  |  |  | ICD | [10 empty] | ● | ●
7 | Common |  |  |  | 7.1 | Revision (B/D) | (27) |  | Revision (B/D) |  |  |  | SED/MBD | ● |  | ● | ● | ● | ● |  | ● | [11 empty] | ● | ● | ● | ●
[5 empty] | 7.2 | Slope | (28) |  | Slope Stability Analysis | **) |  | Slope Protection Design Report | GTD | ● | [8 empty] | ● | ● |  |  |  | ● | ● |  |  |  | ●
[7 empty] | (29) |  | Standard Design (Slope Protection Works) |  |  |  | GTD | ● | [8 empty] | ● | ● |  |  |  | ● | ● |  |  |  | ●
[7 empty] | (30) |  | Slope Protection Plan |  |  |  | GTD | ● | [8 empty] | ● | ● |  |  |  | ● | ● |  |  |  | ●
[5 empty] | 7.3 | Retaining Wall | (31) |  | Retaining Wall Plan | **) |  | Retaining Wall Design Report | SED | ● | [8 empty] | ● | ● |  |  |  | ● | ● |  |  |  | ●
[7 empty] | (32) |  | Standard Design (Retaining Wall) |  |  |  | CDM | ● | [8 empty] | ● | ● |  |  |  | ● | ● |  |  |  | ●
[5 empty] | 7.4 | Softground | (33) |  | Consolidation/Stability Analyses | **) |  | Softground Treatment Design Report | GTD | ● |  |  | ● |  | ● | ● | ● | ● | ●
[7 empty] | (34) |  | Standard Design (Softground Treatment) |  |  |  | GTD | ● |  |  | ● |  | ● | ● | ● | ● | ●
[7 empty] | (35) |  | Softground Treatment Plan |  |  |  | GTD | ● |  |  | ● |  | ● | ● | ● | ● | ●
[5 empty] | 7.5 | Pavement | (36) |  | Standard Design (Pavement Works) | **) |  | Pavement Design Report | PVD | ● | ● | ● | ● | ● | ● |  |  |  | ● | ● | ● |  |  | ● | ● | ● | ● |  | ● | ● | ● |  |  | ●
[7 empty] | (37) |  | Pavement Plan |  |  |  | PVD | ● | ● | ● | ● | ● | ● |  |  |  | ● | ● | ● |  |  | ● | ● | ● | ● |  | ● | ● | ● |  |  | ●
[5 empty] | 7.6 | Drainage | (38) |  | Drainage Analysis | **) |  | Drainage Design Report | DRD | ● | ● | [7 empty] | ● | ● |  |  |  | ● | ● |  | ● |  | ● |  |  |  |  | ●
[7 empty] | (39) |  | Drainage Plan |  |  |  | DRD | ● | ● | [7 empty] | ● | ● |  |  |  | ● | ● |  | ● |  | ● |  |  |  |  | ●
[7 empty] | (40) |  | Standard Design (Drainage Works) |  |  |  | DRD | ● | ● | [7 empty] | ● | ● |  |  |  | ● | ● |  | ● |  | ● |  |  |  |  | ●
[5 empty] | 7.7 | Culvert | (41) |  | Culvert Plan (Thruway) | **) |  | Culvert Plan (Thruway) | CDM | [6 empty] | ● | ● | ● | [13 empty] | ● | ●
[7 empty] | (42) |  | Culvert Plan (Others) | **) |  | Culvert Plan (Others) | SED | [12 empty] | ● | ● |  |  |  |  | ●
[7 empty] | (43) |  | Standard Design (Culvert Works) | **) |  | Standard Design (Culvert Works) | CDM | [6 empty] | ● | ● | ● |  |  |  | ● | ● |  |  |  |  | ● |  |  |  | ● | ●
[5 empty] | 7.8 | Road Accessory | (44) |  | Standard Design (Road Accessory) | **) |  | Road Accessory Design Report | CDM | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ●
[7 empty] | (45) |  | Road Accessory Plan |  |  |  | SED | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ●
[5 empty] | 7.9 | Drawing | (46) |  | Design Drawings (B/D) |  |  |  | SED/MBD | ● |  | ● | ● | ● | ● | [13 empty] | ● | ● | ●
[7 empty] | (47) |  | Design Drawings (D/D) |  |  |  | SED/ICD/MBD/TND/GTD/DRD/TFD/PVD | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ●
[5 empty] | 7.1 | Road Safety | (48) |  | Road Safety Audit | **) |  | Road Safety Audit Report | CDM | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ●
[5 empty] | 7.11 | Quantity | (49) |  | Quantity Taking-off | **) |  | Quantity Reports | SED/ICD/MBD/TND/GTD/DRD/TFD/PVD | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ●
[5 empty] | 7.12 | Report | (50) |  | Basic Design Report (Civil, Draft Design Report) | **) |  | Basic Design Report (Civil, Draft Design Report) | CDM | ● | ● | ● | ● | ● | ● | ● | ● | ● |  | ● | ● | ● | ● |  | ● | ● | ● | ● | ● | ● | ● | ● | ● | ●
[7 empty] | (51) |  | Working Design Reports | **) |  | Working Design Reports | CDM | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ●
[7 empty] | (52) |  | Design Report | **) |  | Design Report | CDM | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ●
Legend |  | : | ●(B/D), ● (D/D)
Code |  | : | RD (Road), TN (Tunnel), BR (Bridge), RB (River Bridge), LRB (Large River Bridge), ORB (Other River Bridge), MRB (Major River Bridge), CB (Culvert Box), WT (Waterway), CP (Culvert Pipe), BL (Building), IRB (Interchange Rampway Bridge), FO (Flyover)
Note |  | : | 1) | LRB (L>100 m), ORB (L<100 m), MRB (L>300 m), Other LRB (100 m<L<300 m)
|  |  | 2) | 5 Bridges (Ky Lam Bridge (LRB08, KM017+662), Chiem Son Bridge (LRB09, KM020+185), Tam Ky Bridge (LRB16, KM068+308), Tra Bong Bridge (LRB19, KM109+320), Tra Khuc Bridge (LRB20, KM125+700))
|  |  | 3) | Stream Bridge (SB), Canal Bridge (CB), Viaduct (VD), Overpass (OP)
|  |  | 4) | Toll Barrier (TB) and Toll Plaza Office (TPO), Service Area (SA), Parking Area (PA), Traffic Management Center (TMC), Expressway Operation Office (EOO)
|  |  | 5) | Toll Gate (TG) and Toll Plaza Office (TPO)
|  |  | 6) | Civil Works Only
|  |  | 7) | 3 Sections based on C.1 Previous Studies Review/Request from Quang Nam PC (Rocky Mountain (KM34-KM36), Shooting Area (KM71-KM82), Water Reservoir/High-voltage Line (KM89-KM107))
|  |  | 8) | Plan and Profile, General View (Bridge)
7)
7)
7)
7)
7)
6)
6)
8)
8)
8)
8)
8)
8)
8)
8)
6)
6)
6)
6)
6)
6)
6)