|  | Ministry of Transport |  |  |
| --- | --- | --- | --- |
|  | Vietnam Expressway Corporation |  |  |
|  | Project Management Unit No. 85 |  |  |

IDA Credit	No.	:	3843-VN

Project ID	No.	:	P106235

Consulting Services

for

Detailed Design for Danang - Quang Ngai Expressway Development Project

Insert Perspective View

Inception Report (Draft)

1 September 2011

| The Joint Venture of |  |
| --- | --- |
|  | THAI ENGINEERING CONSULTANTS CO., LTD. |

Ref. No.	:	DQEDD-PMU-xx-11

Date	:	1 September, 2011

Mr. Nguyen Tien Ha

Project Manager

Project Management Unit No. 85 (PMU85)

Fax. No. : +84-(38)3834705

Subject:		Submission of Inception Report (IC/R)

Dear Sir,

In accordance with Appendix B - Reporting Requirements in the Contract for Consultants’ Services, we would like to submit fifteen (15) copies of the Inception Report (IC/R) in English and Vietnamese versions, respectively.

Sincerely yours,

Ichizuru ISHIMOTO

Project Manager/Team Leader

c.c.	:	Office Copy

Encl.	:	Inception Report (English: 15 copies, Vietnamese: 15 copies)

Insert Project Location Map (A4 Size, MS Excel File)

Insert Project Route Map (A3 Long Size (AutoCAD or PDF Files))

Submission Letter

Project Location Map

Project Route Map

Table of Contents

Abbreviations

Main Part

Part	A	:	General 		1

A.1	Project Features 		1

A.1.1	Background 		1

A.1.2	Location 		2

A.1.3	Objectives 		2

A.1.4	Component 		3

A.1.5	Safeguards 		6

A.1.6	Project Cost 		7

A.1.7	Funding Arrangement 		7

A.1.8	Contract Packaging 		8

A.1.9	Project Implementation Structure 		8

A.1.10	Project Implementation Program 		9

A.2	Outline of the Services 		9

A.2.1	Objectives 		9

A.2.2	Scope 		10

A.2.3	Work Schedule and Reporting 		10

A.2.4	Organization and Staffing 		13

Part	B	:	Project Management 		20

B.1	:	Project Management 		20

Part	C	:	Previous Studies Review and Establishing Detailed Engineering Design Framework

C.1	:	Previous Studies Review 		xx

C.2	:	Detailed Engineering Design Framework 		xx

Part	D	:	Detailed Engineering Design and Procurement Planning

D.1	:	Contract Packaging 		xx

D.2	:	Surveys and Investigations 		xx

D.3	:	Civil Engineering Design 		xx

D.4	:	O&M Plan and Design 		xx

D.5	:	ITS Plan and Design 		xx

D.6	:	Electrical Facilities Design 		xx

D.7	:	Public Utilities Relocation Plan 		xx

D.8	:	Safeguards 		xx

D.9	:	Construction Planning 		xx

D.10	:	Project Cost Estimate 		xx

D.11	:	Procurement Document 		xx

D.12	:	Project Implementation Plan 		xx

Part	E	:	Technology Transfer

Appendix

Appendix	1	:	Baseline Schedule (Microsoft Project)

Abbreviations

XXXXX	:	XXXX XXXX XXXX XXXX XXXX XXXX XXXX XXXX

XXXXX	:	XXXX XXXX XXXX XXXX XXXX XXXX XXXX XXXX

XXXXX	:	XXXX XXXX XXXX XXXX XXXX XXXX XXXX XXXX

XXXXX	:	XXXX XXXX XXXX XXXX XXXX XXXX XXXX XXXX

XXXXX	:	XXXX XXXX XXXX XXXX XXXX XXXX XXXX XXXX

General

Project Features

Background

The preparation of Pre-F/S for the Project under BOT scheme was approved by MOT in Decision No. 2654/QD-BGTVT dated on September 11, 2000.  The Pre-F/S report was prepared by PMU85 and approved by the Prime Minister in his letter No. 493/CP-CN dated on April 21, 2003.  Continually, the preparation of F/S was approved by MOT in Decision No. 134/QD-BGTVT dated January 14, 2004.  The F/S report was also prepared by PMU85 and submitted to MOT in his letter No. 514/BQL-KHDA2 dated on May 11, 2005.  However, this BOT scheme Project did not materialize because of funding sources were not identified at that time.

Two (2) years later, the Project was approved as one (1) of the top priority projects in transport sector by GOVN in Decision No. 412/QD-TTg dated on April 11, 2007.  For carrying forward the Project, GOVN requested JETRO to assist a further study expecting materialization of the Project by a JBIC (currently JICA) loan scheme in June 2007.  JETRO conducted the study and submitted the study report to MOT on April 28, 2008.

In parallel with the JETRO study, WB declared GOVN to be eligible for the IBRD loan in November, 2007 and the Project was identified as the top priority use for the loan.  After submission of the JETRO study report, WB undertook the identification missions in April and June, 2008 and confirmed necessity of updating the JETRO study to meet his requirements and decided to allocate the fund from ongoing RNIP (IDA Credit No.: 3843-VN) to conduct the WB supplemental study.  The study report was prepared by PMU85 and submitted to MOT in his letter No. 551/BQl-KHDA2 dated on June 13, 2009.

In response to the supplemental study, WB engaged international consultants and undertook the WB appraisal study.  In the appraisal study, WB modified the alignment at 3 sections by taking into consideration social and environmental issues.  Based on the modified alignment, TEDI updated the WB supplemental study and submitted as the F/S report to MOT in April, 2010.  At present, this report is being approved by the Prime Minister.

Following the maturity of the Project, WB agreed to allocate the fund from RNIP for D/D and the Prime Minister allowed commencing the procurement of the consultant ahead of the F/S approval.  Through the procurement procedures, NK-NE-Chodai-TEC JV was selected and contracted with VEC.  Currently, VEC issued NTP in his letter No. ***/***-***** dated on August **, 2011 and D/D was officially started from September 1, 2011.

Outline of the Project background is shown in Figure A.1.

Figure A.1   Outline of the Project Background

Location

The Project road is a part of the North-South Expressway located in parallel with the existing NH1A and North-South Railway and passing through Danang city, Quang Nam and Quang Ngai provinces in the central region.  The road starts at the intersection of the Danang Bypass and NH14B in Danang city and ends at the connecting point with the planned City Ring Road at existing NH1A in Quang Ngai province.  The major socio-economic developments along the Project road are the Chu Lai Open Economic Zone in Quang Nam province and the Dung Quat Industrial Zone in Quang Ngai province.  As for the cultural properties, the Hoi An Ancient Town and My Son Sanctuary registered with the world heritage (cultural heritage) are existed along the Project road.

Project location map is shown in Figure A.2.

Figure A.2   Project Location Map

Objectives

The main objective of the Project is to improve transport linkage in the central region.  WB designed the performance indicators, targets and monitoring mechanisms, and surveyed the baseline data in the WB appraisal study (see A.1.1) to measure socioeconomic impacts of the Project.

Outline of the Project framework is shown in Figure A.3.

Figure A.3   Outline of the Project Framework

Component

Expressway Construction and O&M Equipment Provision

The main Project components are the expressway construction and O&M equipment provision.

Main features of the expressway construction and O&M equipment provision are shown in Table A.1, and Project facilities plan is shown in Figure A.4 in the next page, respectively.

Table A.1   Main Features of the Expressway Construction and O&M Equipment Provision

| No. | Item | Main Features |  | Ref. in TOR |
| --- | --- | --- | --- | --- |
| 1 | Road Length | 139.5 km |  | Component A |
|  |  |  | By Road Class: Expressway section: 131.5 km, Linking road section: 8.0 km | (TOR 1(1)) |
|  |  |  | By Jurisdiction: Danang city: 8.0 km, Quang Nam province: 92.0 km, Quang Ngai province: 39.5 km |  |
|  |  |  | BP: Intersection of the existing Danang bypass and NH14B in Danang city |  |
|  |  |  | EP: Connecting point with the planned city ring road at the existing NH1A in Quang Ngai province |  |
| 2 | Road Classification | Type A, Class 120 |  |  |
| 3 | Design Speed | 120 km/hr |  |  |
| 4 | Nos. of Lane | 4 lanes (Initial stage) |  |  |
|  |  |  | Ultimate Stage: Widened to 6 lanes (see Figure A.4) |  |
| 5 | Road With | Road and Bridge sections: 26.0 m, Tunnel section: 2@12.75 m=25.5 m |  |  |
| 6 | Bridges | 130 bridges (L=14,994.85 m) |  |  |
|  |  |  | Large River Bridge (L>100 m): 20 bridges (L=5,687.55 m) 1) |  |
|  |  |  | Other River Bridge (L<100 m): 10 bridges (L=603.85 m) |  |
|  |  |  | Stream Bridge: 8 bridges (L=354.90 m) |  |
|  |  |  | Canal Bridge: 18 bridges (L=666.00 m) |  |
|  |  |  | Viaduct: 21 bridges (L=3,073.45 m) |  |
|  |  |  | Overpass: 22 bridges (L=694.8 m) |  |
|  |  |  | Flyover: 19 bridges (L=2,252.00 m) |  |
|  |  |  | Interchange rampway bridge: 12 bridges (L=1,662.30 m) |  |
| 7 | Major River Bridge | 5 bridges |  |  |
|  |  |  | Thu Bong River: Ky Lam Bridge (KM017+662, L=962.0 m) |  |
|  |  |  | Ba Ren River : Chiem Son Bridge (KM020+185, L=410.0 m) |  |
|  |  |  | Tam Ky River : Tam Ky Bridge (KM068+308, L=307.0 m) |  |
|  |  |  | Tra Bong River : Tra Bong Bridge (KM109+320, L=452.0 m) |  |
|  |  |  | Tra Khuc River : Tra Khuc Bridge (KM125+700, L=846.0 m) |  |
| 8 | Tunnel | 1 tunnel (2@540 m) |  |  |
| 9 | Culvert | 375 culverts |  |  |
|  |  |  | Culvert Box: 188 culvert boxes (106 underpass and 82 drainage culverts) |  |
|  |  |  | Culvert Pipe: 187 culvert pipes |  |
| 10 | Soutground | Approximately 3.6 km |  |  |
| 11 | Interchange | 9 interchanges |  |  |
| 12 | Frontage Road | Approximately 59.7 km |  |  |
| 13 | Earth Works | Soil excavation: 10,000,000 m3, Rock excavation: 1,000,000 m3, Filling: 24,000,000m3 |  |  |
| 14 | Electrical Facilities | Power supply, road lighting, tunnel ventilation and safety facilities |  | Component B |
| 15 | ITS | Traffic management, toll collection1) and communication systems |  | (TOR 1(2)) |
| 16 | O&M Building | 26 locations |  | Component C |
|  |  |  | Traffic Management Center: 1 location | (TOR 1(3)) |
|  |  |  | Expressway Operation Center: 1 location |  |
|  |  |  | Toll Plaza Office: 9 locations |  |
|  |  |  | Toll Barrier: 2 locations |  |
|  |  |  | Toll Gate: 7 locations |  |
|  |  |  | Service Area: 2 locations |  |
|  |  |  | Parking Area: 4 locations |  |
| 17 | O&M Equipment | O&M vehicles, spare parts, maintenance equipment and consumables |  |  |

Note	1)	Including 5 major river bridges (see No.7)

2)	Including electric toll collection system in accordance with MOT Notice No.94/TB-BGTVT dated March 10, 2009

Figure A.4   Project Facilities Plan

Consulting Services

The overall consulting services for the Project consist of the Detailed Engineering Design (D/D), Procurement Assistance (P/A) and Construction Supervision (C/S).  The consulting services in this contract cover D/D and P/A only, without C/S (see A.2.2(2)).

Main scope of the overall consulting services is shown in Table A.2.

Table A.2   Main Scope of the Overall Consulting Services

| No. | Item | Main Scope |
| --- | --- | --- |
| 1 | Detailed Engineering Design (D/D) | Previous studies review and establishing detailed engineering design framework |
|  |  | Detailed engineering design and procurement planning |
| 2 | Procurement Assistance (P/A) | Assist in pre-qualification, bidding and contract negotiations |
| 3 | Construction Supervision (C/S) | Construction supervision |
|  |  | Assist in establishing of an O&M unit including capacity development |
|  |  | Assist in defect liability inspection |

Establishment of an O&M Unit

The O&M framework of the expressway section is under consideration.  Based on the F/S results, the estimated financial return by operating the expressway is low in early stage because of the forecasted traffic volume is small.  Therefore, O&M concessions are not attractive for private sectors, and the expressway is expected to operate by an O&M unit to be established under VEC in early stage.

Expected O&M framework for the Project road is shown in Figure A.5.

Figure A.5   Expected O&M Framework for the Project Road

Safeguards

Social and Environmental Assessment

The original EIA report based on the JETRO study was prepared by PMU85, and approved by MONRE in Decision No. 2378/QD-BTNMT dated on November 12, 2008.  The supplemental EIA report based on the current F/S alignment was also prepared by PMU85 and approved by MONRE in Decision No. ****/**-***** dated on ****** **, ****.

Social and environmental assessment framework for the Project is shown in Figure A.6.

Figure A.6   Social and Environmental Assessment Framework for the Project Road

Land Acquisition and Resettlement

RAP based on the current F/S alignment was prepared by PMU85.

The land acquisition area and nos. of resettlement households in RAP is shown in Table A.3, and CPCSR framework for the Project road is shown in Figure A.7, respectively.

Table A.3   Land Acquisition Area and Nos. of Resettlement Households (Draft RAP)

| No. | Item | Unit | Danang | Quang Nam | Quang Ngai | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Land Acquisition Area | sq.m | 564,520 (6%) | 6,695,975 (66%) | 2,870,615 (28%) | 10,131,110 (100%) |
| 2 | Resettlement Households | nos. | 29 (4%) | 559 (66%) | 254 (30%) | 842 (100%) |

Figure A.7   CPCSR Framework for the Project Road

Project Cost

The estimated total Project cost in the current F/S amounts to 29,839 Bil.VND (1,570 Mil.USD).

Summary of the estimated Project cost is shown in Table A.4.

Table A.4   Summary of the Estimated Project Cost (Current F/S)

| No. | Item |  | Estimated Cost | Equiv. in USD1) | Remark |
| --- | --- | --- | --- | --- | --- |
|  |  |  | (Bil.VND) | (Mil.USD) |  |
| 1 | Construction Cost |  | 20,077 | 1,057 |  |
|  | a. | Road Works | 11,411 | 601 |  |
|  | b. | Bridge Works | 6,552 | 345 |  |
|  | c. | Tunnel Works | 443 | 23 |  |
|  | d. | Electrical/ITS Facilities and O&M Building Works, and O&M Equipment Provision | 1,671 | 88 |  |
| 2 | Other Cost (Project Management, Consulting Services and Others) |  | 2,409 | 127 | 12%*No.1 |
| 3 | Land Acquisition and Compensation Cost |  | 2,380 | 125 |  |
| 4 | Contingency |  | 4,973 | 261 | 20%*(No.1-No.3) |
|  | e. | Price Contingency | 3,730 | 65 | 15%*(No.1-No.3) |
|  | f. | Physical Contingency | 1,243 | 196 | 05%*(No.1-No.3) |
| Total |  |  | 29,839 | 1,570 |  |

Note	1)	1USD=19,000VND (exchange rate applied in the current F/S (April, 2010))

Funding Arrangement

D/D and P/A cost of all packages is funded by ongoing RNIP (IDA Credit No.: 3843-VN).  As for the construction and C/S cost, the civil works of northern section from Danang to Tam Ky and the ITS facilities and O&M building works, and O&M equipment provision for whole section will be funded by JICA loan, and the remaining civil works at the southern section from Tam Ky to Quang Ngai will be funded by a blend of IBRD loan and IDA credit terms.

JICA already signed L/A for a loan on June 15, 2011.  As for WB, the executive directors approved to provide a loan and two credits and schedule to sign L/A in April 2012.

Demarcation among WB, JICA and GOVN is shown in Table A.5.

Table A.5   Demarcation among WB, JICA and GOVN

| No. | Item |  | Section | Demarcation |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | WB | JICA | GOVN |
| 1 | Construction (Civil Works) |  | Danang to Tam Ky |  | ● |  |
|  |  |  | Tam Ky to Quang Ngai | ● |  |  |
| 2 | ITS Facilities and O&M Building Works, and O&M Equipment Provision |  | Whole Section |  | ● |  |
| 3 | Consulting Services | Detailed Engineering Design | Whole Section | ● |  |  |
|  |  | Procurement Assistance | Civil Works | ● |  |  |
|  |  |  | ITS/O&M Works |  | ● |  |
|  |  | Construction Supervision | Danang to Tam Ky |  | ● |  |
|  |  |  | Tam Ky to Quang Ngai | ● |  |  |
| 4 | Other Consulting Services | Project Monitoring Services |  | ● |  |  |
|  |  | Financial Audit (Phase 1) |  | ● |  |  |
|  |  | Financial Audit (Phase 2) |  | ● |  |  |
|  |  | Financial Capacity Building for VEC |  | ● |  |  |
| 5 | Others |  | Whole Section |  |  | ● |

Source:	Decision No. 1423/QD-BGTVT dated on June 30, 2011 (Approval on Bidding Plan of the Expressway Project of Danang - Quang Ngai),

Decision No. 1688/QD-BGTVT dated on July 28, 2011 (Approval on Additional Procurement Plan of the Expressway Project of Danang - Quang Ngai)

Contract Packaging

The procurement plan including the contract packaging for the WB section was approved by MOT in Decision No. 1423/QD-BGTVT dated on June 30, 2011, and the procurement plan for the JICA section was also approved by MOT in Decision No. 1688/QD-BGTVT dated on July 28, 2011.

After receiving NTP on **** **, 2011 for This Consulting Services, the Consultant proposed to revise the boundary of Package A3 and A4 from KM111+000 to KM112+000 because of the KM111+000 is located on the planned bridge in the current F/S.  This proposal was approved by MOT in Decision No. ****/QD-BGTVT dated on **** **, 2011.

Current contract packaging is shown in Table A.6.

Table A.6   Current Contract Packaging

| Contract Packaging |  |  |  |  | Construction Cost (Mil.USD) |  |
| --- | --- | --- | --- | --- | --- | --- |
| Category | Jurisdiction | No. | Station | Length | WB | JICA |
| Civil Works | Danang | PKG1 | KM000+000 - KM008+000 | 8.0km |  | **** |
|  | Quang Nam | PKG2 | KM008+000 - KM017+000 | 9.0km |  | **** |
|  |  | PKG3 | KM017+000 - KM022+000 | 5.0km |  | **** |
|  |  | PKG4 | KM022+000 - KM032+000 | 10.0km |  | **** |
|  |  | PKG5 | KM032+000 - KM042+000 | 10.0km |  | **** |
|  |  | PKG6 | KM042+000 - KM052+000 | 10.0km |  | **** |
|  |  | PKG7 | KM052+000 - KM065+000 | 11.3km |  | **** |
|  |  | PKGA1 | KM065+000 - KM081+500 | 16.5km | **** |  |
|  |  | PKGA2 | KM081+500 - KM100+000 | 18.5km | **** |  |
|  | Quang Ngai | PKGA3 | KM100+000 - KM112+000 | 12.0km | **** |  |
|  |  | PKGA4 | KM112+000 - KM125+000 | 13.0km | **** |  |
|  |  | PKGA5 | KM125+000 - KM139+500 | 14.5km | **** |  |
| ITS/O&M Build, Works, and O&M Equip. Provision | All | PKG8 | KM000+000 - KM131+500 | 131.5km |  | **** |
| Total |  |  |  | 131.5km | **** | **** |
|  |  |  |  |  | **** |  |

Project Implementation Structure

VEC has been designated as the Project Owner by MOT in Decision No. 220/QD-BGTVT dated on January 22, 2010.  On the other hand, VEC has appointed PMU85 and PMU1 as the Project Implementing Agencies in the implementation stage and signed principle contract with PMU85 on **** **, **** and with PMU1 on **** **, ****, respectively.  PMU85 is assigned for the D/D and construction of JICA section, and PMU1 is assigned for the construction of WB section.

Project implementation structure is shown in Figure A.8.

Figure A.8   Project Implementation Structure

Project Implementation Program

The Project implementation program was agreed among WB, JICA and GOVN during the JICA Appraisal in October, 2010.  However, this program is delayed ** months at present.

After receiving NTP on **** **, 2011 the Consultant modified the program in consideration of the above delay, and it was approved by MOT in Decision No. ****/QD-BGTVT dated on **** **, 2011.

Current Project implementation program is shown in Figure A.9.

P/Aの取り扱い方針決定後、

JICA案を修正する

Figure A.9   Current Project Implementation Program

Outline of the Services

Objectives

The objectives of the Services are to ensure the preparation of the D/D and assist VEC/PMU85 in procurement procedures with the most efficient and timely manner to deliver the required outputs in accordance with the Project implementation program (I/P).

Furthermore, appropriate technology transfers for VEC/PMU85 and key local professional staff are also required as a specific component in the Services to ensure smooth execution of the Project and sustainable development of the expressway network in Vietnam.

Scope

Mode

The Services are carried out by the 2 modes as shown in Table A.7.

Table A.7   Mode of the Services

| No. | Mode | Contents |
| --- | --- | --- |
| 1 | Primary Tasks | Arrangement for managing the Services by the Consultant, who is fully responsible to VEC/PMU85, for |
|  |  | adequacy and quality of the end outputs of the Services assuring duly compliance of the scope of the |
|  |  | Services specified in the contract. |
| 2 | Assistance Tasks | The Consultant provides technical advice and assistance in carrying out the works to be accomplished by |
|  |  | VEC/PMU85 through the Consultant’s professional ability; however, the Consultant is not responsible |
|  |  | for the end outputs. |

Scope

Scope of the Services is shown in Table A.8.

Table A.8   Scope of the Services

| Detailed Tasks |  |  |  | Ref. in TOR |
| --- | --- | --- | --- | --- |
| Part B Project Management |  |  |  | Proposed Task |
|  | B.1 |  | Project Management | Proposed Task |
| Part C Previous Studies Review and Establishing Detailed Engineering Design Framework |  |  |  | 3.2 |
|  | C.1 |  | Previous studies Review | 3.2(1) |
|  | C.2 |  | Detailed engineering design framework | 3.2(2) |
| Part D Detailed Engineering Design and Procurement Planning |  |  |  | 3.3 |
|  | D.1 |  | Contract Packaging | 3.3.1 |
|  |  | D.1.1 | Propose contract packaging | 3.3.1 |
|  | D.2 |  | Surveys and Investigations | 3.3.2 |
|  |  | D.2.1 | Collect relevant data and documents | 3.3.2(1) |
|  |  | D.2.2 | Conduct topographic survey | 3.3.2(2)(i), 3.5 |
|  |  | D.2.3 | Conduct hydrological survey and analysis | 3.3.2(2)(ii) |
|  |  | D.2.4 | Conduct geotechnical and geological investigations | 3.3.2(2)(iii) |
|  |  | D.2.5 | Conduct material source survey | 3.3.2(2)(iv) |
|  |  | D.2.6 | Conduct relevant facilities survey | 3.3.2(2)(v) |
|  |  | D.2.7 | Review traffic forecasting and conduct baseline surveys | 3.3.2(2)(vi) |
|  |  | D.2.8 | Conduct independent land valuation survey | 3.3.2(2)(vii) |
|  |  | D.2.9 | Conduct environmental and social surveys | 3.3.2(2)(viii) |
|  | D.3 |  | Civil Engineering Design | 3.3.3 |
|  |  | D.3.1 | Prepare basic design of civil structures | 3.3.3 |
|  |  | D.3.2 | Prepare detailed engineering design of civil structures | 3.3.3 |
|  | D.4 |  | O&M Plan and Design | 3.3.5 |
|  |  | D.4.1 | Prepare institutional and administrative arrangement plan | 3.3.5 |
|  |  | D.4.2 | Prepare O&M plan | 3.3.5 |
|  |  | D.4.3 | Prepare basic design of O&M buildings | 3.3.5 |
|  | D.5 |  | ITS Plan and Design | 3.3.4 |
|  |  | D.5.1 | Prepare ITS plan | 3.3.4(1) |
|  |  | D.5.2 | Prepare basic design of ITS facilities | 3.3.4(2) |
|  | D.6 |  | Electrical Facilities Design | Proposed Task |
|  |  | D.6.1 | Prepare detailed engineering design of electrical facilities | Proposed Task |
|  | D.7 |  | Public Utilities Relocation Plan | Proposed Task |
|  |  | D.7.1 | Prepare relocation plan of public utilities | Proposed Task |
|  | D.8 |  | Safeguards | 3.3.6, Annex A, Annex B |
|  |  | D.8.1 | Assist in updating EIA and EMP | 3.3.6, Annex A |
|  |  | D.8.2 | Assist in preparing and enforcing CPCSR | 3.3.6, Annex B |
|  | D.9 |  | Construction Planning | 3.3.7 |
|  |  | D.9.1 | Prepare construction plan | 3.3.7 |
|  | D.10 |  | Project Cost Estimate | 3.3.8 |
|  |  | D.10.1 | Estimate Project cost | 3.3.8 |
|  | D.11 |  | Procurement Documents | 3.3.9 |
|  |  | D.11.1 | Prepare procurement documents | 3.3.9 |
|  | D.12 |  | Project Implementation Program | 3.3.10 |
|  |  | D.12.1 | Prepare Project I/P | 3.3.10 |
| Part E Procurement Assistance |  |  |  | 3.4 |
|  |  | E.1 | Assist in tendering procedures | 3.4 |
| Part F Technology Transfer |  |  |  | 3.6 |
|  |  | F.1 | Provide training to VEC/PMU85 | 3.6 |
|  |  | F.2 | Provide training to the key local professional staff | Proposed Task |

Work Schedule and Reporting

The Service period is total 14 months, and divide into the basic design (4 months) and detailed engineering design (10 months).

Work schedule and reporting plan are shown in Figure A.10.

Figure A.10   Work Schedule and Reporting Plan (1/2)

Figure A.10   Work Schedule and Reporting Plan (2/2)

Organization and Staffing

Consultant’s Organization

Joint Venture

The Consultant Team consists of the joint venture of NK, NE, Chodai and TEC, and jointly and severally responsible for the Services among the joint venture firms.

Consultant Team

The Consultant Team divides into 6 teams and 4 supporting groups as explained below.

Organization structure of the Consultant Team is shown in Figure A.11.

Management Team

The management team is responsible for managing the Services, and all communications in the Services are exchanged through the team.  In the team, we organize the core team which consists of the representatives of each team and secure the consistent communication among the teams.

Civil Design Team

The civil design team is responsible for planning and designing the civil structures and consists of the civil design management, design group and the survey group.

The civil design management is responsible for establishing the design criteria and conditions, standard design of road accessories, culverts and bridges, and supervising the works of the design and survey groups, preparing the technical specifications and assisting the tendering procedures.

The design group is responsible for preparing the basic design and detailed engineering design, and consists of two (2) sections and each structural design.

O&M and ITS Team

The O&M and ITS team is responsible for preparing the O&M and ITS plan, basic design of the O&M buildings and ITS facilities, and detailed engineering design of the electrical facilities including the preparation of the technical specifications in the bidding documents.

Cost and Document Team

The cost and document team is responsible for preparing the construction plan, engineer’s cost estimate, procurement plan and documents, and assisting the tendering procedures.

Environmental Team

The environmental team works with the relevant organizations for updating EIA and EMP, preparing and enforcing CPCSR, and preparing the requirements for EMP in the bidding documents.

Training Team

The training team is responsible for identifying the training needs with VEC/PMU85, and preparing and coordinating the training materials in cooperation with the engineers/specialists of the respective fields assign in other teams.

Supporting Groups

****************************************************************************************************************************************.

Figure A.11   Organization Structure of the Consultant Team

Home Office Support

NK has the home office support system and utilize the technical, managerial and operational support including the review and verification of the design in the Services.

Conceptual image of NK’s home office support system is shown in Figure A.12

Figure A.12   Conceptual Image of NK’s Home Office Support System

Office Arrangement

ダナン、ハノイ

Staffing

Staffing and Task Assignment

Table A.9

Staffing Schedule

Table A.10-12

Table A.9   Task Assignment Matrix for Key Professional Staff

Table A.10   Time Schedule for Key International Professional Staff

Table A.11   Time Schedule for Key Local Professional Staff

Table A.12   Time Schedule for Local Supporting Staff

Project Management

Project Management

The Consultant established the practical Services management system by utilizing PMBOK and its construction extension and customized it to the characteristics of the Services as attached in Appendix 1.  In consideration of the large-scale and complex assignment, the Consultant prioritizes the communication, quality and schedule managements in the Services.

The system was explained by the Consultant in the kick-off meeting on September 1, 2011, and agreed among VEC/PMU85, the Consultant and other relevant organizations for publicizing, gaining consensus and smooth execution of the Services.  Therefore, the Consultant monitors and controls the activities according to the system during the Services.

The system consists of 13 management areas, and the integration management which is one of the management areas consisting of the processes and activities needed to identify, define, combine, unify and coordinate the various processes and activities within the management process groups, is useful for understanding of overall project management system.

Work diagram of project management based on integration management is shown in Figure B.1, and describes the methodology of work items subsequently.

Figure B.1   Work Diagram of Project Management based on Integration Management

Define the Services

The Consultant prepares the Services charter and its regulations in accordance with the contract of the Services.  The charter consists of the name, targets, requirements, outputs, conditions of completion, budgets, period, organization, responsibility and authority of members, means of communication, and constraints for the Services to be formally authorized the Services among the relevant organizations.

Prepare the Primary Services Scope Statement

The Consultant updates the primary Services scope statement proposed in the proposal with reflection of contract negotiation and defines the needs to be accomplished in the Services.  The statement consists of the objectives, assumptions, constraints and deliverables for the Services and provides a documented basis for making future decisions and for confirming or developing a common understanding of the Services scope among the relevant organizations.

Prepare the Services Management Plan

The Consultant prepares the Services management plan which defines how the Services is executed, monitored and controlled and addresses the communication, quality and schedule managements as explained above.  Based on (1) to (3) above, the Consultant prepares and submits the inception report.

Main contents of the prioritized 3 management areas are shown in Table B.1.

Table B.1   Main Contents of the Prioritized 3 Management Areas

| No. | Management Areas | Main Items | Contents |
| --- | --- | --- | --- |
| 1 | Communication | Communication requirements | among the relevant organizations and inside the consultant team |
|  |  | Communication item | including format, contents, level of detail, frequency, conveyor and receiver |
|  |  | Medium and technologies | meetings, letters, reports, workshops, etc. |
|  |  | Escalation process | identifying time frames and channel for escalation of issues |
|  |  | Method for updating | required conditions and process for updating |
|  |  | Common terminology | definitions for minimizing communication errors |
| 2 | Quality | Quality metrics | operational definition for quality control item, process and measurement |
|  |  | Quality checklists | structured tool for verifying QA/QC performance |
|  |  | Process improvement | process boundaries, configuration and metrics, and performance targets |
|  |  | Quality baseline | records for quality objectives |
|  |  | Method for updating | required conditions and process for updating |
| 3 | Schedule | Activity definition | activity list and attributes, and milestone list |
|  |  | Baseline schedule | baseline for progress monitoring and reporting |
|  |  | Monitoring and reporting | method for monitoring and reporting including format, contents and frequency |
|  |  | Method for updating | required conditions and process for updating |

Kick-off Meeting

Based on the inception report, the Consultant holds the kick-off meeting with not only the Project executing agency but also other relevant organizations for publicizing, gaining the consensus and smooth implementation of the Services.

Direct and Manage the Services Execution

The Consultant directs and manages the Services execution in accordance with the process of executing the Services defined in the Services management plan above (3) to achieve the requirements for the Services defined in the primary Services scope statement in above (2).  Information on the status of the management activities being performed to accomplish the Services is routinely collected, and the Consultant compiles and submits the status as the monthly progress report.

Monitor and control the Services

The Consultant monitors and controls the processes used to initiate, plan, execute and close the Services to meet the performance objectives defined in the Services management plan above (3).  Status of the activity is also compiled and submitted as the monthly progress report.

Control Integrated Change

The Consultant controls integrated change which is the process of reviewing all change requests and approving and controlling changes to deliverables and organizational process assets.  The approved changes are reflected to update the Services scope statement above (2) and the Services management plan above (3).  Status in the activity is also compiled and submitted as the monthly progress report.

Close the Services

The Consultant finalizes all of the activities across the process groups to formally close the Services.  Administrative closing procedure is prepared and reflected to direct and manage the Services execution above (5).  All of documents of the management activities are compiled and submitted as the Project completion report.

List of Outputs

| Category | No. | Output | Related Work Item |
| --- | --- | --- | --- |
| Reports/Documents | ** | Inception Report | B.1(1)-(3) |
|  | ** | Monthly Progress Reports | B.1(5)-(7) |
|  | ** | Draft Final Project Completion Report | B.1(8) |
|  | ** | Project Completion Report | B.1(8) |

Previous Studies Review and Establishing Detailed Engineering Design Framework

Previous Studies Review

The Consultant reviews the previous studies especially current F/S and safeguard documents to take cognizance of the current arrangements of the Project and extracts the key issues which materially affect to the Services for discussing and obtaining the agreement with the relevant organizations.

Work diagram of previous studies review is shown in Figure C.1, and main subjects of reviewing previous studies are shown in Table C.1, respectively.

Figure C.1   Work Diagram of Previous Studies Review

Table C.1   Main Subjects of Reviewing Previous Studies

| No. | Category | Main Subjects |
| --- | --- | --- |
| 1 | Civil | Topography, geology and hydrology of the Project area |
|  |  | Technical standards1), and design criteria and conditions |
|  |  | Route alignment, geometric design and typical cross sections |
|  |  | Preliminary design of civil structures |
|  |  | Construction planning and preliminary Project cost estimates |
|  |  | Environmental impacts and its mitigation measures and RAP |
| 2 | O&M and ITS | O&M and ITS plan and those preliminary facilities design |

Note 1): Applicable technical standards for the Project were approved by MOT (Decision No. 362/QD-BGTVT dated on February 20, 2009)

List of Outputs

| Category | No. | Output | Related Work Item |
| --- | --- | --- | --- |
| Reports/Documents | ** | Previous Studies Review Report (Civil) | C.1(1) |
|  | ** | Previous Studies Review Report (O&M and ITS) | C.1(2) |

Detailed Engineering Design Framework

The Consultant establishes the detailed engineering design framework which consists of the primary matters for execution of the Services based on C.1 above and obtains the approval from the relevant organizations.

Work diagram of detailed engineering framework is shown in Figure C.2, and the main contents of the detailed engineering design framework are shown in Table C.2.

Figure C.2   Work Diagram of Detailed Engineering Design Framework

Table C.2   Main Contents of the Detailed Engineering Design Framework

| No. | Item | Main Contents |
| --- | --- | --- |
| 1 | Detailed Engineering Design Framework | Updated applicable technical standards for the Project |
|  |  | Format and content of the B/Q items, cost estimate and procurement documents |
|  |  | Updated work schedule of the Services |

List of Outputs

| Category | No. | Output | Related Work Item |
| --- | --- | --- | --- |
| Reports/Documents | ** | Detailed Engineering Design Framework | C.2(1) |

Detailed Engineering Design and Procurement Planning

Contract Packaging

Propose Contract Packaging

The contract packaging for the Project was already approved by MOT as shown in A.1.8.  In case modification is requested by VEC/PMU85, the Consultant studies it taking into account the affection for the D/D works and arrangement of the Project.

Work diagram of contract packaging is shown in Figure D.1,

Figure D.1   Work Diagram of Contract Packaging

List of Outputs

| Category | No. | Output | Related Work Item |
| --- | --- | --- | --- |
| Technical Reports | ** | Contract Packaging | D.1.1(1) |

Surveys and Investigations

Collect Relevant Data and Documents

The Consultant collects the relevant data and documents for basis of execution of the Services.

Work diagram of relevant data and documents is shown in Figure D.1, and main contents of relevant data and documents are shown in Table D.1, respectively.

Figure D.2   Work Diagram of Relevant Data and Documents

Table D.1   Main Contents of Relevant Data and Documents

| No. | Category | Main Contents |
| --- | --- | --- |
| 1 | Project Documents | Previous studies report |
|  |  | Related Decisions and Documents for the Project |
| 2 | Other Data and Documents | Relevant developing plan and existing facilities data in the Project area |
|  |  | Report and design document of the relevant project |
|  |  | Data related to the construction planning and cost estimate proper to the Project area |

List of Outputs

| Category | No. | Output | Related Work Item |
| --- | --- | --- | --- |
| Technical Reports | ** | Relevant Data and Documents | D.2.1(1) |

Topographic Survey

The Consultant conducts the topographic and ROW surveys for engineering design, quantity take-off and CPCSR.  In consideration of the huge survey volumes, the Consultant outsources the site survey works to Vietnamese sub-consultants and supervises their performance by the Survey Engineer.

In consideration of the rainy season, and short-period and work procedure of basic design, the Consultant conducts the site survey works in accordance with the following priorities:

1st Priority	:	Control points survey (whole section)

2nd Priority	:	Planimetric survey (thruway, sections for survey centerline study)

3rd Priority	:	Remaining surveys for basic design

Non-priority	:	Surveys for detailed engineering design

Work diagram of topographic survey is shown in Figure D.3, and tentative quantity of topographic survey works is shown in Table D.2, respectively.

Figure D.3   Work Diagram of Previous Studies Review

Table D.2   Tentative Quantity of Topographic Survey Works

Hydrological Survey and Analysis