|  | Ministry of Transport |  |  |
| --- | --- | --- | --- |
|  | Vietnam Expressway Corporation |  |  |
|  | Project Management Unit No. 85 |  |  |

IDA Credit	No.	:	3843-VN

Project ID	No.	:	P106235

Consulting Services

for

Detailed Design for Danang - Quang Ngai Expressway Development Project

Insert Perspective View

Inception Report (Draft)

1 November 2011

| The Joint Venture of |  |
| --- | --- |
|  | THAI ENGINEERING CONSULTANTS CO., LTD. |

Ref. No.	:	DQEDD-PMU-xx-11

Date	:	1 November, 2011

Mr. Nguyen Tien Ha

Project Manager

Project Management Unit No. 85 (PMU85)

Fax. No. : +84-(38)3834705

Subject:		Submission of Inception Report (IC/R)

Dear Sir,

In accordance with Appendix B - Reporting Requirements in the Contract for Consultants’ Services, we would like to submit fifteen (15) copies of the Inception Report (IC/R) in English and Vietnamese versions, respectively.

Sincerely yours,

Ichizuru ISHIMOTO

Project Manager/Team Leader

c.c.	:	Office Copy

Encl.	:	Inception Report (English: 15 copies, Vietnamese: 15 copies)

Insert Project Location Map (A4 Size, MS Excel File)

Insert Project Route Map (A3 Long Size (AutoCAD or PDF Files))

Submission Letter

Project Location Map

Project Route Map

Table of Contents

Abbreviations

Main Part

Part	A	:	General 		1

A.1	Project Features 		1

A.1.1	Background 		1

A.1.2	Location 		2

A.1.3	Objectives 		2

A.1.4	Component 		3

A.1.5	Safeguards 		6

A.1.6	Project Cost 		7

A.1.7	Funding Arrangement 		7

A.1.8	Contract Packaging 		8

A.1.9	Project Implementation Structure 		8

A.1.10	Project Implementation Program 		9

A.2	Outline of the Services 		9

A.2.1	Objectives 		9

A.2.2	Scope 		10

A.2.3	Work Schedule and Reporting 		10

A.2.4	Organization and Staffing 		13

Part	B	:	Project Management 		20

B.1	:	Project Management 		20

Part	C	:	Previous Studies Review and Establishing Detailed Engineering Design Framework

C.1	:	Previous Studies Review 		xx

C.2	:	Detailed Engineering Design Framework 		xx

Part	D	:	Detailed Engineering Design and Procurement Planning

D.1	:	Contract Packaging 		xx

D.2	:	Surveys and Investigations 		xx

D.3	:	Civil Engineering Design 		xx

D.4	:	O&M Plan and Design 		xx

D.5	:	ITS Plan and Design 		xx

D.6	:	Electrical Facilities Design 		xx

D.7	:	Public Utilities Relocation Plan 		xx

D.8	:	Safeguards 		xx

D.9	:	Construction Planning 		xx

D.10	:	Project Cost Estimate 		xx

D.11	:	Procurement Document 		xx

D.12	:	Project Implementation Plan 		xx

Part	E	:	Technology Transfer

Appendix

Appendix	1	:	Baseline Schedule (Microsoft Project)

Abbreviations

XXXXX	:	XXXX XXXX XXXX XXXX XXXX XXXX XXXX XXXX

XXXXX	:	XXXX XXXX XXXX XXXX XXXX XXXX XXXX XXXX

XXXXX	:	XXXX XXXX XXXX XXXX XXXX XXXX XXXX XXXX

XXXXX	:	XXXX XXXX XXXX XXXX XXXX XXXX XXXX XXXX

XXXXX	:	XXXX XXXX XXXX XXXX XXXX XXXX XXXX XXXX

General

Project Features (Recent Updatesを適切な箇所に追加する)

Background

The preparation of Pre-F/S for the Project under BOT scheme was approved by MOT in Decision No. 2654/QD-BGTVT dated on September 11, 2000.  The Pre-F/S report was prepared by PMU85 and approved by the Prime Minister in his letter No. 493/CP-CN dated on April 21, 2003.  Continually, the preparation of F/S was approved by MOT in Decision No. 134/QD-BGTVT dated January 14, 2004.  The F/S report was also prepared by PMU85 and submitted to MOT in his letter No. 514/BQL-KHDA2 dated on May 11, 2005.  However, this BOT scheme Project did not materialize because of funding sources were not identified at that time.

Two (2) years later, the Project was approved as one (1) of the top priority projects in transport sector by GOVN in Decision No. 412/QD-TTg dated on April 11, 2007.  For carrying forward the Project, GOVN requested JETRO to assist a further study expecting materialization of the Project by a JBIC (currently JICA) loan scheme in June 2007.  JETRO conducted the study and submitted the study report to MOT on April 28, 2008.

In parallel with the JETRO study, WB declared GOVN to be eligible for the IBRD loan in November, 2007 and the Project was identified as the top priority use for the loan.  After submission of the JETRO study report, WB undertook the identification missions in April and June, 2008 and confirmed necessity of updating the JETRO study to meet his requirements and decided to allocate the fund from ongoing RNIP (IDA Credit No.: 3843-VN) to conduct the WB supplemental study.  The study report was prepared by PMU85 and submitted to MOT in his letter No. 551/BQl-KHDA2 dated on June 13, 2009.

In response to the supplemental study, WB engaged international consultants and undertook the WB appraisal study.  In the appraisal study, WB modified the alignment at 3 sections by taking into consideration social and environmental issues.  Based on the modified alignment, TEDI updated the WB supplemental study and submitted as the F/S report to MOT in April, 2010.  At present, this report is being approved by the Prime Minister.

Following the maturity of the Project, WB agreed to allocate the fund from RNIP for D/D and the Prime Minister allowed commencing the procurement of the consultant ahead of the F/S approval.  Through the procurement procedures, NK-NE-Chodai-TEC JV was selected and contracted with VEC.  Currently, VEC issued NTP in his letter No. ***/***-***** dated on August **, 2011 and D/D was officially started from September 1, 2011.

Outline of the Project background is shown in Figure A.1.

Figure A.1   Outline of the Project Background

Location

The Project road is a part of the North-South Expressway located in parallel with the existing NH1A and North-South Railway and passing through Danang city, Quang Nam and Quang Ngai provinces in the central region.  The road starts at the intersection of the Danang Bypass and NH14B in Danang city and ends at the connecting point with the planned City Ring Road at existing NH1A in Quang Ngai province.  The major socio-economic developments along the Project road are the Chu Lai Open Economic Zone in Quang Nam province and the Dung Quat Industrial Zone in Quang Ngai province.  As for the cultural properties, the Hoi An Ancient Town and My Son Sanctuary registered with the world heritage (cultural heritage) are existed along the Project road.

Project location map is shown in Figure A.2.

Figure A.2   Project Location Map

Objectives

The main objective of the Project is to improve transport linkage in the central region.  WB designed the performance indicators, targets and monitoring mechanisms, and surveyed the baseline data in the WB appraisal study (see A.1.1) to measure socioeconomic impacts of the Project.

Outline of the Project framework is shown in Figure A.3.

Figure A.3   Outline of the Project Framework

Component

Expressway Construction and O&M Equipment Provision

The main Project components are the expressway construction and O&M equipment provision.

Main features of the expressway construction and O&M equipment provision are shown in Table A.1, and Project facilities plan is shown in Figure A.4 in the next page, respectively.

Table A.1   Main Features of the Expressway Construction and O&M Equipment Provision

| No. | Item | Main Features |  | Ref. in TOR |
| --- | --- | --- | --- | --- |
| 1 | Road Length | 139.5 km |  | Component A |
|  |  |  | By Road Class: Expressway section: 131.5 km, Linking road section: 8.0 km | (TOR 1(1)) |
|  |  |  | By Jurisdiction: Danang city: 8.0 km, Quang Nam province: 92.0 km, Quang Ngai province: 39.5 km |  |
|  |  |  | BP: Intersection of the existing Danang bypass and NH14B in Danang city |  |
|  |  |  | EP: Connecting point with the planned city ring road at the existing NH1A in Quang Ngai province |  |
| 2 | Road Classification | Type A, Class 120 |  |  |
| 3 | Design Speed | 120 km/hr |  |  |
| 4 | Nos. of Lane | 4 lanes (Initial stage) |  |  |
|  |  |  | Ultimate Stage: Widened to 6 lanes (see Figure A.4) |  |
| 5 | Road With | Road and Bridge sections: 26.0 m, Tunnel section: 2@12.75 m=25.5 m |  |  |
| 6 | Bridges | 130 bridges (L=14,994.85 m) |  |  |
|  |  |  | Large River Bridge (L>100 m): 20 bridges (L=5,687.55 m) 1) |  |
|  |  |  | Other River Bridge (L<100 m): 10 bridges (L=603.85 m) |  |
|  |  |  | Stream Bridge: 8 bridges (L=354.90 m) |  |
|  |  |  | Canal Bridge: 18 bridges (L=666.00 m) |  |
|  |  |  | Viaduct: 21 bridges (L=3,073.45 m) |  |
|  |  |  | Overpass: 22 bridges (L=694.8 m) |  |
|  |  |  | Flyover: 19 bridges (L=2,252.00 m) |  |
|  |  |  | Interchange rampway bridge: 12 bridges (L=1,662.30 m) |  |
| 7 | Major River Bridge | 5 bridges |  |  |
|  |  |  | Thu Bong River: Ky Lam Bridge (KM017+662, L=962.0 m) |  |
|  |  |  | Ba Ren River : Chiem Son Bridge (KM020+185, L=410.0 m) |  |
|  |  |  | Tam Ky River : Tam Ky Bridge (KM068+308, L=307.0 m) |  |
|  |  |  | Tra Bong River : Tra Bong Bridge (KM109+320, L=452.0 m) |  |
|  |  |  | Tra Khuc River : Tra Khuc Bridge (KM125+700, L=846.0 m) |  |
| 8 | Tunnel | 1 tunnel (2@540 m) |  |  |
| 9 | Culvert | 375 culverts |  |  |
|  |  |  | Culvert Box: 188 culvert boxes (106 underpass and 82 drainage culverts) |  |
|  |  |  | Culvert Pipe: 187 culvert pipes |  |
| 10 | Soutground | Approximately 3.6 km |  |  |
| 11 | Interchange | 9 interchanges |  |  |
| 12 | Frontage Road | Approximately 59.7 km |  |  |
| 13 | Earth Works | Soil excavation: 10,000,000 m3, Rock excavation: 1,000,000 m3, Filling: 24,000,000m3 |  |  |
| 14 | Electrical Facilities | Power supply, road lighting, tunnel ventilation and safety facilities |  | Component B |
| 15 | ITS | Traffic management, toll collection1) and communication systems |  | (TOR 1(2)) |
| 16 | O&M Building | 26 locations |  | Component C |
|  |  |  | Traffic Management Center: 1 location | (TOR 1(3)) |
|  |  |  | Expressway Operation Center: 1 location |  |
|  |  |  | Toll Plaza Office: 9 locations |  |
|  |  |  | Toll Barrier: 2 locations |  |
|  |  |  | Toll Gate: 7 locations |  |
|  |  |  | Service Area: 2 locations |  |
|  |  |  | Parking Area: 4 locations |  |
| 17 | O&M Equipment | O&M vehicles, spare parts, maintenance equipment and consumables |  |  |

Note	1)	Including 5 major river bridges (see No.7)

2)	Including electric toll collection system in accordance with MOT Notice No.94/TB-BGTVT dated March 10, 2009

Figure A.4   Project Facilities Plan

Consulting Services

The overall consulting services for the Project consist of the Detailed Engineering Design (D/D), Procurement Assistance (P/A) and Construction Supervision (C/S).  The consulting services in this contract cover D/D and P/A only, without C/S (see A.2.2(2)).

Main scope of the overall consulting services is shown in Table A.2.

Table A.2   Main Scope of the Overall Consulting Services

| No. | Item | Main Scope |
| --- | --- | --- |
| 1 | Detailed Engineering Design (D/D) | Previous studies review and establishing detailed engineering design framework |
|  |  | Detailed engineering design and procurement planning |
| 2 | Procurement Assistance (P/A) | Assist in pre-qualification, bidding and contract negotiations |
| 3 | Construction Supervision (C/S) | Construction supervision |
|  |  | Assist in establishing of an O&M unit including capacity development |
|  |  | Assist in defect liability inspection |

Establishment of an O&M Unit

The O&M framework of the expressway section is under consideration.  Based on the F/S results, the estimated financial return by operating the expressway is low in early stage because of the forecasted traffic volume is small.  Therefore, O&M concessions are not attractive for private sectors, and the expressway is expected to operate by an O&M unit to be established under VEC in early stage.

Expected O&M framework for the Project road is shown in Figure A.5.

Figure A.5   Expected O&M Framework for the Project Road

Safeguards

Social and Environmental Assessment

The original EIA report based on the JETRO study was prepared by PMU85, and approved by MONRE in Decision No. 2378/QD-BTNMT dated on November 12, 2008.  The supplemental EIA report based on the current F/S alignment was also prepared by PMU85 and approved by MONRE in Decision No. ****/**-***** dated on ****** **, ****.  Category Aである旨記述。

Social and environmental assessment framework for the Project is shown in Figure A.6.

Figure A.6   Social and Environmental Assessment Framework for the Project Road

Land Acquisition and Resettlement

RAP based on the current F/S alignment was prepared by PMU85.

The land acquisition area and nos. of resettlement households in RAP is shown in Table A.3, and CPCSR framework for the Project road is shown in Figure A.7, respectively.

Table A.3   Land Acquisition Area and Nos. of Resettlement Households (Draft RAP)

| No. | Item | Unit | Danang | Quang Nam | Quang Ngai | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Land Acquisition Area | sq.m | 564,520 (6%) | 6,695,975 (66%) | 2,870,615 (28%) | 10,131,110 (100%) |
| 2 | Resettlement Households | nos. | 29 (4%) | 559 (66%) | 254 (30%) | 842 (100%) |

Figure A.7   CPCSR Framework for the Project Road

Project Cost

The estimated total Project cost in the current F/S amounts to 29,839 Bil.VND (1,570 Mil.USD).

Summary of the estimated Project cost is shown in Table A.4.

Table A.4   Summary of the Estimated Project Cost (Current F/S)

| No. | Item |  | Estimated Cost | Equiv. in USD1) | Remark |
| --- | --- | --- | --- | --- | --- |
|  |  |  | (Bil.VND) | (Mil.USD) |  |
| 1 | Construction Cost |  | 20,077 | 1,057 |  |
|  | a. | Road Works | 11,411 | 601 |  |
|  | b. | Bridge Works | 6,552 | 345 |  |
|  | c. | Tunnel Works | 443 | 23 |  |
|  | d. | Electrical/ITS Facilities and O&M Building Works, and O&M Equipment Provision | 1,671 | 88 |  |
| 2 | Other Cost (Project Management, Consulting Services and Others) |  | 2,409 | 127 | 12%*No.1 |
| 3 | Land Acquisition and Compensation Cost |  | 2,380 | 125 |  |
| 4 | Contingency |  | 4,973 | 261 | 20%*(No.1-No.3) |
|  | e. | Price Contingency | 3,730 | 65 | 15%*(No.1-No.3) |
|  | f. | Physical Contingency | 1,243 | 196 | 05%*(No.1-No.3) |
| Total |  |  | 29,839 | 1,570 |  |

Note	1)	1USD=19,000VND (exchange rate applied in the current F/S (April, 2010))

Funding Arrangement

D/D and P/A cost of all packages is funded by ongoing RNIP (IDA Credit No.: 3843-VN).  As for the construction and C/S cost, the civil works of northern section from Danang to Tam Ky and the ITS facilities and O&M building works, and O&M equipment provision for whole section will be funded by JICA loan, and the remaining civil works at the southern section from Tam Ky to Quang Ngai will be funded by a blend of IBRD loan and IDA credit terms.

JICA already signed L/A for a loan on June 15, 2011.  As for WB, the executive directors approved to provide a loan and two credits and schedule to sign L/A in April 2012.

Demarcation among WB, JICA and GOVN is shown in Table A.5.

Table A.5   Demarcation among WB, JICA and GOVN

| No. | Item |  | Section | Demarcation |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | WB | JICA | GOVN |
| 1 | Construction (Civil Works) |  | Danang to Tam Ky |  | ● |  |
|  |  |  | Tam Ky to Quang Ngai | ● |  |  |
| 2 | ITS Facilities and O&M Building Works, and O&M Equipment Provision |  | Whole Section |  | ● |  |
| 3 | Consulting Services | Detailed Engineering Design | Whole Section | ● |  |  |
|  |  | Procurement Assistance | Civil Works | ● |  |  |
|  |  |  | ITS/O&M Works |  | ● |  |
|  |  | Construction Supervision | Danang to Tam Ky |  | ● |  |
|  |  |  | Tam Ky to Quang Ngai | ● |  |  |
| 4 | Other Consulting Services | Project Monitoring Services |  | ● |  |  |
|  |  | Financial Audit (Phase 1) |  | ● |  |  |
|  |  | Financial Audit (Phase 2) |  | ● |  |  |
|  |  | Financial Capacity Building for VEC |  | ● |  |  |
| 5 | Others |  | Whole Section |  |  | ● |

Source:	Decision No. 1423/QD-BGTVT dated on June 30, 2011 (Approval on Bidding Plan of the Expressway Project of Danang - Quang Ngai),

Decision No. 1688/QD-BGTVT dated on July 28, 2011 (Approval on Additional Procurement Plan of the Expressway Project of Danang - Quang Ngai)

Contract Packaging

The procurement plan including the contract packaging for the WB section was approved by MOT in Decision No. 1423/QD-BGTVT dated on June 30, 2011, and the procurement plan for the JICA section was also approved by MOT in Decision No. 1688/QD-BGTVT dated on July 28, 2011.

After receiving NTP on **** **, 2011 for This Consulting Services, the Consultant proposed to revise the boundary of Package A3 and A4 from KM111+000 to KM112+000 because of the KM111+000 is located on the planned bridge in the current F/S.  This proposal was approved by MOT in Decision No. ****/QD-BGTVT dated on **** **, 2011.

Current contract packaging is shown in Table A.6.

Table A.6   Current Contract Packaging

| Contract Packaging |  |  |  |  | Construction Cost (Mil.USD) |  |
| --- | --- | --- | --- | --- | --- | --- |
| Category | Jurisdiction | No. | Station | Length | WB | JICA |
| Civil Works | Danang | PKG1 | KM000+000 - KM008+000 | 8.0km |  | **** |
|  | Quang Nam | PKG2 | KM008+000 - KM017+000 | 9.0km |  | **** |
|  |  | PKG3 | KM017+000 - KM022+000 | 5.0km |  | **** |
|  |  | PKG4 | KM022+000 - KM032+000 | 10.0km |  | **** |
|  |  | PKG5 | KM032+000 - KM042+000 | 10.0km |  | **** |
|  |  | PKG6 | KM042+000 - KM052+000 | 10.0km |  | **** |
|  |  | PKG7 | KM052+000 - KM065+000 | 11.3km |  | **** |
|  |  | PKGA1 | KM065+000 - KM081+500 | 16.5km | **** |  |
|  |  | PKGA2 | KM081+500 - KM100+000 | 18.5km | **** |  |
|  | Quang Ngai | PKGA3 | KM100+000 - KM112+000 | 12.0km | **** |  |
|  |  | PKGA4 | KM112+000 - KM125+000 | 13.0km | **** |  |
|  |  | PKGA5 | KM125+000 - KM139+500 | 14.5km | **** |  |
| ITS/O&M Build, Works, and O&M Equip. Provision | All | PKG8 | KM000+000 - KM131+500 | 131.5km |  | **** |
| Total |  |  |  | 131.5km | **** | **** |
|  |  |  |  |  | **** |  |

Project Implementation Structure

VEC has been designated as the Project Owner by MOT in Decision No. 220/QD-BGTVT dated on January 22, 2010.  On the other hand, VEC has appointed PMU85 and PMU1 as the Project Implementing Agencies in the implementation stage and signed principle contract with PMU85 on **** **, **** and with PMU1 on **** **, ****, respectively.  PMU85 is assigned for the D/D and construction of JICA section, and PMU1 is assigned for the construction of WB section.

Project implementation structure is shown in Figure A.8.

Figure A.8   Project Implementation Structure

Project Implementation Program

The Project implementation program was agreed among WB, JICA and GOVN during the JICA Appraisal in October, 2010.  However, this program is delayed ** months at present.

After receiving NTP on **** **, 2011 the Consultant modified the program in consideration of the above delay, and it was approved by MOT in Decision No. ****/QD-BGTVT dated on **** **, 2011.

Current Project implementation program is shown in Figure A.9.

P/Aの取り扱い方針決定後、

JICA案を修正する

Figure A.9   Current Project Implementation Program

Outline of the Services

Objectives

The objectives of the Services are to ensure the preparation of the D/D and assist VEC/PMU85 in procurement procedures with the most efficient and timely manner to deliver the required outputs in accordance with the Project implementation program (I/P).

Furthermore, appropriate technology transfers for VEC/PMU85 and key local professional staff are also required as a specific component in the Services to ensure smooth execution of the Project and sustainable development of the expressway network in Vietnam.

Scope

Mode

The Services are carried out by the 2 modes as shown in Table A.7.

Table A.7   Mode of the Services

| No. | Mode | Contents |
| --- | --- | --- |
| 1 | Primary Tasks | Arrangement for managing the Services by the Consultant, who is fully responsible to VEC/PMU85, for |
|  |  | adequacy and quality of the end outputs of the Services assuring duly compliance of the scope of the |
|  |  | Services specified in the contract. |
| 2 | Assistance Tasks | The Consultant provides technical advice and assistance in carrying out the works to be accomplished by |
|  |  | VEC/PMU85 through the Consultant’s professional ability; however, the Consultant is not responsible |
|  |  | for the end outputs. |

Scope

Scope of the Services is shown in Table A.8.

Table A.8   Scope of the Services

| Detailed Tasks |  |  |  | Ref. in TOR |
| --- | --- | --- | --- | --- |
| Part B Project Management |  |  |  | Proposed Task |
|  | B.1 |  | Project Management | Proposed Task |
| Part C Previous Studies Review and Establishing Detailed Engineering Design Framework |  |  |  | 3.2 |
|  | C.1 |  | Previous studies Review | 3.2(1) |
|  | C.2 |  | Detailed engineering design framework | 3.2(2) |
| Part D Detailed Engineering Design and Procurement Planning |  |  |  | 3.3 |
|  | D.1 |  | Contract Packaging | 3.3.1 |
|  |  | D.1.1 | Propose contract packaging | 3.3.1 |
|  | D.2 |  | Surveys and Investigations | 3.3.2 |
|  |  | D.2.1 | Collect relevant data and documents | 3.3.2(1) |
|  |  | D.2.2 | Conduct topographic survey | 3.3.2(2)(i), 3.5 |
|  |  | D.2.3 | Conduct hydrological survey and analysis | 3.3.2(2)(ii) |
|  |  | D.2.4 | Conduct geotechnical and geological investigations | 3.3.2(2)(iii) |
|  |  | D.2.5 | Conduct material source survey | 3.3.2(2)(iv) |
|  |  | D.2.6 | Conduct relevant facilities survey | 3.3.2(2)(v) |
|  |  | D.2.7 | Review traffic forecasting and conduct baseline surveys | 3.3.2(2)(vi) |
|  |  | D.2.8 | Conduct independent land valuation survey | 3.3.2(2)(vii) |
|  |  | D.2.9 | Conduct environmental and social surveys | 3.3.2(2)(viii) |
|  | D.3 |  | Civil Engineering Design | 3.3.3 |
|  |  | D.3.1 | Prepare basic design of civil structures | 3.3.3 |
|  |  | D.3.2 | Prepare detailed engineering design of civil structures | 3.3.3 |
|  | D.4 |  | O&M Plan and Design | 3.3.5 |
|  |  | D.4.1 | Prepare institutional and administrative arrangement plan | 3.3.5 |
|  |  | D.4.2 | Prepare O&M plan | 3.3.5 |
|  |  | D.4.3 | Prepare basic design of O&M buildings | 3.3.5 |
|  | D.5 |  | ITS Plan and Design | 3.3.4 |
|  |  | D.5.1 | Prepare ITS plan | 3.3.4(1) |
|  |  | D.5.2 | Prepare basic design of ITS facilities | 3.3.4(2) |
|  | D.6 |  | Electrical Facilities Design | Proposed Task |
|  |  | D.6.1 | Prepare detailed engineering design of electrical facilities | Proposed Task |
|  | D.7 |  | Public Utilities Relocation Plan | Proposed Task |
|  |  | D.7.1 | Prepare relocation plan of public utilities | Proposed Task |
|  | D.8 |  | Safeguards | 3.3.6, Annex A, Annex B |
|  |  | D.8.1 | Assist in updating EIA and EMP | 3.3.6, Annex A |
|  |  | D.8.2 | Assist in preparing and enforcing CPCSR | 3.3.6, Annex B |
|  | D.9 |  | Construction Planning | 3.3.7 |
|  |  | D.9.1 | Prepare construction plan | 3.3.7 |
|  | D.10 |  | Project Cost Estimate | 3.3.8 |
|  |  | D.10.1 | Estimate Project cost | 3.3.8 |
|  | D.11 |  | Procurement Documents | 3.3.9 |
|  |  | D.11.1 | Prepare procurement documents | 3.3.9 |
|  | D.12 |  | Project Implementation Program | 3.3.10 |
|  |  | D.12.1 | Prepare Project I/P | 3.3.10 |
| Part E Procurement Assistance |  |  |  | 3.4 |
|  |  | E.1 | Assist in tendering procedures | 3.4 |
| Part F Technology Transfer |  |  |  | 3.6 |
|  |  | F.1 | Provide training to VEC/PMU85 | 3.6 |
|  |  | F.2 | Provide training to the key local professional staff | Proposed Task |

Work Schedule and Reporting (Meetingを抽出。先行着手･BD/DD理由の説明)

The Service period is total 14 months, and divide into the basic design (4 months) and detailed engineering design (10 months).

Work schedule and reporting plan are shown in Figure A.10.

Figure A.10   Work Schedule and Reporting Plan (1/2)

Figure A.10   Work Schedule and Reporting Plan (2/2)

Organization and Staffing

Consultant’s Organization

Joint Venture

The Consultant Team consists of the joint venture of NK, NE, Chodai and TEC, and jointly and severally responsible for the Services among the joint venture firms.

Consultant Team

The Consultant Team divides into 6 teams and 4 supporting groups as explained below.

Organization structure of the Consultant Team is shown in Figure A.11.

Management Team

The management team is responsible for managing the Services, and all communications in the Services are exchanged through the team.  In the team, we organize the core team which consists of the representatives of each team and secure the consistent communication among the teams.

Civil Design Team

The civil design team is responsible for planning and designing the civil structures and consists of the civil design management, design group and the survey group.

The civil design management is responsible for establishing the design criteria and conditions, standard design of road accessories, culverts and bridges, and supervising the works of the design and survey groups, preparing the technical specifications and assisting the tendering procedures.

The design group is responsible for preparing the basic design and detailed engineering design, and consists of two (2) sections and each structural design.

O&M and ITS Team

The O&M and ITS team is responsible for preparing the O&M and ITS plan, basic design of the O&M buildings and ITS facilities, and detailed engineering design of the electrical facilities including the preparation of the technical specifications in the bidding documents.

Cost and Document Team

The cost and document team is responsible for preparing the construction plan, engineer’s cost estimate, procurement plan and documents, and assisting the tendering procedures.

Environmental Team

The environmental team works with the relevant organizations for updating EIA and EMP, preparing and enforcing CPCSR, and preparing the requirements for EMP in the bidding documents.

Training Team

The training team is responsible for identifying the training needs with VEC/PMU85, and preparing and coordinating the training materials in cooperation with the engineers/specialists of the respective fields assign in other teams.

Supporting Groups

****************************************************************************************************************************************.

Figure A.11   Organization Structure of the Consultant Team

Home Office Support

NK has the home office support system and utilize the technical, managerial and operational support including the review and verification of the design in the Services.

Conceptual image of NK’s home office support system is shown in Figure A.12

Figure A.12   Conceptual Image of NK’s Home Office Support System

Office Arrangement

ダナン、ハノイ

Staffing

Staffing and Task Assignment

Table A.9

Staffing Schedule

Table A.10-12

Table A.9   Task Assignment Matrix for Key Professional Staff

Table A.10   Time Schedule for Key International Professional Staff

Table A.11   Time Schedule for Key Local Professional Staff

Table A.12   Time Schedule for Local Supporting Staff

Project Management

Project Management

The Consultant established the practical Services management system by utilizing PMBOK and its construction extension and customized it to the characteristics of the Services as attached in Appendix 1.  In consideration of the large-scale and complex assignment, the Consultant prioritizes the communication, quality and schedule managements in the Services.

The system was explained by the Consultant in the kick-off meeting on September 1, 2011, and agreed among VEC/PMU85, the Consultant and other relevant organizations for publicizing, gaining consensus and smooth execution of the Services.  Therefore, the Consultant monitors and controls the activities according to the system during the Services.

The system consists of 13 management areas, and the integration management which is one of the management areas consisting of the processes and activities needed to identify, define, combine, unify and coordinate the various processes and activities within the management process groups, is useful for understanding of overall project management system.

Work diagram of project management based on integration management is shown in Figure B.1, and describes the methodology of work items subsequently.

Figure B.1   Work Diagram of Project Management based on Integration Management

Define the Services

The Consultant prepares the Services charter and its regulations in accordance with the contract of the Services.  The charter consists of the name, targets, requirements, outputs, conditions of completion, budgets, period, organization, responsibility and authority of members, means of communication, and constraints for the Services to be formally authorized the Services among the relevant organizations.

Prepare the Primary Services Scope Statement

The Consultant updates the primary Services scope statement proposed in the proposal with reflection of contract negotiation and defines the needs to be accomplished in the Services.  The statement consists of the objectives, assumptions, constraints and deliverables for the Services and provides a documented basis for making future decisions and for confirming or developing a common understanding of the Services scope among the relevant organizations.

Prepare the Services Management Plan

The Consultant prepares the Services management plan which defines how the Services is executed, monitored and controlled and addresses the communication, quality and schedule managements as explained above.  Based on (1) to (3) above, the Consultant prepares and submits the inception report.

Main contents of the prioritized 3 management areas are shown in Table B.1.

Table B.1   Main Contents of the Prioritized 3 Management Areas

| No. | Management Areas | Main Items | Contents |
| --- | --- | --- | --- |
| 1 | Communication | Communication requirements | among the relevant organizations and inside the consultant team |
|  |  | Communication item | including format, contents, level of detail, frequency, conveyor and receiver |
|  |  | Medium and technologies | meetings, letters, reports, workshops, etc. |
|  |  | Escalation process | identifying time frames and channel for escalation of issues |
|  |  | Method for updating | required conditions and process for updating |
|  |  | Common terminology | definitions for minimizing communication errors |
| 2 | Quality | Quality metrics | operational definition for quality control item, process and measurement |
|  |  | Quality checklists | structured tool for verifying QA/QC performance |
|  |  | Process improvement | process boundaries, configuration and metrics, and performance targets |
|  |  | Quality baseline | records for quality objectives |
|  |  | Method for updating | required conditions and process for updating |
| 3 | Schedule | Activity definition | activity list and attributes, and milestone list |
|  |  | Baseline schedule | baseline for progress monitoring and reporting |
|  |  | Monitoring and reporting | method for monitoring and reporting including format, contents and frequency |
|  |  | Method for updating | required conditions and process for updating |

Kick-off Meeting

Based on the inception report, the Consultant holds the kick-off meeting with not only the Project executing agency but also other relevant organizations for publicizing, gaining the consensus and smooth implementation of the Services.

Direct and Manage the Services Execution

The Consultant directs and manages the Services execution in accordance with the process of executing the Services defined in the Services management plan above (3) to achieve the requirements for the Services defined in the primary Services scope statement in above (2).  Information on the status of the management activities being performed to accomplish the Services is routinely collected, and the Consultant compiles and submits the status as the monthly progress report.

Monitor and control the Services

The Consultant monitors and controls the processes used to initiate, plan, execute and close the Services to meet the performance objectives defined in the Services management plan above (3).  Status of the activity is also compiled and submitted as the monthly progress report.

Control Integrated Change

The Consultant controls integrated change which is the process of reviewing all change requests and approving and controlling changes to deliverables and organizational process assets.  The approved changes are reflected to update the Services scope statement above (2) and the Services management plan above (3).  Status in the activity is also compiled and submitted as the monthly progress report.

Close the Services

The Consultant finalizes all of the activities across the process groups to formally close the Services.  Administrative closing procedure is prepared and reflected to direct and manage the Services execution above (5).  All of documents of the management activities are compiled and submitted as the Project completion report.

Previous Studies Review and Establishing Detailed Engineering Design Framework

Previous Studies Review

The Consultant reviews the previous studies especially current F/S and safeguard documents to take cognizance of the current arrangements of the Project and extracts the key issues which materially affect to the Services for discussing and obtaining the agreement with the relevant organizations.

Work diagram of previous studies review is shown in Figure C.1, and main subjects of reviewing previous studies are shown in Table C.1, respectively.

Figure C.1   Work Diagram of Previous Studies Review

Table C.1   Main Subjects of Reviewing Previous Studies

| No. | Category | Main Subjects |
| --- | --- | --- |
| 1 | Civil | Topography, geology and hydrology of the Project area |
|  |  | Technical standards1), and design criteria and conditions |
|  |  | Route alignment, geometric design and typical cross sections |
|  |  | Preliminary design of civil structures |
|  |  | Construction planning and preliminary Project cost estimates |
|  |  | Environmental impacts and its mitigation measures and RAP |
| 2 | O&M and ITS | O&M and ITS plan and those preliminary facilities design |

Note 1): Applicable technical standards for the Project were approved by MOT (Decision No. 362/QD-BGTVT dated on February 20, 2009)

Detailed Engineering Design Framework

The Consultant establishes the detailed engineering design framework which consists of the primary matters for execution of the Services based on C.1 above and obtains the approval from the relevant organizations.

Work diagram of detailed engineering framework is shown in Figure C.2, and the main contents of the detailed engineering design framework are shown in Table C.2.

Figure C.2   Work Diagram of Detailed Engineering Design Framework

Table C.2   Main Contents of the Detailed Engineering Design Framework

| No. | Item | Main Contents |
| --- | --- | --- |
| 1 | Detailed Engineering Design Framework | Updated applicable technical standards for the Project |
|  |  | Format and content of the B/Q items, cost estimate and procurement documents |
|  |  | Updated work schedule of the Services |

Detailed Engineering Design and Procurement Planning

Contract Packaging

Propose Contract Packaging

The contract packaging for the Project was already approved by MOT as shown in A.1.8.  In case modification is requested by VEC/PMU85, the Consultant studies it taking into account the affection for the D/D works and arrangement of the Project.

Work diagram of contract packaging is shown in Figure D.1,

Figure D.1   Work Diagram of Contract Packaging

Surveys and Investigations

Collect Relevant Data and Documents

The Consultant collects the relevant data and documents for basis of execution of the Services.

Work diagram of relevant data and documents is shown in Figure D.1, and main contents of relevant data and documents are shown in Table D.1, respectively.

Figure D.2   Work Diagram of Relevant Data and Documents

Table D.1   Main Contents of Relevant Data and Documents

| No. | Category | Main Contents |
| --- | --- | --- |
| 1 | Project Documents | Previous studies report |
|  |  | Related Decisions and Documents for the Project |
| 2 | Other Data and Documents | Relevant developing plan and existing facilities data in the Project area |
|  |  | Report and design document of the relevant project |
|  |  | Data related to the construction planning and cost estimate proper to the Project area |

Topographic Survey

The Consultant conducts the topographic and ROW surveys for engineering design, quantity take-off and CPCSR.  In consideration of the huge survey volumes, the Consultant outsources the site survey works to Vietnamese sub-consultants and supervises their performance by the Survey Engineer.  The selection of sub-consultant(s) and work plan including survey specifications shall be approved by VEC/PMU85.

In consideration of the rainy season, and short-period and work procedure of basic design, the Consultant conducts the site survey works in accordance with the following priorities:

1st Priority	:	Control points survey (whole section)

2nd Priority	:	Planimetric survey (thruway, sections for survey centerline study)

3rd Priority	:	Remaining surveys for basic design

Non-priority	:	Surveys for detailed engineering design

Work diagram of topographic survey is shown in Figure D.3, and tentative specifications and quantity for topographic survey works is shown in Table D.2, respectively.

Figure D.3   Work Diagram of Topographic Survey

Table D.2   Tentative Specifications and Quantity for Topographic Survey Works

Hydrological Survey and Analysis (洗堀深はこのタスク？or D.3.1でRiver担当？)

The Project road is on inundation plains; therefore, the Consultant conducts an inundation analysis to establish the hydrological requirements for not only river bridges but also bridges and culverts on land.

The Consultant analyzes the cost-effectiveness to optimize the viaduct plan.  However, flood control is required fairness to inhabitant; therefore, the Consultant takes into account social considerations to the result of cost-benefit analysis.

Work diagram of hydrological survey and analysis is shown in Figure D.4, and describes the methodology of work items subsequently.

Figure D.4   Work Diagram of Hydrological Survey and Analysis

Site Investigation

The Consultant conducts site investigations to identify the river locations, channels and crossing points with the Project road, and updates the specifications for hydrological survey including the river profile and cross-section surveys in the topographic survey (D.2.2).

-(4)	Hydrological Survey (Outsourcing Works)

The Consultant conducts hydrological survey by outsourcing to the Vietnamese sub-consultant(s), and supplements the existing hydrological data collected in Work Item (5) below.  The selection of sub-consultant(s) and work plan including survey specifications shall be approved by VEC/PMU85.

Tentative specifications for hydrological survey are shown in Table D.3.

Table D.3   Tentative Specifications for Hydrological Survey

| No. | Item | Object | Qty | Remarks |
| --- | --- | --- | --- | --- |
| 1 | Flood Water Level (Record) | Main Line (Road) | 417 points | 3 points/location*139 locations (1 location/km) |
|  |  | Viaduct, River Bridge | 153 points | 3 points/bridge*51 bridges (21 VDs, 20 LRBs, 10 ORBs) |
|  |  | Drainage Culvert | 807 points | 3 points/culvert*269 culverts (82 CBs-WT, 187 CPs) |
| 2 | Water Level (Observation) | 5 Large Rivers1) | 30 points | 2 points/section*3 sections/bridge*5 bridges |
| 3 | Water Velocity (Observation) |  | 30 points | 2 points/section*3 sections/bridge*5 bridges |

Note 1): Thu Bong (KM017+662), Ba Ren (KM020+185), Tam Ky (KM068+308), Tra Bong (KM109+320) and Tra Khuc (KM125+700) Rivers

- (5)	Data Collection

The Consultant collects hydro-meteorological data which is necessary for hydrological analysis.  Those data can be obtained from Hydro-meteorological Data Center.

Available hydro-meteorological data around the Project area is shown in Table D.4.

Table D.4   Available Hydro-meteorological Data around the Project Area

| No. | Category | Item | Station | Period |
| --- | --- | --- | --- | --- |
| 1 | Meteorology | Daily/Hourly Rainfall | 5 Meteorological and 9 Hydrological Stations | From 1947 to Present |
| 2 | Hydrology | Water Level | 10 Hydrological Stations | From 1976 to Present |
| 3 |  | Discharge and H-Q Curve | 2 Hydrological Stations (Thu Bon River) |  |

Source: BOT-F/S (2005)

- (6)	Rainfall Analysis

The Consultant analyzes and interpolates the rainfall data collected in Work Item (5) above, and estimates the probable basin mean rainfall and design hourly rainfall pattern for the runoff analysis.

Main contents of rainfall analysis are shown in Table D.5.

Table D.5   Main Contents of Rainfall Analysis

| No. | Category | Contents | Methodology |
| --- | --- | --- | --- |
| 1 | Analysis | Data Availability | Double Mass Curve Method |
| 2 | Interpolation | Missing Data |  |
| 3 | Estimation | Basin Mean Rainfall | Thiessen’s Polygon Method (Each Sub-basin) |
| 4 |  | Probable Basin Mean Rainfall | Pearson III Method or Gumbel Method |
| 5 |  | Design Hourly Rainfall Pattern |  |

- (7)	Runoff Analysis

The Consultant establishes basin model and conducts runoff analysis by storage function method.  The Consultant sets probable rainfall, hourly discharge record, runoff coefficient, river base flow, sub-basin parameter, river channel parameter and lag time, and estimates the discharge volume.  Probable rainfall adopts 2, 5, 10, 20, 50, 100 and 200 years return period plus year 1999 which is the maximum rainfall in the past.  Firstly, the Consultant calibrates the parameters in Thu Bon River with the discharge record collected in Work Item (5) above, and the parameters are reflected to others.

- (8)	River Flow Capacity Estimation

The Consultant prepares H-Q curves by utilizing the river cross-section survey data in D.2.2.  In case of discharge volume in 100 years return period is smaller than the river flow capacity, the Consultant estimates the design high-water-level at river bridges by unsteady analysis with HEC-RAS.  In case of the larger, the Consultant estimates the design high-water-level by inundation analysis in Work Item (9) below.

- (9)	Inundation Analysis

The Consultant sets inundation plain areas in consideration of the existing flood map and result in Work Item (8) above, and analyzes the flood water level and duration by inundation analysis with Mike-11.  The Consultant utilizes Aster GDEM as the geographical map, and reflects the topographic survey data and major facilities which heights are more than 50 cm to the mean elevation.  The Consultant conducts with/without cases, and the parameters in with cases are viaduct and culvert arrangements.

Image of Aster GDEM and inundation analysis is shown in Figure D.5.

| Aster GDEM | Inundation Analysis (MIKE-11) |
| --- | --- |

Figure D.5   Image of Aster GDEM and Inundation Analysis

- (10)	Cost-benefit Analysis

The Consultant divides the area into 500 m appropriate size of mesh and estimate the amount of inundation damages by the flood depth and duration estimated in Work Item (9) above.  The damages are estimated by each probable period, and sum up the amount in 100 years period.  The objects for the damages are mainly houses, crops and livestock.  The Consultant studies the unit prices and set the assets in each mesh, and applies the damage rates in Manual for Economic Analysis of Flood Control Project issued by MLIT-Japan.  Based on Work Item (1) to (10) above, the Consultant prepares the hydrological survey and analysis report.

Geotechnical and Geological Investigations (調査項目番号を統一する)

The Consultant conducts the geotechnical and geological investigations for detailed engineering design.  In consideration of the huge investigation volumes, the Consultant outsources the investigation works to Vietnamese sub-consultants and supervises their performance by the Soil/Geotechnical Engineer 2 and Geological Engineer (Tunnel).  The selection of sub-consultant(s) and work plan including investigation specifications shall be approved by VEC/PMU85.

The basic design of civil structures as described in D.3.1 may be modified from the current F/S in accordance with the results of several surveys and analyses, especially hydrological survey and analysis as described in D.2.3.  Therefore, the commencement of geotechnical and geological investigations shall be taken into account the maturity of the basic design of civil structures for avoiding re-investigations.

Work diagram of geotechnical and geological investigations, timing of commencement of each geotechnical and geological investigation items, and tentative specifications and quantity for geotechnical and geological investigations are shown in Figure D.6 and Tables D.6-7, respectively.

Figure D.6   Work Diagram of Geotechnical and Geological Investigations

Table D.6   Timing of Commencement of Each Geotechnical and Geological Investigation Items

| No. | Item |  | Timing | Predecessor |
| --- | --- | --- | --- | --- |
| 1 | Main Line (ML) | Normal Embankment and Excavation Section (NEE, h<12m) |  |  |
|  |  | High Embankment Section (HE, h>12m) |  |  |
|  |  | Deep Excavation Section (DE, h>12m) |  |  |
|  |  | Softground Section (SG) |  |  |
| 2 | Tunnel (TN) |  |  |  |
| 3 | Bridge (BR) | Large River Bridge (LRB, L>100m) |  |  |
|  |  | Other River Bridge (ORB, L<100m) |  |  |
|  |  | Stream Bridge (SB) |  |  |
|  |  | Canal Bridge (CB) |  |  |
|  |  | Viaduct (VD) |  |  |
|  |  | Overpass (OP) |  |  |
|  |  | Interchange Rampway Bridge (IRB) |  |  |
|  |  | Flyover (FO) |  |  |
| 4 | Culvert Box (CB) | Roadway (Thruway) |  |  |
|  |  | Roadway (Interchange) |  |  |
|  |  | Waterway (Thruway) |  |  |
|  |  | Waterway (Interchange) |  |  |
| 5 | Culvert Pipe (CP) | Thruway |  |  |
|  |  | Interchange |  |  |
| 6 | Interchange (IC) |  |  |  |
| 7 | Building (BL) |  |  |  |
| 8 | Existing Road (ER) |  |  |  |

Table D.7   Tentative Specifications and Quantity for Geotechnical and Geological Investigations

Material Source Survey

The Consultant conducts the material source survey by outsourcing to Vietnamese sub-consultant at locations identified with the local PCs to confirm quality and volume of borrow, sand and rock materials for detailed engineering design and construction planning.  The selection of sub-consultant(s) and work plan including investigation specifications shall be approved by VEC/PMU85.

Work diagram of material source survey is shown in Figure D.7, and tentative specifications and quantity for material source survey is shown in Table D.8, respectively.

Figure D.7   Work Diagram of Material Source Survey

Table D.8   Tentative Specifications and Quantity for Material Source Survey

| No. | Item | Unit | Quantity | Remarks |
| --- | --- | --- | --- | --- |
| A | Sampling and Laboratory Test |  |  |  |
| 1 | Borrow Material |  |  | 1 location/20 km*140 km = 8 locations |
| 1.1 | Undisturbed Sample Test | nos. | 24 | 3 samples/location*8 locations |
| 1.2 | Standard Compaction Test | nos. | 24 | 3 samples/location*8 locations |
| 1.3 | CBR Test | nos. | 24 | 3 samples/location*8 locations |
| 2 | Rock |  |  |  |
| 2.1 | Rock Sample Test | nos. | 15 | 3 samples/location*5 locations |
| 3 | Fine Sand |  |  |  |
| 3.1 | Sand Sample Test | nos. | 24 | 3 samples/location*8 locations |
| 3.2 | Standard Compaction Test | nos. | 24 | 3 samples/location*8 locations |
| 4 | Coarse Sand |  |  |  |
| 4.1 | Sand Sample Test | nos. | 6 | 3 samples/location*2 locations |

Relevant Facilities Survey

The Consultant conducts the relevant facilities survey in the Project area to identify the obstacles and cultural properties for extracting the design controls, and evaluate the level of capacity of existing roads and structures for construction planning.

Work diagram of relevant facilities survey is shown in Figure D.8, and main contents of relevant facilities survey is shown in Table D.9, respectively.

Figure D.8   Work Diagram of Relevant Facilities Survey

Table D.9   Tentative Specifications and Quantity for Material Source Survey

| No. | Category | Unit |
| --- | --- | --- |
| 1 | Design Controls | Identify the location, capacity and specification of the obstacles in the Project area |
|  |  | Identify the cultural buildings, temples, pagodas and relevant legal religious buildings |
| 2 | Construction Planning | Evaluate current traffic conditions of the existing roads in the Project area |
|  |  | Identify and evaluate loading capacity of bridges/culverts on potential construction roads |

Traffic Forecasting Review and Baseline Surveys

The Consultant reviews the traffic forecasting in the current F/S to establish the requirements for the engineering design from the traffic aspects.  In addition, the Consultant reviews the traffic survey data above and other relevant studies around the Project area to collect the available baseline data for the performance indicators in the Project framework (A.1.3).

In case of the appropriate data is not identified, the Consultant conducts the additional traffic survey by outsourcing to the Vietnamese sub-consultant.  The selection of sub-consultant(s) and work plan including survey specifications shall be approved by VEC/PMU85.

Work diagram of traffic forecasting review and baseline surveys is shown in Figure D.9, and tentative specifications and quantity for additional traffic survey is shown in Table D.10, respectively.

Figure D.9   Work Diagram of Traffic Forecasting Review and Baseline Surveys

Table D.10   Tentative Specifications and Quantity for Additional Traffic Survey

| No. | Surveys | Contents |  |
| --- | --- | --- | --- |
| 1 | Traffic Count | Day and Time | 1 weekday and 1 holiday, 24 hours in each day |
|  |  | Location | On the existing NH1A (2 segments Danang to Tam Ky and Tam Ky to Quang Ngai) |
|  |  | Survey Item | Traffic volume and composition on the both directions |
| 2 | Travel Time | Day and Time | 1 weekday and 1 holiday, peak traffic hour identified in the traffic count survey |
|  |  | Location | On the existing NH1A (2 segments Danang to Tam Ky and Tam Ky to Quang Ngai) |
|  |  | Survey Item | Travel time by each vehicle classification on the both directions |
| 3 | Traffic Accident | Period | Annual (the last 3 years) |
|  |  | Location | On the existing NH1A (2 segments Danang to Tam Ky and Tam Ky to Quang Ngai) |
|  |  | Survey Item | Nos. and type of traffic accident |

Independent Land Valuation Survey

The Consultant conducts the independent land valuation survey by outsourcing to the qualified land valuation consultant who is licensed by MOF and independent of all Project stakeholders to confirm the current market prices of land by location and use in each commune in the Project area.  The selection of sub-consultant(s) and work plan including survey specifications shall be approved by VEC/PMU85.

Work diagram of independent land valuation survey is shown in Figure D.10, and the potential land valuation consultants in the Project area is shown in Table D.11, respectively.

Figure D.10   Work Diagram of Independent Land Valuation Survey

Table D.11   Potential Land Valuation Consultants in the Project Area

| No. | City/Province | Name of Consultant | Tel | Fax | e-mail |
| --- | --- | --- | --- | --- | --- |
| 1 | Danang | Danang Valuation & Financial Services Limited Company | 0511-3887628 | 0511-3887532 | divc@vnn.vn |
| 2 | Quang Nam | Quang Nam Financial & Price Consultancy Joint-stock Company | 0510-3811657 | --- | mylangbd@yahoo.com.vn |
| 3 | Quang Ngai | Central Information & Valuation of Cost Joint-stock Company | 055-3818348 | --- | --- |

Environmental and Social Surveys

The Consultant conducts the site surveys for updating the existing EIA and EMP (A.1.5(1)) to confirm the environmental and social conditions in the Project area in accordance with the WB safeguard policies and JICA Guidelines for Environmental and Social Considerations, if necessary.

Work diagram of environmental and social surveys is shown in Figure D.11.

Figure D.11   Work Diagram of Environmental and Social Surveys

Civil Engineering Design

The Consultant divides the civil engineering design into the basic design (B/D) and detailed design (D/D) stages to proceed the design works efficiently.  The numbers of structure are huge; therefore, the Consultant prepares and utilizes the standard designs to assure the design quality.

Work items and demarcation between B/D and D/D stages is shown in Table D.12 in the next page.

Basic Design of Civil Structures

In the B/D stage, the Consultant establishes the fundamental conditions for thruway, and obtains the approval from PMU85 and other relevant organizations to avoid the re-design in the D/D design stage.

Main contents of the B/D stage are summarized below:

Establish design criteria and conditions;

Define typical cross sections;

Define thruway geometric design;

Prepare general view of all thruway bridges;

Prepare thruway culverts, tunnel and interchanges plan.

Work diagram of basic design of civil structures is shown in Figure D.12 in page **.

Detailed Design of Civil Structures

In the D/D stage, the Consultant conducts the remaining plan and design works in accordance with the B/D, and outsources all of bridges and interchanges design to the Vietnamese sub-consultants who have abundant experiences and resources for minimize the personnel inputs and shorten the design period.

Work diagram of detailed design of civil structures is shown in Figure D.13 in page **, and main contents of the road safety audit are shown in Table D.13, respectively.

Table D.13   Main Contents of the Road Safety Audit (PIARC Road Safety Manual 2004)

| No. | Classification | Category |  |  | Indicators |
| --- | --- | --- | --- | --- | --- |
| 1 | All Roads | Horizontal alignment |  |  | Curve radius, speed differentials, surface conditions, overturning, super-elevation, |
|  |  |  |  |  | road width, shoulders, roadside sight distance/forgiving road, passing in curve |
|  |  |  |  |  | warning signs and devices, combination of features |
| 2 |  | Vertical | Grade | Downhill | Generalities (stopping distance, brake temperature, compound grades, etc.), |
|  |  | alignment |  |  | location of road sign, drainage capacity and structure, brake check area, arrester beds |
|  |  |  |  | Uphill | Generalities (deceleration rate, speed reduction, etc.), climbing lanes, drainages |
|  |  |  | Curves |  | Generalities (sight distance, etc.), passing (pavement marking), drainages |
| 3 |  | Human factors (driver) |  |  | Strain, workload, perception, lane tracking, choice of speed, orientation, anticipation |
| 4 | Non-access | Sight distance | At grade intersections |  | Stopping, maneuvering, passing sight and decision sight distances, sight triangles |
|  | Control Roads |  | Two-way, two lane roads |  | Stopping, decision, passing and meeting sight distances |
| 5 |  | At grade intersections |  |  | Generalities (intersection type, access control, sight distance, |
|  |  |  |  |  | distance between intersections, conflict points at intersections, etc.) |

Note: The sight distance and at grade intersection are astride the plural categories in the table.

Table D.12   Work Items and Demarcation between B/D and D/D Stages

Figure D.12   Work Diagram of Basic Design of Civil Structures

Figure D.13   Work Diagram of Detailed Design of Civil Structures

O&M Plan and Design

Prepare Institutional and Administrative Arrangement Plan

Prepare O&M Plan

Prepare Basic Design of O&M Buildings

ITS Plan and Design

Prepare ITS Plan

Prepare Basic Design of ITS Facilities

Electrical Facilities Design

Prepare Detailed Engineering Design of electrical Facilities

The Consultant prepares the detailed engineering design of electrical facilities in relation with the basic design of civil structures (D.3.1), O&M plan (D.4.2) and ITS plan (D.5.1).  The works are included to coordinate and agree the power receiving plan with the power suppliers in the Project area.

Work diagram of electrical facilities design is shown in Figure D.19, and summary of electrical facilities plan in the current F/S is shown in Table D.x, respectively.

Figure D.19   Work Diagram of Electrical Facilities Design

Table D.xx   Summary of Electrical Facilities Plan in the Current F/S

| No. | Item | Facilities |
| --- | --- | --- |
| 1 | Power Supply | Power receiving points, receiving power voltages and capacities, and back-up power supply facilities |
| 2 | Road Lighting | Lighting source and output power, height, interval and location of lighting poles, and lighting calculation |
| 3 | Tunnel Ventilation and Safety | Reporting system, information system, fire-fighting facilities, and ventilation facilities, etc. |

Public Utilities Relocation Plan

Prepare Relocation Plan of Public Utilities

The Consultant confirms the public utilities which are necessary to relocate by the implementation of the Project based on the topographic survey (D.2.2), relevant facilities survey (D.2.6) and basic design of civil structures (D.3.1).  The Consultant prepares and agrees the relocation plan and cost estimate in cooperation with the relevant agencies.

Work diagram of public utilities relocation plan is shown in Figure D.20, and probable public utilities to be relocated by the Project are shown in Table D.xx, respectively.

Figure D.20   Work Diagram of Public Utilities Relocation Plan

Table D.xx   Probable Public Utilities to be relocated by the Project

| No. | Public utilities | Owners |
| --- | --- | --- |
| 1 | Electrical Line | Power Transmission Company No.2 (PTC2) |
| 2 | Telecommunication Line | Vietnam Posts and Telecommunications Group (VNPT) or |
|  |  | Vietnam Military Electronic and Telecommunications Corporation (VIETTEL) |
| 3 | Water Supply Pipe | Water Supply Company in each City/Province |
| 4 | Sewerage Pipe | Transport Works Management Company or Drainage Company |
| 5 | Irrigation Canal | Department of Agriculture and Rural Development (DARD) |

Safeguard

Assist in Updating EIA and EMP

The Consultant assists PMU85 in updating the EIA and EMP.  The environmental assessment for the Project is required to satisfy not only the Vietnamese law and regulations but also the WB/JICA safeguards policy.各種ガイドラインの名称を明示する。

The alignment in the current F/S was finalized through the appraisal process of the previous F/S.  However, existing EIA report describes that the used map of the F/S is too small scale (1/50,000) and not suitable for confirmation of appropriateness of the alignment.  Therefore, the Consultant reviews and confirms the appropriateness of the F/S alignment with the alternative study based on the adequate scale maps and design details. D/Dでもルート見直しがある旨説明。

In relation with the engineering design, the Consultant analyzes the environmental impacts by the Project and incorporates the environmental requirements to the engineering design.  Based on above, the Consultant develops the mitigation measures and updates the existing EIA and EMP including the preparation of draft TOR for the external monitoring by the third party during the construction stage.

Work diagram of updating EIA and EMP is shown in Figure D.xx.

Figure D.xx   Work Diagram of Updating EIA and EMP

Assist in Preparing and Enforcing CPCSR

The Consultant prepares the Resettlement Monitoring Plan (Inception Report) for the CPCSR activities and reports the internal monitoring results every month to assist the monitoring by PMU85.  As for the external monitoring by independent organizations, the Consultant assists PMU85 in preparing the draft TOR.

Work diagram of preparing and enforcing CPCSR is shown in Figure D.xx, and describes the methodology of work items subsequently.

Figure D.xx   Work Diagram of Updating EIA and EMP

Prepare Resettlement Monitoring Plan

The Consultant prepares the Resettlement Monitoring Plan (Inception Report), and obtains the approval from PMU85.  Based on the approved plan, the Consultant has a kick-off meeting with CARBs and confirms/obtains the consensus for the activities, procedures and schedule including the measurement for the gaps between the WB/JICA safeguards policy and the GOVN laws and regulations.

各種ガイドラインの名称を明示する。

Assist in Updating Census of PAPs

The Consultant assists CARBs in updating the list of PAPs in the current RAP in accordance with the ROW survey (D.2.2(16)) and cadastral maps in each PC.  The Consultant also assists CARBs in updating the census of PAPs by utilizing the existing data of PCs.  Detailed Measurement Survey (DMS) and Socio-economic Survey (SES) which mentioned in TOR are not carried out in the Services in accordance with the conclusions of contract negotiation.

Assist in Establishing Land Acquisition and Compensation Policy

The Consultant assists CARBs in conducting the consultation and disclosure program to all of key stakeholders and establishes the land acquisition and compensation policy as follows:

Options for compensation and resettlement;

Proposed resettlement sites, infrastructures, amenities and environmental management;

Assistance for generation of income, and restoration of livelihood and quality of life;

Special assistance program for poor and vulnerable PAPs;

Consideration for cultural sites, common properties and traditional resources;

Public consultation and disclosure mechanisms;

Entitlements and grievance procedures;

Unit price for compensation and resettlement;

Institutional, organizational and budgeting arrangements;

Implementation schedule.

Assist in Finalizing CPCSR

Based on the land acquisition and compensation policy above, the Consultant assists CARBs in finalizing the Comprehensive Plan on Compensation, Support and Resettlement (CPCSR) and obtains the approval from the relevant organizations.

Assist in Preparing Draft TOR (External Resettlement Monitoring)

As explained in Figure A.1.7, PMU85 shall engage the independent organizations for conducting the external resettlement monitoring in CPCSR framework.  The Consultant assists PMU85 in preparing the draft TOR for the external resettlement monitoring.

Internal Monitoring (CPCSR)

During the Services, the Consultant prepares and submits internal resettlement monitoring report every month to assist the monitoring by PMU85.

Construction Planning

Prepare Construction Plan

The Consultant prepares the construction methods and schedule, temporary facilities, and procurement plan of labors, materials and construction machines to estimate the proper Project cost.  Particularly, the volume of borrow materials are huge; therefore, the Consultant prepares the mass curve to estimate the proper hauling cost.

Work diagram of construction planning is shown in Figure D.xx, and image of construction scheduling and mass curve is shown in Figure D.xx, respectively.

Figure D.xx   Image of Construction Scheduling and Mass Curve

| Construction Scheduling (P3) | Mass Curve |
| --- | --- |

Figure D.xx   Image of Construction Scheduling and Mass Curve

Project Cost Estimate

Estimate Project Cost

The Consultant estimates the Project cost and annual fund requirements by contract packages in relation with the construction plan (D.9.1).  The cost estimate conditions are severely affected to the outputs; therefore, the Consultant proposes those conditions in advance and obtains the approval from VEC/PMU85 and other relevant organizations.

Work diagram of Project cost estimate is shown in Figure D.xx, and main contents of cost estimate conditions are shown in Table D.xx, respectively.

Figure D.xx   Work Diagram of Project Cost Estim

Table D.xx   Main Contents of Cost Estimate Conditions

| No. | Item | Contents |
| --- | --- | --- |
| 1 | Time of Cost Estimate | Time applied in the cost estimate (quarter) |
| 2 | Currency | Foreign currency applied in the cost estimate |
| 3 | Exchange Rate | Exchange rate for the foreign currency applied in the cost estimate |
| 4 | Classification Condition of Currency | Classification conditions of foreign and local currencies applied in the cost estimate |
| 5 | Tax Exemption | Items of the tax exemption applied in the cost estimate |
| 6 | Cost Estimate Standards | Cost estimate standards applied in the cost estimate |
|  |  | (productivity, and unit cost of materials, labors, construction machine operation and hauling ) |
| 7 | Price Fluctuation Rate | Price fluctuation rate of the foreign and local currencies applied in the cost estimate |
| 8 | Physical Contingency Rate | Physical contingency rate applied in the cost estimate |

Procurement Documents

Prepare Procurement Documents

The Consultant prepares the procurement plan, P/Q and bidding documents including those evaluation criteria in accordance with the current WB/JICA procurement guidelines and standard forms.

The conditions of contract in the bidding documents are applied the appropriate series of FIDIC, and the technical specifications including EMP with supervision of engineers/specialists in every technical field for ensuring the quality.

Work diagram of procurement documents preparation is shown in Figure D.xx.

Figure D.xx   Work Diagram of Procurement Documents Preparation

Project Implementation Program

Prepare Project I/P

The current Project I/P is shown in Figure A.9.  The Consultant confirms and updates this Project I/P with VEC/PMU85 in the beginning of the Services.  During the Services, the Consultant studies the construction period in each contract package and updates the Project I/P in accordance with the results of construction planning (D.9), if required.ネゴでは開始後4カ月以内に関係機関を交えて決定とした。

Work diagram of Project implementation program is shown in Figure D.xx.

Figure D.xx   Work Diagram of Project Implementation Program

Procurement Assistance

Assist in Tendering Procedures

The Consultant assists VEC/PMU85 in tendering procedures of all civil contract packages in accordance with the WB/JICA procurement guidelines.  In the assistance, the Consultant conducts the independent P/Q and bid evaluations to advise VEC/PMU85 on issues related to contract negotiations.

Work diagram of procurement assistance is shown in Figure E.1.

Figure E.1   Work Diagram of Procurement Assistance

Technology Transfer

Provide Training to VEC/PMU85

The Consultant provides the appropriate technology transfer to VEC/PMU85 for enhancing the necessary knowledge and capacity to ensure the smooth execution of the Project and sustainable development of the expressway network in Vietnam.

The objectives of the training are that VEC/PMU85 acquires the knowledge and capacity which are necessary to manage and control the Project smoothly and to make decisions with sufficient technical backgrounds for the important issues and peculiar matters of expressway in the Project.  Based on the knowledge and capacity acquired by the training program, VEC/PMU85 is able to manage and control the expressway development projects by themselves.

The Consultant assigns the key professional staff as the Training Specialists and identifies the training needs with VEC/PMU85 in the beginning of the Services.  Based on the needs above, the Consultant prepares the training plan which consists of the training themes, program, trainees and implementation schedule.  The training schedule is taken into account the work schedule of the Services to provide the workshops at appropriate timing in advance of the execution of the Services.

In corporation with each engineer/specialist in the respective fields, the training specialists prepare the appropriate training materials and hold the workshops to VEC/PMU85.

Tentative training themes are as follows:

Project management of all project phases (PMBOK);

Safeguards (WB/JICA safeguards policy);

Expressway road safety and auditing system (PIARC road safety manual);

Expressway administration, O&M, ITS and ETC systems (including overseas study tour).

Work program of technology transfer to VEC/PMU85 is shown in Figure F.1, and tentative training program of the overseas study tour is shown in Table F.1, respectively.

Figure F.1   Work Diagram of Technology Transfer to VEC/PMU85

Table F.1   Tentative Training Program of Overseas Study Tour

| Day | Time | Program | Contents | Stay at |
| --- | --- | --- | --- | --- |
| 1 | Night | Move to Narita | - Move from Hanoi to Narita by airplane | Flying overnight |
| 2 | AM | Move to Tokyo | - Move from Narita to Tokyo by car | Tokyo |
|  | PM | Visit to MLIT | - Introduce expressway administrative policy |  |
| 3 | AM | Visit to JEHDRA | - Introduce expressway business and implementation scheme | Tokyo |
|  |  | Visit to ORSE | - Introduce ETC technology and standardized system |  |
|  | PM | Visit to HIDO | - Introduce advanced ITS technology |  |
|  |  | Visit to VICS center | - Introduce traffic information and VICS system |  |
| 4 | AM | Visit to MEX | - Introduce traffic management and O&M system for intra-urban expressway | Tokyo |
|  | PM | Visit to NEXCO | - Introduce traffic management and O&M system for inter-urban expressway |  |
| 5 | AM | Move to Narita | - Move from Tokyo to Narita by car | Hanoi |
|  |  | Move to Hanoi | - Move to Narita to Hanoi by airplane |  |

Provide Training to the Key Local Professional Staff

During the Services, the Consultant provides person-to-person technology transfer to key local professional staff by co-working style in the respective fields.  It is expected that the key local professional staff are acquired day-to-day knowledge and skills necessary for the execution of the Services.

Work diagram of technology transfer to key local professional staff is shown in Figure F.2.

Figure F.2   Work Diagram of Technology Transfer to Key Local Professional Staff