## 111004
[23 empty] | As of | [5 empty] | 2011-10-06
Progress Monitoring of Instruction of Cross Structure Survey
Contract Package | WBS No. |  | Work Item | Person in Charge | Taget Completed Date | September |  | October | [14 empty] | November | [5 empty] | Next work as of Today
[6 empty] | 15 | 30 | 1 | [6 empty] | 15 | [6 empty] | 31 | 1 |  |  |  |  | 15
PKG01 （1～8km） | 01 | 2 | 3D Point Survey | STP | 13/9/2011 | [23 empty] | STP Preparation of Instruction
|  | 5 | Fix Design CL | Nakai | 21/9/2011
|  | 6 | Design CL Handover | Ishimoto | 30/9/2011
|  | 9 | Crossing Plan (for Roadway/Waterway/HVL) | Nakai | 3/10/2011
|  | 10 | Prepare Instruction Material | Si/Chau | [5 empty] | 01-10
|  | 11 | Instruction to Suveyor | Nagai | [6 empty] | 01-11
PKG02 （8～17km） | 02 | 2 | 3D Point Survey | STP | 17/9/2011 | [23 empty] | Nakai Crossing Planning
|  | 5 | Fix Design CL | Nakai | 23/9/2011
|  | 6 | Design CL Handover | Ishimoto | 30/9/2011
|  | 9 | Crossing Plan (for Roadway/Waterway/HVL) | Nakai | 7/10/2011 |  |  |  | 02-9
|  | 10 | Prepare Instruction Material | Si/Chau | [5 empty] | 02-10
|  | 11 | Instruction to Suveyor | Nagai | [7 empty] | 02-11
PKG03 （17～22km） | 03 | 2 | 3D Point Survey | STP | 3/10/2011 | [23 empty] | No Action
|  | 5 | Fix Design CL | Nakai | 24/9/2011
|  | 6 | Design CL Handover | Nagai | 3/10/2011
|  | 9 | Crossing Plan (for Roadway/Waterway/HVL) | Nakai | [7 empty] | 03-9
|  | 10 | Prepare Instruction Material | Si/Chau | [8 empty] | 03-10
|  | 11 | Instruction to Suveyor | Nagai | [10 empty] | 03-11
PKG04 （22～32km） | 04 | 2 | 3D Point Survey | STP | 3/10/2011 | [23 empty] | STP 3D Survey
|  | 5 | Fix Design CL | Nakai | 27/9/2011
|  | 5a | Revise Design CL | Nakai | 6/10/2011
|  | 6 | Design CL Handover | Nagai | (10/10/2011) | [6 empty] | 04-6
|  | 9 | Crossing Plan (for Roadway/Waterway/HVL) | Nakai | [10 empty] | 04-9
|  | 10 | Prepare Instruction Material | Si/Chau | [11 empty] | 04-10
|  | 11 | Instruction to Suveyor | Nagai | [12 empty] | 04-11
PKG05 （32～42km） | 05 | 2 | 3D Point Survey | STP | (7/10/2011) | [23 empty] | STP 3D Survey Nakai Design CL
|  | 5 | Fix Design CL | Nishioka | (8/10/2011) | [5 empty] | 05-5
|  | 6 | Design CL Handover | Nagai | [7 empty] | 05-6
|  | 9 | Crossing Plan (for Roadway/Waterway/HVL) | Nakai | [12 empty] | 05-9
|  | 10 | Prepare Instruction Material | Si/Chau | [13 empty] | 05-10
|  | 11 | Instruction to Suveyor | Nagai | [14 empty] | 05-11
PKG06 （42～52km） | 06 | 2 | 3D Point Survey | STP | (10/10/2011) | [23 empty] | STP 3D Survey Nakai Design CL
|  | 5 | Fix Design CL | Nishioka | (11/10/2011) | [6 empty] | 06-5
|  | 6 | Design CL Handover | Nagai | [8 empty] | 06-6
|  | 9 | Crossing Plan (for Roadway/Waterway/HVL) | Nakai | [14 empty] | 06-9
|  | 10 | Prepare Instruction Material | Si/Chau | [15 empty] | 06-10
|  | 11 | Instruction to Suveyor | Nagai | [16 empty] | 06-11
PKG07 （52～65km） | 07 | 2 | 3D Point Survey | STP | (8/10/2011) | [23 empty] | STP 3D Survey
|  | 5 | Fix Design CL | Nishioka | (15/10/2011) | [9 empty] | 07-5
|  | 6 | Design CL Handover | Nagai | [11 empty] | 07-6
|  | 9 | Crossing Plan (for Roadway/Waterway/HVL) | Nakai | [16 empty] | 07-9
|  | 10 | Prepare Instruction Material | Si/Chau | [17 empty] | 07-10
|  | 11 | Instruction to Suveyor | Nagai | [18 empty] | 07-11
PKGA1 （65～81.5km） | A1 | 2 | 3D Point Survey | STP | (20/10/2011) | [23 empty] | STP 3D Survey
|  | 5 | Fix Design CL | Nishioka | (13/10/2011) | [8 empty] | A1-5
|  | 6 | Design CL Handover | Nagai | [10 empty] | A1-6
|  | 9 | Crossing Plan (for Roadway/Waterway/HVL) | Magario | [11 empty] | A1-9
|  | 10 | Prepare Instruction Material | New A/B | [12 empty] | A1-10
|  | 11 | Instruction to Suveyor | Nagai | [14 empty] | A1-11
PKGA2 （81.5～100km） | A2 | 2 | 3D Point Survey | STP | (12/10/2011) | [23 empty] | STP 3D Survey
|  | 5 | Fix Design CL | Nishioka | (13/10/2011) | [8 empty] | A2-5
|  | 6 | Design CL Handover | Nagai | [10 empty] | A2-6
|  | 9 | Crossing Plan (for Roadway/Waterway/HVL) | Magario | [14 empty] | A2-9
|  | 10 | Prepare Instruction Material | New A/B | [15 empty] | A2-10
|  | 11 | Instruction to Suveyor | Nagai | [16 empty] | A2-11
PKGA3 （100～112km） | A3 | 2 | 3D Point Survey | STP | (12/10/2011) | [23 empty] | STP 3D Survey
|  | 5 | Fix Design CL | Nishioka | (13/10/2011) | [8 empty] | A3-5
|  | 6 | Design CL Handover | Nagai | [10 empty] | A3-6
|  | 9 | Crossing Plan (for Roadway/Waterway/HVL) | Magario | [16 empty] | A3-9
|  | 10 | Prepare Instruction Material | New A/B | [17 empty] | A3-10
|  | 11 | Instruction to Suveyor | Nagai | [18 empty] | A3-11
PKGA4 （112～125km） | A4 | 2 | 3D Point Survey | STP | (12/10/2011) | [23 empty] | STP 3D Survey
|  | 5 | Fix Design CL | Nishioka | (13/10/2011) | [8 empty] | A4-5
|  | 6 | Design CL Handover | Nagai | [10 empty] | A4-6
|  | 9 | Crossing Plan (for Roadway/Waterway/HVL) | Magario | [18 empty] | A4-9
|  | 10 | Prepare Instruction Material | New A/B | [19 empty] | A4-10
|  | 11 | Instruction to Suveyor | Nagai | [20 empty] | A4-11
PKGA5 （125～139.5km） | A5 | 2 | 3D Point Survey | STP | (8/10/2011) | [23 empty] | STP 3D Survey
|  | 5 | Fix Design CL | Nishioka | (13/10/2011) | [8 empty] | A5-5
|  | 6 | Design CL Handover | Nagai | [10 empty] | A5-6
|  | 9 | Crossing Plan (for Roadway/Waterway/HVL) | Magario | [20 empty] | A5-9
|  | 10 | Prepare Instruction Material | New A/B | [21 empty] | A5-10
|  | 11 | Instruction to Suveyor | Nagai | [22 empty] | A5-11
Ishimoto
|  |  |  | Nagai | [6 empty] | 01-11 | 02-11 04-6 05-6 | 06-6 |  | 03-11 A1-6 A2-6 A3-6 A4-6 A5-6 | 07-6 | 04-11 |  | 05-11 A1-11 |  | 06-11 A2-11 |  | 07-11 A3-11 |  | A4-11 |  | A5-11
|  |  |  | Nakai |  |  |  |  | 02-9 |  |  | 03-9 |  |  | 04-9 |  | 05-9 |  | 06-9 |  | 07-9
|  |  |  | Magario | [11 empty] | A1-9 |  |  | A2-9 |  | A3-9 |  | A4-9 |  | A5-9
|  |  |  | Nishioka | [6 empty] | 05-5 | 06-5 |  | A1-5 A2-5 A3-5 A4-5 A5-5
|  |  |  | Si/Chau | [5 empty] | 01-10 02-10 |  |  | 03-10 |  |  | 04-10 |  | 05-10 |  | 06-10 |  | 07-10
|  |  |  | New A/B | [12 empty] | A1-10 |  |  | A2-10 |  | A3-10 |  | A4-10 |  | A5-10