## Task_Table (111128)
ID | Task Name |  |  |  | Person in Charge | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Milestone | [8 empty] | 1
2 |  | Approval | [7 empty] | 2
3 |  |  | Approval by MOT | [6 empty] | 3
4 |  |  |  | MOT: Modified Bidding Plan | [5 empty] | 4
5 |  |  |  | MOT: Basic Design Report | [5 empty] | 4
6 |  |  |  | MOT: Design Report | [5 empty] | 4
7 |  |  |  | MOT: Bidding Documents | [5 empty] | 4
8 |  |  | Approval by JICA | [6 empty] | 3
9 |  |  |  | JICA: Modified Contract Packaging | [5 empty] | 4
10 |  |  |  | JICA: PQ Documents | [5 empty] | 4
11 |  |  |  | JICA: Bidding Documents | [5 empty] | 4
12 |  |  | Approval by Quang Nam Province | [6 empty] | 3
13 |  |  |  | Basic Design Report | [5 empty] | 4
14 |  | Meeting | [7 empty] | 2
15 |  |  | QN-PC: Basic Desgin Meeting | [6 empty] | 3
16 |  |  | MOT: Basic Design Meeting | [6 empty] | 3
17 |  |  | MOT: Appraisal Meeting | [6 empty] | 3
18 |  | Submission of Report | [7 empty] | 2
19 |  |  | Basic Design Report | [6 empty] | 3
20 |  |  | Design Documents | [6 empty] | 3
21 |  |  | Construction Plan Report | [6 empty] | 3
22 |  |  | Work Quantity Report | [6 empty] | 3
23 |  |  | Cost Estimate Report | [6 empty] | 3
24 |  | Submission of Procurement Documents | [7 empty] | 2
25 |  |  | Revised Contract Packaging Plan | [6 empty] | 3
26 |  |  | PQ Document | [6 empty] | 3
27 |  |  | Bidding Documents | [6 empty] | 3
28 | Procurement Assistance |  |  |  | Hung |  |  |  |  | 1
29 |  | Revised Contract Packaging Plan | [7 empty] | 2
30 |  | PQ Document | [7 empty] | 2
31 |  | Bidding Documents | [7 empty] | 2
32 | Engineering Survey | [8 empty] | 1
33 |  | Topographic Survey |  |  | Suzuki |  |  |  |  | 2
34 |  | Hydrological Survey |  |  | Lamsal |  |  |  |  | 2
35 |  | Geological Survey | [7 empty] | 2
36 |  | Utilities Relocation Survey |  |  | Suzuki |  |  |  |  | 2
37 | Engineering Design | [8 empty] | 1
38 |  | Road Design |  |  | Nagai |  |  |  |  | 2
39 |  |  | Basic Design Report | [6 empty] | 3
40 |  |  | Detailed Design Report | [6 empty] | 3
41 |  |  | Drawings | [6 empty] | 3
42 |  |  | Work Quantity Report | [6 empty] | 3
43 |  |  | Technical Specifications | [6 empty] | 3
44 |  | Bridge Design |  |  | Oba |  |  |  |  | 2
45 |  |  | Basic Design Report | [6 empty] | 3
46 |  |  | Detailed Design Report | [6 empty] | 3
47 |  |  | Drawings | [6 empty] | 3
48 |  |  | Work Quantity Report | [6 empty] | 3
49 |  |  | Technical Specifications | [6 empty] | 3
50 |  | Other Structure Design |  |  | Nagai |  |  |  |  | 2
51 |  | Construction Plan |  |  | Nakagi |  |  |  |  | 2
52 |  | Cost Estimate |  |  | Nakagi |  |  |  |  | 2
53 | Update EIA/EMP/RAP | [8 empty] | 1
54 |  | Update EIA | [7 empty] | 2
55 |  | Update EMP | [7 empty] | 2
56 |  | Update RAP |  |  | Long |  |  |  |  | 2
57 | Imploementaion Program |  |  |  | Ishimoto |  |  |  |  | 1
58 | Land Acquisition Monitoring | [8 empty] | 1
59 |  | ROW Drawings |  |  | Nagai |  |  |  |  | 2
60 |  | ROW Staking |  |  | Nagai |  |  |  |  | 2
61 |  | Land Evaluation |  |  | Long |  |  |  |  | 2
62 |  | Payment to Land Owner |  |  | Long |  |  |  |  | 2