## Sheet1
Version 2: October 19, 2011
Recent Updates (Main Update after Proposals Submission (1 June 2010))
Items |  |  |  | Issued by | Ref. No. | Date | Subject | Remark
F/S | MOT Approval | Approval |  | MOT | Decision No. 2656/QD-BGTVT | 10 September 2010 | Approval on investment of Danang - Quang Ngai Expressway Development Project
|  |  |  | Government Office | Document No. 4684/VPCP-KTN | 07 July 2010 | Approval of the Prime Minister on investment of Danang - Quang Ngai Expressway Development Project and assigning the Ministry of Transpot to approve
|  | Appraisal |  | MOT | Document No. 6188/BGTVT-KHDT | 08 September 2010 | Appraisal results of Danang - Quang Ngai Expressway Development Project
|  | Request for Approval |  | VEC | Letter No. 384/TTr-VEC | 07 September 2010
|  |  |  | VEC | Letter No. 160/TTr-VEC | 30 July 2010 |  | w/ TEDI F/S July 2010
|  | Comments on Draft F/S | Answer by TEDI | TEDI | Document No. 1826/TEDI-VPDA | 14 July 2010
|  |  | (F/S Consultant) | TEDI | Document No. 1220/TEDI-VPDA | 14 May 2010
|  |  | Comments from | MPI | Document No. 3528/BKH-KCHT | 28 May 2010
|  |  | Relevant Organizations | MOF | Document No. 7713/BTC-DT | 15 June 2010
|  |  |  | MOT-TISD | Document No. 99/KCHT | 20 April 2010
|  |  |  | MOT-ED | Document No. 86/MT | ---
|  |  |  | MOT-ICD | Document No. 153/HTQT | 15 April 2010
|  |  |  | MOT-FD | --- | 16 April 2010
|  |  |  | MOT-LD | Document No. 141/PC | 16 April 2010
|  |  |  | MOT-TCQM | Document No. 291/QLXD-TD1 | 21 April 2010
|  |  |  | State Bank | Document No. 3897/NHNN-HTQT | 26 May 2010
|  |  |  | Danang CPC | Document No. 3058/NBND-QLDT | 26 May 2010
|  |  |  | Quang Nam PPC | Document No. 1732/UBND-KTN | 31 May 2010
|  |  |  | Quang Ngai PPC | Document No. 720/UBND-KTN | 26 March 2009
|  |  |  | Command of Military Zone No. 5 | Document No. 1024/BTL-TC | 30 June 2010
|  |  | Request to Ministries | Government Office | Document No. 3170/VPCP-KTN | 13 May 2010
|  |  | Request to Localities | VEC | Document No. 647/VEC-DA | 15 April 2010
Funding | JICA Loan | L/A |  | GOVN-JICA |  | 15 June 2011
|  | Minutes (L/A) |  | GOVN-JICA |  | 17 January 2011
|  | M/D (Appraisal) |  | GOVN-JICA |  | 21 October 2010
| WB Loan | Minutes (Appraisal) |  | GOVN-WB |  | 21 April 2011
| Common |  |  | MOT | Decision No. 666/QD-BGTVT | 06 April 2011 | Approval on adjustment of investment structure for Danang - Quang Ngai Expressway Development Project
|  | VEC's Responsibility |  | Government Office | Document No. 4684/VPCP-KTN | 07 July 2010 | Approval of the Prime Minister on investment of Danang - Quang Ngai Expressway Development Project and assigning the Ministry of Transpot to approve
|  | (Borrowing/Paying Loan) |  | MOF | Document No. 695/BTC-QLN | 13 August 2010
Procurement | JICA Portion | Approval |  | MOT | Decision No. 1688/QD-BGTVT | 28 July 2011 | Approval on additional procurement plan of Danang - Quang Ngai Expressway Development Project, section funded by JICA
|  | Appraisal |  | MOT | Document No. 520/CQLXD-PCDT | 13 July 2011
|  | Request |  | VEC | Letter No. 1145/TTr-VEC | 29 June 2011
| WB Portion | Approval |  | MOT | Decision No. 1423/QD-BGTVT | 30 June 2011 | Approval on additional procurement plan of Danang - Quang Ngai Expressway Development Project, section funded by WB
|  |  |  | MOND | Decision No. 3825/QD-BQP | 04 October 2010
|  | Appraisal |  | MOT | Document No. 454/CQLXD-PCDT | 16 June 2011
|  | Procurement Plan |  | VEC | Letter No. 333/VEC-DA | 04 March 2011
|  | Demining Plan |  | VEC | Letter No. 1225/TTr-VEC | 27 September 2010
| Common | Approval |  | MOND | Decision No. 1286/QD-BQP | 20 April 2011 | Approval of technical execution plan for searching and eliminating bombs and explosives for Danang - Quang Ngai Expressway Development Project
|  | Appraisal |  | MOT | Document No. 387/CQLXD-PCDT | 20 May 2011
|  | Procurement/Demining Plan |  | VEC | Letter No. 948/VEC-DA | 01 June 2011
|  |  |  | VEC | Letter No. 719/TTr-VEC | 25 April 2011
Organization |  |  |  | MOT | Decision No. 2149/QD-BGTVT | 19 September 2011 | (PMU85: Implementation Organization)
Design Change |  |  |  | PMU85 | Letter No. 50/BQL-DNQN | 04 October 2011
(Additional IC at KM13+625 and Re-alignment between KM70 to KM80) |  |  |  | PMU85 | Letter No. 49/BQL-DNQN | 03 October 2011
|  |  |  | VEC | Letter No. 1855/VEC-KTCNMT | 30 September 2011
|  |  |  | Quang Nam PPC | Circular No. 346/TB0UBND | 13 September 2011
|  |  |  | PMU85 | Letter No. 43/BQL-DNQN | 01 September 2011
|  |  |  | VEC | Letter No. 1449/VEC-KTCNMT | 10 August 2011
|  |  |  | VEC | Letter No. 1269/VEC-KTCNMT | 18 July 2011
|  |  |  | Quang Nam PPC | Document No. 2107/UBND-KTN | 17 June 2011
|  |  |  | MOND | Document No. 2489/QD-TM | 01 December 2010
|  |  |  | MOT | Decision No. 2656/QD-BGTVT | 10 September 2010 | Approval on investment of Danang - Quang Ngai Expressway Development Project
|  |  |  | MOT | Notice No. 325 | 06 August 2010
|  |  |  | Quang Nam PPC | Document No. 1732/UBND-KTN | 31 May 2010
|  |  |  | Government Office | Document No. 8745/VPCP-KTN | 08 December 2009 | (Approval of Updating Project for DT609)
Project I/P (Commencement of Construction Works for Priority Packages in Q3 2012) |  |  |  | It was instructed in Letter No. 1816/PMU85-PP2 dated on 22 September 2011 by PMU85 and M/D for finalizing of the contract for D/D (15 October 2011) only. At present, official instruction from MOT/VEC is not issued yet.