## Sheet1
No. | Position | Name | Contract MM | Mobilized | Demobilized | MM | Accumulative MM | Balance MM
|  |  | (A) |  |  | (B) | (C)=Sum(B) | (A)-(C)
I1 | Project Manager/Team Leader | Ichizuru Ishimoto | 14.5 | 2011-07-15 | 2011-07-16 | 0.066667 | 0.066667 | 14.4333
|  |  |  | 2011-07-18 | 2011-07-20 | 0.1 | 0.16667 | 14.3333
|  |  |  | 2011-08-01 | 2011-08-08 | 0.26667 | 0.43333 | 14.0667
|  |  |  | 2011-08-19 | 2011-08-28 | 0.33333 | 0.76667 | 13.7333
|  |  |  | 2011-09-24 | 2011-09-30 | 0.23333 | 1 | 13.5
I2 | Senior Highway Engineer | Akira Magario | 14
|  | Takayasu Nagai |  | 2011-07-15 | 2011-07-24 | 0.33333 | 0.33333 | 13.6667
|  |  |  | 2011-08-21 | 2011-08-31 | 0.36667 | 0.7 | 13.3
|  |  |  | 2011-09-01 | 2011-09-28 | 0.93333 | 1.6333 | 12.3667
I3 | Road Safety Audit Specialist | Takehiko Tsuji | 3
I4 | Senior Bridge Engineer | Yoshinori Abe | 13
|  | Yoshito Oba |  | 2011-09-24 | 2011-09-30 | 0.23333 | 0.23333 | 12.7667
I5 | Highway Engineer 1 | Koji Nakai | 12.5 | 2011-08-21 | 2011-08-31 | 0.36667 | 0.36667 | 12.1333
|  |  |  | 2011-09-01 | 2011-09-11 | 0.36667 | 0.73333 | 11.7667
|  |  |  | 2011-09-18 | 2011-09-30 | 0.43333 | 1.1667 | 11.3333
I6 | Bridge/Structural Engineer 1 | Tetsuya Maeda | 13 | 2011-07-15 | 2011-07-24 | 0.33333 | 0.33333 | 12.6667
|  |  |  | 2011-08-21 | 2011-08-31 | 0.36667 | 0.7 | 12.3
|  |  |  | 2011-09-01 | 2011-09-18 | 0.6 | 1.3 | 11.7
|  |  |  | 2011-09-25 | 2011-09-30 | 0.2 | 1.5 | 11.5
I7 | Bridge/Structural Engineer 2 | Yoshiaki Nakakubo | 4
I8 | Highway Engineer 2 | Decha Sa-ngaunprasith | 12
I9 | Bridge/Structural Engineer 3 | Hiroo Jin | 12
I10 | Bridge/Structural Engineer 4 | Yuichi Sano | 4
I11 | Senior Interchange Specialist | Chanchai Techashongs | 7
I12 | Bridge/Structural Engineer 5 | Hiroyuki Yokoyama | 11
I13 | Tunnel Engineer | Wako Noto | 4
I14 | Soil/Geotechnical Engineer 1 (Slope) | Manoon Arayasiri | 2
I15 | Soft Ground Treatment Specialist | Suvichai Methpreechakul | 3
I16 | Drainage Engineer | Suntichai Horpaopan | 7
I17 | River Engineer | Arristeo B. Rabajante | 2
I18 | Bridge/Structural Engineer 6 | Akira Yanagisawa | 7
I19 | Pavement/Material Engineer | Bundit Kitsuwannarut | 4
I20 | Survey Engineer | Kazuhiro Ishizuka | 6
|  | Masashi Suzuki |  | 2011-07-15 | 2011-07-28 | 0.46667 | 0.46667 | 5.5333
|  |  |  | 2011-08-08 | 2011-08-31 | 0.8 | 1.2667 | 4.7333
|  |  |  | 2011-09-01 | 2011-09-30 | 1 | 2.2667 | 3.7333
I21 | Soil/Geotechnical Engineer 2 | Jirarote Piyapornpong | 5
I22 | Geological Engineer (Tunnel) | Seichiro Kanai | 2
I23 | Senior Hydrologist | Khadananda Lamsal | 3 | 2011-08-21 | 2011-08-31 | 0.36667 | 0.36667 | 2.6333
|  |  |  | 2011-09-01 | 2011-09-16 | 0.53333 | 0.9 | 2.1
I24 | Inundation Analyst | Silver Yance | 3
I25 | Operating&Maintenance Specialist | Shigeki Takahashi | 4
I26 | Expressway Management Unit Specialist | Yuichi Tsujimoto | 2
I27 | Traffic Management Specialist | Hisanori Tomitaka | 2
I28 | Asset Management Specialist | Kyoichi Takeuchi | 2
I29 | Architect | Yoshinori Yamazaki | 3
I30 | ITS Specialist | Koichi Nishimura | 5
I31 | Communication System Engineer | Masahiro Sakagami | 3
I32 | Senior Electrical Engineer | Eiji Matsuda | 7
I33 | Toll Collection System Specialist | Masashi Iwamoto | 4
I34 | Construction Planner/Cost Estimator | Masayuki Iwashita | 11
I35 | Senior Procurement/Contract Specialist | Anothai Boonthikul | 12
I36 | Social and Environmental Specialist | Yasuhira Minami | 4
I37 | Resettlement Specialist | Vu Ngoc Long | 8
I38 | Training Specialist | Noppong Unhabhokha | 4

## Sheet2
No. | Position | Name | Contract MM | Mobilized | Demobilized | MM | Accumulative MM | Balance MM
|  |  | (A) |  |  | (B) | (C)=Sum(B) | (A)-(C)
L1 | Co-Project Manager | Le Kim An | 14.5
|  | Doan Van Thang |  | 2011-07-15 | 2011-07-18 | 0.13333 | 0.13333 | 14.3667
L2 | Highway Engineer 1 (Geometric) | Tran Dinh Van | 13
L3 | Highway Engineer 2 (Road Structure) | Phan Dang Viet Anh | 13
L4 | Road Safety Audit Specialist | Tran Quang Huy | 3
L5 | Bridge/Structural Engineer 1 (Superstructure) | Le Toan Thang | 13
L6 | Bridge/Structural Engineer 2 (Substructure/Foundation) | Dao Ngoc Vinh | 13
L7 | Highway Engineer 3 (Geometric) | Le Thi Thanh Thuy | 12
L8 | Highway Engineer 4 (Road Structure) | Vu Gia Hung | 12
L9 | Bridge/Structural Engineer 3 | Do Hong Phuc | 4
L10 | Bridge/Structural Engineer 4 | Pham Anh Kiet | 4
L11 | Highway Engineer 5 (Geometric) | Nguyen Dinh Trung | 12
L12 | Highway Engineer 6 (Road Structure) | Dao Manh Son | 12
L13 | Bridge/Structural Engineer 5 | Le Kien Cuong | 4
L14 | Bridge/Structural Engineer 6 | Tran Anh Tuan | 4
L15 | Interchange Specialist | Le Thanh Hung | 2
L16 | Bridge/Structural Engineer 7 | Pham Ngoc Tuan | 3
L17 | Tunnel Engineer | Tran Phong Nha | 4
L18 | Soil/Geotechnical Engineer 1 (Slope) | Quach Thi Thu | 2
L19 | Soft Ground Treatment Specialist | Trinh Viet Linh | 3
L20 | Drainage Engineer 1 | Nguyen Minh Ngoc | 7
L21 | Drainage Engineer 2 | Nguyen Phuc Hoa | 6
L22 | River Engineer | Nguyen Son | 2
L23 | Pavement/Material Engineer 1 | Tran Trong Nghia | 4
L24 | Pavement/Material Engineer 2 | Nguyen Viet Hai | 4
L25 | Senior Surveyor 1 | Vo Thanh Binh | 7.5
|  | Le Van Thu |  | 2011-07-15 | 2011-07-20 | 0.2 | 0.2 | 7.3
|  |  |  | 2011-08-12 | 2011-08-31 | 0.66667 | 0.86667 | 6.6333
|  |  |  | 2011-09-01 | 2011-09-30 | 1 | 1.8667 | 5.6333
L26 | Senior Surveyor 2 | Le Van Thu | 6
|  | Dao Tran Chau |  | 2011-09-26 | 2011-09-30 | 0.16667 | 0.16667 | 5.8333
L27 | Senior Surveyor 3 | Nguyen Anh Tuan | 4
L28 | Soil/Geotechnical Engineer 2 | Nguyen Doan Tinh | 5
L29 | Soil/Geotechnical Engineer 3 | Nguyen Manh Tuan | 4
L30 | Soil/Geotechnical Engineer 4 | Trinh Minh Khiem | 4
L31 | Geological Engineer (Tunnel) | Tran Ngoc Nhan | 2
L32 | Hydraulic Engineer 1 | Ngo The Hung | 3
L33 | Hydraulic Engineer 2 | Pham Huu Nhu | 3
L34 | Inundation Analyst | Nguyen Huy Phuong | 3
L35 | Transport Economist | Vo Hoang Anh | 3
L36 | Operating & Maintenance Specialist | Ha Quoc Hieu | 4
L37 | Expressway Management Unit Specialist | Le Tung Lam | 2
L38 | Traffic Management Specialist | Phan Minh Tuan | 3
L39 | Asset Management Specialist | Trinh Ngoc Hai Thang | 2
L40 | Architect 1 | Pham Quang Minh | 3
L41 | Architect 2 | Ngo Vu Quang Khoa | 3
L42 | ITS Specialist | Nguyen Huu Tinh | 5
L43 | Communication System Engineer | To Minh Tri | 3
L44 | Electrical Engineer 1 | Trinh Dinh Khiem | 7
L45 | Electrical Engineer 2 | Vo Hong | 5
L46 | Toll Collection System Specialist | Bui Phu Huy | 4
L47 | Cost Estimator 1 (Civil Work Packages) | Nguyen Thi Bich Thuy | 11
L48 | Cost Estimator 2 (Civil Work Packages) | Phan Thi Thuy Trinh | 7
L49 | Cost Estimator 3 (Other Packages) | Nguyen Thi Sinh | 3
L50 | Procurement/Contract Specialist 1 | Nguyen The Truong | 12
|  | Tran Sy Hung |  | 2011-09-05 | 2011-09-30 | 0.86667 | 0.86667 | 11.1333
L51 | Procurement/Contract Specialist 2 | Ha Ngoc Anh Minh | 6
L52 | Senior Environmental Specialist | Pham Van Xuan | 8
L53 | Environmental Specialist | Pham The Giang | 8
L54 | Senior Resettlement Specialist | To be named | 14
L55 | Social and Resettlement Specialist | Ho Thi Thu Thuy | 14
L56 | Cultural and Archaeological Specialist | Le Duy Son | 14
L57 | Training Specialist | To be named | 4