# TABLE OF CONTENTS

# Project Location Map

# Part A: General

1.	Background	1

2.	Project Outline	2

2.1	Project Location	2

2.2	Objectives of the Project	2

2.3	Scopes of the Project	2

2.4	Project Structure	4

2.5	Implementation Program	7

3.	Outline of the Consulting Services	8

3.1	Chronicle of Procurement of the Design Consultant	8

3.2	Objectives of the Consulting Services	8

3.3	Scope of the Consulting Services	8

3.4	Consulting Service Contract	8

3.5	Terms of Reference (TOR)	9

3.6	Additional Scope to TOR	11

3.7	Addendum to Original Contract	13

3.8	Organization of the Consultant	14

3.9	Mobilization Status	16

3.10	Planned vs. Actual Implementation Schedules	19

Part B: Performed Services against the TOR

4.	Review of Previous Studies and Ensblishing the Detailed Design Framework (TOR 3.2)	29

4.1	Review of Previous Studies	29

4.2	Establish Detailed Engineering Design Framework	29

4.3	Technical Standards	29

4.3.1	Civil Work	29

4.3.2	ITS Work	31

4.3.3	Additional Standards	32

5.	Basic Design (Additional to TOR)	33

5.1	Design Modified	33

5.2	Updated Work Quantities	34

5.3	Cost Change by Major Design Modification	34

6.	Detailed Engineering Design and Procurement Planning (TOR 3.3)	35

6.1	Packaging (TOR 3.3.1)	35

6.2	Surveys and Investigations (TOR 3.3.2)	35

6.2.1	Data Collection (TOR 3.3.2 (1))	35

6.2.2	Topographic Survey (TOR 3.3.2 (2) (i))	37

6.2.3	Survey of Hydrographical Data (TOR 3.3.2 (2) (ii))	38

6.2.4	Engineering Geological Survey (TOR 3.3.2 (2) (iii))	39

6.2.5	Material Source Survey (TOR 3.3.2 (2) (iv))	39

6.2.6	Survey of Other Relevant Structures (TOR 3.3.2 (2) (v))	40

6.2.7	Additional Traffic Survey (TOR 3.3.2 (2) (vi))	40

6.2.8	Independent Land Valuation Survey (TOR 3.3.2 (2) (vii))	40

6.2.9	Environmental and Social Surveys (TOR 3.3.2 (2) (viii))	41

6.3	Detailed Design of Road, Bridges and Other Structures (TOR 3.3.3)	41

6.3.1	Approval date of Design Documents (Civil Works) by Package	41

6.3.2	Submitted Design Documents for Civil Works	41

6.3.3	List of Bridges	46

6.3.4	List of Cross Structures	46

6.4	Detailed Design of Electrical Works (Additional to TOR)	46

6.4.1	Approval date of Design Documents (Electrical Works) by Package	46

6.4.2	Submitted Design Documents for Electrical Works	46

6.5	Study and Design of ITS and Toll Collection System (TOR 3.3.4)	46

6.6	Expressway Operation and Maintenance (TOR 3.3.5)	47

6.7	Review and Update, as necessary, an Environmental Impact Assessment (EIA), Environmental Management Plan (EMP), Ethnic Minority Development Plan (EMDP) and Resettlement Action Plan (RAP) (TOR 3.3.6)	47

6.7.1	Update of Environmental Impact Assessment (EIA) and Environmental Management Plan (EMP)	47

6.7.2	Preparation of Ethnic Minority Development Plan (EMDP)	50

6.7.3	Update of Resettlement Action Plan (RAP)	50

6.8	Construction Method and Schedule (TOR 3.3.7)	55

6.9	Cost Estimate (TOR 3.3.8)	55

6.10	Pre-qualification, Bidding and Contract Documents (TOR 3.3.9)	56

6.10.1	Pre-qualification (PQ) Documents	56

6.10.2	Bidding and Documents	57

6.10.3	Contract Documents	58

6.11	Preparation of Implementation Program (TOR 3.3.10)	58

7.	Procurement Assistance (TOR 3.4)	58

8.	Land Acquisition Staking (TOR 3.5)	60

9.	Technology Transfer (TOR 3.6)	61

Part C: List of Submitted Documents

10.	List of Submitted Documents	65

# Appendix-1: Major Features and Facilities of Expressway (by Package)

Appendix-2: List of Electrical Crossing

Appendix-3: List of Bridges

Appendix-4: List of Cross Structures

# Abbreviations

AC	:	Appraisal Consultant

AIDS	:	Acquired Immune Deficiency Syndrome

AM	:	Ante Meridiem

AP	:	Affected Person

B/D	:	Basic Design

BOT	:	Build-Operate-Transfer

BP	:	Beginning Point

B/Q	:	Bill of Quantities

BR	:	Bridge

CARB	:	Compensation, Assistance and Resettlement Boards

CB	:	Culvert Box

CDM	:	Civil Design Management

CID	:	Civil Design Team

COD	:	Cost and Document Team

COR	:	Core Team

COS	:	Cost Estimate

CP	:	Culvert Pipe

CPC	:	City People’s Committee

CPCSR	:	Comprehensive Plan on Compensation, Support and Resettlement

C/S	:	Construction Supervision

CSC	:	Construction Supervision Consultant

CU	:	Triaxial Compression Test

Cv	:	Consolidation Test

DARD	:	Department of Agriculture and Rural Development

DC	:	Design Consultant

DDC	:	Detailed Design Consultant

D/D	:	Detailed Engineering Design

# DE	:	Deep Excavation

DEG	:	Design Group

DMS	:	Detailed Measurement Survey

DN	:	Danang city

DOC	:	Document

DOFPP	:	Department of Fire Prevention and Protection

DOLA	:	Department of Land Administration

DONRE	:	Department of Natural Resources and Environment

DOT	:	Department of Transport

DOTP	:	Department of Traffic Office

DP	:	Displaced Person

DPC	:	District People’s Committee

DRC	:	District Resettlement Committee

DRD	:	Drainage Design

ED	:	Evaluation Department

EIA	:	Environmental Impact Assessment

EID	:	Electrical Facility and Intelligent Transport Systems Design

EMP	:	Environmental Management Plan

ENV	:	Environmental Team

EOI	:	Expression of Interest

EOO	:	Expressway Operation Office

EP	:	Ending Point

ER	:	Existing Road

ESCRD	:	Environmental and Social Considerations Review Division

ETC	:	Electric Toll Collection

EVN	:	Electricity of Vietnam

FIDIC	:	International Federation of Consulting Engineers

FO	:	Flyover

F/S, FS	:	Feasibility Study

GOVN	:	Government of Vietnam

GPS	:	Global Positioning System

GTD	:	Geotechnical Design

GTS	:	Geotechnical Survey

HCMC	:	Ho Chi Minh City

HDS	:	Hydrological Survey

HE	:	High-embankment

HEC-RAS	:Hydrologic Engineering Centers River Analysis System, US Army Corps of Engineer

HIDO	:	Highway Industry Development Organization, Japan

HIV	:	Human Immunodeficiency Virus

HVL	:	High-voltage Line

IBRD	:	International Bank for Reconstruction and Development

IC	:	Interchange

ICB	:	International Competitive Bidding

ICD	:	Interchange Design

ICR	:	Inception Report

ID	:	Identification

IDA	:	International Development Association

IMO	:	Independent Monitoring Organization

IOL	:	Inventory of Losses

I/P	:	Implementation Program

IRB	:	Interchange Rampway Bridge

IS	:	Intersection

ITS	:	Intelligent Transport Systems

JBIC	:	Japan Bank for International Cooperation

JEHDRA	:	Japan Expressway Holding and Debt Repayment Agency

JETRO	:	Japan External Trade Organization

JICA	:	Japan International Cooperation Agency

JV	:	Joint Venture

L/A	:	Loan Agreement

LOS	:	Level of Services

LRB	:	Large River Bridge

MBD	:	Major Bridges Design

M/D	:	Minutes of Discussion

MEX	:	Metropolitan Expressway Co., Ltd., Japan

MGT	:	Management Team

ML	:	Main Line

MLIT	:	Ministry of Land, Infrastructure, Transport and Tourism, Japan

MLS	:	Material Source Survey

MOF	:	Ministry of Finance

MOND	:	Ministry of National Defense

MONRE	:	Ministry of Natural Resources and Environment

MOPS	:	Ministry of Public Security

MOT	:	Ministry of Transport

MRB	:	Major River Bridge

MS	:	Milestone

MS	:	Microsoft

NE	:	Nippon Engineering Consultants Co., Ltd., Japan

NEE	:	Normal Embankment and Excavation

NEXCO	:	Nippon Expressway Company Limited, Japan

NH	:	National Highway

NK	:	Nippon Koei Co., Ltd., Japan

NTP	:	Notice to Proceed

OAM	:	Operation and Maintenance

OED	:	Operations Evaluation Department

O&M	:	Operation and Maintenance

OMI	:	Operation and Intelligent Transport Systems Team

OP	:	Overpass

ORB	:	Other River Bridge

ORSE	:	Organization for Road System Enhancement, Japan

PA	:	Parking Area

PAP	:	Project Affected People

PC	:	People’s Committee

PIARC	:	Permanent International Association of Road Congresses

PIS	:	Project Implementation Support for Vietnam Expressway Corporation

PKG	:	Package

PM	:	Prime Minister

PM	:	Post Meridiem

PMBOK	:	Project Management Body of Knowledge

PMU	:	Project Management Unit

PPC	:	Provincial People’s Committee

P/Q	:	Pre-qualification

PSMD	:	Project Site Management Department

PTC2	:	Power Transmission Company No. 2

PVD	:	Pavement Design

QACU	:	Quality Assurance and Compliance Unit

QA/QC	:	Quality Assurance and Quality Control

QN	:	Quang Nam province

QNg	:	Quang Ngai province

RAP	:	Resettlement Action Plan

RB	:	River Bridge

RC	:	Resettlement Committee

RCS	:	Replacement Cost Survey

RD	:	Roadway

RDD	:	Road Design

RES	:	Resettlement

RFP	:	Request for Proposals

RMP	:	Resettlement Monitoring Plan

RNIP	:	Road Network Improvement Program

ROW	:	Right of Way

RP	:	Resettlement Plan

RRD	:	Revetment and River Bed Protection Design

SA	:	Service Area

SAE	:	Social and Environmental

SB	:	Stream Bridge

SED	:	Section Design

SES	:	Socio-economic Survey

SG	:	Softground

SPG	:	Supporting Group

SPT	:	Standard Penetration Test

T/A	:	Technical Assistance

TB	:	Toll Barrier

TEC	:	Thai Engineering Consultants Co., Ltd., Thailand

TEDI	:	Transport Engineering Design Incorporated

TFD	:	Bridge Temporary Facility Design

TG	:	Toll Gate

TMC	:	Traffic Management Center

TN	:	Tunnel

TND	:	Tunnel Design

TOR	:	Terms of reference

TPO	:	Toll Plaza Office

TPS	:	Topographic Survey

TRG	:	Training Team

TRS	:	Traffic Survey

USD	:	United States Dollars

UU	:	Triaxial Compression Test

VAT	:	Value Added Tax

VEC	:	Vietnam Expressway Corporation

VD	:	Viaduct

VICS	:	Vehicle Information and Communication System

VIETTEL	:	Vietnam Military Electronic and Telecommunications Corporation

VND	:	Vietnamese Dong

VNPT	:	Vietnam Posts and Telecommunications Group

VNR	:	Vietnam National Railway

VST	:	Vane Shear Test

WB	:	The World Bank

WT	:	Waterway

# Part A: General

# Background

The preparation of Pre-F/S for the Project under BOT scheme was approved by MOT in Decision No. 2654/QD-BGTVT dated September 11, 2000. The Pre-F/S report was prepared by PMU85 and approved by the Prime Minister in his letter No. 493/CP-CN dated April 21, 2003. Continually, the preparation of F/S was approved by MOT in Decision No. 134/QD-BGTVT dated January 14, 2004. The F/S report was also prepared by PMU85 and submitted to MOT in his letter No. 514/BQL-KHDA2 dated May 11, 2005. However, this BOT scheme Project did not materialize because of funding sources were not identified at that time.

Two (2) years later, the Project was approved as one (1) of the top priority projects in transport sector by GOVN in Decision No. 412/QD-TTg dated April 11, 2007. For carrying forward the Project, GOVN requested JETRO to assist a further study expecting materialization of the Project by a JBIC (currently JICA) loan scheme in June 2007. JETRO conducted the study and submitted the study report to MOT on April 28, 2008.

In parallel with the JETRO study, WB declared GOVN to be eligible for the IBRD loan in November, 2007 and the Project was identified as the top priority use for the loan. After submission of the JETRO study report, WB undertook the identification missions in April and June, 2008 and confirmed necessity of updating the JETRO study to meet his requirements and decided to allocate the fund from on-going RNIP (IDA Credit No.: 3843-VN) to conduct the WB supplemental study. The study report was prepared by PMU85 and submitted to MOT in his letter No. 551/BQl-KHDA2 dated June 13, 2009.

In response to the supplemental study, WB engaged an international consultant, CPCS of Canada, and undertook the WB appraisal study. In the appraisal study, WB modified the alignment at three (3) sections by taking into consideration social and environmental issues.

Based on the modified alignment, TEDI updated the supplemental study and submitted as the draft F/S report to MOT in April, 2010.  The draft F/S report was also finalized by TEDI in accordance with the MOT appraisal report No. 6188/BGTVT-KHDT dated September 8, 2011 and submitted by VEC as the F/S report to MOT in September 2010. The F/S report was approved by MOT in Decision No. 2656/QD-BGTVT dated September 10, 2010.

In parallel with the F/S approval, WB agreed to allocate the fund from RNIP for D/D and the Prime Minister allowed commencing the procurement of D/D consultant. Through the procurement procedures, NK-NE-Chodai-TEC JV (the Consultant) was selected and signed the contract with PMU85 on November 15, 2011. Subsequently, PMU85 issued NTP in his letter No. 1622/PMU85-PP2 dated November 18, 2011 and the consulting service was officially commenced from December 1, 2011.

In April 2014, after issuance of several times of Addendums to the original contract which are mainly for extension of the period of the consulting services, the Consultant has completed his duties, except the social environmental, as shown in this report.

This report summarizes the results of the consulting services for the detailed design for Danang – Quang Ngai Expressway Development Project (DQEDP).

# Project Outline

## Project Location

The expressway is a part of the North-South Expressway located in parallel with the existing NH1A and North-South Railway and passing through Danang city, Quang Nam and Quang Ngai provinces in the central region.  The road starts at the intersection of the Danang Bypass and NH14B in Danang city and ends at the connecting point with the planned City Ring Road at existing NH1A in Quang Ngai province.  The major socio-economic developments along the expressway are Chu Lai Open Economic Zone in Quang Nam province and Dung Quat Industrial Zone in Quang Ngai province.  As for the cultural properties, Hoi An Ancient Town and My Son Sanctuary, registered as the world heritage (cultural heritage), are existed along the expressway.

Project location map is shown in cover page.

## Objectives of the Project

The objective of the Project is to meet increasing traffic demand, to reduce travel time and uncertainly for passenger users and freight, and to enhance travel safety for road users, by constructing an expressway from Da Nang to Quang Ngai – a top priority section of the North-South Expressway, thereby contributing to economic growth and international competitiveness of Da Nang City and Central Vietnam.

## Scopes of the Project

Major features and facilities of the expressway is summarized in Table 2.1.

Major features and facilities of the expressway of each package is shown in Appendix-1

Contract packages of the Project were divided into 13 civil works contract packages, ITS/O&M packages and Traffic Safety/Lighting packages as shown in Table 2.2.

Sub-division of PKG13 into PKG13A/13B/13C is still under discussion as of December 2014.

Table 2.1   Major Features and Facilities of Expressway

| No. | Items | Main Features |  |
| --- | --- | --- | --- |
| 1 | Road Length | 139.204 km |  |
|  |  |  | By Road Class: Expressway section: 131.500 km, Linking road section: 7.704 km |
|  |  |  | By Jurisdiction: Danang city: 8.0 km, Quang Nam province: 91.3 km, Quang Ngai province: 39.904 km |
|  |  |  | Beginning Point (BP): Intersection of the existing Danang bypass and NH14B in Danang city |
|  |  |  | Ending Point (EP): Connecting point with the planned city ring road at the existing NH1A (KM1063+700) in Quang Ngai province |
| 2 | Road Classification | Expressway: Type A, Class 120, Linking Road: Class III, Delta |  |
| 3 | Design Speed | Expressway: 120 km/h, Linking Road: 80 km/h |  |
| 4 | Nos. of Lane | 4 lanes (Ultimate stage: Widened to 6 lanes) |  |
| 5 | Road Width | Expressway: Road section: 25.5m, Bridge sections: 25.5m (PC-Box: 26.0m), Tunnel section: 2@12.75 m, Linking Road: 12.0 m |  |
| 6 | Design Frequency | DHWL (Design High Water Level): Expressway: 1 %, Linking Road: 4 % |  |
|  |  | Pavement Drainage: 4% |  |
|  |  | Bridge Deck Drainage: 4% |  |
| 7 | Bridge | 104 bridges (L=9,226.81 m) |  |
|  |  |  | Large River Bridge (LRB, L>100 m):13 bridges (L=2,137 m), Other River Bridge (ORB, L<100 m):27 bridges (L=1,482.0 m), |
|  |  |  | Canal Bridge (CB): 12 bridges (L=539.1 m), |
|  |  |  | Viaduct (VD):13 bridges (L=2,780 m), Overpass (OP): 23 bridges (L=1,156.41 m), |
|  |  |  | Interchange Rampway Bridge (IRB):5 bridges (L=427.6 m), Flyover (FO): 11 bridges (L=704.7 m) |
| 8 | Major River Bridge | 4 bridges (L=2,724.90 m) |  |
|  |  |  | Thu Bong River (KM017+503): Ky Lam Bridge (L=1,044.80 m), Ba Ren River (KM020+209): Chiem Son Bridge (L=451.10 m), |
|  |  |  | Tra Bong River (KM109+001): Tra Bong Bridge (L=454.50 m), Tra Khuc River (KM125+367): Tra Khuc Bridge (L=774.50 m) |
| 9 | Tunnel | 1 tunnel (KM022+900, North Bound L=556m & South Bound L=551 m) |  |
| 10 | Culvert | 561 culverts |  |
|  |  |  | Culvert Box: 320 culvert boxes (125 roadway culverts and 195 waterway culverts), Culvert Pipe: 241 culvert pipes |
| 11 | Softground | 24.206 km (FS: 4.190km) |  |
| 12 | Interchange | 8 interchanges (KM0+000:Tuy Loan IC, KM13+260:My Son IC, KM40+880:Ha Lam IC, KM64+510:Tam Ky IC, KM82+990:Chu Lai IC, KM101+740:Dung Quat IC, KM123+700:Quang Ngai North IC, KM130+502:Quang Ngai IC) |  |
| 13 | Frontage Road | Approximately 59.7km |  |
| 14 | Earth Works | Soil excavation: 5,161,829 m3, Rock excavation: 4,655,367 m3, Filling: 9,817,196m3 |  |
| 15 | Electrical Facilities | Power supply, road lighting, tunnel ventilation and safety facilities |  |
| 16 | ITS | Traffic management, toll collection and communication systems |  |
| 17 | O&M Building | 26 locations |  |
|  |  |  | Main Management Center (MMC): 1 location, Management Office (MO):2 locations, Toll Office (TO):9 locations, |
|  |  |  | Toll Barrier (TB): 2 locations, Toll Gate (TG): 7 (initial stage) locations, Service Area (SA):1 location, Parking Area (PA): 4 locations |
| 18 | O&M Equipment | O&M vehicles, spare parts, maintenance equipment and consumables |  |

Table 2.2   Contract Packaging of the Project

| Work | Jurisdiction | No. | Section |  |  | Length (km) | Fund |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | JICA | WB |
| Civil | Danang | PKG1 | KM000+000 | - | KM008+000 | 8.000 | X |  |
|  | Quang Nam | PKG2 | KM008+000 | - | KM016+880 | 8.880 | X |  |
|  |  | PKG3A | KM016+880 | - | KM018+100 | 1.220 | X |  |
|  |  | PKG3B | KM018+100 | - | KM021+500 | 3.400 | X |  |
|  |  | PKG4 | KM021+500 | - | KM032+600 | 11.100 | X |  |
|  |  | PKG5 | KM032+600 | - | KM042+000 | 9.400 | X |  |
|  |  | PKG6 | KM042+000 | - | KM052+000 | 10.000 | X |  |
|  |  | PKG7 | KM052+000 | - | KM065+000 | 13.000 | X |  |
|  |  | PKG A1 | KM065+000 | - | KM081+150 | 16.150 |  | X |
|  |  | PKG A2 | KM081+150 | - | KM099+500 | 18.350 |  | X |
|  | Quang Ngai | PKG A3 | KM099+500 | - | KM110+100 | 10.600 |  | X |
|  |  | PKG A4 | KM110+100 | - | KM124+700 | 14.600 |  | X |
|  |  | PKG A5 | KM124+700 | - | KM131+500 | 6.800 |  | X |
|  |  |  | KM131+500 | - | KM139+204 | 7.704 |  | X |
| ITS/O&M | Building Works | PKG 13A | KM000+000 | - | KM139+204 | 139.204 | X |  |
|  | Equipment | PKG 13B |  |  |  |  |  |  |
|  | ITS Works | PKG 13C |  |  |  |  |  |  |
| Traffic Safety/ Lighting | DN-Tam Ky | PKG 14A | KM000+000 | - | KM065+000 | 65.000 | X |  |
|  | Tam Ky-QNg | PKG 14B | KM065+000 | - | KM139+204 | 74.204 |  | X |
| Consulting Services | Danang – Quang Ngai |  | KM000+000 | - | KM139+204 | 139.204 |  | X |

## Project Structure

Vietnam Expressway Corporation (VEC) is executing agency (EA), and Project Management Unit No.85 (PMU85) is implementation agency (IA) for the project. Overall project structure is shown in Figure 2.1.

Figure 2.1   Overall Project Structure

Figure 2.2 shows organization of VEC.

Figure 2.3 shows project organization of PMU85.

Figure 2.2   VEC Organization

DIRECTOR OF PPTAF/PROJECT MANAGER

Mr. NGUYEN TRUNG SY

DEPUTY PROJECT MANAGER

Mr. LE TRONG DO

DEPUTY PROJECT MANAGER

MS. HUYNH THI NGOC HOA

DEPUTY PROJECT MANAGER

Mr. NGUYEN KHAC SON

Technical and Land Acquisition team

+ Team’s members

- Mr.Le Thanh Hue

- Mr.Pham Xuan Thai

- Mr.Tran Huu Qui

- Mr. Hoang van Nghi

- Mr. Nguyen Phuc Nguyen

+ Duties:

- Check Documents of Survey, Detailed Design, and Bidding

- Land Acquisition and Resettlement at site

-Acceptance of Quantities, Technical reports, Surveys …

-Check Payment Documents.

Economic team

+ Team’s members

- Ms. Phan Thi Lien (Team leader)

- Ms. Nguyen Thi Thanh Nhan

+ Duties:

- Check, Review Documents of Bidding, EIA, SIA, EMP, Price Evaluation.

- Personnel management.

# Source: Letter No.129-BQL-DNQN dated 30 May 2012 from PMU85 &1777/TB-BQL dated 13 November 2012

Figure 2.3   PMU85 Project Organization

## Implementation Program

The construction and construction supervision will be carried out under JICA and WB loan separately. The first package of the construction is Package 3A and commenced the construction work on 19 May 2013. Other packages have been commenced time to time as shown in Figure 2.4.

Figure 2.4   Implementation Schedule

# Outline of the Consulting Services

## Chronicle of Procurement of the Design Consultant

Chronicle of the procurement of the design consultant can be summarized as shown in Table 3.1.

It should be noted that early commencement of the topographic survey works was agreed during the first contract negotiation in order to finalize the site work of the survey works before rainy season which usually starts late September every year.

Table 3.1   Chronicle of Procurement of Design Consultant

| No. | Date | Event |
| --- | --- | --- |
| 1 | 25.03.2009 | Announcement of EOI by PMU85 |
| 2 | 20.04.2009 | Deadline of Submission of EOI |
| 3 | 06.02.2010 | Issuance of RFP |
| 4 | 26.02.2010 | Pre-proposal Conference |
| 5 | 19.04.2010 | Issuance of Revised RFP (Addendum No.1) |
| 6 | 28.05.2010 | Issuance of Revised RFP (Addendum No.2) |
| 7 | 01.06.2010 | Deadline of Submission of Proposal |
| 8 | 20.04.2011 | WB issued NOL to VEC |
| 9 | 16-26.05.2011 | Contract Negotiation (1st) |
| 10 | 15.07.2011 | Commencement of Survey Works |
| 11 | 20.09.2011 | Contract Negotiation (2nd) |
| 12 | 15.10.2011 | Contract Negotiation (3rd) |
| 13 | 15. 11.2011 | Contract Sign |
| 14 | 18.11.2011 | Issuance of NTP |
| 15 | 01.12.2011 | Commencement of Services |

## Objectives of the Consulting Services

The consulting services for detailed design for Da Nang – Quang Ngai (DNQN) expressway development project comprises of the following three (3) objectives:

  - To undertake the efficient and proper preparation of the detailed engineering design;

  - To prepare an implementation program that can ensure delivery of the project in an efficient and timely manner infrastructure in accordance with the implementation program; and

  - To promote technology transfer by employing suitably qualified Vietnamese professionals for the detailed design and implementation planning for the Project and by providing appropriate training for staff of the related agencies who will be at various times responsible for the Project.

## Scope of the Consulting Services

Expressway Design and Procurement is designed to assist Vietnam Expressway Corporation (VEC), said executing agency (EA), and Project Management Unit No.85 (PMU85), for DNQN expressway construction project, said implementation agency (IA) to implement pre-construction activities for the project.

The scope of the consulting services broadly consists of the following works:

- Review of previous studies.

- Detailed engineering design including cost estimation and preparation of tender documents and other supporting documentation.

- Assistance with calling and assessing tenders for works and for contract negotiations.

## Consulting Service Contract

Contract No. 01/DD-EDDQP/2011 is made on 15th November 2011 (the Original Contract) for Consulting Services for Detailed Design for Expressway Development ( Da Nang – Quang Ngai) Project between PMU85 and a joint venture of Nippon Koei Co., Ltd. – Nippon Engineering Consultants Co., Ltd. – Chodai Co., Ltd. – Thai Engineering Consultants Co., Ltd. (the Consultant) as shown in Table 3.2.

Table 3.2   Consulting Service Contract

| Item | Description |
| --- | --- |
| Contract Title | Consulting Services Contract for Detailed Design (No.01/DD-EDDQP/2011) |
| Employer Name | Project Management Unit No. 85 (PMU85) |
| Consultant Name | The Joint Venture of Nippon Koei Co., Ltd. – Nippon Engineering Consultants Co., Ltd. – Chodai Co., Ltd. – Thai Engineering Consultants Co., Ltd. |
| Contracted Date | 15 November 2011 |
| Contract Period | 1 December 2011 – 30 June 2014 (by Addendum No.6) |
| Notice to Proceed | PMU85 letter No. 1622/PMU85-PP2 dated November 18, 2011 |
| Commencement of Services | 1 December 2011 |

## Terms of Reference (TOR)

Terms of reference (TOR) in the consulting service contract consists of the contents shown in Table 3.3.

Table 3.3   Scope stipulated in TOR

| TOR Clause | Item |  |  | Title |
| --- | --- | --- | --- | --- |
| 3.1 |  |  |  | General |
| 3.2 |  |  |  | Review of Previous Studies and Establishing the Detailed Design Framework |
|  |  | (1) |  | Review Previous Studies |
|  |  | (2) |  | Establish Detailed Engineering Design Framework |
| 3.3 |  |  |  | Detailed Engineering Design and Procurement Planning |
|  | 3.3.1 |  |  | Packaging |
|  | 3.3.2 |  |  | Surveys and Investigations |
|  |  | (1) |  | Data collection |
|  |  | (2) |  | Surveys |
|  |  |  | (i) | Topographic survey |
|  |  |  | (ii) | Survey of hydrographical data |
|  |  |  | (iii) | Engineering geological survey |
|  |  |  | (iv) | Material Source Survey |
|  |  |  | (v) | Survey of other relevant structures |
|  |  |  | (vi) | Additional Traffic Surveys |
|  |  |  | (vii) | Independent Land Valuation Survey |
|  |  |  | (viii) | Environmental and Social Surveys |
|  | 3.3.3 |  |  | Detailed Design of Road, Bridges and Other Structures |
|  |  | (1) |  | Comparative Analysis |
|  |  | (2) |  | Review of Previous studies with Survey Results |
|  |  | (3) |  | Maintain Records of Changes in Features of the Project |
|  |  | (4) |  | Detailed Engineering Designs |
|  |  | (5) |  | Drafting of Engineering Drawings |
|  |  | (6) |  | Work Quantities with Agreed Form and Content of Bill of Quantities (BOQ) |
|  |  | (7) |  | Road Safety Audit |
|  |  | (8) |  | Detailed Design of Service Areas |
|  |  | (9) |  | Detailed Design and Construction Supervision of Resettlement Area |
|  |  | (10) |  | Documentation for Land Acquisition Staking |
|  | 3.3.4 |  |  | Study and Design of ITS and Toll Collection System |
|  |  | (1) |  | Concept Design |
|  |  |  | a | Identification of potential data and information needs |
|  |  |  | b | Conceptual design of ITS and toll collection systems |
|  |  |  | c | Setting of design standards for each system component and configuration of each item of equipment |
|  |  |  | d | Conceptual plan for institutional arrangements and staffing needed |
|  |  | (2) |  | Basic Design and Cost Estimate |
|  |  |  | a | Central Control and Operation Center and Branch Offices (Building) |
|  |  |  | b | ITS facilities other than Toll Collection Facilities |
|  |  |  | c | Toll Collection Facilities |
|  |  |  | d | Communication Facilities |
|  | 3.3.5 |  |  | Expressway Operations and Maintenance (O&M) |
|  |  |  | a | Expressway Management Unit (EMU) |
|  |  |  | b | Office and Facilities for EMU |
|  |  |  | c | Bidding Documents for O&M Facilities |
|  | 3.3.6 |  |  | Review and update, as necessary, an Environmental Impact Assessment (EIA), Environmental Management Plan (EMP), Ethnic Minority Development Plan (EMDP) and Resettlement Action Plan (RAP) |
|  | 3.3.7 |  |  | Construction Method and Schedule |
|  | 3.3.8 |  |  | Cost Estimate |
|  |  |  | a | Bills of Quantities (BOQ) |
|  |  |  | b | Cost Estimate (Each Package) |
|  |  |  | c | Total Project Cost |
|  |  |  | d | Annual Disbursement Schedule |
|  | 3.3.9 |  |  | Pre-qualification, Bidding and Contract Documents |
|  | 3.3.10 |  |  | Preparation of Implementation Program |
| 3.4 |  |  |  | Procurement Assistance |
|  |  | (1) |  | Procurement Plan |
|  |  | (2) |  | Pre-Qualification and Bidding Documents |
|  |  | (3) |  | Assistance to Pre-Qualification |
|  |  | (4) |  | Assistance to Bidding |
|  |  | (5) |  | Assistance to Contract Negotiation |
| 3.5 |  |  |  | Staking for Land Acquisition |
| 3.6 |  |  |  | Training and Technology Transfer |
|  |  |  |  | Reports and Documents |
|  |  | (1) |  | Inception Report |
|  |  | (2) |  | Review and Detailed Design Framework Report |
|  |  | (3) |  | Monthly Progress Reports |
|  |  | (4) |  | EIA, EMP, EMDP, RAP Reports |
|  |  | (5) |  |  |
|  |  |  | (i) | Design Reports |
|  |  |  | (ii) | Pre-Qualification Documents |
|  |  |  | (iii) | Bidding Documents |
|  |  | (6) |  | Road Safety Audit Reports |
|  |  |  |  | Consultant Personnel |
| 5.1 |  |  |  | Key Consultant Personnel |
| 5.2 |  |  |  | Key Local Personnel |
|  |  |  |  | Undertakings of PMU85 - MOT |
|  |  | (1) |  | Arrange for Necessary Meetings with Local Authorities |
|  |  | (2) |  | Assist in Procedures with Other Relevant Authorities |
|  |  | (3) |  | Assist the Consultant to Collect Data from Relevant Authorities |
|  |  |  |  | Obligations of the Consultants |
|  |  |  |  | Updating the Environmental Impact Assessment and Management Plan for the Proposed Danang to Quang Ngai Expressway Project Detail Design Stage |
|  |  |  |  | Resettlement Study Methodology Preparation of an Updated Resettlement Plan |

## Additional Scope to TOR

At the initial stage of the services, it was confirmed that some scope, which were not clearly required in the TOR of the consulting service contract. The consultant proposed to carry out scope shown in Table 3.4, and the client agreed.

Table 3.4   Additional Scope to TOR

| No. | Additional Scope | Description |
| --- | --- | --- |
| 1 | Inundation Analysis | - Some sections of the expressway located flood areas and inundated almost every rainy season. - The Consultant carried out inundation analysis and studied the impact of building the expressway crossing such areas. - A long viaduct (L=780m) was allocated at Dien Quang commune, Dien Ban district, Quang Nam province, in order to minimize the negative impact of expressway during rainy seasons. |
| 2 | Basic Design (Updating F/S) | - The feasibility study report was finalized by TEDI in April 2010 and approved by MOT in Decision No. 2656/QD-BGTVT dated September 10, 2010. - The Consultant identified several critical design controls, during the “Review of Previous Studies” stage, which were missing in TEDI F/S (April 2010). - The Consultant thoroughly revised the TEDI F/S and submitted “Basic Design Report” including modifications of the alignment, location and type of interchanges, typical cross section, and bridge types. |
| 3 | Electrical Design | - Electrical engineer is nominated in the TOR, however, no work description stipulated in the TOR. - The Consultant carried out necessary electrical design including relocation of HVL and street lighting. |

During the implementation of the services, many additional works had been carried out in accordance with the instruction by the client.

The consultant made 27 contractual claims for the additional works and nine (9) items were approved by MOT as shown in Table 3.5.

Those additional works had been carried out through whole of the service period, and made negative impact on the progress of the design works, as shown in Figure 3.1

Table 3.5   List of All Additional Works

| No. | Additional Work Item | Survey | Design | RAP | MOT Approved |
| --- | --- | --- | --- | --- | --- |
| 01 | Modification of Alignment | Yes | Yes | Yes | Yes |
| 02 | Detailed Design of Ky Lam Bridge | --- | Yes | -- | --- |
| 03 | Basic Design of Road Cross Structures | --- | Yes | -- | --- |
| 04 | Basic Design of Other Bridges | --- | Yes | -- | --- |
| 05 | Additional Study on Tuy Loan IC | Yes | Yes | Yes | --- |
| 06 | Study on Temporary Access Roads | Yes | Yes | --- | --- |
| 07 | Additional Depth of Bearing Layer of Ky Lam Bridge | Yes | --- | --- | --- |
| 08 | Additional O&M Buildings | Yes | Yes | -- | --- |
| 09 | Additional Topographic and Environmental Survey at Populous Residential Areas | Yes | Yes | --- | Yes |
| 10 | Supplemental Socio-Economic Survey | --- | --- | Yes | --- |
| 11 | Detailed Hydrological Analysis with Additional Elevation Survey | Yes | Yes | --- | --- |
| 12 | Additional Length of Softground Sections | Yes | Yes | -- | Yes |
| 13 | Chu Lai IC (New Location) | Yes | Yes | --- | --- |
| 14 | Detailed Design of Chiem Son Bridge and Tra Khuc Bridge | --- | Yes | --- | --- |
| 15 | Additional Boring at ORB00a | Yes | --- | --- | --- |
| 16 | Binh Son IC (Diamond Type) | --- | Yes | --- | --- |
| 17 | Re-alignment at Major Cemeteries | Yes | Yes | Yes | Yes |
| 18 | Detailed Design of Type of Other Bridges | --- | Yes | -- | --- |
| 19 | Relocation of Quang Ngai North IC | Yes | Yes | --- | Yes |
| 20 | Handbook for Income Restoration Program | --- | --- | Yes | --- |
| 21 | Existence of Underground Void Space | Yes | --- | -- | --- |
| 22 | Avoidance of High Voltage Lines (HVLs) | Yes | Yes | -- | --- |
| 23 | Preliminary Design of Dung Quat 2 IC | Yes | Yes | --- | Yes |
| 24 | Change of Pavement Structure, Application of ATB/CTB | Yes | Yes | -- | Yes |
| 25 | Shift of Parking Area at Package A2 | Yes | Yes |  | --- |
| 26 | Preliminary Study on Connecting Plan between DQE and PR620 | --- | Yes | --- | --- |
| 27 | Additional Office Operation Cost | --- | --- | --- | Yes |

Figure 3.1   Work Period of Additional Works

## Addendum to Original Contract

There were eight (8) addendums to the Original Contract. Contract Addendum No.1 dated 27th December 2011; Contract Addendum No.2 dated 29th November 2012; Contract Addendum No.3 dated 30 January 2013, Contract Addendum No.4 dated 26th April 2013; Contract Addendum No.5 dated 31st July 2013, Contract Addendum No.6 dated 9th January 2014, Contract Addendum No.7 dated 29th December 2014 and Addendum No.8 dated 31st December 2014.

# Table 3.6  Addendum to Original Contract

| Amendment | Signed Date | Contents/Scope |
| --- | --- | --- |
| No.1 | 27.12.2011 | - Modification of Clause 6.4 in the Special Conditions of the Original Contract regarding bank accounts |
| No.2 | 29.11.2012 | - Modification of Clause 2.6.1 in the General Conditions of the Original Contract regarding the applicable guidelines for the selection of the Consultant. - Modification of Clause 6.4 in the Special Conditions of the Original Contract regarding the Consultant’s bank account for local currency. - Modification of Clause 6.6 in the Special Conditions of the Original Contract regarding setting of the exchange rates. |
| No.3 | 30.01.2013 | - Extension of the contract period until 30 April 2013. |
| No.4 | 26.04.2013 | - Extension of the contract period until 31 July 2013 |
| No.5 | 31.07.2013 | - Extension of the contract period until 31 December 2013. |
| No.6 | 09.01.2014 | - Extension of the contract period until 30 June 2014. |
| No.7 | 29.12.2014 | - Extension of the contract period until 31 December 2014. |
| No.8 | 31.12.2014 | - Payment for additional works. |

## Organization of the Consultant

Organization of the Consultant is given in Figure 3.2.

# Figure 3.2 Organization of the Consultant

## Mobilization Status

Staff mobilization status as of 31/12/2013 is summarized in Table 3.7. As shown in the table, considerable amount of additional staff had been mobilized in order to cover the extended time by delay of approval and additional works.

Table 3.7   Staff Mobilization Record (As of 31/12/2013)

|  |  |  | Staff-months (MM) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Contract | Actual (31/12/2013) | Total | Variance |
|  |  |  | a | b | c=b+c | d=c-a |
| 1 | Staff Approved |  |  |  |  |  |
|  | 11 | International Staff | 239 | 293(123%) | 295(123%) | 56 (23%) |
|  | 12 | National Staff | 357 | 607(170%) | 616(173%) | 259 (73%) |
|  | 13 | Supporting Staff | 250 | 414(166%) | 424(170%) | 174 (70%) |
| 2 | Staff Not Approved |  |  |  |  |  |
|  | 21 | International Staff |  | 42 |  |  |
|  | 22 | National Staff |  | 159 |  |  |
|  | 23 | Supporting Staff |  | 27 |  |  |

38 approved international staff for expressway design service were mobilized as shown in Table 3.8.

# Table 3.8  Mobilization Status (International Staff, Approved)

| No. | Position | Name | Staff-months |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Contract | Actual | Variance |
| I1 | Project Manager/Team Leader | Ichizuru Ishimoto | 14 | 20.87 | 6.87 |
| I2 | Senior Highway Engineer | Takayasu Nagai | 13 | 23.17 | 10.17 |
| I3 | Road Safety Audit Specialist | Maurice Frederick Burley | 3 | 3.01 | 0.01 |
| I4 | Senior Bridge Engineer | Yoshito Oba | 13 | 15.34 | 2.34 |
| I5 | Highway Engineer 1 | Koji Nakai | 12 | 16.74 | 4.74 |
| I6 | Bridge/Structural Engineer 1 | Tetsuya Maeda | 12 | 21.21 | 9.21 |
| I7 | Bridge/Structural Engineer 2 | Yoshiaki Nakakubo | 4 | 6.07 | 2.07 |
| I8 | Highway Engineer 2 | Naresh Sthapit | 12 | 15.37 | 3.37 |
| I9 | Bridge/Structural Engineer 3 | Takeyuki Takada | 12 | 14.63 | 2.63 |
| I10 | Bridge/Structural Engineer 4 | Kentaro Okuno | 4 | 1 | -3 |
| I11 | Senior Interchange Specialist | Akira Magario | 7 | 4.1 | -2.9 |
| I12 | Bridge/Structural Engineer 5 | Hiroyuki Yokoyama | 11 | 14.6 | 3.6 |
| I13 | Tunnel Engineer | Wako Noto | 4 | 6.14 | 2.14 |
| I14 | Soil/Geotechnical Engineer 1 (Slope) | Fumio Nakamura | 2 | 0.2 | 1.8 |
| I15 | Soft Ground Treatment Specialist | Yasuhiro Nozue | 3 | 1.13 | 1.87 |
| I16 | Drainage Engineer | Vachira Charanyanon | 7 | 12.05 | 5.05 |
| I17 | River Engineer | David Rojaz | 2 | 1.67 | -0.33 |
| I18 | Bridge/Structural Engineer 6 | Akira Yanagisawa | 7 | 7.26 | 0.26 |
| I19 | Pavement/Material Engineer | Keishi Ihara | 4 | 0.97 | -3.03 |
| I20 | Survey Engineer | Masashi Suzuki | 6 | 8.27 | 2.27 |
| I21 | Soil/Geotechnical Engineer 2 | Ichiro Noguchi | 5 | 12.83 | 7.83 |
| I22 | Geological Engineer (Tunnel) | Seichiro Kanai | 2 | 0.87 | -1.13 |
| I23 | Senior Hydrologist | Khadananda Lamsal | 3 | 4.9 | 1.9 |
| I24 | Inundation Analyst | Yukishi Tomida | 3 | 0.43 | -2.57 |
| I25 | Operation& Maintenance Specialist | Kazuya Hiraguri | 4 | 4.03 | 0.03 |
| I26 | Expressway Management Unit Specialist | Yuichi Tsujimoto | 2 | 2.0 | 0 |
| I27 | Traffic Management Specialist | Hisanori Tomitaka | 2 | 1.6 | -0.4 |
| I28 | Asset Management Specialist | Kyoichi Takeuchi | 2 | 0.3 | -1.7 |
| I29 | Architect | Yoshinori Yamazaki | 3 | 3.1 | 0.1 |
| I30 | ITS Specialist | Koichi Nishimura | 5 | 5.29 | 0.29 |
| I31 | Communication System Engineer | Masahiro Sakagami | 3 | 1.47 | -1.53 |
| I32 | Senior Electrical Engineer | Shinichi Ando | 7 | 3.47 | -3.53 |
| I33 | Toll Collection System Specialist | Masashi Iwamoto | 4 | 4.1 | 0.1 |
| I34 | Construction Planner/Cost Estimator | Masanori Nakagi | 11 | 23.94 | 12.94 |
| I35 | Senior Procurement/Contract Specialist | William John Davy | 12 | 8.87 | -3.13 |
| I36 | Social and Environmental Specialist | Yasuhira Minami | 5 | 4.73 | -0.27 |
| I37 | Resettlement Specialist | Vu Ngoc Long | 10 | 18.73 | 8.73 |
| I38 | Training Specialist | Noppong Unhabhokha | 4 | 0 | -4 |
|  |  | Total | 239 | 294.5 | 55.5 |

12 non-approved international staff for expressway design service were mobilized as shown in Table 3.9.

# Table 3.9  Mobilization Status (International Staff, Not-Approved)

| No. | Position | Name | Mobilized | Demobilized | MM |
| --- | --- | --- | --- | --- | --- |
| I2-2 | Senior Highway Engineer | Ippei Iwamoto | 15/07/2011 | 05/5/2013 | 15.22 |
| I7-2 | Bridge/Structural Engineer 2 | Yoshinori Uchiumi | 19/8/2012 | 31/3/2013 | 9.56 |
| I9-2 | Bridge/Structural Engineer 3 | Toshiyuki Osugi | 18/4/2012 | 25/10/2012 | 2.99 |
| I10 | Bridge/Structural Engineer 4 | Atsushi Kawamura | 15/02/2012 | 16/5/2012 | 2.93 |
| I14 | Soil/Geotechnical Engineer 1 (Slope) | Motohiro Ura | 15/02/2012 | 05/9/2012 | 0.60 |
| I14 | Soil/Geotechnical Engineer 1 (Slope) | Yutaka Inagaki | 06/9/2012 | 26/9/2012 | 0.70 |
| I18-2 | Bridge/Structural Engineer 6 | Kyung Duk Kim | 07/01/2013 | 31/3/2013 | 2.83 |
| I21 | Soil/Geotechnical Engineer 2 | Sutham Sattayakom | 25/3/2012 | 12/5/2012 | 1.63 |
| I24-2 | Inundation Analyst | Toru Koike | 06/12/2011 | 23/12/2011 | 0.60 |
| I24-3 | Inundation Analyst | Akira Sasaki | 15/11/2011 | 25/12/2011 | 1.36 |
| I35 | Senior Procurement/Contract Specialist | Uthai Patarasuk | 25/3/2012 | 31/5/2012 | 2.23 |
| I35-2 | Senior Procurement/Contract Specialist | Kenji Nomoto John | 15/6/2012 | 13/7/2012 | 0.96 |
|  |  | Total |  |  | 41.61 |

57 approved Vietnamese domestic staff for expressway design service were mobilized as shown in Table 3.10.

# Table 3.10 Mobilization Status (Vietnamese Staff, Approved)

| No. | Position | Name | Staff-months |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Contract | Actual | Variance |
| L1 | Co-Project Manager | Nguyễn Lam Hồng | 14 | 15.57 | 1.57 |
| L2 | Highway Engineer 1 (Geometric) | Phạm Việt Hùng | 13 | 18.80 | 5.80 |
| L3 | Highway Engineer 2 (Road Structure) | Hà Phước Thuần | 13 | 23.00 | 10.00 |
| L4 | Road Safety Audit Specialist | Nguyễn Anh Phương | 3 | 3.10 | 0.10 |
| L5 | Bridge/Structural Engineer 1 (Superstructure) | Nguyễn Văn Lê | 13 | 26.40 | 13.40 |
| L6 | Bridge/Structural Engineer 2 (Substruct/Foundation) | Cát Trọng Tiến | 13 | 19.00 | 6.00 |
| L7 | Highway Engineer 3 (Geometric) | Hoàng Đức Châu | 12 | 25.00 | 13.00 |
| L8 | Highway Engineer 4 (Road Structure) | Nguyễn Nho Sĩ | 12 | 23.33 | 11.33 |
| L9 | Bridge/Structural Engineer 3 | Phan Đức Dũng | 4 | 13.83 | 9.83 |
| L10 | Bridge/Structural Engineer 4 | Nguyễn Tâm Đạt | 4 | 17.83 | 13.83 |
| L11 | Highway Engineer 5 (Geometric) | Nguyễn Vũ Mạnh | 12 | 23.50 | 11.50 |
| L12 | Highway Engineer 6 (Road Structure) | Huỳnh Văn Quang | 12 | 17.9 | 5.90 |
| L13 | Bridge/Structural Engineer 5 | Hồ Lê Thái | 4 | 16.90 | 12.90 |
| L14 | Bridge/Structural Engineer 6 | Lê Thanh Tùng | 4 | 19.83 | 15.83 |
| L15 | Interchange Specialist | Phan Đặng Việt Anh | 2 | 5.79 | 3.79 |
| L16 | Bridge/Structural Engineer 7 | Phan Công Thành | 3 | 11.00 | 8.0 |
| L17 | Tunnel Engineer | Nguyễn Quang Toàn | 4 | 1.4 | -2.6 |
| L18 | Soil/Geotechnical Engineer 1 (Slope) | Quach Thi Thu | 2 | 0 | -2 |
| L19 | Soft Ground Treatment Specialist | Bùi Xuân Hạnh | 3 | 18.66 | 15.66 |
| L20 | Drainage Engineer 1 | Lương Tiến Hùng | 7 | 19.16 | 12.16 |
| L21 | Drainage Engineer 2 | Nguyễn Phúc Hòa | 6 | 9.00 | 3.00 |
| L22 | River Engineer | Nguyễn Sơn | 2 | 0 | -2 |
| L23 | Pavement/Material Engineer 1 | Trần Trọng Nghĩa | 4 | 7.0 | 3.0 |
| L24 | Pavement/Material Engineer 2 | Nguyễn Việt Hải | 4 | 5.00 | 1.0 |
| L25 | Senior Surveyor 1 | Lê Văn Thủ | 6 | 21.87 | 15.87 |
| L26 | Senior Surveyor 2 | Đào Trân Châu | 5 | 9.14 | 4.14 |
| L27 | Senior Surveyor 3 | Nguyễn Anh Tuấn | 5 | 0 | -5 |
| L28 | Soil/Geotechnical Engineer 2 | Nguyễn Doãn Tĩnh | 5 | 9.73 | 4.73 |
| L29 | Soil/Geotechnical Engineer 3 | Lê Xuân Vũ | 4 | 15.23 | 11.23 |
| L30 | Soil/Geotechnical Engineer 4 | Trần Duy Khiêm | 4 | 15.23 | 11.23 |
| L31 | Geological Engineer (Tunnel) | Phùng Văn Thời | 2 | 6.47 | 2.47 |
| L32 | Hydraulic Engineer 1 | Nguyễn Minh Lương | 3 | 10.62 | 7.62 |
| L33 | Hydraulic Engineer 2 | Nguyễn Đức Duy | 3 | 16.90 | 13.90 |
| L34 | Inundation Analyst | Nguyễn Ngọc Bách | 3 | 1.63 | -1.37 |
| L35 | Transport Economist | TRịnh Đức Thắng | 3 | 3.67 | 0.67 |
| L36 | Operating & Maintenance Specialist | Ha Quoc Hieu | 4 | 0 | -4 |
| L37 | Expressway Management Unit Specialist | Le Tung Lam | 2 | 0 | -2 |
| L38 | Traffic Management Specialist | Phan Minh Tuan | 3 | 0 | -3 |
| L39 | Asset Management Specialist | Trinh Ngoc Hai Thang | 2 | 0 | -2 |
| L40 | Architect 1 | Nguyễn Văn Hòa | 3 | 4.8 | 1.8 |
| L41 | Architect 2 | Ngo Vu Quang Khoa | 3 | 0 | -3 |
| L42 | ITS Specialist | Nguyen Huu Tinh | 5 | 0 | -5 |
| L43 | Communication System Engineer | Man Thành Nam | 3 | 6 | 3 |
| L44 | Electrical Engineer 1 | Trinh Dinh Khiem | 7 | 0 | -7 |
| L45 | Electrical Engineer 2 | Võ Hồng | 5 | 16.29 | 11.29 |
| L46 | Toll Collection System Specialist | Bui Phu Huy | 4 | 0 | -4 |
| L47 | Cost Estimator 1 (Civil Work Packages) | Văn Hồng Liên | 11 | 19.93 | 8.93 |
| L48 | Cost Estimator 2 (Civil Work Packages) | Hoàng Thanh Minh | 8 | 12.53 | 4.53 |
| L49 | Cost Estimator 3 (Other Packages) | Nguyen Thi Sinh | 2 | 0 | -2 |
| L50 | Procurement/Contract Specialist 1 | Trần Sỹ Hùng | 12 | 27.87 | 15.87 |
| L51 | Procurement/Contract Specialist 2 | Ha Ngoc Anh Minh | 8 | 0 | -8 |
| L52 | Senior Environmental Specialist | Ngô Thế Hùng | 8 | 20 | 12 |
| L53 | Environmental Specialist | Pham The Giang | 8 | 7.9 | -0.1 |
| L54 | Senior Resettlement Specialist | Nguyễn Mạnh Hà | 14 | 13 | -1 |
| L55 | Social and Resettlement Specialist | Lâm Đình Uy | 14 | 23.50 | 9.50 |
| L56 | Cultural and Archaeological Specialist | Trần Văn Bình | 14 | 13 | -1 |
| L57 | Training Specialist | To be named | 4 | 0 | -4 |
|  |  | Total | 357 | 616.34 | 259.34 |

15 non-approved Vietnamese domestic staff for expressway design service were mobilized as shown in Table 3.11.

# Table 3.11 Mobilization Status (Vietnamese Staff, Not Approved)

| No. | Position | Name | Mobilized | Demobilized | MM |
| --- | --- | --- | --- | --- | --- |
| L12-2 | Highway Engineer 7 (Road Structure) | Mai Xuân Ngọc | 01/8/2012 | 31/5/2013 | 10.00 |
| L12-3 | Highway Engineer 8 (Road Structure) | Vũ Anh Tuấn | 01/8/2012 | 31/5/2013 | 10.00 |
| L16-2 | Bridge/Structural Engineer 8 | Phạm Kim Mỹ | 01/12/2011 | 28/02/2013 | 15.00 |
| L16-3 | Bridge/Structural Engineer 9 | Cao Cự Vinh | 01/12/2011 | 31/10/2013 | 22.00 |
| L16-4 | Bridge/Structural Engineer 10 | Lê Kiên Cường | 15/7/2012 | 31/8/2013 | 13.57 |
| L19-2 | Soft Ground Treatment Specialist 2 | Nguyễn Trần Hải | 01/10/2012 | 31/8/2013 | 11.00 |
| L21-2 | Drainage Engineer 3 | Vũ Trần Sơn | 01/6/2012 | 20/5/2013 | 11.67 |
| L21-3 | Drainage Engineer 4 | Nguyễn Xuân Đạt | 15/11/2012 | 31/8/2013 | 9.53 |
| L21-4 | Drainage Engineer 5 | Vương Hồng Thắng | 15/11/2012 | 31/8/2013 | 6.63 |
| L21-5 | Drainage Engineer 6 | Phạm Văn Quân | 15/11/2012 | 31/8/2013 | 9.00 |
| L30-2 | Soil/Geotechnical Engineer 5 | Nguyễn Anh Ngọc | 01/8/2012 | 31/7/2013 | 12.00 |
| L30-3 | Soil/Geotechnical Engineer 6 | Đào Quang Huy | 01/8/2012 | 15/01/2013 | 5.50 |
| L30-4 | Soil/Geotechnical Engineer 7 | Mai Huy Đạo | 01/8/2012 | 15/01/2013 | 5.50 |
|  | KCS/ road | Nguyễn Mạnh Chung | 01/12/2012 | 14/9/2013 | 9.47 |
|  | KCS/bridge | Nguyễn Đăng Hoàng | 18/12/2012 | 30/9/2013 | 9.47 |
|  |  | Total |  |  | 160.33 |

Totaling 97.11 MM of international and 419.67 MM of Vietnamese staff were mobilized for the expressway design as shown in Table 3.12. This is mainly because of the following reasons:

- Quality of the feasibility study was poor and the DD consultant spent much time for “updating F/S” including additional topographic survey and discussion with local authorities.

- Approval process of the client is poor. Even PMU85 approved, VEC changed, Even VEC approved, MOT changed during the detailed design process, and such poor decision making caused much un-necessary works which the consultant needed to input more staff for recovering the delay of the services.

- Delays of appraisal comments also caused much delays, and therefore the Consultant was forced to keep our staff in order to wait those delayed comments from the client.

# Table 3.12 Total Additional Input of Staffing

| No. | Position | As contract | Mobilized | Variance |
| --- | --- | --- | --- | --- |
| 1 | International staffs | 239 | 294.5 + 41.61 = 336.11 | 97.11 |
| 2 | Domestic staffs | 357 | 616.34+ 160.33 = 776.67 | 419.67 |

## Planned vs. Actual Implementation Schedules

During the first contract negotiation completed on 26th May 2011, VEC(EA) agreed with early commencement of GPS Survey, topographic survey and hydrological survey in order to complete those site works before rainy seasons. Accordingly, the Consultant mobilized to Danang city on 15th July 2011 and commenced the survey works.

Upon the signing of the Original Contract on 15th November 2011, PMU85(IA) issued Notice to Proceed (NPT) with his letter No. 1622/PMU85-PP2 dated 18th November 2011 and the consulting service contract was commenced on 1st December 2011 for 14 months period which ends 31st January 2013.

Because of mainly the following reasons, the services has been delayed more than one year:

- Many additional works was required to correct the design in feasibility study which was in poor and not acceptable quality as shown in Table 5.1 below.

- Delay of appraisal comments and approval as shown in Table 6.14 for civil works. For the electrical works, the comments were issued on 7/3/2014, and for the ITS works, the MOT comments were issued on 21/5/2014.

- Many changes instructed even once those final outcomes were already submitted to the client.

Actual implementation against the milestones stipulated in the contract is tabulated in Table 3.13.

# Table 3.13  Achievement of Contractual Milestones

| No. | Milestone | Actual | Schedule in Contract | Clause in Contract |
| --- | --- | --- | --- | --- |
| 01 | Contract signing | ---- | 15/11/2011 | Contract |
| 02 | Issuance of Notice to Proceed | ---- | 18/11/2011 | PMU85 letter No. 1622/PMU85-PP2 dated November 18, 2011 |
| 03 | Commencement of Consulting services | ---- | 1/12/2011 | Consultant letter No. DQEDD-PMU85-52-11 dated November 18, 2011. |
| 04 | Submission and approval of Bank Guarantee for 20% of the Contract Price. | 30/01//2012 | --- | Item 6.4 of Special Conditions of Contract, Condition of 1st Payment (20%) |
| 05 | Submission of draft design report for the first contract package | 13/02/2012 | 31/12/2011 | Item I.3.6 of Minutes of Discussion dated 15/10/2011 |
| 06 | Inception Report | 27/12/2011 | 31/12/2011 | Item (1), Appendix B: Reporting Requirements |
| 07 | Submission of 1st Interim Payment for Inception Report | 21/02/2012 | 31/12/2011 | Item 6.4 of Special Conditions of Contract, Condition of 2nd Payment (10%) |
| 08 | Inception report of Replacement Cost Survey | 13/03/2012 | 31/12/2011 | Item IV, TOR of RCS, Annex B, TOR, Item (9), Appendix B: Reporting Requirements |
| 09 | Submission of a brief report on the appropriateness of the proposed alignment | 13/03/2012 | 15/1/2012 | Item 7, Annex A, TOR, Item (8), Appendix B: Reporting Requirements |
| 10 | Review and Detailed Design Framework Report | 27/02/2012 | 31/1/2012 | Item (2), Appendix B: Reporting Requirements |
| 11 | Completion of detailed design for the first contract package | 30/6/2012. | 15/2/2012 | Item I.3.6 of Minutes of Discussion dated 15/10/2011 |
| 12 | Submission and approval of Interim Report (ITR), Basic Design Report (BDR) and Prequalification Documents (PQD). |  | 31/3/2012 | Item 6.4 of Special Conditions of Contract, Condition of 3rd Payment (25%) |
| 12-1 | Interim Report (ITR) | 5/4/2012 |  |  |
| 12-2 | Basic Design Report (BDR) | 4/7/2012 |  |  |
| 12-3 | Prequalification Documents (PQD). | 29/03/2012 |  |  |
| 13 | Release of bank guarantee when the total payments reach 55% | 15/1/2013 | 31/3/2012 | Item 6.4 of Special Conditions of Contract Condition of Release of Bank Guarantee |
| 14 | Submission of overall implementation plan of the project | 14/06/2012 | 31/3/2012 | Item B.2 of Minutes of Contract Negotiation dated 26/05/2011 |
| 15 | Submission of updated draft EIA and EMP reports |  | 15/4/2012 | Item 7, Annex A, TOR, Item (8), Appendix B: Reporting Requirements |
| 15-1 | EIA | 14/06/2012 |  |  |
| 15-2 | EMP | 30/07/2012 |  |  |
| 16 | Submission of RCS reports |  | 15/5/2012 | Item IV, TOR of RCS, Annex B, TOR, Item (9), Appendix B: Reporting Requirements |
| 16-1 | Hoa Vang | 12/01/2013 |  |  |
| 16-2 | Dien Ban | 27/6/2012 |  |  |
| 16-3 | Duy Xuyen | 15/01/2013 |  |  |
| 16-4 | Que Son | 14/01/2013 |  |  |
| 16-5 | Thang Binh | 19/03/2013 |  |  |
| 16-6 | Phu Ninh | 29/03/2013 |  |  |
| 16-7 | TP.Tam Ky | 20/06/2012 |  |  |
| 16-8 | Nui Thanh | 21/01/2013 |  |  |
| 16-9 | Binh Son | 07/06/2012 |  |  |
| 16-10 | Son Tinh | 07/06/2012 |  |  |
| 16-11 | TP.Quang Ngai | N/A |  |  |
| 16-12 | Tu Nghia | 03/01/2013 |  |  |
| 16-13 | Nghia Hanh | 03/01/2013 |  |  |
| 17 | Submission of 3 sets of draft design report (DDR), prequalification (PQ) and tender documents (TB) for the first three contract packages |  | 31/5/2012 | Appendix B: Reporting Requirements |
| 17-1 | PKG3A |  |  |  |
| 17-1-1 | draft design report (DDR) | 30/06/2012 |  |  |
| 17-1-2 | prequalification (PQ) | 19/11/2011 |  |  |
| 17-1-3 | tender documents (TB) | 26/07/2012 |  |  |
| 17-2 | PKGA4: |  |  |  |
| 17-2-1 | draft design report (DDR) | 15/10/2012 |  |  |
| 17-2-2 | prequalification (PQ) | 17/01/2012 |  |  |
| 17-2-3 | tender documents (TB) | 29/11/2012 |  |  |
| 17-3 | PKG6 |  |  |  |
| 17-3-1 | draft design report (DDR) | 11/05/2012 |  |  |
| 17-3-2 | prequalification (PQ) | 18/12/2013 |  |  |
| 17-3-3 | tender documents (TB) | 1/3/2013 |  |  |
| 18 | Submission of updated draft final EIA and EMP reports |  | 15/7/2012 | Item 7, Annex A, TOR, Item (8), Appendix B: Reporting Requirements |
| 18-1 | draft final EIA report | EIA: 05/10/2012 |  |  |
| 18-2 | draft final EMP report | EMP: 3/11/2012 |  |  |
| 19 | Completion of design works and preparation of bidding documents of the first 3 packages |  | 31/8/2012 | Item B.2 of Minutes of Contract Negotiation dated 26/05/2011 |
| 19-1 | PKG3A |  |  |  |
| 19-1-1 | Draft Detailed Design Report | 5/11/2012 |  |  |
| 19-1-2 | Draft Bidding Documents | 5/11/2012 |  |  |
| 19-2 | PKGA4 |  |  |  |
| 19-2-1 | Draft Detailed Design Report | 15/10/2012 |  |  |
| 19-2-2 | Draft Bidding Documents | 29/11/2012 |  |  |
| 19-3 | PKG6 |  |  |  |
| 19-3-1 | Draft Detailed Design Report | 18/12/2013 |  |  |
| 19-3-2 | Draft Bidding Documents | 1/3/2013 |  |  |
| 20 | Submission and approval of Monthly Progress Report No.9, Detailed Design Report and Bidding Documents of the first 3 packages. |  | 15/9/2012 | Item 6.4 of Special Conditions of Contract, Condition of 4th Payment (20%) |
| 20-1 | MPR No.9 | 05/09/2012 |  |  |
| 20-2 | PKG3A |  |  |  |
| 20-2-1 | Approval of Detailed Design Report | 5/11/2012 |  |  |
| 20-2-2 | Approval of Bidding Documents | 5/11/2012 |  |  |
| 20-3 | PKGA4 |  |  |  |
| 20-3-1 | Approval of Detailed Design Report | 15/10/2012 |  |  |
| 20-3-2 | Approval of Bidding Documents | 29/11/2012 |  |  |
| 20-4 | PKG6 |  |  |  |
| 20-4-1 | Approval of Detailed Design Report | 18/12/2013 |  |  |
| 20-4-2 | Approval of Bidding Documents | 1/3/2013 |  |  |
| 21 | Commencement of the first package | 19/5/2013 | 30/9/2012 | Item I.1 of Minutes of Discussion dated 15/10/2011, Item 3.3.1 of TOR |
| 22 | Submission of full sets of design reports, prequalification and tender documents for the whole project |  | 30/11/2012 30/11/2012 | Appendix B: Reporting Requirements Appendix B: Reporting Requirements |
| 22-1 | PKG1 |  |  |  |
| 22-1-1 | Submission of full sets of design reports | 14/06/2013 |  |  |
| 22-1-2 | Prequalification documents | 02/05/2012 |  |  |
| 22-1-3 | Tender documents | 05/9/2013 |  |  |
| 22-2 | PKG2 |  |  |  |
| 22-2-1 | Submission of full sets of design reports | 13/06/2013 |  |  |
| 22-2-2 | Prequalification documents | 02/05/2012 |  |  |
| 22-2-3 | Tender documents | 26/8/2013 |  |  |
| 22-3 | PKG3A |  |  |  |
| 22-3-1 | Submission of full sets of design reports | 30/06/2012 |  |  |
| 22-3-2 | Prequalification documents | 19/11/2012 |  |  |
| 22-3-3 | Tender documents | 26/07/2012 |  |  |
| 22-4 | PKG3B |  |  |  |
| 22-4-1 | Submission of full sets of design reports | 22/04/2013 |  |  |
| 22-4-2 | Prequalification documents | 02/05/2012 |  |  |
| 22-4-3 | Tender documents | 12/7/2013 |  |  |
| 22-5 | PKG4 |  |  |  |
| 22-5-1 | Submission of full sets of design reports | 25/06/2013 |  |  |
| 22-5-2 | Prequalification documents | 12/05/2012 |  |  |
| 22-5-3 | Tender documents | 25/11/2013 |  |  |
| 22-6 | PKG5 |  |  |  |
| 22-6-1 | Submission of full sets of design reports | 20/03/2013 |  |  |
| 22-6-2 | Prequalification documents | 11/05/2012 |  |  |
| 22-6-3 | Tender documents | 5/8/2013 |  |  |
| 22-7 | PKG6 |  |  |  |
| 22-7-1 | Submission of full sets of design reports | 18/12/2012 |  |  |
| 22-7-2 | Prequalification documents | 11/05/2012 |  |  |
| 22-7-3 | Tender documents | 01/03/2013 |  |  |
| 22-8 | PKG7 |  |  |  |
| 22-8-1 | Submission of full sets of design reports | 07/02/2013 |  |  |
| 22-8-2 | Prequalification documents | 12/05/2012 |  |  |
| 22-8-3 | Tender documents | 17/7/2013 |  |  |
| 22-9 | PKGA1 |  |  |  |
| 22-9-1 | Submission of full sets of design reports | 24/04/2013 |  |  |
| 22-9-2 | Prequalification documents | 04/04/2012 |  |  |
| 22-9-3 | Tender documents | 9/10/2013 |  |  |
| 22-10 | PKGA2 |  |  |  |
| 22-10-1 | Submission of full sets of design reports | 21/03/2012 |  |  |
| 22-10-2 | Prequalification documents | 06/04/2012 |  |  |
| 22-10-3 | Tender documents | 30/09/2013 |  |  |
| 22-11 | PKGA3 |  |  |  |
| 22-11-1 | Submission of full sets of design reports | 24/5/2013 |  |  |
| 22-11-2 | Prequalification documents | 13/04/2012 |  |  |
| 22-11-3 | Tender documents | 11/10/2013 |  |  |
| 22-12 | PKGA4 |  |  |  |
| 22-12-1 | Submission of full sets of design reports | 15/10/2012 |  |  |
| 22-12-2 | Prequalification documents | 17/01/2012 |  |  |
| 22-12-3 | Tender documents | 25/6/2013 |  |  |
| 22-13 | PKGA5 |  |  |  |
| 22-13-1 | Submission of full sets of design reports | 28/12/2013 |  |  |
| 22-13-2 | Prequalification documents | 13/04/2012 |  |  |
| 22-13-3 | Tender documents | 21/11/2013 |  |  |
| 22-14 | PKG13 |  |  |  |
| 22-14-1 | Submission of full sets of design reports | 9/5/2013 |  |  |
| 22-14-2 | Prequalification documents | N/A |  |  |
| 22-14-3 | Tender documents | N/A |  |  |
| 22-15 | PKG14A-1 |  |  |  |
| 22-15-1 | Submission of full sets of design reports | 06/11/2013 |  |  |
| 22-15-2 | Prequalification documents | 19/11/2013 |  |  |
| 22-15-3 | Tender documents | Under preparation |  |  |
| 22-16 | PKG14A-2 |  |  |  |
| 22-16-1 | Submission of full sets of design reports | 21/11/2013 |  |  |
| 22-16-2 | Prequalification documents | N/A |  |  |
| 22-16-3 | Tender documents | Under preparation |  |  |
| 23 | Submission and approval of Detailed Design Report and Bidding Documents of the remaining packages, Draft Final Project Completion Report and satisfactory completion of the following works: - Review and update EIA, EMP, EMDP, RAP - Construction method and schedule - Preparation of implementation program - Study and design of ITS and toll collection system - Cost Estimate - Expressway operation and maintenance |  | 30/11/2012 | Item 6.4 of Special Conditions of Contract Condition of 5th Payment (15%) |
| 23-1 | Approval of Detailed Design Report |  | 30/11/2012 |  |
| 23-1-1 | PKG 1 | 21/08/2013 |  |  |
| 23-1-2 | PKG 2 | 15/08/2013 |  |  |
| 23-1-3 | PKG 3A | 23/11/2012 |  |  |
| 23-1-4 | PKG 3B | 05/06/2013 |  |  |
| 23-1-5 | PKG 4 | 25/10/2013 |  |  |
| 23-1-6 | PKG 5 | 14/06/2013 |  |  |
| 23-1-7 | PKG 6 | 09/07/2013 |  |  |
| 23-1-8 | PKG 7 | 09/07/2013 |  |  |
| 23-1-9 | PKG A1 | 20/08/2013 |  |  |
| 23-1-10 | PKG A2 | 09/07/2013 |  |  |
| 23-1-11 | PKG A3 | 20/08/2013 |  |  |
| 23-1-12 | PKG A4 | 08/03/2013 |  |  |
| 23-1-13 | PKG A5 | 20/08/2013 |  |  |
| 23-1-14 | PKG 13 A/B/C |  |  |  |
| 23-1-15 | PKG 14 A | 16/06/2014 |  |  |
| 23-1-16 | PKG 14 B | 16/06/2014 |  |  |
| 23-2 | Approval of Bidding Documents |  | 30/11/2012 |  |
| 23-2-1 | PKG 1 | 06/09/2013 |  |  |
| 23-2-2 | PKG 2 | 28/08/2013 |  |  |
| 23-2-3 | PKG 3A | 08/01/2013 |  |  |
| 23-2-4 | PKG 3B | 25/07/2013 |  |  |
| 23-2-5 | PKG 4 | 13/12/2013 |  |  |
| 23-2-6 | PKG 5 | 27/09/2013 |  |  |
| 23-2-7 | PKG 6 | 27/09/2013 |  |  |
| 23-2-8 | PKG 7 | 27/09/2013 |  |  |
| 23-2-9 | PKG A1 | N/A |  |  |
| 23-2-10 | PKG A2 |  |  |  |
| 23-2-11 | PKG A3 |  |  |  |
| 23-2-12 | PKG A4 | 24/06/2013 | 30/11/2012 |  |
| 23-2-13 | PKG A5 | 26/03/2014 |  |  |
| 23-2-14 | PKG A1-A2-A3 | 31/12/2013 | 30/11/2012 |  |
| 23-2-15 | PKG 13 A/B/C | To be prepared by Supervision Consultant |  |  |
| 23-2-16 | PKG 14 A |  | 30/11/2012 |  |
| 23-2-17 | PKG 14 B |  |  |  |
| 23-3 | Draft Final Project Completion Report | 15/12/2014 | 30/11/2012 |  |
| 23-4 | Approval of Update EIA | 10/07/2013 | 30/11/2012 |  |
| 23-5 | Approval of Update EMP | 10/07/2013 | 30/11/2012 |  |
| 23-6 | Method Statement |  | 30/11/2012 |  |
| 23-6-1 | PKG 1 | 25/10/2013 |  |  |
| 23-6-2 | PKG 2 | 21/10/2013 |  |  |
| 23-6-3 | PKG 3A | 11/3/2013 |  |  |
| 23-6-4 | PKG 3B | 12/9/2013 |  |  |
| 23-6-5 | PKG 4 | 8/2/2014 |  |  |
| 23-6-6 | PKG 5 | 2/11/2013 |  |  |
| 23-6-7 | PKG 6 | 14/11/2013 |  |  |
| 23-6-8 | PKG 7 | 7/11/2013 |  |  |
| 23-6-9 | PKG A1 | 29/10/2013 |  |  |
| 23-6-10 | PKG A2 | 3/9/2013 |  |  |
| 23-6-11 | PKG A3 | 9/1/2014 |  |  |
| 23-6-12 | PKG A4 | 11/5/2013 |  |  |
| 23-6-13 | PKG A5 | 18/4/2013 |  |  |
| 23-7 | Implementation Program | 4/12/2012 | Time to time |  |
| 23-8 | Design of ITS and toll collection system | 12/02/2014 | 30/11/2012 |  |
| 23-9 | Cost Estimate |  | 30/11/2012 |  |
| 23-9-1 | PKG 1 | 25/10/2013 |  |  |
| 23-9-2 | PKG 2 | 29/10/2013 |  |  |
| 23-9-3 | PKG 3A | 28/2/2013 |  |  |
| 23-9-4 | PKG 3B | 27/9/2013 |  |  |
| 23-9-5 | PKG 4 | 24/1/2014 |  |  |
| 23-9-6 | PKG 5 | 8/11/2013 |  |  |
| 23-9-7 | PKG 6 | 14/11/2013 |  |  |
| 23-9-8 | PKG 7 | 7/11/2013 |  |  |
| 23-9-9 | PKG A1 | 24/1/2014 |  |  |
| 23-9-10 | PKG A2 | 20/1/2014 | 30/11/2012 |  |
| 23-9-11 | PKG A3 | 2/1/2014 |  |  |
| 23-9-12 | PKG A4 | 27/8/2013 |  |  |
| 23-9-13 | PKG A5 | 15/4/2013 |  |  |
| 23-9-14 | PKG 13 A/B/C |  |  |  |
| 23-9-15 | PKG 14 A | 07/07/2014 |  |  |
| 23-9-16 | PKG 14 B | 07/07/2014 |  |  |
| 23-10 | Expressway Operation & Maintenance | 12/02/2014 |  |  |
| 24 | Commencement of 2nd to 5th package | A4:24/22/2013 | Every 2 month | Item I.1 of Minutes of Discussion dated 15/10/2011 |
| 25 | Commencement of 6th package to the last one | Not yet. | Every one month |  |
| 26 | Submission and approval of Project Completion Report. | Under preparation | 31/1/2013 | Item 6.4 of Special Conditions of Contract Condition of Final Payment (10%) |

# Part B: Performed Services against the TOR

# Review of Previous Studies and Ensblishing the Detailed Design Framework (TOR 3.2)

## Review of Previous Studies

The Consultant submitted the review reports shown in Table 4.1. The results of review and concerned discussion were carried to subsequent “Basic Design Stage”.

# Table 4.1  Review Reports

| No. | Report Title | Submission Date | Update | Approval |
| --- | --- | --- | --- | --- |
| 1 | Previous Studies Review Reports (Civil) | 27/2/2012 | R1 (23/3/2012) | --- |
| 2 | Brief Report on Environmental Considerations | 13/3/2012 | R1 (25/3/2012) | --- |
| 3 | Previous Studies Review Reports (ITS) | 31/10/2012 | --- | --- |
| 4 | Previous Studies Review Reports (O&M) | 1/11/2012 | --- | -- |
| 5 | Finalization of Expressway Alignment | 19/5/2012 | --- | -- |

## Establish Detailed Engineering Design Framework

The Consultant submitted the following detailed engineering design framework, and those were used for the subsequent design stages:

# Table 4.2  Detailed Engineering Design Framework

| No. | Report Title | Submission Date | Update | Approval |
| --- | --- | --- | --- | --- |
| 1 | List of Technical Standards (Civil) | 29/11/2011 | --- | --- |
| 2 | List of Technical Standards (ITS) - Planning Standard Report | 2/11/2012 | --- | --- |
| 3 | List of Technical Standards (O&M) - Planning Standards Report | 23/10/2012 | --- | --- |
| 4 | Geometric Design Criteria | 27/2/2012 | 27/3/2012 | 20/3/2012 |
| 5 | Bridge Design Criteria | 18/1/2012 | --- | -- |
| 6 | Typical Cross Sections | 18/4/2012 | --- | --- |
| 7 | Sample PQ Document, BOQ, Cost Estimate | 19/3/2012 | --- | --- |

## Technical Standards

### Civil Work

Technical standards to be applied for the design of civil works in the project had been approved several times:

- Decision No. 362/QD-BGTVT dated on 20 February 2009,

- Decision No. 727/QD-BGTVT dated 6 April 2012,

Finally, Decision No. 994/QD-BGTVT dated 16 April 2013, updated the previous approval as shown in Table 4.3.

Table 4.3   Design Standards for Civil Work

| No | Technical Standard | Standards approved in Decision No.362/QD-BGTVT dated 20/2/2009 and No. 727/QD-BGTVT dated 6/4/2013 | Updated/Approved Standards In No. 994/QD-BGTVT dated 16/4/2013 |
| --- | --- | --- | --- |
| 1 | Asphalt Concrete Pavement – Specification for Construction and Acceptance | 22TCN 249-1998 | TCVN 8819:2011 |
| 2 | Graded Aggregate Base and Subbase Pavement - Specification for Construction and Acceptance | 22TCN 334-2006 | TCVN 8859:2011 |
| 3 | Bituminous Surface Treatment – Specification for Construction and Acceptance | 22TCN 271-2001 | TCVN 8863:2011 |
| 4 | Standard Test Method for Measuring Road Pavement Surface Roughness Using a 3m Straight Edge | 22TCN 16-1979 | TCVN 8864:2011 |
| 5 | Method for Measuring and Assessment Roughness by International Roughness Index (IRI) | 22TCN 277-2001 | TCVN 8865:2011 |
| 6 | Standard Test Method for Measuring Pavement Macrotexture Depth Using a Volumetric Technique | 22TCN 278-2001 | TCVN 8866:2011 |
| 7 | Flexible Pavement – Standard Test Method for Determination of Elastic Modulus of Pavement Structure Using Benkelman beam | 22TCN 251-1998 | TCVN 8867:2011 |
| 8 | National Technical Regulation on Road Signs and Signals | 22TCN 237-2001 | QCVN 41:2012/BGTVT |
| 9 | Soil - Methods laboratory of determination of specific weight | TCVN4195:1995 | TCVN4195:2012 |
| 10 | Soil - Methods laboratory of determination of volume weight | TCVN4202:1995 | TCVN4202:2012 |
| 11 | Soils - Sampling, packing, transportation and curing of samples | TCVN2683:1991 | TCVN2683:2012 |
| 12 | Bored Piles- Construction, check and acceptance | TCXDVN 326:2004 | TCVN 9395:2012 |
| 13 | Bored piles – Determination of homogeneity of concrete - sonic pulse method | TCXDVN 358:2005 | TCVN 9396:2012 |
| 14 | Piles - standard test method in situ for piles under axial compressive load | TCXDVN 269:2002 | TCVN 9393:2012 |
| 15 | Cement Treated Aggregate Base for Road Pavement – Specification for Construction and Acceptance | 22TCN 245-1998 | TCVN 8858:2011 |
| 16 | Painting Traffic signal – Road marking by thermoplastic reflective material – Specification, testing method, construction and acceptance. | 22TCN 283-2002 | TCVN 8791:2011 |
| 17 | Painting for protection of steel structure – Specification and testing method | 22TCN 235-97 | TCVN8789:2011 |
| 18 | Painting for protection of steel structure – Construction and acceptance | 22TCN 253-98 | TCVN8790:2011 |
| 19 | Paint and metal covering – Testing method in natural conditions | 22TCN 300-02 | TCVN8785-1:2011 TCVN8785-14:2011 |
| 20 | Concrete structure and precast reinforced concrete | TCXDVN 390:2007 | TCVN 9115:2012 |
| 21 | Drainage reinforced concrete culvert pipe | TCXDVN 372:2006 | TCVN 9113:2012 |
| 22 | Reinforced concrete box culvert | TCXDVN 392:2007 | TCVN 9116:2012 |
| 23 | Product of pre-stressed concrete – Technical specification and acceptance | TCXDVN 389:2007 | TCVN 9114:2012 |
| 24 | Bored pile – Specification for construction and acceptance | TCXDVN 326:2004 | TCVN 9395:2012 |
| 25 | Bored pile – Ultrasonic impulse method for determining the uniform of concrete | TCXDVN 358:2005 | TCVN 9396:2012 |
| 26 | Cement – Testing method – Determination of durability | TCVN 6016:1995 | TCVN 6016:2001 |
| 27 | Portland cements – Specifications | TCVN 2682 – 1999 | TCVN 2682 - 2009 |
| 28 | Portland blended cements – Specifications. | TCVN 2660 – 1987 | TCVN 6260 - 2009 |
| 29 | Water for mixing concrete and mortar – Technical Specification | TCVN 4506:1987 | TCXDVN 4506:2012 |
| 30 | Heavy concrete – Nondestructive method by using both ultrasonic counter and rebound hammer for determining compressive strength | TCXD 171-1989 | TCVN 9335:2012 |
| 31 | The finalization works in construction – Construction and acceptance | TCXD 303-2006 | TCVN 9397-2:2012 TCVN 9397-3:2012 |
| 32 | Mass concrete – Specification for construction and acceptance | TCXDVN 305-2004 | TCVN 9395-2012 |
| 33 | Bitumen – Testing method for physico-mechanical characteristic | 22TCN 279-01 | TCVN 7493:2005 ÷TCVN 7405:2005 |
| 34 | Bitumen –Method for sampling | 22TCN 231-96 | TCVN 7494:2005 |
| 35 | Installation of conduct line in house and public works – Design specification | TCXD25:1991 | TCVN 9207:2012 |
| 36 | Installation of electric facilities in house and public works – Design specification | TCXD27:1991 | TCVN 9206:2012 |
| 37 | Anti-lightning for civil works – Instruction of design, inspection and maintenance for its system | TCXDVN 46:2007 | TCVN 9385:2012 |
| 38 | Chemical admixture for concrete | TCXDVN 325-2004 | TCVN 8826:2011 |
| 39 | Concrete – Requirements on natural moisture curing | TCXDVN 391:2007 | TCVN 8828:2011 |
| 40 | Structure of concrete and reinforced concrete – Technical instruction on preventing cracks under impact of hot- moist climate | TCXDVN 313:2004 | TCVN 9345:2012 |
| 41 | Structure of concrete and reinforced concrete – Instruction on maintenance works. | TCXDVN 318:2004 | TCVN 9343 |

### ITS Work

Decision No.270/QD-BGTVT dated 29 January 2013 shown design standards to be applied for the design or ITS Work.

Table 4.4   Design Standards for ITS Work

| No. | Standards to be applied | Reference |
| --- | --- | --- |
| I | TO BE APPLIED FOR TRAFFICE MANAGEMENT SYSTEM |  |
| 1 | Reference model architecture for the ITS sector | ISO 14813 |
| 2 | Transport information and control systems – Requirements for ITS/TICS central data registry and ITS/TICS data dictionaries | ISO 14817:2002 |
| 3 | Transport information and control systems – Data interfaces between centers for transport information and control system – Part1: message definition requirements | ISO 14827-1:2005 |
| 4 | Transport information and control systems – Data interfaces between centers for transport information and control systems – Part 2: DATEX-ASN | ISO 14827-2:2005 |
| 5 | Intelligent transport systems (ITS) – Data exchange involving roadside modules communication Part1: General principles and documentation framework of application profiles | ISO 15784-1:2008 |
| 6 | Intelligent transport systems (ITS) – Data exchange involving roadside modules communication Part2:Application Profile-SNMP | ISO 15784-2:2008 |
| 7 | Intelligent transport systems (ITS) – Data exchange involving roadside modules communication --- Part3: Application profile-data exchange (AP-DATEX) | ISO 15784-3:2008 |
| II | TO BE APPLIED FOR TOLL COLLECTION SYSTEM |  |
| 1 | Information technology – specification and standardization of data elements | ISO/IEC 11179 |
| 2 | ITS – Dedicated Short Range Communication (DSRC) at 5.8GHz | ITU-R M.1453-2 |
| 3 | Road transport and traffic telematics – Dedicated Short Range Communication (DSRC) – Application Layer | ISO 15628 |
| 4 | DSRC System | ARIB STD-T75 |
| 5 | Road transport and traffic telematics – Electronic fee collection Application Interface Definition for DSRC | ISO 14906 |
| 6 | Electronic fee collection -- Interface Definition for on-board account using integrated circuit card (ICC) | ISO/TS 25110 |
| 7 | Road transport and traffic telematics – Electronic fee collection (EFC) – systems architecture for vehicle related transport services | ISO 17573 |
| 8 | Identification cards – Contactless integrated circuit cards – Proximity cards – Part 1: Physical characteristics | ISO/IEC 14443-1 |
| 9 | Identification cards – Contactless integrated circuit cards – Proximity cards – Part 2: Radio frequency power and signal interface | ISO/IEC 14443-2 |
| 10 | Identification cards – Contactless integrated circuit cards – Proximity cards – Part 3: Initialization and anti-collision | ISO/IEC 14443-3 |
| 11 | Identification cards – Contactless integrated circuit cards – Proximity cards – Part 4: Transmission protocol | ISO/IEC 14443-4 |
| 12 | Identification cards – Integrated circuit cards – Part 4: Organization, security and commands for interchange | ISO/IEC 7816-4 |
| 13 | Information technology – Telecommunication and information exchange between systems – Near Field Communication – Interface and Protocol (NFCIP-1) | ISO/IEC 18092 |
| 14 | Classification of environment conditions – Part 3 : Classification of groups of environmental parameters and their severities – Section 4: Stationary use at non-weather-protected locations | IEC 60721-3-4 |
| 15 | Classification of environment conditions – Part 3 : Classification of groups of environmental parameters and their severities – Section 5: Ground vehicle installations | IEC 60721-3-5 |
| 16 | Road transport and traffic telematics – Automatic vehicle and equipment identification –System specifications | ISO 14815 |
| 17 | Environmental testing. Part 1: General and guidance | IEC 60068-1 |
| 18 | Road transport and traffic telematics – Electronic fee collection – Test procedures for user and fixed equipment – Part 1: Description of test procedures | ISO/TS 14907-1 |
| 19 | Road transport and traffic telematics – Electronic fee collection – Test procedures for user and fixed equipment – Part 2: Conformance test for the onboard unit application interface | ISO/TS 14907-2 |
| III | TO BE APPLIED FOR COMMUNICATION SYSTEM |  |
| 1 | • 8802-3: 2000 (ISO/IEC) (ANSI/IEEE Std 802.3 2000 Edition): Information Technology – Telecommunications and information exchange between systems – Local and Metropolitan area networks – Specific equipment -- Part3: Carrier sence multiple access with collision detection (CAMA/CD) access method and physical layer specifications. | Ethernet |
| 2 | • IEEE 802.3u-1995 IEEE Standards for Local and metropolitan area networks: Supplement to Carrier sense multiple access with collision detection (CSMA/CD) access method and physical layer specifications: Media access control (MAC) Parameters, Physical Layer, Medium Attachment Units, and Repeater for 100Mb/s Operation, Type 100BaseT (Clauses 21-30) (ANSI) • EIA/TIA568B (AT and T-258A) Commercial Building Telecommunications Wiring Standard, 1991 | Fast Ethernet |
| 3 | • IEEE 802.3ab : Physical coding sublayer (PCS), physical medium attachment (PMA) sublayer and baseband medium, type 1000BASE-T • IEEE 802.3z : Media Access Control(MAC) Parameters, Physical Layer, Repeater and Management Parameters for 1000 Mb/s Operation | Gigabit Ethernet |
| 4 | • RFC 959 File Transfer Protocol, J. Postel, J.K. Reynolds, Oct-01-1985 • RFC 1350 The TFTP Protocol (Revision 2), K. Sollins, July 1992 (TFTP) | FTP |
| 5 | • RFC 1945 Hypertext Transfer Protocol -- HTTP/1.0. R. Fielding, H. Frystyk, T. Berners-Lee • RFC 2068 Hypertext Transfer Protocol -- HTTP/1.1. R. Fielding, J. Gettys, J. Mogul, H. Frystyk, T. Berners-Lee, January 1997 (Status: PROPOSED STANDARD) • RFC 2616 Hypertext Transfer Protocol /1.1 June 1999 • RFC 2617 HTTP Authentication: Basic and Digest Access Authentication, June 1999 | HTTP |
| 6 | • RFC 791 Internet Protocol. J. Postel. Sep-01-1981 | IP |
| 7 | • RFC 1661 The Point-to-Point Protocol (PPP), W. Simpson, July 1994 | PPP |
| 8 | • RFC 1157 Simple Network Management Protocol (SNMP), J.D. Case, M. Fedor, M.L.Schoffstall, C. Davin, May-01-1990 | SNMP |
| 9 | • RFC 793 Transmission Control Protocol. J. Postel. Sep-01-1981 | TCP |
| 10 | • RFC 768 User Datagram Protocol. J. Postel. Aug-28-1980 | UDP |
| 11 | • ISO/IEC 144916-1:1999 Information technology -- Coding of audio visual objects -- Part 1: Systems • ISO/IEC 144916-2:1999 Information technology -- Coding of audio-visual objects -- Part 2: Visual • ISO/IEC 144916-2:1999 Information technology -- Coding of audio-visual objects -- Part 3: Audio • ISO/IEC 14496-10:2003: Information technology -- Coding of audio-visual objects -- Part 10: Advanced Video Coding | MPEG4 |
| 12 | • ITU-T G 652: Characteristics of a single-mode optical fiber and cable • ITU-T G 655: Characteristic of a non-zero dispersion-shifted single-mode optical fiber and cable | FOC |
| 13 | Telecom Peripheral Construction – Technical regulations | TCN 68-254:2006 |
| 14 | Cable duct and cable connected box - Technical requirements | TCN 68-153:1995 |
| 15 | Rigid PVC pipes for underground cables - Technical standards | TCN 68-144:1995 |
| 16 | Rigid PVC pipes for underground cables - Technical standards | TC.VNPT-06:2003 |
| 17 | Code of practice for the construction for optical fiber communication system | TCN 68-178:1999 |

### Additional Standards

Other than the above, the following additional standards, shown in Table 4.5, are applied in the design.

Table 4.5   Additional Design Standards

| No | Technical Standard | Code |
| --- | --- | --- |
| 1 | Standard test method for CBR (California Bearing Ratio) of soils and unbound road base in place | TCVN 8821-2011 |
| 2 | Steel for the reinforcement of concrete – Threaded coupler splice | TCVN 8163:2009 |
| 3 | Water-stop membrane used in construction joints - Requires in using | TCXDVN 290:2002 |
| 4 | Standard Specification for Packaged Dry, Hydraulic-Cement Grout (Nonshrink) | ASTM C1107 |
| 5 | Materials, Equipment, and Procedures for Mixing Standard Compounds and Preparing Standard Vulcanized Sheets - Evaluation of Rubber for Bridge bearing. | ASTM D3182÷D3190; D3192 |
| 6 | Reflective membrane for road signaling | TCVN 7887:2008 |
| 7 | Temporary regulation on normal cement concrete formation with joint in construction of traffic works. | Decision No.3230/QD-BGTVT dated 14/12/2012. |
| 8 | Temporary regulation on construction engineering and acceptance for cement concrete pavement in construction of traffic works. | Decision No.1951/QD-BGTVT dated 17/08/2012. |
| 9 | Flexible pavement – Determination of elastic modul of ground base and pavement structure courses by using hard steel plates | TCVN 8861:2001 |
| 10 | Water supply – Network of pipe and structures – Specification for design | TCXDVN 33:2006 |
| 11 | National technical codes on safety for fire for house and structures | QCVN 06:2010/BXD |
| 12 | Regulations on earthen connection and neutral connection for electric facilities | TCVN 4756:1989 |
| 13 | Geotextile fabric – Testing method | TCVN 8871-1:2011- TCVN 8871-6:2011 |
| 14 | Painting for traffic signal | TCVN 8786:2011 TCVN 8788:2011 |
| 15 | Structure of stone brick – Regulations on construction and acceptance | TCVN 4085:2011 |
| 16 | Asphalt concrete – Testing method | TCVN 8860-1:2011- TCVN 8860-12:2011 |
| 17 | Hot asphalt concrete mixing plant – Specification and checking method | 22TCN 255-99 |
| 18 | Pavement for highway – Construction and acceptance | TCVN 9436-2012 |
| 19 | Polymer Modified Cationic Emulsified Asphalt | TCVN 8816:2011 |
| 20 | Cationic Emulsified Asphalt | TCVN 8817-1:2011 - TCVN 8817-15:2011 |
| 21 | Cut-back asphalt | TCVN 8818-1:2011 - TCVN 8818-5:2011 |

# Basic Design (Additional to TOR)

## Design Modified

As described in Para 19 above, the Consultant carried out “Basic Design”, said “Updating the F/S”, after identification of several critical design controls, during the “Review of Previous Studies” stage, which were missing in TEDI F/S (April 2010). The Consultant thoroughly revised the TEDI F/S (2010) and submitted “Basic Design Report” including modifications of the alignment, location and type of interchanges, typical cross section, and bridge types.

There are 12 major design modifications from TEDI F/S (2010), during the basic design phase, as shown in Table 5.1

Table 5.1   Major Modifications from TEDI F/S (2010)

| No. | Design Area | Modifications |
| --- | --- | --- |
| 1 | Alignment | - 11 sections of the alignment were modified in accordance with design controls newly identified. Total length of the expressway was updated as 131.2km which is 300m shorter than that in the F/S. |
| 2 | Cross sections | - Typical cross sections were fully studied and necessary typical cross sections for i) Throughway, ii) Linking Road, iii) interchange’s rampways and iv) crossing roads were defined. |
| 3 | Pavement Structures | - Application of ATB (10cm) is decided for whole of the expressway. |
| 4 | Design High Water Level (DHWL) | - Design High Water Level (DHWL) was determined for each hydrological sections in the whole of the expressway included alignment shifted sections. Revised DHWLs are lower than that of F/S for some sections and higher for some sections. |
| 5 | Profile | - In accordance with the approved technical standards, the vertical design controls are duly studied including DHWL, required clearance for each crossing roads and waterways, and so on. Cost minimized profile is developed after alternative studies for several sections. |
| 6 | Interchanges | - Design criteria for the interchange design was modified. Basically the scale of interchanges are downsized by lowering the design speed of rampways and reducing the radius of loops. Stage construction method is applied for Tuy Loan IC and Binh Son IC. |
| 7 | Bridges/Viaducts | - All site conditions and requirements are updated by site reconnaissance, hydrological and hydraulic study, geotechnical investigation, clearance requirements and so on. As the result, more than 20 bridges, which is reduction of more than 3,500m of bridge, are cancelled or replaced by underpass or box culverts. |
| 8 | Tunnel | - Location of the tunnel alignment was shifted 200m westward avoiding school, temple and pagoda. Tunnel elevation was lowered from FS approximately 3m, with grade-separation of the alignment, avoiding high embankment at the approach sections. As the results, tunnel length is 556m for East and 515m for West line. In the F/S, 540m for both lines. - Tunnel inner width is changed to 13.05m from 12.75m in order to secure lane arrangement for 120km/hr travel speed. |
| 9 | Softground Treatment | - Softground sections are newly identified and some additional countermeasures are required. Table 5.2 Confirmed Softground Section in B/D PKG; F/S; B/D. 1; 3.14 km; 5.62 km. 2; 1.05 km; 5.61 km. A2; -; 4.46 km. A3; -; 2.50 km. Total; 4.19 km; 18.19 km (+14.00 km). - Note that the total length of the softground section became longer than the above during the detailed design. |
| 10 | Slope Protection at Deep Cut Sections | - 29 deep cut excavation (H>12m, L>100m) sections are identified and slope protection method for each section is studied. |
| 11 | Road Crossing Structures | - All crossing structures are examined and updated, not only road but also waterways: Underpass (Vehicles and Pedestrian): 126 Flyover: 11 Waterways: 186 |
| 12 | O&M | - Locations of O&M buildings are revised in order to avoid design controls newly identified by the detailed topographic survey. |

## Updated Work Quantities

The work quantities are updated after design modification above.

Earthwork volume is reduced by narrowing the median and improving the vertical alignment.

Many bridges are replaced by underpass boxes or waterway boxes.

# Table 5.3   Updated Work Quantities

| No. | Work Item | Increase/Decrease |
| --- | --- | --- |
| 1 | Earthworks Excavation: Embankment: | - 3,700,000m3 (30%) - 3,000,000m3 (13%) |
| 2 | Pavement |  |
| 3 | Softground Treatment | + 14 km (334%) |
| 4 | Underpass Box | + 5 nos. (4%) |
| 5 | Bridge Major River Bridges Other Bridges | + 58m (2%) - 3,740m (29%) |
| 6 | Waterway Box | + 76 nos. (93%) |
| 7 | Tunnel | - 9m (1%) |

## Cost Change by Major Design Modification

Cost change made by major design modifications is summarized in Table 5.4. In total, the design modification contributes the cost saving with the amount of 560 Billion VND which is equivalent to 27 Million US Dollar.

Table 5.4   Cost Change by Major Design Modifications

| No. | Design Area | Cost Change (Billion VND) |
| --- | --- | --- |
| 1 | Alignment | -100 |
| 2 | Cross sections | -200 |
| 3 | Pavement Structures | +600 |
| 4 | Design High Water Level (DHWL) | - |
| 5 | Profile | - |
| 6 | Interchanges | -220 |
| 7 | Bridges/Viaducts | -1200 |
| 8 | Tunnel | - |
| 9 | Softground Treatment | +200 |
| 10 | Slope Protection at Deep Cut Sections | +200 |
| 11 | Road Crossing Structures | +160 |
| 12 | O&M | - |
|  | Total | -560 |
| (By FS unit cost) |  |  |

# Detailed Engineering Design and Procurement Planning (TOR 3.3)

## Packaging (TOR 3.3.1)

The procurement plan for JICA portion including construction contract packaging was approved by MOT in Decision No. 1688/QD-BGTVT dated July 28, 2011. As for the WB portion, it was also approved by MOT in Decision No. 1423/QD-BGTVT dated June 30, 2011.

In December 2011, the Consultant submitted our procurement plan several times. After several times of discussion with PMU85/VEC, the contract packaging is finalized as shown in Table 2.2 above which was submitted by the Consultant’s letter No. DQEDD-PMU85-77-11 dated December 15, 2011.

## Surveys and Investigations (TOR 3.3.2)

### Data Collection (TOR 3.3.2 (1))

In accordance with the requirements stipulated in TOR 3.3.2 (1), the Consultant carried out the data collection as shown in Tables 6.1 – 6.4.

Table 6.1   Data Collection (TOR 3.3.2 (1))

| No. | Item | Data Collected |
| --- | --- | --- |
| 1 | Cost estimate | - See Table 6.2 |
| 2 | Transportation cost of construction materials |  |
| 3 | Other project plan | - See Table 6.3 and 6.4 |
| 4 | Minutes of Acceptance | - See Table 6.5 |

Table 6.2   Data Collection for Cost Estimate

| No. | Document Code | Issue Date | Document Title |
| --- | --- | --- | --- |
| 1 | 04/2010/TT-BXD | 26 May2010 | Guideline of project cost establishment and management (MOC) |
| 2 | No. 16/2003/QH11 | 26 Nov 2003 | Construction law (NA) |
| 3 | No.13/2003/QH11 | 26Nov 2003 | Law on Land (NA) |
| 4 | No. 13/2008/QH12 | 03 Jun 2008 | Law of Value Added Tax (NA) |
| 5 | Decree no.12/2009/NĐ-CP | 12 Feb 2009 | Management of project construction investment cost (Government) |
| 6 | Decree no.85/2009/NĐ-CP | 15 Oct 2009 | Law on Bidding (Government) |
| 7 | Decision No. 957/QĐ-BXD | 29 Sep 2009 | Management and consultancy cost of construction investment project (MOC) |
| 8 | letter No. 1776/2007/BXD-VP | 16 Aug 2007 | Capital construction norms for work construction part (MOC) |
| 9 | letter No. 1777/2007/BXD-VP | 16 Aug 2007 | Capital construction norms for installation part (MOC) |
| 10 | No. 2274/BXD-VP | 10 Nov 2008 | The norm on maintenance of public lighting system (MOC) |
| 11 | No. 2565/BXD-KTCL | 29 Nov 2006 | Application of traffic safety cost (MOC) |
| 12 | Letter No. 1784/BXD-VP | 16 Aug 2007 | The norms for materials (MOC) |
| 13 | Decision No. 131/2007/QD-TTg | 08 Sep 2007 | Publishing regulation of foreign consultant choosy cost in construction activities in Viet Nam (Prime Minister) |
| 14 | Decision No. 33/2004/QD-BTC | 12 Apr 2004 | Insurance fee (MOF) |
| 15 | Decree No. 123/2008/ND-CP | 08 Dec 2008 | VAT law (Government) |
| 16 | Circular No. 194/2010/TT-BTC | 6 Dec 2010 | Guiding customs procedures (MOF) |
| 17 | Decree no.209/2004/NĐ-CP | 16 Dec 2004 | Quality control of construction Project (Government) |
| 18 | Decree no.112/2009/NĐ-CP | 14 Dec 2009 | Management of project construction investment cost (Government) |
| 19 | Decree no.205/2004/NĐ-CP | 14 Dec 2009 | Regulates the salary and allowances system in the state company (Government) |
| 20 | Decree no.70/2011/NĐ-CP | 22 Aug 2011 | Regulates the minimum, zone salary level of the labor working in companies, enterprises, co-operatives, cooperative groups, farms, households, individual and other organizations of Vietnam employ labor. (Government) |
| 21 | Decision No. 38/2005/QĐ-BXD | 2 Nov 2005 | Cost estimate norm of urban drainages maintenance and public lighting (MOC) |
| 22 | Decision No.18/2007/QĐ-UBND | 19 Jul 2007 | Construction unit price-installation part in Quang Ngai Province |
| 23 | Decision No.19/2007/QĐ-UBND | 19 Jul 2007 | Construction survey unit price in Quang Ngai Province |
| 24 | Decision No.20/2007/QĐ-UBND | 19 Jul 2007 | Construction unit price-Construction part in Quang Ngai Province |
| 25 | Decision No.70/2006/QĐ-UBND | 28 Nov 2006 | Estimated price list of machine shift and construction work in Quang Ngai Province |
| 26 | No. 1138/SXD-KTKHXD&HT | 05 Dec 2011 | Declaration on material price: Material price of Quang Ngai Province |
| 27 | No. 1254/CB-LS | 07 oct 2011 | Declaration on material price: Material price of Quang Nam Province |
| 28 | No. 3911/CB-LS | 21 Nov 2011 | Declaration on material price: Material price of Danang City |
| 29 | Letter 324/2008/UBND-QLĐT | 16 Jan 2008 | Construction unit price-Construction part in Da Nang City |
| 30 | Letter 325/2008/UBND-QLĐT | 16 Jan 2008 | Estimated price list of machine shift in Da Nang City |
| 31 | Decision No.28/2007/QĐ-UBND | 28 May 2007 | Highway transport Fee in Da Nang City |
| 32 | Decision No 2236/2006/QĐ-UBND | 01 Aug 2006 | Estimated price list of machine shift in Quang Nam Province |
| 33 | Decision No 3075/2006/QĐ-UBND | 30 Oct 2006 | Estimated price list of machine shift in Quang Nam Province |
| 34 | Decision No.2637/2008/QĐ-UBND | 12 Aug 2008 | Highway transport Fee in Quang Nam Province |
| 35 | Decision No.13/2011/QĐ-UBND | 17 June 2011 | Highway transport Fee in Quang Ngai Province |

Table 6.3   Regional Development Plan along the Expressway

| No. | Document No. | Issued on | Issued by | Subject |
| --- | --- | --- | --- | --- |
| 1 | 1734/QD-TTg | 01/12/2008 | Prime minister | The planning of Vietnam expressway network up to 2020 and vision to 2030 |
| 2 | 35/2009/QD-TTg | 03/03/2009 | Prime minister | The Vietnam transportation development strategy up to 2020 and vision 2030 |
| 3 | 1327/QD-TTg | 24/08/2009 | Prime minister | The Vietnam highway development planup to 2020 and vision to 2030 |
| 4 | 136/QD-TTg | 10/09/2009 | Prime minister | The Vietnam railway transportation development strategy to 2020 and vision to 2030 |
| 5 | 1601/QD-TTg | 15/10/2009 | Prime minister | The Vietnam maritime transportation development plan up to 2020 and vision to 2030 |
| 6 | 2190/QD-TTg | 24/12/2009 | Prime minister | The Vietnam seaport system development plan up to 2020, vision to 2030 |
| 7 | 140/QD-TTg | 21/01/2010 | Prime minister | The detailed planning of North – South expressway |
| 8 | 07/2011/QĐ-TTg | 25/01/ 2011 | Prime minister | The master transportation plan of the key economic zone of the central up to 2020 and orientation to 2030 |

Table 6.4   Relevant Projects along the Expressway

| No | Name of Industrial Zone | Area (ha) | Location/Description |
| --- | --- | --- | --- |
| 1 | Chu Lai Open Economic Zone | 3,100 | North Chu Lai (630ha), Truong Hai Automobile Mechanic EZ (243ha), Tam Anh EZ (1.915ha)…; construct and develop Tam Thang high technology zone (300 ha). |
| 2 | Dung Quat Economic Zone | 46,000 |  |
| 3 | Hoa Khuong IZ | 400 | Hoa Khuong, Hoa Vang, Da Nang |
| 4 | Hoa Minh IZ | 200 | Hoa Minh, Hoa Vang, Da Nang |
| 5 | 6 Industrial Groups at some districts of Da Nang | 316 | Districts of Hoa Van, Ngu Hanh Son, Thanh Khe, Lien Chieu, Son Tra - Da Nang |
| 6 | Dien Nam - Dien Ngoc IZ | 418 | Dien Ban District – Quang Nam |
| 7 | Thuan Yen IZ | 130 | Tam Ky Town – Quang Nam |
| 8 | Tam Hiep IZ | 120 | Nui Thanh district – Quang Nam |
| 9 | Bac Chu Lai IZ | 120 | Nui Thanh district – Quang Nam |
| 10 | Tam Thang IZ | 292 | Thang Binh district - Quang Nam |
| 11 | Dong Que Son IZ | 381 | Que Son district - Quang Nam |
| 12 | An Hoa - Dong Son Iz | 300 | Duy Xuyen District – Quang Nam |
| 13 | Phu My Xuan IZ | 550 | Phu Ninh district – Quang Nam |
| 14 | Phu My Xuan IZ (Phase 1) | 350 | Huyện Phú Ninh – Quang Nam |
| 15 | 157 Industrial Groups located in Quang Nam province | 3,096 | Districts of Tay Giang, Dong Giang, Nam Giang, Dai Loc, Que Son, Phuoc Son, Nam Tra My, Hiep Duc, Tien Phuoc, Dien Ban, Quy Xuyen, Hoi An, Thang Binh, Tam Ky, Phu Ninh, Nui Thanh – Quang Nam |
| 16 | IZ at the East (Dung Quat EZ) | 5,054 | Dung Quat EZ – Quang Ngai |
| 17 | IZ at the West (Dung Quat EZ) | 2,100 | Dung Quat EZ – Quang Ngai |
| 18 | Tinh Phong IZ | 350 | Quang Ngai |
| 19 | Quang Phu IZ | 147 | At the west of Quang Ngai town |
| 20 | Pho Phong IZ | 138 | Duc Pho – Quang Ngai |
| 21 | IZ at the West of Son Tinh | 80 | Quang Ngai |
| 22 | Industrial Groups at some districts of Quang Ngai | 25 | Quang Ngai town, Nghia Hanh dist |

### Topographic Survey (TOR 3.3.2 (2) (i))

In accordance with the requirements stipulated in TOR 3.3.2 (2) (i), the Consultant carried out the topographic survey as shown in Table 6.5.

Table 6.5   Topographic Survey

| No. | Package/ Item | Outcome Submission Date | Acceptance Minutes Date |
| --- | --- | --- | --- |
| 1 | Control Point Survey | 19/12/2012 | 20/12/2012 |
| 2 | Topographic Survey of PKG1 | 16/5/2013 | 24/5/2013 |
| 3 | Topographic Survey of PKG2 | 10/5/2013 | 24/5/2013 |
| 4 | Topographic Survey of PKG3A | 9/10/2012 | 2210/2012 |
| 5 | Topographic Survey of PKG3B | 2/4/2013 | 18/4/2013 |
| 6 | Topographic Survey of PKG4 | 5/6/2013 | 31/5/2013 |
| 7 | Topographic Survey of PKG5 | 13/5/2013 | 18/4/2013 |
| 8 | Topographic Survey of PKG6 | 5/2/3013 | 19/4/2013 |
| 9 | Topographic Survey of PKG7 | 15/3/2013 | 22/4/2013 |
| 10 | Topographic Survey of PKGA1 | 6/5/2013 | 27/5/2013 |
| 11 | Topographic Survey of PKGA2 | 8/3/2013 | 11/4/2013 |
| 12 | Topographic Survey of PKGA3 | 24/4/2013 | 28/5/2013 |
| 13 | Topographic Survey of PKGA4 | 31/5/2013 | 29/4/2013 |
| 14 | Topographic Survey of PKGA5 | 21/5/2013 | 28/4/2013 |

After completion of the procurement of the civil contractor for each contract package, the design consultant handed-over the GPS monuments, at the site, to the contractors as shown in Table 6.6.

Table 6.6   List of Site Handover of GPS Monuments

| No. | Package | Site handover Date |
| --- | --- | --- |
| 1 | PKG1 | 19/02/2014 |
| 2 | PKG2 | 03/01/2014 |
| 3 | PKG3A | 26/06/2013 |
| 4 | PKG3B | 11/12/2013 |
| 5 | PKG4 | 07/05/2014 |
| 6 | PKG5 | 07/04/2014 |
| 7 | PKG6 | 17/03/2014 |
| 8 | PKG7 | 04/2014 |
| 9 | PKGA1 | 25/06/2014 |
| 10 | PKGA2 | 25/06/2014 |
| 11 | PKGA3 | 02/07/2014 |
| 12 | PKGA4 | 16/12/2013 |
| 13 | PKGA5 | 17/07/2014 |

### Survey of Hydrographical Data (TOR 3.3.2 (2) (ii))

In accordance with the requirements stipulated in TOR 3.3.2 (2) (ii), the Consultant carried out the hydrological survey and analysis as shown in Table 6.7.

Table 6.7   Hydrological Survey and Analysis

| No. | Package/ Item | Outcome Submission Date | Acceptance Minutes Date |
| --- | --- | --- | --- |
|  | 1. Hydrological Survey Reports |  |  |
| 1 | V 1 Hydro-Metrological Data Report | 25/12/2012 |  |
| 2 | V 2.1 Report on water level survey along the Expressway centerline |  |  |
| 3 | V 2.2 Drawing of water level survey along the Expressway centerline |  |  |
| 4 | V 3.1 Report on additional survey for flood inundation analysis | 27/3/2013 |  |
| 5 | V 3.2 Drawing of additional survey for flood inundation analysis |  |  |
| 6 | V 4.1 Water level survey and velocity of flow survey for Ky Lam bridge | 25/12/2012 |  |
| 7 | V 4.2 Water level survey and velocity of flow survey for Chiem Son bridge |  |  |
| 8 | V 4.3 Water level survey and velocity of flow survey for Tra Bong bridge |  |  |
| 9 | V 4.4 Water level survey and velocity of flow survey for Tra Khuc bridge |  |  |
| - | 2. Hydraulic and Hydrological Calculation Reports |  |  |
| 10 | 2.1 Hydrological Study Report | 22/10/2012 |  |
| 11 | 2.2 Supporting Document for Hydrological Study | 17/11/2012 |  |
| 12 | 2.3 Flood Inundation Analysis Report | 3/12/2012 |  |

### Engineering Geological Survey (TOR 3.3.2 (2) (iii))

In accordance with the requirements stipulated in TOR 3.3.2 (2) (iii), the Consultant carried out the engineering geological survey as shown in Table 6.8.

Table 6.8   Engineering Geological Survey

| No. | Package/ Item | Outcome Submission Date | Acceptance Minutes Date |
| --- | --- | --- | --- |
| 1 | Geotechnical Investigation of PKG1 | 10/5/2013 | 15/7/2013 |
| 2 | Geotechnical Investigation of PKG1 (Tuy Loan IC) | 27/6/2013 | 10/7/ 2013 |
| 3 | Geotechnical Investigation of PKG1 (Realignment section) | 8/8/2013 | 30/7/2013 |
| 4 | Geotechnical Investigation of PKG1 (LRB02) | 04/06/2013 | 16/7/2013 |
| 5 | Geotechnical Investigation of PKG2 (Embankment) | 29/1/2013 | 27/2/2013 |
| 6 | Geotechnical Investigation of PKG2 (Bridge) | 1/7/2013 | 8/7/2013 |
| 7 | Geotechnical Investigation of PKG2 (My Son IC) | 11/5/2013 | 4/6/2013 |
| 8 | Geotechnical Investigation of PKG2 (Geologic Profile) | 5/7/2013 | 6/7/2013 |
| 9 | Geotechnical Investigation of PKG3A (Ky Lam Bridge) | 17/10/2012 | 27/3/2013 |
| 10 | Geotechnical Investigation of PKG3B | 22/6/2013 | 26/6/2013 |
| 11 | Geotechnical Investigation of PKG3B (Chiem Son Bridge) | 4/4/2013 | 28/5/2013 |
| 12 | Geotechnical Investigation of PKG4-1 | 7/8/2013 | 3/7/2013 |
| 13 | Geotechnical Investigation of PKG4-2 | 7/8/2013 | 10/8/2013 |
| 14 | Geotechnical Investigation of PKG 4- Tunnel Section | 15/4/2013 | 29/5/2013 |
| 15 | Geotechnical Investigation of PKG5 | 11/4/2013 | 23/5/2013 |
| 16 | Geotechnical Investigation of PKG5 (Ha Lam IC) | 25/5/2013 | 4/6/2013 |
| 17 | Geotechnical Investigation of PKG6 | 5/2/2013 | 24/6/2013 |
| 18 | Geotechnical Investigation of PKG6 (ORB-13) | 24/6/2013 | 25/6/2013 |
| 19 | Geotechnical Investigation of PKG7 | 22/3/2013 | 24/5/2013 |
| 20 | Geotechnical Investigation of PKG7 (Tam Ky IC) | 25/5/2013 | 4/6/2013 |
| 21 | Geotechnical Investigation of PKGA1 | 5/7/2013 | 12/7/2013 |
| 22 | Geotechnical Investigation of PKGA1 (FO06a, ORB17a) | 5/7/2013 | 12/7/2013 |
| 23 | Geotechnical Investigation of PKGA2-1 | 9/4/2013 | 3/6/2013 |
| 24 | Geotechnical Investigation of PKGA2-1 (CB23, OP19) | 24/6/2013 | 25/6/2013 |
| 25 | Geotechnical Investigation of PKGA2-1 (Chu Lai IC) | 25/5/2013 | 4/6/2013 |
| 26 | Geotechnical Investigation of PKGA2-2 | 2/4/2013 | 31/5/2013 |
| 27 | Geotechnical Investigation of PKGA2-2 (CB25) | 24/6/2013 | 25/6/2013 |
| 28 | Geotechnical Investigation of PKGA3 | 5/7/2013 | 11/7/2013 |
| 29 | Geotechnical Investigation of PKGA3 (Dung Quat IC) | 25/5/2013 | 4/6/2013 |
| 30 | Geotechnical Investigation of PKGA3 (Tra Bong Bridge) | 4/4/2013 | 5/6/2013 |
| 31 | Geotechnical Investigation of PKGA4 | 9/4/2013 | …Jan 2013 |
| 32 | Geotechnical Investigation of PKGA4 (Box culvert) | 24/6/2013 | 25/6/2013 |
| 33 | Geotechnical Investigation of PKGA4 (Quang Ngai North IC) | 25/6/2013 | 4/6/2013 |
| 34 | Geotechnical Investigation of PKGA5 | 19/6/2013 | 20/6/2013 |
| 35 | Geotechnical Investigation of PKGA5 (Box culvert) | 24/6/2013 | 25/6/2013 |
| 36 | Geotechnical Investigation of PKGA5 (Tra Khuc Bridge) | 4/4/2013 | 27/6/2013 |
| 37 | Geotechnical Investigation of PKG13 (O&M Building) | 13/6/2013 | 31/7/2013 |

### Material Source Survey (TOR 3.3.2 (2) (iv))

In accordance with the requirements stipulated in TOR 3.3.2 (2) (iv), the Consultant carried out the material source survey as shown in Table 6.9.

Material survey for ATB was additionally instructed during MOT meeting on 13/3/2013.

Table 6.9   Material Source Survey

| No. | Package/ Item | Outcome Submission Date | Acceptance Minutes Date |
| --- | --- | --- | --- |
| 1 | Construction Material Survey Report (Whole) | 24/7/2013 |  |
| 2 | Construction Material Survey Report (Each Package) | 9/8/2013 |  |
| 3 | Construction Material Survey Report (ATB) | 16/9/2013 |  |

### Survey of Other Relevant Structures (TOR 3.3.2 (2) (v))

In accordance with the requirements stipulated in TOR 3.3.2 (2) (v), the Consultant carried out the other relevant surveys as shown in Table 6.10.

List of Electrical crossing is shown in Appendix-2.

Table 6.10   Other Relevant Surveys

| No. | Package/ Item | Outcome Submission Date | Acceptance Minutes Date |
| --- | --- | --- | --- |
| 1 | Topographic Survey of Populous Residential Areas | 4/5/2013 | 16/5/2013 |
| 2 | Topographic Survey of Temporary Access Road | 9/5/2013 |  |
| 3 | Topographic Survey of Public Utility | 17/5/2013 | 16/5/2013 |
| 4 | High Voltage Lines (HVL) | 24/10/2012 |  |
| 5 | Medium and Low Voltage Lines (MVL-LVL) | 20/6/2012 |  |

### Additional Traffic Survey (TOR 3.3.2 (2) (vi))

In accordance with the requirements stipulated in TOR 3.3.2 (2) (vi), the Consultant carried out the additional traffic survey as shown in Table 6.11.

Table 6.11   Additional Traffic Survey

| No. | Package/ Item | Outcome Submission Date | Acceptance Minutes Date |
| --- | --- | --- | --- |
| 1 | Additional Traffic Survey Report | 9/1/2013 |  |

### Independent Land Valuation Survey (TOR 3.3.2 (2) (vii))

In accordance with the requirements stipulated in TOR 3.3.2 (2) (vii), the Consultant carried out the independent land valuation survey as shown in Table 6.12.

Table 6.12   Independent Land Valuation Survey

| No. | Package/ Item | Outcome Submission Date | Acceptance Minutes Date |
| --- | --- | --- | --- |
| 1 | Hòa Vang (Km0+000 – Km7+965) | 12/01/2013 |  |
| 2 | Điện Bàn (Km7+965 – Km21+115) | 27/6/2012 |  |
| 3 | Duy Xuyên (Km21+115 – Km29+465) | 15/01/2013 |  |
| 4 | Quế Sơn (Km29+465 – Km39+650) | 14/01/2013 |  |
| 5 | Thăng Bình (Km39+650 – Km52+350) | 19/03/2013 |  |
| 6 | Phú Ninh (Km52+350 – Km66+480) | 29/03/2013 |  |
| 7 | Tam Kỳ (Km66+480 – Km68+425) | 20/06/2012 |  |
| 8 | Núi Thành (Km68+425 – Km99+200) | 21/01/2013 |  |
| 9 | Bình Sơn (Km99+200 – Km111+512) | 07/06/2012 |  |
| 10 | Sơn Tịnh (Km111+512 – Km125+200) | 07/06/2012 |  |
| 11 | Tư Nghĩa (Km125+200 – Km139+263) | 03/01/2013 |  |
| 12 | Nghĩa Hành (Km132+600 – Km134+640) | 03/01/2013 |  |

### Environmental and Social Surveys (TOR 3.3.2 (2) (viii))

Please refer to Sub-clause 6.7 which covers the scope of TOR 3.3.6.

## Detailed Design of Road, Bridges and Other Structures (TOR 3.3.3)

### Approval date of Design Documents (Civil Works) by Package

In accordance with the requirements stipulated in TOR 3.3.3, the Consultant carried out the detailed design of road, bridges and other structures.

After receiving the AC comments and Approval Decision, each report were finalized, time to time, as shown in Table 6.13.

Table 6.13   Approval date of Design Documents (Civil Works) by Package

| No. | PKG | Submission |  |  | Appraisal Comment (1) | Answer to Comment (1) | Appraisal Comment (2) | Answer to Comment (2) | Approval |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Draft | D Final | Final |  |  |  |  |  |
| 1 | 3A | 30/6/2012 |  | 28/12/2012 |  |  |  |  | 23/11/2012 |
| 2 | A4 | 27/9/2012 | 3/4/2013 | 4/6/2013 | 1/3/2013 | 3/3/2013 | 23/4/2013 | 9/5/2013 | 8/3/2013 |
| 3 | 3B | 22/4/2013 |  | 24/6/2013 | 3/6/2013 | 6/6/2013 |  |  | 5/6/2013 |
| 4 | 6 | 5/2/2013 |  | 15/7/2013 | 26/3/2013 | 12/4/2013 | 8/5/2013 |  | 9/7/2013 |
| 5 | 5 | 24/4/2013 |  | 8/7/2013 | 6/5/2013 | 25/5/2013 |  |  | 14/6/2013 |
| 6 | 7 | 24/4/2013 |  | 29/7/2013 | 6/5/2013 | 25/5/2013 |  |  | 9/7/2013 |
| 7 | A2 | 24/4/2013 |  | 29/7/2013 | 6/5/2013 | 25/5/2013 |  |  | 9/7/2013 |
| 8 | A1 | 22/4/2013 |  | 11/9/2013 | 1/7/2013 | 12/7/2013 |  |  | 20/8/2013 |
| 9 | A3 | 27/5/2013 |  | 23/9/2013 | 1/7/2013 | 12/7/2013 |  |  | 20/8/2013 |
| 10 | A5 | 4/4/2013 |  | 2/10/2013 | 26/3/2013 | 24/4/2013 | 8/5/2013 |  | 20/8/2013 |
| 11 | 1 | 29/5/2013 |  | 4/9/2013 | 9/7/2013 | 17/7/2013 |  |  | 21/8/2013 |
| 12 | 2 | 30/5/2013 |  | 26/8/2013 | 24/6/2013 | 4/7/2013 |  |  | 15/8/2013 |
| 13 | 4 | 25/6/2013 |  | 20/11/2013 | 17/7/2013 | 23/7/2013 |  |  | 25/10/2013 |
| 14 | 14A-1 | 2/7/2013 |  |  |  |  | 24/9/2013 | 11/10/2013 | 16/06/2014 |
| 15 | 14B-1 | 2/7/2013 |  |  |  |  | 24/9/2013 | 11/10/2013 | 16/06/2014 |

### Submitted Design Documents for Civil Works

Table 6.14 summarizes all design documents for the civil works submitted for each contract package.

Table 6.14   Submitted Design Documents by Package (Civil Works)

| No. | PKG | Category | Report Title | Rev | Submission Date |
| --- | --- | --- | --- | --- | --- |
| 1 | PKG1 | Road | Detailed Design Reports | 1 | 03/09/2013 |
| 2 |  |  | Drawings |  |  |
| 3 |  |  | Structural Calculation Report | 1 | 03/09/2013 |
| 4 |  |  | Work Qty Report | 1 | 03/09/2013 |
| 5 |  | Geotechnical | Detailed Design Reports | 2 | 06/12/2013 |
| 6 |  |  | Drawings | 2 | 06/12/2013 |
| 7 |  |  | Structural Calculation Report | 2 | 06/12/2013 |
| 8 |  |  | Work Qty Report | 2 | 06/12/2013 |
| 9 |  | Bridge | Detailed Design Reports | 1 | 03/09/2013 |
| 10 |  |  | Drawings |  |  |
| 11 |  |  | Structural Calculation Report |  |  |
| 12 |  |  | Work Qty Report |  |  |
| 13 |  | Drainage | Hydrological and Hydraulic Calculation Report (1) Cross Drainage | 3 | 27/04/2013 |
| 14 |  |  | Hydrological and Hydraulic Calculation Report (2) Longitudinal Drainage | 0 | 10/05/2013 |
| 15 | PKG2 | Road | Detailed Design Reports | 1 | 30/08/2013 |
| 16 |  |  | Drawings |  |  |
| 17 |  |  | Structural Calculation Report | 1 | 30/08/2013 |
| 18 |  |  | Work Qty Report | 1 | 30/08/2013 |
| 19 |  | Geotechnical | Detailed Design Reports | 1 | 27/11/2013 |
| 20 |  |  | Drawings | 3 | 30/12/2013 |
| 21 |  |  | Structural Calculation Report |  |  |
| 22 |  |  | Work Qty Report |  |  |
| 23 |  | Bridge | Detailed Design Reports | 1 | 30/08/2013 |
| 24 |  |  | Drawings |  |  |
| 25 |  |  | Structural Calculation Report |  |  |
| 26 |  |  | Work Qty Report |  |  |
| 27 |  | Drainage | Hydrological and Hydraulic Calculation Report (1) Cross Drainage | 3 | 27/04/2013 |
| 28 |  |  | Hydrological and Hydraulic Calculation Report (2) Longitudinal Drainage | 0 | 10/05/2013 |
| 29 | PKG3A | Road Ky Lam Bridge | Detailed Design Reports | 2 | 28/12/2012 |
| 30 |  |  | Drawings |  |  |
| 31 |  |  | Structural Calculation Report |  |  |
| 32 |  |  | Work Qty Report |  |  |
| 33 | PKG3B | Road | Detailed Design Reports | 1 | 16/08/2013 |
| 34 |  |  | Drawings |  |  |
| 35 |  |  | Structural Calculation Report |  |  |
| 36 |  |  | Work Qty Report |  |  |
| 37 |  | Bridge | Detailed Design Reports | 1 | 16/08/2013 |
| 38 |  |  | Drawings |  |  |
| 39 |  |  | Structural Calculation Report |  |  |
| 40 |  |  | Work Qty Report |  |  |
| 41 |  | Chiem Son Bridge | Detailed Design Reports | 1 | 16/08/2013 |
| 42 |  |  | Drawings |  |  |
| 43 |  |  | Structural Calculation Report |  |  |
| 44 |  |  | Work Qty Report |  |  |
| 45 |  | Drainage | Hydrological and Hydraulic Calculation Report (1) Cross Drainage | 3 | 10/04/2013 |
| 46 |  |  | Hydrological and Hydraulic Calculation Report (2) Longitudinal Drainage | 0 | 05/04/2013 |
| 47 | PKG4 | Road | Detailed Design Reports | 1 | 20/11/2013 |
| 48 |  |  | Drawings |  |  |
| 49 |  |  | Structural Calculation Report |  |  |
| 50 |  |  | Work Qty Report | 1 | 20/11/2013 |
| 51 |  | Geotechnical | Detailed Design Reports | 1 | 20/11/2013 |
| 52 |  |  | Drawings |  |  |
| 53 |  |  | Structural Calculation Report |  |  |
| 54 |  |  | Work Qty Report |  |  |
| 55 |  | Bridge | Detailed Design Reports | 1 | 20/11/2013 |
| 56 |  |  | Drawings |  |  |
| 57 |  |  | Structural Calculation Report |  |  |
| 58 |  |  | Work Qty Report |  |  |
| 59 |  | Tunnel | Detailed Design Reports | 2 | 20/11/2013 |
| 60 |  |  | Drawings |  |  |
| 61 |  |  | Work Qty Report |  |  |
| 62 |  | Drainage | Hydrological and Hydraulic Calculation Report (1) Cross Drainage | 3 | 27/04/2013 |
| 63 |  |  | Hydrological and Hydraulic Calculation Report (2) Longitudinal Drainage | 0 | 24/05/2013 |
| 64 |  |  | Hydrological and Hydraulic Calculation Report (3) Cross Drainage | 3 | 27/04/2013 |
| 65 | PKG5 | Road | Detailed Design Reports | 1 | 08/07/2013 |
| 66 |  |  | Drawings |  |  |
| 67 |  |  | Structural Calculation Report |  |  |
| 68 |  |  | Work Qty Report |  |  |
| 69 |  | Geotechnical | Detailed Design Reports | 1 | 08/07/2013 |
| 70 |  |  | Drawings |  |  |
| 71 |  |  | Structural Calculation Report |  |  |
| 72 |  |  | Work Qty Report |  |  |
| 73 |  | Bridge | Detailed Design Reports | 1 | 08/07/2013 |
| 74 |  |  | Drawings |  |  |
| 75 |  |  | Structural Calculation Report |  |  |
| 76 |  |  | Work Qty Report |  |  |
| 77 |  | Drainage | Hydrological and Hydraulic Calculation Report (1) Cross Drainage | 3 | 26/03/2013 |
| 78 |  |  | Hydrological and Hydraulic Calculation Report (2) Longitudinal Drainage | 0 | 25/03/2013 |
| 79 | PKG6 | Road | Detailed Design Reports | 1 | 15/7/2013 |
| 80 |  |  | Drawings |  |  |
| 81 |  |  | Structural Calculation Report |  |  |
| 82 |  |  | Work Qty Report |  |  |
| 83 |  | Geotechnical | Detailed Design Report s | 1 | 15/7/2013 |
| 84 |  |  | Drawings |  |  |
| 85 |  |  | Structural Calculation Report |  |  |
| 86 |  |  | Work Qty Report |  |  |
| 87 |  | Bridge | Detailed Design Reports | 1 | 15/7/2013 |
| 88 |  |  | Drawings |  |  |
| 89 |  |  | Structural Calculation Report |  |  |
| 90 |  |  | Work Qty Report |  |  |
| 91 |  | Drainage | Hydrological and Hydraulic Calculation Report (1) Cross Drainage | 3 | 10/04/2013 |
| 92 |  |  | Hydrological and Hydraulic Calculation Report (2) Longitudinal Drainage | 0 | 25/03/2013 |
| 93 | PKG7 | Road | Detailed Design Reports | 1 | 30/07/2013 |
| 94 |  |  | Drawings |  |  |
| 95 |  |  | Structural Calculation Report |  |  |
| 96 |  |  | Work Qty Report |  |  |
| 97 |  | Geotechnical | Detailed Design Reports | 1 | 30/07/2013 |
| 98 |  |  | Drawings |  |  |
| 99 |  |  | Structural Calculation Report |  |  |
| 100 |  |  | Work Qty Report |  |  |
| 101 |  | Bridge | Detailed Design Reports | 1 | 30/07/2013 |
| 102 |  |  | Drawings |  |  |
| 103 |  |  | Structural Calculation Report |  |  |
| 104 |  |  | Work Qty Report |  |  |
| 105 |  | Drainage | Hydrological and Hydraulic Calculation Report (1) Cross Drainage | 3 | 10/04/2013 |
| 106 |  |  | Hydrological and Hydraulic Calculation Report (2) Longitudinal Drainage | 0 | 25/03/2013 |
| 107 |  |  | Hydrological and Hydraulic Calculation Report (3) Relocation of Rivers and Streams | 0 | 10/04/2013 |
| 108 | PKGA1 | Road | Detailed Design Reports | 1 | 11/9/2013 |
| 109 |  |  | Drawings |  |  |
| 110 |  |  | Structural Calculation Report |  |  |
| 111 |  |  | Work Qty Report |  |  |
| 112 |  | Geotechnical | Detailed Design Reports | 1 | 11/9/2013 |
| 113 |  |  | Drawings |  |  |
| 114 |  |  | Structural Calculation Report |  |  |
| 115 |  |  | Work Qty Report |  |  |
| 116 |  | Bridge | Detailed Design Reports | 1 | 11/9/2013 |
| 117 |  |  | Drawings |  |  |
| 118 |  |  | Structural Calculation Report |  |  |
| 119 |  |  | Work Qty Report |  |  |
| 120 |  | Drainage | Hydrological and Hydraulic Calculation Report (1) Cross Drainage | 3 | 22/04/2013 |
| 121 |  |  | Hydrological and Hydraulic Calculation Report (2) Longitudinal Drainage | 0 | 16/4/2013 |
| 122 |  |  | Hydrological and Hydraulic Calculation Report (3) Relocation of Rivers and Streams | 0 | 22/04/2013 |
| 123 | PKGA2 | Road | Detailed Design Reports | 1 | 30/07/2013 |
| 124 |  |  | Drawings |  |  |
| 125 |  |  | Structural Calculation Report |  |  |
| 126 |  |  | Work Qty Report |  |  |
| 127 |  | Geotechnical | Detailed Design Reports | 3 | 15/01/2014 |
| 128 |  |  | Drawings |  |  |
| 129 |  |  | Structural Calculation Report |  |  |
| 130 |  |  | Work Qty Report |  |  |
| 131 |  | Bridge | Detailed Design Reports | 1 | 30/07/2013 |
| 132 |  |  | Drawings |  |  |
| 133 |  |  | Structural Calculation Report |  |  |
| 134 |  |  | Work Qty Report |  |  |
| 135 |  | Drainage | Hydrological and Hydraulic Calculation Report (1) Cross Drainage | 3 | 26/03/2013 |
| 136 |  |  | Hydrological and Hydraulic Calculation Report (2) Longitudinal Drainage | 0 | 25/03/2013 |
| 137 | PKGA3 | Road | Detailed Design Reports | 1 | 23/9/2013 |
| 138 |  |  | Drawings |  |  |
| 139 |  |  | Structural Calculation Report |  |  |
| 140 |  |  | Work Qty Report |  |  |
| 141 |  | Geotechnical | Detailed Design Reports | 3 | 11/01/2014 |
| 142 |  |  | Drawings |  |  |
| 143 |  |  | Structural Calculation Report |  |  |
| 144 |  |  | Work Qty Report |  |  |
| 145 |  | Bridge | Detailed Design Reports | 1 | 23/9/2013 |
| 146 |  |  | Drawings |  |  |
| 147 |  |  | Structural Calculation Report |  |  |
| 148 |  |  | Work Qty Report |  |  |
| 149 |  | Tra Bong Bridge | Detailed Design Reports | 1 | 23/9/2013 |
| 150 |  |  | Drawings |  |  |
| 151 |  |  | Structural Calculation Report |  |  |
| 152 |  |  | Work Qty Report |  |  |
| 153 |  | Drainage | Hydrological and Hydraulic Calculation Report (1) Cross Drainage | 3 | 18/04/2013 |
| 154 |  |  | Hydrological and Hydraulic Calculation Report (2) Longitudinal Drainage | 0 | 26/04/2013 |
| 155 | PKGA4 | Road | Detailed Design Reports | 3 | 04/06/2013 |
| 156 |  |  | Drawings |  |  |
| 157 |  |  | Structural Calculation Report | 1 | 04/06/2013 |
| 158 |  |  | Work Qty Report | 4 | 21/08/2013 |
| 159 |  | Bridge | Detailed Design Reports | 4 | 04/06/2013 |
| 160 |  |  | Drawings |  |  |
| 161 |  |  | Structural Calculation Report |  |  |
| 162 |  |  | Work Qty Report |  |  |
| 163 |  | Drainage | Hydrological and Hydraulic Calculation Report (2) Longitudinal Drainage | 1 | 25/03/2013 |
| 164 |  |  | Topographic Survey Reports and Drawings | 1 | 02/04/2013 |
| 165 | A5 | Road | Detailed Design Reports | 1 | 2/10/2013 |
|  |  |  | Drawings |  |  |
| 166 |  |  | Structural Calculation Report |  |  |
| 167 |  |  | Work Qty Report |  |  |
| 168 |  | Geotechnical | Detailed Design Reports | 3 | 16/01/2014 |
| 169 |  |  | Drawings |  |  |
| 170 |  |  | Structural Calculation Report |  |  |
| 171 |  |  | Work Qty Report |  |  |
| 172 |  | Bridge | Detailed Design Reports | 1 | 2/10/2013 |
| 173 |  |  | Drawings |  |  |
| 174 |  |  | Structural Calculation Report |  |  |
| 175 |  |  | Work Qty Report |  |  |
| 176 |  | Tra Khuc Bridge | Detailed Design Reports | 1 | 10/10/2013 |
| 177 |  |  | Drawings |  |  |
| 178 |  |  | Structural Calculation Report |  |  |
| 179 |  |  | Work Qty Report |  |  |
| 180 |  | Drainage | Hydrological and Hydraulic Calculation Report (1) Cross Drainage | 3 | 10/04/2013 |
| 181 |  |  | Hydrological and Hydraulic Calculation Report (2) Longitudinal Drainage | 0 | 25/03/2013 |
| 182 | PKG14A-1 | Traffic Safety | Traffic Safety, Report | 1 | 06/11/2013 |
| 183 |  |  | Traffic Safety, Drawings | 3 | 12/05/2014 |
| 184 |  |  | Traffic Safety, Work Qty Report | 3 | 12/05/2014 |
| 185 | PKG14B-1 | Traffic Safety | Traffic Safety, Report | 1 | 21/11/2013 |
| 186 |  |  | Traffic Safety, Drawings | 3 | 12/05/2014 |
| 187 |  |  | Traffic Safety, Work Qty Report | 3 | 12/05/2014 |

### List of Bridges

List of bridge is shown in Appendix-3.

### List of Cross Structures

List of cross structure is shown in Appendix-4.

## Detailed Design of Electrical Works (Additional to TOR)

### Approval date of Design Documents (Electrical Works) by Package

Design of the electrical works was not included in the TOR, however, the Consultant designed necessary electrical works.

After receiving the AC comments and Approval Decision, each report were finalized, time to time, as shown in Table 6.15.

Table 6.15   Approval date of Design Documents (Electrical Works) by Package

| No. | PKG | Submission |  |  | Appraisal Comment (1) | Answer to Comment (1) | Appraisal Comment (2) | Answer to Comment (2) | Approval |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Draft | D Final | Final |  |  |  |  |  |
| 1 | 14A-2 | 23/5/2013 |  | 2/7/2014 | 18/7/2013 | 25/7/2013 | 24/9/2013 | 11/10/2013 | 16/06/2014 |
| 2 | 14B-2 |  |  |  |  |  |  |  | 16/06/2014 |

### Submitted Design Documents for Electrical Works

Table 6.16 summarizes all design documents for the electrical works submitted for each contract package.

Table 6.16   Submitted Design Documents by Package (Electrical Works)

| No. | PKG | Category | Report Title | Rev | Submission Date |
| --- | --- | --- | --- | --- | --- |
| 1 | PKG14A-2 | Electrical | Detailed Design Reports | 2 | 02/07/2014 |
| 2 |  |  | Drawings |  |  |
| 3 | PKG14B-2 | Electrical | Detailed Design Reports | 2 | 02/07/2014 |
| 4 |  |  | Drawings |  |  |

## Study and Design of ITS and Toll Collection System (TOR 3.3.4)

In accordance with the requirements stipulated in TOR 3.3.4, the Consultant carried out the detailed design of ITS works.

After receiving the AC comments and Approval Decision, each report were finalized, time to time, as shown in Table 6.17.

Table 6.17   Approval date of Design Documents (ITS Works) by Package

| No. | PKG | Submission |  |  | Appraisal Comment (1) | Answer to Comment (1) | Appraisal Comment (2) | Answer to Comment (2) | Approval |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Draft | D Final | Final |  |  |  |  |  |
| 1 | 13C | 10/5/2013 | 12/2/2014 |  |  |  | 24/9/2013 | 28/10/2013 |  |

Table 6.18 summarizes all design documents for the ITS works submitted for each contract package.

Table 6.18   Submitted Design Documents by Package (ITS Works)

| No. | PKG | Category | Report Title | Rev | Submission Date |
| --- | --- | --- | --- | --- | --- |
| 1 | PKG13C | ITS | Detailed Design Reports | 0 | 27/01/2013 |
| 2 |  |  | Drawings |  |  |

## Expressway Operation and Maintenance (TOR 3.3.5)

In accordance with the requirements stipulated in TOR 3.3.5, the Consultant carried out the operation and maintenance (O&M) plan and detailed design of O&M building works.

After receiving the AC comments and Approval Decision, each report were finalized, time to time, as shown in Table 6.19.

Table 6.19   Approval date of Design Documents (O&M Works) by Package

| No. | PKG | Submission |  |  | Appraisal Comment (1) | Answer to Comment (1) | Appraisal Comment (2) | Answer to Comment (2) | Approval |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Draft | D Final | Final |  |  |  |  |  |
| 1 | 13A | 10/5/2013 | 12/2/2014 |  |  |  | 24/9/2013 | 28/10/2013 |  |
| 2 | 13B |  |  |  |  |  |  |  |  |

Table 6.20 summarizes all design documents for the O&M works submitted for each contract package.

Table 6.20   Submitted Design Documents by Package (O&M Works)

| No. | PKG | Category | Report Title | Rev | Submission Date |
| --- | --- | --- | --- | --- | --- |
| 1 | --- | O&M Plan | O&M Plan Report | 2 | 03/05/2013 |
| 2 |  |  | Traffic Management Plan Report | 1 | 03/05/2013 |
| 3 |  |  | Heavy Vehicle Control System Report | 1 | 03/05/2013 |
| 4 |  |  | O&M Building Plan Report | 3 | 03/05/2013 |
| 5 | PKG13A | O&M Building | Detailed Design Reports | 0 | 27/01/2013 |
| 6 |  |  | Drawings |  |  |
| 7 |  |  | Work Qty Report |  |  |
| 8 |  |  | Specifications |  |  |
| 9 | PKG13B | O&M Vehicles | Specifications | 0 | 27/01/2013 |

## Review and Update, as necessary, an Environmental Impact Assessment (EIA), Environmental Management Plan (EMP), Ethnic Minority Development Plan (EMDP) and Resettlement Action Plan (RAP) (TOR 3.3.6)

### Update of Environmental Impact Assessment (EIA) and Environmental Management Plan (EMP)

In accordance with the requirements stipulated in TOR 3.3.6, the Consultant carried out the update of Environmental Impact Assessment (EIA) and Environmental Management Plan (EMP) reports.

Table 6.21   Work Progress of Update of EIA and EMP Reports

| Task | Required Tasks | Time | Contents |
| --- | --- | --- | --- |
| 1 | Review the latest EIA Report, the EMP, and the World Bank comments. | Mar 2012 | The latest version of EIA Report and the EMP (which were submitted to WB in October 2010) had been reviewed, and inadequacy/shortcomings of these reports had been identified. Results of review are summarized and described in the Brief Report. The Brief Report had been submitted to PMU85 on March 13, 2012. |
| 2 | Carry out the field survey to confirm the appropriateness and adequacy of road alignment planning and impact mitigation measures. | Jul 2012 | A list of environmentally-sensitive spots/structures, including all populous residential areas along the proposed alignment, was made. Carried out field surveys at these environmentally-sensitive spots/structures to identify environmental issues, potential impacts that may cause by the proposed alignment, and examined proper measures to avoid/mitigate these impacts if necessary. |
| 3 | Co-work with the Resettlement Team in organizing the public consultation meetings at the project-affected communes and districts. | Jul 2012 | With aim to diffuse information on the Project to local residents, promote local residents’ understanding about the Project, and collect local residents’ comments/opinions on the project design and impact mitigation measures, Co-working with the Resettlement Team in organizing the public consultation meetings at the project-affected communes. Information such as project outlines, impacts that may cause by the project to the commune, proposed impact mitigation measures, etc. are explained to local people during those public consultation meetings. It is also an opportunity for local residents to raise questions, comments, opinions, etc. on the Project, and for collecting information on the environmentally-sensitive spots/structures which could not identified on topographic maps. Comments and opinions raised by participants in the public consultation meetings are also useful and contributable to plan the impact mitigation measures that match with the actual natural and socio-economic conditions of the localities. |
| 4 | Review the comparison of the alternatives and the selection of the options. | Mar 2012 | The process of alignment planning for the Da Nang – Quang Ngai Expressway since 2003, including the comparison of alignment alternatives and the selection of optimum alternative had been reviewed and summarized in the Brief Report. The Brief Report had been submitted to PMU85 on March 13, 2012. |
| 5 | Review, comment on the adequacy of impacts assessment and discuss any potential environmental impacts or issues not raised in the EIA Report. | Mar 2012 | The impact assessment described in the EIA reports had been reviewed. Result of the review was summarized in the Brief Report. The Brief Report had been submitted to PMU85 on March 13, 2012. It can conclude that all potential impacts had been described to some extent in these EIA reports except for the following impacts: - Impact caused by the excavation and transportation of construction materials - Impact caused by the transportation and disposal of waste soils generated from construction works of road, bridges, and tunnels. |
| 6 | Review the environmental mitigation measures proposed for the design, construction and operation phases, and confirm the appropriateness and adequacy of the proposed mitigation measures. | Mar 2012 | The impact mitigation measures described in the EIA reports had been reviewed. Result of the review was summarized in the Brief Report. All impact mitigation measures had been described to some extent in these EIA reports. However, the following impact mitigation measures should be examined further in detail during D/D stage: - Mitigation measures for impact of noise and vibration (during design phase, construction phase and operation phase) - Mitigation measures for impact of air pollution (during construction phase and operation phase) - Mitigation measures for impact of waste water (during construction phase and operation phase) and polluted runoff water from road surface of large bridges (during design phase and operation phase) - Mitigation measures for impacts caused by the transportation and disposal of waste soils and construction wastes (during design phase and construction phase) - Mitigation measures for impact of inundation (during design phase and operation phase) - Mitigation measures for impacts caused by the exploitation and transportation of construction materials (during design phase and construction phase) - Mitigation measures for impact of split of communities, impedance of movements, etc. |
| 7 | Recommend supplemental impact mitigation measures as needed. | Mar 2012 | Necessary supplemental to the impact mitigation measures (which has not been described appropriately in the existing EIA reports) are being examined, those were be described in the Draft Updated EIA Report. |
| 8 | Confirm the appropriateness of the road alignment planning. | Mar 2012 | Process of alignment planning (comparison of alignment alternatives, selection of optimum alternative, appropriateness of topographic maps and information used for alignment planning, etc.) was reviewed. Validity of the alignment planning was assessed and summarized in the Brief Report on Environmental Considerations. In addition, identified 25 sections of the alignment where is relatively high population density and where there is the need to collect more detailed information for assessing the validity of the proposed alignment. Additional topographic Survey for 250m from the centerline at these 25 sections was carried out for confirmation on the validity of the proposed alignment. |
| 9 | Prepare a brief report on the comparison and selection of the alternatives and the final alignment | Mar 2012 | The Brief Report on Environmental Considerations was submitted to PMU85 on March 13, 2012 (Letter Ref No. DQEDD-PMU85-75-12) |
| 10 | Confirm the appropriateness of the mitigation measures and ensure that the mitigation measures are included in the design, technical specifications and contract documents | Jul 2012 | Working close with the design teams in incorporating the impact mitigation measures into design of road, bridges and tunnel. The following measures are considered important and should be discussed carefully with the design teams in D/D stage: - Mitigation measures for impact of noise and vibration in operation phase: co-work with the road design team; - Mitigation measures for impact of polluted runoff water from road surface of large bridges in operation phase: co-work with the bridge design team; - Mitigation measures for impacts caused by the transportation and disposal of waste soils and construction wastes during construction phase: co-work with the cost team; - Mitigation measures for impact of inundation in operation phase: co-work with the road design team; - Mitigation measures for impacts caused by the exploitation and transportation of construction materials during construction phase: co-work with the cost and procurement Team; - Mitigation measures for impact of split of communities, impedance of movements, etc. in operation phase: co-work with the road design Team. |
| 11 | Prepare the Draft Updated EIA Report | Jun 2012 | The following parts of the EIA Report are likely to be revised and updated greatly: - Vietnam legal framework on EIA - Project descriptions (including changes in project design between F/S and D/D) - Anticipated impact and mitigation measures - Public consultation and information disclosure - The Draft Updated EIA Report had been submitted to PMU85 on June 14, 2012. |
| 12 | Prepare the Draft Updated EMP | Jul 2012 | Since there are 13 proposed contract packages for civil work, it will be better to make a common part of EMP for all packages (general regulations, standards, policy, etc.), and the separate parts for 13 packages (which will concentrate into impacts, mitigation measures, responsibilities of contractor, etc. for each package). Depending on the geographical and socio-environmental conditions of each road section, the contract packages can be categorized into each. Doing like this, the separate parts of EMP can describe concretely in detail the measures to avoid/mitigate impacts specialized for the each package in concern. |
| 13 | Make the Draft Final Updated EIA Report | Aug 2012 | The Draft Updated EIA Report described in the previous Section 11 was revised based on comments from PMU85 and WB to make the Draft Final EIA Report in August 2012. |
| 14 | Make the Draft Final Updated EMP | Sep 2012 | The Draft Updated EMP described in the previous Section 12 was revised based on comments from PMU85 and WB to make the Draft Final EMP in September 2012. |
| 15 | Prepare TOR for independent environmental monitoring and supervision during construction phase | Sep 2012 | TOR for independent environmental monitoring and supervision during construction phase was prepared and included in the Updated EIA Report and EMP. |

After receiving the World Bank specialist’s comments the report was finalized as shown in Table 6.22.

Table 6.22   Submitted EIA and EMP Reports

| No. | PKG | Category | Report Title | Rev | Submission Date | Approval Date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | ---- | EIA | Updated draft EIA Report | - | 2012/6/13 | 10/07/2014 |
| 2 |  |  | Draft final Updated EIA Report | - | 2012/12/10 |  |
| 3 |  |  | Final Updated EIA Report | - | 2013/7/22 |  |
| 4 | ---- | EMP | Updated draft EMP Report | - | 2012/7/30 | 27/03/2014 |
| 5 |  |  | Draft final Updated EMP Report | - | 2013/3/20 |  |
| 6 |  |  | Final Updated EMP Report | - | 2013/7/22 |  |

### Preparation of Ethnic Minority Development Plan (EMDP)

It was confirmed that there is no ethnic minority in the project site, and therefore, this report was not required.

### Update of Resettlement Action Plan (RAP)

In accordance with the requirements stipulated in TOR 3.3.6, the Consultant carried out the preparation of Resettlement Action Plan (RAP) report.

There are 42 communes along the expressway and public consultation meetings were carried out for those communes along the expressway, and the expressway alignment were agreed by each local community as shown in Table 6.23.

To facilitate RAP updating and implementation of priority sections, at the request of VEC, WB, JICA agreed that the updated RAPs were prepared separately for affected districts and divided into several stages. Four(4) updated RAPs were found acceptable by VEC and WB and compensation payment is ongoing.

Pegging out works completed and handed over to provincial authorities. However, updating of RAPs are being delayed and will unlikely be completed before the LCD due to delays in carrying out the detailed measurement survey (DMS). Therefore, implementation monitoring of resettlement activities, which are carried by Project Supervision Consultants (PSCs), need to be extended and continued for the entire section after the LCD. External monitoring of resettlement activities will be handed over to PSC to ensure the independence from the implementation monitoring

Consultant has designed an Income Restoration Guideline and handed over to VEC. In addition, feasibility study for Income Restoration Program (IRP) were also completed in all project’s districts.

As of December 2014, progress of the preparing S-RAP report is still in progress as shown in Table 6.24-6.26. It was agreed to transfer the remaining works to Construction Supervision Concusltant (CSC) under WB portion.

Table 6.23   List of Communes along the Expressway

| No. | Province | Contract Package | District | Commune |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Name | From | To | Length (m) |
| 1 | Danang | PKG01 (Km0 - Km8) | Hòa Vang | Hòa Nhơn | Km0+000 | Km1+615 | 1,615 |
| 2 |  |  |  | Hòa Phong | Km1+615 | Km2+515 | 900 |
| 3 |  |  |  | Hòa Tiến | Km2+515 | Km7+965 | 5,450 |
| 4 | Quang Nam |  | Điện Bàn | Điện Tiến | Km7+965 | Km8+000 | 35 |
| 5 |  | PKG02 (Km8 - Km16+880) |  |  | Km8+000 | Km9+580 | 1,580 |
| 6 |  |  |  | Điện Thọ | Km9+580 | Km16+880 | 7,300 |
| 7 |  | PKG03A (16+880 - Km18+100) |  |  | Km16+880 | Km17+700 | 820 |
| 8 |  |  |  | Điện Quang | Km17+700 | Km18+100 | 400 |
| 9 |  | PKG03B (18+100 - Km21+500) |  |  | Km18+100 | Km20+200 | 2,100 |
| 10 |  |  | Duy Xuyên | Duy Trinh | Km20+200 | Km21+500 | 1,300 |
| 11 |  | PKG04 (Km21+500 - Km32+600) |  |  | Km21+500 | Km22+840 | 1,340 |
| 12 |  |  |  | Duy Sơn | Km22+840 | Km26+460 | 3,620 |
| 13 |  |  |  | Duy Trung | Km26+460 | Km29+465 | 3,005 |
| 14 |  |  | Quế Sơn | Quế Xuân | Km29+465 | Km32+600 | 3,135 |
| 15 |  | PKG05 (Km32+600 - Km42) |  |  | Km32+600 | Km34+190 | 1,590 |
| 16 |  |  |  | Phúc Thọ | Km34+190 | Km39+650 | 5,460 |
| 17 |  |  | Thăng Bình | Bình Quý | Km39+650 | Km42+000 | 2,350 |
| 18 |  | PKG06 (Km42 - Km52) |  |  | Km42+000 | Km45+433 | 3,433 |
| 19 |  |  |  | Bình Chánh | Km45+433 | Km48+393 | 2,960 |
| 20 |  |  |  | Bình Quế | Km48+393 | Km49+513 | 1,120 |
| 21 |  |  |  | Bình An | Km49+513 | Km50+817 | 1,304 |
| 22 |  |  |  | Bình Quế | Km50+817 | Km51+650 | 833 |
| 23 |  |  |  | Bình An | Km51+650 | Km52+000 | 350 |
| 24 |  | PKG07 (Km52 - Km65) |  |  | Km52+000 | Km52+350 | 350 |
| 25 |  |  | Phú Ninh | Tam Thành | Km52+350 | Km55+296 | 2,946 |
| 26 |  |  |  | Tam Phước | Km55+296 | Km58+250 | 2,954 |
| 27 |  |  |  | Tam Đàn | Km58+250 | Km60+820 | 2,570 |
| 28 |  |  |  | Tam Thái | Km60+820 | Km65+025 | 4,205 |
| 29 |  | PKGA1 (Km65 - Km81+150) |  | Tam Đại | Km65+025 | Km66+465 | 1,440 |
| 30 |  |  | Tam Kỳ | Tam Ngọc | Km66+465 | Km68+412 | 1,947 |
| 31 |  |  | Núi Thành | Tam Xuân 1 | Km68+412 | Km70+404 | 1,992 |
| 32 |  |  |  | Tam Xuân 2 | Km70+404 | Km75+187 | 4,783 |
| 33 |  |  |  | Tam Anh Bắc | Km75+187 | Km76+800 | 1,613 |
| 34 |  | PKGA2 (Km81+150 - Km99+500) |  | Tam Anh Nam | Km76+800 | Km82+395 | 5,595 |
| 35 |  |  |  | Tam Hiệp | Km82+395 | Km85+625 | 3,230 |
| 36 |  |  |  | Tam Mỹ Tây | Km85+625 | Km87+980 | 2,355 |
| 37 |  |  |  | Tam Mỹ Đông | Km87+980 | Km92+100 | 4,120 |
| 38 |  |  |  | Tam Nghĩa | Km92+100 | Km99+200 | 7,100 |
| 39 | Quang Ngai |  | Bình Sơn | Bình Chánh | Km99+200 | Km99+500 | 300 |
| 40 |  | PKGA3 (Km99+500 - Km110+100) |  |  | Km99+500 | Km100+285 | 785 |
| 41 |  |  |  | Bình Nguyên | Km100+285 | Km105+800 | 5,515 |
| 42 |  |  |  | Bình Trung | Km105+800 | Km109+100 | 3,300 |
| 43 |  |  |  | Bình Chương | Km109+100 | Km109+600 | 500 |
| 44 |  |  |  | Bình Long | Km109+600 | Km110+100 | 500 |
| 45 |  | PKGA4 (Km110+100 - Km124+700) |  |  | Km110+100 | Km111+512 | 1,412 |
| 46 |  |  | Sơn Tịnh | Tịnh Thọ | Km111+512 | Km121+000 | 9,488 |
| 47 |  |  |  | Tịnh Hà | Km121+000 | Km124+700 | 3,700 |
| 48 |  | PKGA5 (Km124+700 - Km131+500) |  |  | Km124+700 | Km125+200 | 500 |
| 49 |  |  | Tư Nghĩa | Nghĩa Kỳ | Km125+200 | Km129+905 | 4,705 |
| 50 |  |  | TP Quảng Ngãi | Quảng Phú | Km129+905 | Km130+175 | 270 |
| 51 |  |  | Tư Nghĩa | Nghĩa Điền | Km130+175 | Km131+500 | 1,325 |
| 52 |  | PKGA5 (Km131+500 - Km139+263) |  |  | Km131+500 | Km132+620 | 1,120 |
| 53 |  |  | Nghĩa Hành | Hành Thuận | Km132+620 | Km133+100 | 480 |
| 54 |  |  | Tư Nghĩa | Nghĩa Điền | Km133+100 | Km133+375 | 275 |
| 55 |  |  | Nghĩa Hành | Hành Thuận | Km133+375 | Km134+640 | 1,265 |
| 56 |  |  | Tư Nghĩa | Nghĩa Trung | Km134+640 | Km138+365 | 3,725 |
| 57 |  |  |  | Nghĩa Thương | Km138+365 | Km139+263 | 898 |
|  | 3 |  | 13 | 42 |  |  | 139,263 |

Table 6.24   List of Consultation Meeting

| No | Location |  |  | Meeting date |
| --- | --- | --- | --- | --- |
|  | Province/ City | District | Commune |  |
| 1 | Da Nang | Hoa Vang | Hoa Nhon | 14/06/2013 |
| 2 |  |  | Hoa Phong | 12/4/2012 |
| 3 |  |  | Hoa Tien | 13/4/2012 |
| 4 | Quang Nam | Dien Ban | Dien Tien | 13/01/2012 |
| 5 |  |  | Dien Tho | 11/01/2012 |
| 6 |  |  | Dien Quang | 12/01/2012 |
| 7 |  | Duy Xuyen | Duy Trinh | 09/10/2012 |
| 8 |  |  | Duy Sơn | 09/10/2012 |
| 9 |  |  | Duy Trung | 10/10/2012 |
| 10 |  | Que Son | Que Xuan 2 | 08/04/2013 |
| 11 |  |  | Phu Tho | 09/11/2012 |
| 12 |  | Thang Binh | Binh Quy | 26/11/2012 |
| 13 |  |  | Binh Chanh | 26/11/2012 |
| 14 |  |  | Binh Que | 27/11/2012 |
| 15 |  |  | Binh An | 27/11/2012 |
| 16 |  | PhuNinh | Tam Thanh | 21/11/2012 |
| 17 |  |  | Tam Phuoc | 21/11/2012 |
| 18 |  |  | Tam Đan | 22/11/2012 |
| 19 |  |  | Tam Thai | 23/4/2012 |
| 20 |  |  | Tam Đai | 23/4/2012 |
| 21 |  | Tam Ky City | Tam Ngoc | 19/4/2012 |
| 22 |  | Nui Thanh | Tam Xuan 1 | 20/4/2012 |
| 23 |  |  | Tam Xuan 2 | 21/4/2012 |
| 24 |  |  | Tam Anh Bac | 04/01/2013 |
| 25 |  |  | Tam Anh Nam | 08/01/2013 |
| 26 |  |  | Tam Hiep | 04/01/2013 |
| 27 |  |  | Tam My Tay | 09/01/2013 |
| 28 |  |  | Tam My Dong | 08/01/2013 |
| 29 |  |  | Tam Nghia | 09/01/2013 |
| 30 | Quang Ngai | Binh Sơn | Binh Chanh | 07/11/2012 |
| 31 |  |  | Binh Nguyen | 10/11/2012 |
| 32 |  |  | Binh Trung | 07/11/2012 |
| 33 |  |  | Binh Chuong | 10/11/2012 |
| 34 |  |  | Binh Long | 14/3/2012 |
| 35 |  | Son Tinh | Tinh Tho | 15/3/2012 |
| 36 |  |  | Tinh Ha | 16/3/2012 |
| 37 |  | Tu Nghia | Nghia Ky | 23/3/2012 |
| 38 |  |  | Nghia Đien | 19/3/2012 |
| 39 |  |  | Nghia Trung | 20/3/2012 |
| 40 |  |  | Nghia Thuong | 21/3/2012 |
| 41 |  | Nghia Hành | Hanh Thuan | 22/3/2912 |

Table 6.25   Agreements with Relevant Authorities

| No. | Document | Date | Local government |
| --- | --- | --- | --- |
| 1 | Minutes of meeting regarding alignment of expressway, road crossing structures, drainage culverts, realigned canals | February 8, 2012 | Dien Ban district, Quang Nam province |
| 2 | Minutes of meeting regarding alignment of expressway, road crossing structures, drainage culverts, realigned canals | February 20, 2012 | Hoa Vang district, Da Nang city |
| 3 | Minutes of meeting regarding alignment of expressway, road crossing structures, drainage culverts, realigned canals | March 7, 2012 | Tam Ky city, Quang Nam province |
| 4 | Minutes of meeting regarding alignment of expressway, road crossing structures, drainage culverts, realigned canals | March 16, 2012 | Binh Son district, Quang Ngai province |
| 5 | The Letterregarding alignment of expressway, road crossing structures, drainage culverts, realigned canals | March 19, 2012 | Son Tinh district, Quang Ngai province |
| 6 | Minutes of meeting regarding alignment of expressway, road crossing structures, drainage culverts, realigned canals | March 24, 2012 | Nui Thanh district, Quang Nam province |
| 7 | Minutes of meeting regarding alignment of expressway, road crossing structures, drainage culverts, realigned canals | March 29, 2012 | Phu Ninh district, Quang Nam province |
| 8 | Minutes of meeting regarding alignment of expressway, road crossing structures, drainage culverts, realigned canals | April 5, 2012 | Thang Binh district, Quang Nam province |
| 9 | Minutes of meeting regarding alignment of expressway, road crossing structures, drainage culverts, realigned canals | April 11, 2012 | Que Son district, Quang Nam province |
| 10 | Minutes of meeting regarding alignment of expressway, road crossing structures, drainage culverts, realigned canals | April 18, 2012 | Tu Nghia district, Quang Ngai province |
| 11 | Minutes of meeting regarding alignment of expressway, road crossing structures, drainage culverts, realigned canals | April 18, 2012 | Nghia Hanh district, Quang Ngai province |
| 12 | Minutes of meeting regarding alignment of expressway, road crossing structures, drainage culverts, realigned canals | April, 2012 | Duy Xuyen district, Quang Nam province |

Table 6.26   Update of Resettlement Action Plan (RAP)

| SURAP No. | PKG | Province | District | Scale of completion (%) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | DMS | RCS | IRP | SES | RS | Completion of SURAP |
| 1 | 1 | Da Nang | Hòa Vang | 70 | 100 | 0 | 100 | 45 | 75 |
| 2 | 1, 2 | Quang Nam | Điện Bàn | 80 | 100 | 100 | 100 | 100 | 95 |
|  | 3A |  |  | 100 | 100 | 100 | 100 | 100 | 100 |
| 3 | 3B, 4 |  | Duy Xuyên | 50 | 100 | 100 | 100 | 60 | 80 |
| 4 | 4, 5 |  | Quế Sơn | 50 | 100 | 100 | 100 | 30 | 60 |
| 5 | 5, 6, 7 |  | Thăng Bình | 50 | 100 | 100 | 100 | 30 | 60 |
| 6 | 7, A1 |  | Phú Ninh | 50 | 100 | 100 | 100 | 55 | 65 |
| 7 | A1 |  | Tam Kỳ City | 100 | 100 | 100 | 100 | 100 | 100 |
| 8 | A1, A2 |  | Núi Thành | 50 | 100 | 100 | 100 | 60 | 70 |
| 9 | A2, A3 | Quang Ngai | Bình Sơn | 50 | 100 | 100 | 100 | 55 | 65 |
|  | A4 |  |  | 100 | 100 | 100 | 100 | 100 | 100 |
| 10 |  |  | Sơn Tịnh | 100 | 100 | 100 | 100 | 100 | 100 |
|  | A5 |  |  | 90 | 100 | 100 | 100 | 100 | 95 |
| 11 |  |  | Tư Nghĩa, | 95 | 100 | 100 | 100 | 100 | 88 |
| 12 |  |  | Quang Ngai city | 70 | 100 | 0 | 100 | 100 | 0 |
| 13 |  |  | Nghĩa Hành | 95 | 100 | 100 | 100 | 100 | 94 |
| Responsible/involved parties |  |  |  | District authorities, PMU85, PMU1, Consultant | Consultant, PPCs, PMU85, PMU1 | Consultant, VEC, District authorities | Consultant | Province/District authorities, VEC, Consultant | Consultant |
| RCS = Replacement Cost Survey (conducted by sub-consultants) DMS = Detailed Measurement Survey (conducted by district authorities) |  |  |  |  |  | RS = Relocation Strategy SES = Supplementary Socio-economic Survey IRP = Income Restoration Program |  |  |  |

## Construction Method and Schedule (TOR 3.3.7)

In accordance with the requirements stipulated in TOR 3.3.7, the Consultant carried out the preparation of the construction method and schedule and submitted as “Method Statement” for each package.

After receiving the AC comments and Approval Decision, each report were finalized, time to time, as shown in Table 6.27.

Table 6.27   Submitted Method Statement by Package

| No. | PKG | Category | Report Title | Rev | Submission Date | Approval Date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | Method Statement | Method Statement | 1 | 25/10/2013 |  |
| 2 | 2 |  |  | 1 | 21/10/2013 |  |
| 3 | 3A |  |  | 2 | 11/3/2013 |  |
| 4 | 3B |  |  | 2 | 12/9/2013 |  |
| 5 | 4 |  |  | 1 | 8/2/2014 |  |
| 6 | 5 |  |  | 1 | 2/11/2013 |  |
| 7 | 6 |  |  | 3 | 14/11/2013 |  |
| 8 | 7 |  |  | 1 | 7/11/2013 |  |
| 9 | A1 |  |  | 0 | 29/10/2013 |  |
| 10 | A2 |  |  | 0 | 3/9/2013 |  |
| 11 | A3 |  |  | 0 | 9/1/2014 |  |
| 12 | A4 |  |  | 2 | 11/5/2013 |  |
| 13 | A5 |  |  | 0 | 18/4/2013 |  |

## Cost Estimate (TOR 3.3.8)

In accordance with the requirements stipulated in TOR 3.3.8, the Consultant carried out the preparation of the cost estimate reports for each package.

After receiving the AC comments and Approval Decision, each report were finalized, time to time, as shown in Table 6.28.

Table 6.28   Submitted Cost Estimate Report by Package

| No. | PKG | Category | Report Title | Rev | Submission Date | Approval Date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | Cost Estimate | Cost Estimate Report | 1 | 25/10/2013 | 28/10/2013 |
| 2 | 2 |  |  | 2 | 29/10/2013 | 30/10/2013 |
| 3 | 3A |  |  | 4 | 28/2/2013 | 01/03/2013 |
| 4 | 3B |  |  | 3 | 27/9/2013 | 13/09/2013 |
| 5 | 4 |  |  | 1 | 24/1/2014 | 13/02/2014 |
| 6 | 5 |  |  | 1 | 8/11/2013 | 18/11/2013 |
| 7 | 6 |  |  | 3 | 14/11/2013 | 28/11/2013 |
| 8 | 7 |  |  | 1 | 7/11/2013 | 25/11/2013 |
| 9 | A1 |  |  | 1 | 24/1/2014 | 13/03/2014 |
| 10 | A2 |  |  | 1 | 20/1/2014 | 13/03/2014 |
| 11 | A3 |  |  | 0 | 2/1/2014 | 13/03/2014 |
| 12 | A4 |  |  | 4 | 27/8/2013 | 30/08/2013 |
| 13 | A5 |  |  | 0 | 15/4/2013 | 07/05/2014 |
| 14 | 13A |  |  |  |  |  |
| 15 | 13B |  |  |  |  |  |
| 16 | 13C |  |  |  |  |  |
| 17 | 14A |  |  | 2 | 07/07/2014 |  |
| 18 | 14B |  |  | 3 | 07/07/2014 |  |

## Pre-qualification, Bidding and Contract Documents (TOR 3.3.9)

### Pre-qualification (PQ) Documents

In accordance with the requirements stipulated in TOR 3.3.9, the Consultant carried out the preparation of the Pre-qualification (PQ) Documents for each package.

After receiving the AC/VEC comments, each report were finalized, time to time, as shown in Table 6.29.

Table 6.29   Pre-qualification (PQ) Documents by Package

| No. | PKG | Category | Report Title | Rev | Submission Date | Approval Date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | PQ Documents | PQ Documents | 3 | 5/11/2012 |  |
| 2 | 2 |  |  | 3 | 5/11/2012 |  |
| 3 | 3A |  |  | 2 | 12/02/2012 |  |
| 4 | 3B |  |  | 3 | 5/11/2012 |  |
| 5 | 4 |  |  | 3 | 12/11/2012 |  |
| 6 | 5 |  |  | 3 | 12/11/2012 |  |
| 7 | 6 |  |  | 3 | 12/11/2012 |  |
| 8 | 7 |  |  | 3 | 12/11/2012 |  |
| 9 | A1 |  |  | 4 | 05/07/2012 |  |
| 10 | A2 |  |  | 4 | 05/07/2012 |  |
| 11 | A3 |  |  | 3 | 05/07/2012 |  |
| 12 | A4 |  |  | 1 | 17/01/2012 |  |
| 13 | A5 |  |  | 3 | 05/07/2012 |  |
| 14 | 13A |  |  | 1 | 06/06/2014 |  |
| 15 | 13B |  |  |  | N/A |  |
| 16 | 13C |  |  | 1 | 16/06/2014 |  |
| 17 | 14A |  |  | 2 | 19/11/2013 |  |
| 18 | 14B |  |  |  | N/A |  |

### Bidding and Documents

In accordance with the requirements stipulated in TOR 3.3.9, the Consultant carried out the preparation of the Pre-qualification (PQ) Documents for each package.

After receiving the AC/VEC comments, each report were finalized, time to time, as shown in Table 6.30.

Table 6.30   Bidding Documents by Package

| No. | PKG | Category | Report Title | Rev | Submission Date | Approval Date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | Bidding Documents | Parts 1&3 | 0 | 12/04/2013 | 06/09/2013 |
| 2 |  |  | V2.1 Technical Specifications | 0 | 5/9/2013 |  |
| 3 |  |  | V2.3 BOQ | 0 | 5/9/2013 |  |
| 4 | 2 |  | Parts 1&3 | 0 | 12/04/2013 | 28/08/2013 |
| 5 |  |  | V2.1 Technical Specifications | 0 | 26/08/2013 |  |
| 6 |  |  | V2.3 BOQ | 0 | 26/08/2013 |  |
| 7 | 3A |  | Parts 1&3 | 0 | 22/03/2012 | 08/01/2013 |
| 8 |  |  | V2.1 Technical Specifications | 3 | 09/01/2013 |  |
| 9 |  |  | V2.3 BOQ | 3 | 09/01/2013 |  |
| 10 | 3B |  | Parts 1&3 | 0 | 12/04/2013 | 25/07/2013 |
| 11 |  |  | V2.1 Technical Specifications | 1 | 12/07/2013 |  |
| 12 |  |  | V2.3 BOQ | 1 | 12/07/2013 |  |
| 13 | 4 |  | Parts 1&3 | 0 | 31/05/2013 | 13/12/2013 |
| 14 |  |  | V2.1 Technical Specifications | 1 | 14/12/2013 |  |
| 15 |  |  | V2.3 BOQ | 1 | 14/12/2013 |  |
| 16 | 5 |  | Parts 1&3 | 0 | 31/05/2013 | 27/09/2013 |
| 17 |  |  | V2.1 Technical Specifications | 1 | 17/9/2013 |  |
| 18 |  |  | V2.3 BOQ | 1 | 17/9/2013 |  |
| 19 | 6 |  | Parts 1&3 | 0 | 22/03/2013 | 27/09/2013 |
| 20 |  |  | V2.1 Technical Specifications | 1 | 19/09/2013 |  |
| 21 |  |  | V2.3 BOQ | 0 | 19/9/2013 |  |
| 22 | 7 |  | Parts 1&3 | 0 | 31/05/2013 | 27/09/2013 |
| 23 |  |  | V2.1 Technical Specifications | 1 | 23/09/2012 |  |
| 24 |  |  | V2.3 BOQ | 1 | 17/07/2012 |  |
| 25 | A1 |  | Parts 1&3 | 0 | 26/6/2013 | N/A |
| 26 |  |  | V2.1 Technical Specifications | 0 | 09/10/2013 |  |
| 27 |  |  | V2.3 BOQ | 0 | 09/10/2013 |  |
| 28 | A2 |  | Parts 1&3 | 0 | 26/7/2013 |  |
| 29 |  |  | V2.1 Technical Specifications | 0 | 30/9/2013 |  |
| 30 |  |  | V2.3 BOQ | 0 | 30/9/2013 |  |
| 31 | A3 |  | Parts 1&3 | 0 | 26/7/2013 |  |
| 32 |  |  | V2.1 Technical Specifications | 0 | 11/10/2013 |  |
| 33 |  |  | V2.3 BOQ | 0 | 11/10/2013 |  |
| 34 | A4 |  | Parts 1&3 | 0 | 19/04/2012 | 24/06/2013 |
| 35 |  |  | V2.1 Technical Specifications | 6 | 29/07/2013 |  |
| 35 |  |  | V2.3 BOQ | 7 | 20/08/2013 |  |
| 37 | A5 |  | Parts 1&3 | 0 | 26/7/2013 | 26/03/2014 |
| 38 |  |  | V2.1 Technical Specifications | 0 | 16/01/2014 |  |
| 39 |  |  | V2.3 BOQ | 0 | 16/01/2014 |  |
| 40 | A1-A2-A3 |  | V2.1 Technical Specifications | 1 | 30/12/2013 | 31/12/2013 |
| 41 |  |  | V2.3 BOQ | 1 | 30/12/2013 |  |
| --- | 13A |  | To be prepared by CSC under JICA portion. |  |  |  |
| --- | 13B |  |  |  |  |  |
| --- | 13C |  |  |  |  |  |
| 42 | 14A-1 |  | Parts 1&3 |  |  | 12/12/2014 |
| 43 |  |  | Traffic Safety, Specifications |  |  |  |
| 44 |  |  | Traffic Safety, BOQ |  |  |  |
| 45 | 14A-2 |  | Parts 1&3 |  |  |  |
| 46 |  |  | Street Lighting, Specifications |  |  |  |
| 47 |  |  | Street Lighting, BOQ |  |  |  |
| 48 | 14B-1 |  | Parts 1&3 |  |  |  |
| 49 |  |  | Traffic Safety, Specifications |  |  |  |
| 50 |  |  | Traffic Safety, BOQ |  |  |  |
| 51 | 14B-2 |  | Parts 1&3 |  |  |  |
| 52 |  |  | Street Lighting, Specifications |  |  |  |
| 53 |  |  | Street Lighting, BOQ |  |  |  |

### Contract Documents

Preparation of the contract documents were carried out by VEC.

## Preparation of Implementation Program (TOR 3.3.10)

Implementation program has been prepared time to time in accordance with actual progress of design work, procurement work.

Updated implementation program is shown in Figure 2.1 above.

# Procurement Assistance (TOR 3.4)

Most of the procurement processes have been carried out by VEC.

Updated procurement plan is shown in Table 7.1.

The Consultant has supported whenever requested by VEC, i.e. answer to the bidders for “Request of Clarifications” during the bidding period.

Table 7.1   Updated Procurement Plan (As of May 2014)

| Ref. No | Contract Description | Estimated Cost (USD million) | Procurement method | Contract Mode | Contract Duration (month) | Date of issuance of PQ documents | Date of issuance of bidding documents/RFP | Pre-qualification/EOI required | Prior Review | Funding Sources |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Civil Works Contract Package 1 (KM000+000 - KM008+000) | 71.43 | ICB | unit price | 36 | 20/12/2012-20/02/2013 | 9/9/2013 | Yes | Yes | JICA |
| 2 | Civil Works Contract Package 2 (KM008+000 - KM016+880) | 72.69 | ICB | unit price | 36 | 20/12/2012-20/02/2013 | 30/8/2013 | Yes | Yes | JICA |
| 3 | Civil Works Contract Package 3A (KM016+880 - KM018+100) | 42.68 | ICB | unit price | 36 | 15/8/2012-10/10/2012 | 16/1/2013 | Yes | Yes | JICA |
| 4 | Civil Works Contract Package 3B (KM018+100 - KM021+500) | 38.65 | ICB | unit price | 36 | 20/12/2012-20/02/2013 | 26/7/2013 | Yes | Yes | JICA |
| 5 | Civil Works Contract Package 4 (KM021+500 - KM032+600) | 70.36 | ICB | unit price | 36 | 04/3/2013-3/5/2013 | 16/9/2013 | Yes | Yes | JICA |
| 6 | Civil Works Contract Package 5 (KM032+600 - KM042+000) | 61.28 | ICB | unit price | 36 | 04/3/2013-3/5/2013 | 30/9/2013 | Yes | Yes | JICA |
| 7 | Civil Works Contract Package 6 (KM042+000 - KM052+000) | 63.86 | ICB | unit price | 36 | 04/3/2013-3/5/2013 | 30/9/2013 | Yes | Yes | JICA |
| 8 | Civil Works Contract Package 7 (KM052+000 - KM065+000) | 84.61 | ICB | unit price | 36 | 04/3/2013-3/5/2013 | 30/9/2013 | Yes | Yes | JICA |
| 9 | Civil Works Contract Package A1 (KM065+000 - KM081+150) | 84.54 | ICB | unit price | 36 | 15/3/2013-10/5/2013 | 3/1/2014 | Yes | Yes | WB |
| 10 | Civil Works Contract Package A2 (KM081+150 - KM099+500) | 89.37 | ICB | unit price | 36 | 15/3/2013-10/5/2013 |  | Yes | Yes | WB |
| 11 | Civil Works Contract Package A3 (KM099+500 - KM110+100) | 76.14 | ICB | unit price | 36 | 15/3/2013-10/5/2013 |  | Yes | Yes | WB |
| 12 | Civil Works Contract Package A4 (KM110+100 - KM124+700) | 90.70 | ICB | unit price | 36 | 23/4/2012-18/6/2012 | 25/6/2013 | Yes | Yes | WB |
| 13 | Civil Works Contract Package A5 (KM124+700 - KM131+500; & KM131+500 - KM139+204) | 91.65 | ICB | unit price | 36 | 15/3/2013-10/5/2013 | 27/3/2014 | Yes | Yes | WB |
| 14 | Contract Package 13 (Electrical/O&M Building/ITS Works and Equipment Provision) | 60.28 | ICB | unit price (EPC) | 24 | Under supervision service |  | Yes | Yes | JICA |
| 15 | Contract Package 14A (Traffic safety/Lighting) | 14.27 | ICB | unit price | 12 | - | Under supervision service | Yes | Yes | JICA |
| 16 | Contract Package 14B (Traffic safety/Lighting) | 18.02 | ICB | unit price | 12 | Not Applicable |  | No | Yes | WB |
| Exchange rate: 1USD=19000 VND |  |  |  |  |  |  |  |  |  |  |

# Land Acquisition Staking (TOR 3.5)

In accordance with the requirements stipulated in TOR 3.5, the Consultant carried out the land acquisition staking.

Firstly, prepare and submit the “ROW Report”. After receiving approval by PMU85, the staking works have been carried out at the site as shown in Table 8.1.

Table 8.1   Right of Way and Land Acquisition Staking

| District | Item | From | To | ROW Report | Minutes of Hnading-over | Approval |
| --- | --- | --- | --- | --- | --- | --- |
| Hòa Vang | Tuy Loan IC | 00-800 | 00+900 | No. 9 | 6/11/12 |  |
|  |  |  |  | No. 14 | 21/05/13 | 226/QĐ-VEC, 20/5/2013 |
|  | TMC/PA | 03+400 | 05+934 | No. 9 | 6/11/12 |  |
|  | Re-Aligned | 00+518 | 02+601 | No. 11 | 11/1/13 | 40/QĐ-VEC, 24/01/2013 |
| Điện Bàn | My Son IC | 12+840 | 13+820 | No. 12 | 10/4/13 | 41/QĐ-VEC, 24/01/2013 |
|  | Thruway | 17+850 | 20+100 | No. 1 | 17/8/12 |  |
| Duy Xuyên | Thruway | 20+400 | 24+700 | No. 6 | 17/8/12 |  |
|  | Thruway | 24+700 | 29+465 | No. 5 | 17/8/12 |  |
|  | PA (29+130) | Chuyển sang gói 5 |  |
|  | Re-Aligned | 20+657 | 22+080 | No. 11 | 1/2/13 | 40/QĐ-VEC, 24/01/2013 |
|  | Re-Aligned | 25+210 | 30+100 | No. 11 | 1/2/13 | 40/QĐ-VEC, 24/01/2013 |
| Quế Sơn | Thruway | 29+465 | 39+650 | No. 2 | 27/9/12 |  |
|  | Re-Aligned | 30+100 | 32+600 | No. 11 | 1/2/13 | 40/QĐ-VEC, 24/01/2013 |
|  | Re-Aligned | 34+298 | 35+100 | No.15 | 7/08/13 |  |
|  | PA (36+000) | 35+501 | 36+641 | No. 15 | 7/08/13 |  |
| Thăng Bình | Thruway | 39+650 | 52+350 | No. 3 | 29/9/12 |  |
|  | Ha Lam IC | 40+300 | 41+400 | No. 12 | 10/4/13 | 41/QĐ-VEC, 24/01/2013 |
| Phú Ninh | Thruway | 52+350 | 60+140 | No. 4 | 1/10/12 |  |
|  | Tam Ky IC | 63+900 | 64+950 | No. 12 | 11/4/13 | 41/QĐ-VEC, 24/01/2013 |
|  | SA (66+460) | 66+409 | 67+785 | No. 15 | 8/8/13 |  |
| Núi Thành | Thruway | 71+100 | 99+200 | No. 8* | 1/11/12 |  |
|  |  |  |  |  | 28/11/12 | Stakes were restored |
|  | Chu Lai IC | 82+430 | 83+500 | No. 12 | 11/4/13 | 41/QĐ-VEC, 24/01/2013 |
|  | PA (96+300) | 95+810 | 96+800 | No. 16 | 17/12/13 | 477/QĐ-VEC, 27/9/2013 |
| Bình Sơn | Thruway | 99+200 | 109+300 | No. 7 | 5/10/12 |  |
|  |  |  |  |  | 28/11/12 | Stakes were restored |
|  | Dung Quat IC | 101+190 | 102+240 | No. 12 | 12/4/13 | 41/QĐ-VEC, 24/01/2013 |
|  | Revised (Frontage Rd) | 110+100 | 111+600 | No. 13 | 24/7/13 | 166/QĐ-VEC, 18/4/2013 |
| Sơn Tịnh | Revised (Frontage Rd) | 111+600 | 124+700 | No. 13 | 24/7/13 |  |
|  | Dung Quat 2 IC | 116+685 | 117+485 | No. 15 | 24/7/13 |  |
|  | PA | 120+300 | 121+700 | No. 10 |  | Suspended |
|  | Quang Ngai North IC | 123+000 | 124+450 | No. 13 | 23/7/13 | 166/QĐ-VEC, 18/4/2013 |
|  | GPMB bổ sung | 123+989 | 124+072 | No. 18 | 10/2013 | 543/QĐ-VEC, 14/10/2013 |
| Tư Nghĩa | TB (129+500) | 129+321 | 131+550 | No. 15 | 24/7/13 |  |
|  | Additional Land | 127+878 | 129+078 | No.15 | 23/7/13 |  |
|  | Additional Land | 134+646 | 135+326 | No.15 | 23/7/13 |  |
|  | NH1 Intersection | 138+891 | 139+204 | No.15 | 24/7/13 |  |
| TP Quảng Ngãi | Quang Ngai IC | 130+050 | 130+870 | No.15 | 24/7/13 |  |
| Whole Section |  |  |  | No. 17 | 19/12/13 | 477/QĐ-VEC, 27/9/2013 |

Table 8.2   Acceptance Minutes of Land Acquisition Staking

| No. | Description | Sign- date |
| --- | --- | --- |
| 1 | Land acquisition & ROW staking works | 01 June 2014 |

# Technology Transfer (TOR 3.6)

Technology transfer had been carried out by i) on the job training (OJT) and ii) off the job training (OffJT).

OJT type technology transfer had been carried out through day-to-day discussion on both technical and project management.

OffJT type technology transfer was carried out the following technical seminar. The Consultant proposed to hold a technical proposal with the program shown in Table 9.2 by his letter No. DQEDD-PMU85-294-13 dated 21/5/2013, however unfortunately, it did not realized by some reason.

Table 9.1   Technology Transfer Work Shop

| Workshop No. | Workshop Title | Date | Venue | Attendance | Trainee no. | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | ITS/O&M Workshop | 16/10/2012 | VEC Hanoi | MOT, VEC, PMU85 | 15 |  |

Table 9.2   Proposed Training Program (June 2013)

| No. | Title | Presenter | Position |
| --- | --- | --- | --- |
| 1 | Highway Design utilizing Google Earth | Dr Naresh Sthapit | Highway Engineer 2 |
| 2 | ITS Plan and Design | Mr Koichi Nishimura | ITS Specialist |
| 3 | Preparation of SURAP Report | Dr Vu Ngoc Long | Resettlement Specialist |
| 4 | Preparation of Bidding Documents | Mr William John Davy | Sr Procurement/Contract Specialist |
| 5 | Project Management of D/D Project | Mr Ichizuru Ishimoto | Project Manager |

# Part C: List of Submitted Documents

# List of Submitted Documents

List of submitted documents is summarized in Table 10.1.

Table 10.1   List of Submitted Documents

| No. | Title of Report |  | Required quantity in the contract (set) |  | Submitted quantity (set) | Cover Letter (Date) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Inception Report |  | 15 |  | 15 | 27/12/2011 |
| 2 | Review Study reports and design framework |  | 15 |  | 14 | 27/02/2012 |
| 3 | Monthly Reports |  | 15 |  | 8 set- English 8 set-Vietnamese | Every month |
| 4 | EIA Report |  | 15 |  | 15 | 22/07/2013 |
| 5 | EMP Report |  | 15 |  | 15 | 22/07/2013 |
| 6 | Brief report on the appropriateness of proposed alignment (Study report – Finalization of Expressway Alignment) |  | Not specific mentioned |  | 3 sets | 19/05/2012 |
| 7 | Updated Sub-RAP |  | 15 |  | 0 |  |
| Survey report |  |  |  |  |  |  |
| 8 | Topographic Survey: |  | Not specific mentioned |  |  |  |
|  | Package No. 1 |  | 14 |  | 14 | 16/5/2013 |
|  | Package No. 2 |  | 14 |  | 14 | 10/5/2013 |
|  | Package No. 3A |  | 15 |  | 15 | 9/10/2012 |
|  | Package No. 3B |  | 14 |  | 14 | 2/4/2013 |
|  | Package No. 4 |  | 14 |  | 14 | 5/6/2013 |
|  | Package No. 5 |  | 14 |  | 14 | 13/5/2013 |
|  | Package No. 6 |  | 14 |  | 14 | 5/2/3013 |
|  | Package No. 7 |  | 14 |  | 14 | 15/3/2013 |
|  | Package No. A1 |  | 14 |  | 14 | 6/5/2013 |
|  | Package No. A2 |  | 14 |  | 14 | 8/3/2013 |
|  | Package No. A3 |  | 14 |  | 14 | 24/4/2013 |
|  | Package No. A4 |  | 14 |  | 14 | 31/5/2013 |
|  | Package No. A5 |  | 14 |  | 14 | 21/5/2013 |
| 9 | Survey hydrological data |  | Not specific mentioned |  | 14 | 22/08/2013 |
| 10 | Engineering geological survey |  | Not specific mentioned |  |  |  |
|  | Geotechnical Investigation of PKG1 |  | 14 |  | 14 | 10/5/2013 |
|  | Geotechnical Investigation of PKG1 (Tuy Loan IC) |  | 14 |  | 14 | 27/6/2013 |
|  | Geotechnical Investigation of PKG1 (Realignment section) |  | 14 |  | 14 | 8/8/2013 |
|  | Geotechnical Investigation of PKG1 (LRB02) |  | 14 |  | 14 | 04/06/2013 |
|  | Geotechnical Investigation of PKG2 (Embankment) |  | 14 |  | 14 | 29/1/2013 |
|  | Geotechnical Investigation of PKG2 (Bridge) |  | 14 |  | 14 | 1/7/2013 |
|  | Geotechnical Investigation of PKG2 (My Son IC) |  | 14 |  | 14 | 11/5/2013 |
|  | Geotechnical Investigation of PKG2 (Geologic Profile) |  | 14 |  | 14 | 5/7/2013 |
|  | Geotechnical Investigation of PKG3A (Ky Lam Bridge) |  | 14 |  | 14 | 17/10/2012 |
|  | Geotechnical Investigation of PKG3B |  | 14 |  | 14 | 22/6/2013 |
|  | Geotechnical Investigation of PKG3B (Chiem Son Bridge) |  | 14 |  | 14 | 4/4/2013 |
|  | Geotechnical Investigation of PKG4-1 |  | 14 |  | 14 | 7/8/2013 |
|  | Geotechnical Investigation of PKG4-2 |  | 14 |  | 14 | 7/8/2013 |
|  | Geotechnical Investigation of PKG 4- Tunnel Section |  | 14 |  | 14 | 15/4/2013 |
|  | Geotechnical Investigation of PKG5 |  | 14 |  | 14 | 11/4/2013 |
|  | Geotechnical Investigation of PKG5 (Ha Lam IC) |  | 14 |  | 14 | 25/5/2013 |
|  | Geotechnical Investigation of PKG6 |  | 14 |  | 14 | 5/2/2013 |
|  | Geotechnical Investigation of PKG6 (ORB-13) |  | 14 |  | 14 | 24/6/2013 |
|  | Geotechnical Investigation of PKG7 |  | 14 |  | 14 | 22/3/2013 |
|  | Geotechnical Investigation of PKG7 (Tam Ky IC) |  | 14 |  | 14 | 25/5/2013 |
|  | Geotechnical Investigation of PKGA1 |  | 14 |  | 14 | 5/7/2013 |
|  | Geotechnical Investigation of PKGA1 (FO06a, ORB17a) |  | 14 |  | 14 | 5/7/2013 |
|  | Geotechnical Investigation of PKGA2-1 |  | 14 |  | 14 | 9/4/2013 |
|  | Geotechnical Investigation of PKGA2-1 (CB23, OP19) |  | 14 |  | 14 | 24/6/2013 |
|  | Geotechnical Investigation of PKGA2-1 (Chu Lai IC) |  | 14 |  | 14 | 25/5/2013 |
|  | Geotechnical Investigation of PKGA2-2 |  | 14 |  | 14 | 2/4/2013 |
|  | Geotechnical Investigation of PKGA2-2 (CB25) |  | 14 |  | 14 | 24/6/2013 |
|  | Geotechnical Investigation of PKGA3 |  | 14 |  | 14 | 5/7/2013 |
|  | Geotechnical Investigation of PKGA3 (Dung Quat IC) |  | 14 |  | 14 | 25/5/2013 |
|  | Geotechnical Investigation of PKGA3 (Tra Bong Bridge) |  | 14 |  | 14 | 4/4/2013 |
|  | Geotechnical Investigation of PKGA4 |  | 14 |  | 14 | 9/4/2013 |
|  | Geotechnical Investigation of PKGA4 (Box culvert) |  | 14 |  | 14 | 24/6/2013 |
|  | Geotechnical Investigation of PKGA4 (Quang Ngai North IC) |  | 14 |  | 14 | 25/6/2013 |
|  | Geotechnical Investigation of PKGA5 |  | 14 |  | 14 | 19/6/2013 |
|  | Geotechnical Investigation of PKGA5 (Box culvert) |  | 14 |  | 14 | 24/6/2013 |
|  | Geotechnical Investigation of PKGA5 (Tra Khuc Bridge) |  | 14 |  | 14 | 4/4/2013 |
|  | Geotechnical Investigation of PKG13 (O&M Building) |  | 14 |  | 14 | 13/6/2013 |
| 11 | Material Source Survey |  | Not specific mentioned |  | 1 set/1 package | 09/8/2013 |
| 12 | Relevant structures survey |  | Not specific mentioned |  | 14 |  |
|  | Topographic Survey of Populous Residential Areas |  |  |  | 14 | 4/5/2013 |
|  | Topographic Survey of Temporary Access Road |  |  |  | 14 | 9/5/2013 |
|  | Topographic Survey of Public Utility |  |  |  | 14 | 17/5/2013 |
|  | High Voltage Lines (HVL) |  |  |  | 14 | 24/10/2012 |
|  | Medium and Low Voltage Lines (MVL-LVL) |  |  |  | 14 | 20/6/2012 |
| 13 | Additional Traffic Surveys |  | Not specific mentioned |  | 03 | 09/01/2013 |
| 14 | Detailed Design, reports |  | 3 set (draft) for each submission |  |  |  |
|  | Package No. 1 |  | 14 |  | 14 | 03/09/2013 |
|  | Package No. 2 |  | 14 |  | 14 | 30/08/2013 |
|  | Package No. 3A |  | 14 |  | 14 | 28/12/2012 |
|  | Package No. 3B |  | 14 |  | 14 | 16/08/2013 |
|  | Package No. 4 |  | 14 |  | 14 | 20/11/2013 |
|  | Package No. 5 |  | 14 |  | 14 | 08/07/2013 |
|  | Package No. 6 |  | 14 |  | 14 | 15/07/2013 |
|  | Package No. 7 |  | 14 |  | 14 | 30/07/2013 |
|  | Package No. A1 |  | 14 |  | 14 | 11/09/2013 |
|  | Package No. A2 |  | 14 |  | 14 | 30/07/2013 |
|  | Package No. A3 |  | 14 |  | 14 | 23/09/2013 |
|  | Package No. A4 |  | 14 |  | 14 | 04/06/2013 |
|  | Package No. A5 |  | 14 |  | 14 | 02/10/2013 |
|  | Package No. 13 |  | 14 |  | 14 | ??? |
|  | Package No. 14A |  | 14 |  | 14 | 12/05/2014 |
|  | Package No. 14B |  | 14 |  | 14 | 12/05/2014 |
| 15 | Cost Estimate Report |  | Not specific mentioned |  |  |  |
|  | Package No. 1 |  |  |  | 03 | 25/10/2013 |
|  | Package No. 2 |  |  |  | 03 | 29/10/2013 |
|  | Package No. 3A |  |  |  | 03 | 28/2/2013 |
|  | Package No. 3B |  |  |  | 03 | 27/9/2013 |
|  | Package No. 4 |  |  |  | 03 | 24/1/2014 |
|  | Package No. 5 |  |  |  | 03 | 8/11/2013 |
|  | Package No. 6 |  |  |  | 03 | 14/11/2013 |
|  | Package No. 7 |  |  |  | 03 | 7/11/2013 |
|  | Package No. A1 |  |  |  | 03 | 24/1/2014 |
|  | Package No. A2 |  |  |  | 03 | 20/1/2014 |
|  | Package No. A3 |  |  |  | 03 | 2/1/2014 |
|  | Package No. A4 |  |  |  | 03 | 27/8/2013 |
|  | Package No. A5 |  |  |  | 03 | 15/4/2013 |
|  | Package No. 13 |  |  |  | 03 | included in B/D report |
|  | Package No. 14A |  |  |  | 04 | 07/07/2014 |
|  | Package No. 14B |  |  |  | 04 | 07/07/2014 |
| 16 | PQ Documents |  | 3 set (draft) for each submission |  |  |  |
|  | Package No. 1 |  | 10 |  | 10 | 5/11/2012 |
|  | Package No. 2 |  | 10 |  | 10 | 5/11/2012 |
|  | Package No. 3A |  | 10 |  | 10 | 12/02/2012 |
|  | Package No. 3B |  | 10 |  | 10 | 5/11/2012 |
|  | Package No. 4 |  | 10 |  | 10 | 12/11/2012 |
|  | Package No. 5 |  | 10 |  | 10 | 12/11/2012 |
|  | Package No. 6 |  | 10 |  | 10 | 12/11/2012 |
|  | Package No. 7 |  | 10 |  | 10 | 12/11/2012 |
|  | Package No. A1 |  | 10 |  | 10 | 05/07/2012 |
|  | Package No. A2 |  | 10 |  | 10 | 05/07/2012 |
|  | Package No. A3 |  | 10 |  | 10 | 05/07/2012 |
|  | Package No. A4 |  | 10 |  | 10 | 17/01/2012 |
|  | Package No. A5 |  | 10 |  | 10 | 05/07/2012 |
|  | Package No. 13A |  | 10 |  | 10 | 06/06/2014 |
|  | Package No. 13B |  | 10 |  | 10 | N/A |
|  | Package No. 13C |  | 10 |  | 10 | 16/06/2014 |
|  | Package No. 14A |  | 10 |  | 10 | 19/11/2013 |
|  | Package No. 14B |  | 10 |  | 10 | N/A |
| 17 | Bidding Documents |  | 3 set (draft) for each submission |  |  |  |
|  | Package No. 1 |  | 14 |  | 14 | 5/09/2013 |
|  | Package No. 2 |  | 14 |  | 14 | 26/08/2013 |
|  | Package No. 3A |  | 14 |  | 14 | 09/01/2013 |
|  | Package No. 3B |  | 14 |  | 14 | 12/07/2013 |
|  | Package No. 4 |  | 14 |  | 14 | 14/12/2013 |
|  | Package No. 5 |  | 14 |  | 14 | 17/09/2013 |
|  | Package No. 6 |  | 14 |  | 14 | 19/09/2013 |
|  | Package No. 7 |  | 14 |  | 14 | 23/09/2013 |
|  | Package No. A1 |  | 14 |  | 14 | 09/10/2013 |
|  | Package No. A2 |  | 14 |  | 14 | 30/09/2013 |
|  | Package No. A3 |  | 14 |  | 14 | 11/10/2013 |
|  | Package No. A4 |  | 14 |  | 14 | 29/07/2013 |
|  | Package No. A5 |  | 14 |  | 14 | 16/01/2014 |
|  | Package No. A1-A2-A3 |  | 14 |  | 14 | 30/12/2013 |
|  | Package No. 13 A |  | 14 |  | 14 | prepared by the C.SC |
|  | Package No. 13 B |  | 14 |  | 14 |  |
|  | Package No. 13 C |  | 14 |  | 14 |  |
|  | Package No. 14A |  | 14 |  | 14 | 19/08/2014 |
|  | Package No. 14B |  | 14 |  | 14 | 04/09/2014 |
| 18 | Safety Audit Report |  | 15 |  | 15 | 27/11/2013 |
| Independent Land Valuation Survey |  |  |  |  |  |  |
| 19 | Inception Report | 6 |  | 6 |  | 15/06/2012 |
| 20 | Replacement Cost Survey | 6 |  | 6 |  |  |
|  | Hoa Vang |  |  |  |  | 12/01/2013 |
|  | Dien Ban |  |  |  |  | 25/09/2012 |
|  | Duy Xuyen |  |  |  |  | 15/01/2013 |
|  | Que Son |  |  |  |  | 14/01/2013 |
|  | Thang Binh |  |  |  |  | 19/03/2013 |
|  | Phu Ninh |  |  |  |  | 29/03/2013 |
|  | Tam Ky |  |  |  |  | 25/09/2012 |
|  | Nui Thanh |  |  |  |  | 21/01/2013 |
|  | Tu Nghia |  |  |  |  | 03/01/2013 |
|  | Nghia Hanh |  |  |  |  | 03/01/2013 |
|  | Binh Son |  |  |  |  | 07/06/2012 |
|  | Son Tinh |  |  |  |  | 07/06/2012 |
| 21 | ROW No. | Not specific mentioned |  |  |  |  |
|  | Report No. 1 |  |  | 3 |  | 15/05/2012 |
|  | Report No. 2 |  |  | 3 |  | 15/05/2012 |
|  | Report No. 3 |  |  | 3 |  | 15/05/2012 |
|  | Report No. 4 |  |  | 4 |  | 15/05/2012 |
|  | Report No. 5 |  |  | 3 |  | 15/05/2012 |
|  | Report No. 6 |  |  | 2 |  | 05/06/2012 |
|  | Report No. 7 |  |  | 3 |  | 15/06/2012 |
|  | ROW for Km17+900 – Km109+300 |  |  | 12 |  | 05/07/2012 |
|  | Report No. 9 and No. 10 |  |  | 3 |  | 03/10/2012 |
|  | Report No. 11 |  |  | 3 |  | 20/12/2012 |
|  | Report No. 12 |  |  | 3 |  | 08/01/2013 |
|  | Report No. 13 |  |  | 3 |  | 03/04/2013 |
|  | Report No. 14 |  |  | 3 |  | 10/05/2013 |
|  | Report No. 15 |  |  | 3 |  | 29/05/2013 |
|  | Report No. 16 |  |  | 3 |  | 13/08/2013 |
|  | Report No. 17 |  |  | 3 |  | 01/10/2013 |
|  | Report No. 18 |  |  | 3 |  | 8/10/2013 |

http://www.cpcs.ca/en/