Meeting Memo

| Date | 18th June, 2015 |
| --- | --- |
| Time | 10:00-11:00 |
| Venue | NK Hanoi Office |
| Participants | Mr. Ha (Vice Director, BRITEC), Mr. Thuy (Chief of Planning and Tendering Dept.) |
|  | Maeda (NK-KR), Ms Bang (NKV), Ms Lan (NKV) |
| Items Discussed | See below |

Items Discussed

1. Draft Overall Work Schedule NK and BRITEC confirmed the draft overall work schedule of the Consulting Services as attached. 2. Key Issues in Bridge Design NK and BRITEC confirmed the key issues and solutions in the bridge design as follows: Existing Underground Utilities NK will conduct the existing utilities survey prior to the official commencement of Consulting Service. In case of finding un-relocatable existing underground utilities in the Project area, NK and BRITEC will adjust the span length within 3 to 4 spans by reducing girder length to avoid the pier locations at un-relocatable existing underground utilities. Temporary Support at Narrow Sections In the F/S, temporary steel portal support was planned to construct cross beam of pier at Narrow Section. BRITEC suggested that construction plan in consideration of construction safety and proposed to apply the composite steel beam. NK agreed to study it in the review of F/S in the beginning of D/D stage; however, it shall be considered project budget. Steel Box Girder (Fewness Type) and Rotation Pile In the F/S, steel box girder (fewness type) and rotation piles were planned. NK and BRITEC confirmed those structures would be the 1st time in Vietnam and needed special attention in the design works. 3. Work Plan BRITEC proposed to mobilize his bridge engineers (9 positions) in his head office. NK and BRITEC agreed its work plan with the following conditions: - Mobilizing 1 to 2 bridge engineers from BRITEC to the Project Office (permanent) to work in preparation of design criteria, bridge planning, technical specifications, etc. with other design teams. - Mobilizing bridge engineers from BRITEC to the Project Office (permanent) to work in designing of steel box girder (fewness type9 and rotation piles in cooperation with the international engineers. BRITEC requested to mobilize 5 CAD Operators in his head office (NK’s Proposal: 4). This issue will be necessary further discussions. BRITEC requested NK to determine the work demarcation between NKV and BRITEC. NKV agreed to send the task responsibility matrix (TECH-5) to BRITEC by e-mail.