Meeting Memo

| Date | 18th June, 2015 |
| --- | --- |
| Time | 09:00-10:00 |
| Venue | NK Hanoi Office |
| Participants | Mr. Tu (T&C) |
|  | Maeda (NK-KR), Ms Bang (NKV), Ms Lan (NKV) |
| Items Discussed | See below |

Items Discussed

1. Control Points Survey T&C explained NK in the followings: T&C already conducted site surveys and discussion with PMUTL. T&C confirmed the conditions of existing control point in the Project area as follows: - Lost 1 Primary Control Point (GPS) (F/S Stage: Installed 3 Points by the F/S Consultant) - Lost 5 Secondary Control Points (F/S Stage: Installed 27 Points by the F/S Consultant) - Broke 7 Secondary Control Points T&C agreed to conduct the re-installation works with PMUTL free of charge. 2. Existing Utilities Survey NK and T&C confirmed the importance of existing utilities survey to avoid the re-design of bridge structure and re-boring survey in the D/D stage. 3. Survey Schedule NK and T&C agreed the survey schedule as attached. Main points of survey schedule are as follows: - NK will issue the request letter (hand-over) to PMUTL after receiving Notice to Proceed. - T&C will prepare work plan and conduct the works of re-installation of control points and existing utilities survey prior to the official commencement of the Consulting Services. - NK will complete the review of horizontal alignment within 2 weeks after the official commencement of Consulting Services. - T&C will commence the profile and cross section surveys and boring survey in parallel after completion of review of horizontal alignment by NK.