2015/9/18

借上外注付託作成依頼

作業科目	：	JA15R1003

案件名	：	ハノイ環状3号線建設事業 (Hanoi City Ring Road No. 3 Construction Project)

業務段階	：	実施設計

作業場所	：	ベトナム国ハノイ市

要員氏名	：	松原　正知（個人）

担当業務	：	I12：Construction Planner/Safety Engineer

派遣期間	：	2015/10/15-2016/01/13（3.0M/M）

勤務時間	：	元契約書の規定に準じ、44時間/週とする

(月-金：8:00-12:00、13:00-17:00)

(土：8:00-12:00)

報酬	：	800,000円/月

現地PIT	：	元契約の規定に準じ、免除

日当宿泊	：	NK社員と同じ

旅行保険	：	NK付保

航空券	：	NK支給(ビジネスクラス)

査証	：	NK手配

特記事項	：	a.航空券の種別は社内規定に準じ、ビジネスクラスとする

b.航空券の代金は元契約の単価(238,000円/往復)を上限とする。

外注付託書に添付する案件概要・業務内容：次頁以降参照

- Project Location Map

- Main Project Features

| No. | Item | Main Features |  |  |
| --- | --- | --- | --- | --- |
|  |  | Stage 1: Initial Stage (The Project) |  | Stage 2: Ultimate Stage |
| 1 | Beginning Point (BP) | KM0+130, North side of the existing Mai Dich Flyover |  |  |
| 2 | End Point (EP) | KM5+493.7, South side of the existing Thang Long Bridge |  |  |
| 3 | Road Length | 5.364km |  |  |
| 4 | Road Classification | Expressway Class A, Grade 100 |  |  |
| 5 | Design Speed | 100km/hr |  |  |
| 6 | Nos. of Lane | 4 lanes |  |  |
| 7 | Road Width | 24.0m |  |  |
| 8 | Cross Section Elements | 0.5m+2.5m+2@3.75m+0.75m+1.5m+0.75m+2@3.75m+2.5m+0.5m |  |  |
|  |  | - Carriageway : 4@3.75m= 15.0m |  |  |
|  |  | - Outer Safe Line : 2@2.50m= 5.0m |  |  |
|  |  | - Median : 1@1.50m= 1.5m |  |  |
|  |  | - Inner Safe Line : 2@0.75m= 1.5m |  |  |
|  |  | - Concrete Barrier : 2@0.50m= 1.0m |  |  |
| 9 | Interchange (IC) | 1 Interchange |  | 2 ICs (Half-diamond) |
|  |  | South Thang Long IC |  | - Hoang Quoc Viet IC |
|  |  | - IC Type: Half-diamond |  | - Co Nhue IC |
|  |  | - Rampway: 1 lane (Width: 7.0m (0.5m+2.5m+3.5m+0.5m)) |  |  |
| 10 | Viaduct | Total Length: 4.803km |  |  |
|  |  | Superstructure |  |  |
|  |  | - Typical Type: PC Super T Girder (Span Length: 30-40m) |  |  |
|  |  | - At Hoang Quoc Viet/Co Nhue Intersections: Steel Box Girder |  |  |
|  |  | (Fewness Type, Span Arrangement: 63m+78m+63m) |  |  |
|  |  | Substructure |  |  |
|  |  | - All Sections: One Column RC Pier |  |  |
|  |  | Foundation |  |  |
|  |  | - Standard Section : RC Bored Pile |  |  |
|  |  | - Narrow Section : Rotation Steel Pile |  |  |
| 11 | Pavement Structure | Ultra-thin Bonded Wearing Course, t=2cm |  |  |
|  |  | (Urban Road: Porous Course, t=4cm) |  |  |
| 12 | Auxiliary Works | Retaining wall, drainage system, lighting system, plants, ditch, noise |  |  |
|  |  | barrier and preparation works for future installation of ITS equipment. |  |  |
|  |  | Urban Road: Improvement of existing pavement after construction, |  |  |
|  |  | restoration of existing drainage system and road lighting. |  |  |
| Typical Cross Sections |  |  |  |  |
| Approach Road (At Beginning Point) |  |  | PC Super T Girder |  |
| Approach Road (At End Point) |  |  | Steel Box Girder (Fewness Type) (At Intersections) |  |

- Overall Work Schedule

- Organization Structure of Consultant Team

- Work Responsibility Matrix

- Methodology (Main Responsibility Tasks Only)

Task 4.7	Study construction plan

1)	General

The Consultant will study the construction plan by the following reasons:

Obtain agreement with relevant organizations

Estimate Project cost

Prepare Tender Documents

Refer to Bid evaluation

The Consultant will prepare comprehensive construction plan including the following main items:

Procurement Plan (Labors, materials and equipment, etc.)

Construction Method

Temporary Yards and Facilities Plan

Traffic Management Plan

Construction Safety Plan

Pollution Control Plan

Construction Sequence and Schedule

2)	Particular Issues

(a)	Construction Safety and Temporary Facilities

The Consultant will conduct bridge construction planning taking into account construction safety and temporary facilities to ensure safety for workers, traffic and local residents during construction works.

For construction safety, MOC conducted the “Project for Capacity Enhancement in Construction Quality Assurance” in JICA T/A scheme and prepared “Construction Safety Management Manual”.

The Consultant will confirm the above manual and utilize it to the preparation of construction planning and tender documents in the Services to ensure appropriate safety measures in the Project.

(b)	Provision of Practical Construction Plan

Currently, actual construction practices by contractors are much different from construction plan prepared by D/D consultants in many projects and it is important issue in Vietnam.  Therefore, it is required to provide the practical construction plan in the Services in response to this important issue.

The Consultant will provide the practical construction plan by performing the following measures:

Study current actual construction practices of similar projects in Vietnam.

Study current available construction/erection machines in Vietnam

Assign a construction planner who has abundant experience in construction works.

(c)	Construction Method: Erection Works

In order to erect the steel box girders (fewness type) over the intersections, the erection method with minimum influence on the existing traffic and local residents should be applied in the Project.

There are many options for erection method of steel box girders (fewness type).

In the F/S plan, the crane method is planned as the most common and safest method if the construction site satisfies the following conditions:

Adequate crane working space is available.

A temporary stage can be provided between piers.

In the F/S plan, the steel box girders with 50m long are planned to erect by two cranes to lift-up these girders without using temporary stage.  In case a temporary stage can be provided, the girders can be divided into two parts for a single crane to lift-up them as shown in the next page.

The Consultant will review the possible cranes and other machines and select the safe, fast and reasonable method in the Services.

Source: Japan Iron and Steel Federation

Erection Method of Steel Box Girder (Fewness Type) (Example)

(d)	Traffic Management Plan: Detour Plan

Viaducts will be constructed on the median of existing Pham Van Dong Street, where the current traffic volumes are very large.  Therefore, once viaduct construction works have commenced, central part of the existing road will be utilized as construction area.  Therefore, it is better that the detour roads will be constructed before commencement of construction works in order to provide temporary diversion roads in the Standard Sections.

However, in the Narrow Section, there is no available land for the temporary diversion roads and the stabilized shoulder parts and/or the safety parts stipulated in TCVN4054-2005 are scarified during construction.  Therefore, in addition to narrowing the construction area as planned in the F/S stage, it is recommended to reduce the lane width of carriageways for detoured traffic from 3.5m to 2.75m by regulating the speed limit from 60km/hr to 40km/hr in accordance with TCVN4054-2005 for securing the safety of traffic and pedestrians as shown below.

The Consultant will prepare the road diversion plans considering these critical conditions in order to maintain smooth traffic flow even during the construction works.

Source: F/S Report, PMUTL

Detour Road at Narrow Sections

(e)	Construction Sequence and Schedule

In order to meet planned construction schedule and ensure traffic safety and flow, the Consultant will prepare proper construction sequence and schedule as shown below.

Main Consideration Points of Construction Sequence

| Work Items | Considerations |
| --- | --- |
| Construction and Erection Method at Intersections | In order to construct at the intersections, the erection method should have the minimum influence possible on the existing traffic and surrounding residents. The Consultant will examine and propose the best erection method. Finally, the Consultant will prepare drawings for the construction sequence including diversion plan for foundation and substructure construction works. |
| Construction Plan for Bridge at General Sections | In order to keep the existing traffic flowing smoothly, a temporary diversion should be planed. The Consultant will compare several construction procedures and propose the most suitable procedure for the vehicles during construction work. |
| Relocation of Utilities | Relocation works of utilities will be carried out simultaneously with the widening of existing roads and/or excavation of structure foundations. The Consultant will determine the suitable timing for these relocation works of utilities and assist PMUTL in coordinating the relocation works to be implemented on time. |

| Construction Sequence Drawings | Construction Schedule |
| --- | --- |

Source: Da Nang - Quang Ngai Expressway Construction Project (D/D Stage), Nippon Koei Co., Ltd.

Construction Sequence Drawings and Schedule (Example)