## Tab._2-5
| Calender | [5 empty] | Calender Year |  |  |  | 2015 | [10 empty] | 2016
[7 empty] | Calender Month |  |  |  | J | A |  | S |  | O |  | N |  | D |  | J |  | F |  | M |  | A |  | M |  | J |  | J |  | A |  | S
[7 empty] | Cumulative Month |  |  |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14
| Stage | [5 empty] | Step I: Detailed Engineering Design Stage
Step II: Tender Assistance Stage
Work Schedule
| Common | [8 empty] | 14 months
|  | Task Series 1 |  |  | Project Management |  |  |  |  | 14 months
|  |  | Task 1.1 |  | Establish and control practical management system |  |  |  |  | 14 months
| Step I: Detailed Engineering Design Stage | [8 empty] | 7 months
| Step I-A: Review of Preliminary Design | [8 empty] | 1 months
|  | Task Series 2 |  |  | Review of Preliminary Design |  |  |  |  | 1 months
|  |  | Task 2.1 |  | Review preliminary design |  |  |  |  | 1 months
|  |  | Task 2.2 |  | Establish detailed engineering design framework |  |  |  |  | 1 months
| Step I-B: Execution of Detailed Investigation and Detailed Engineering Design | [8 empty] | 6 months
|  | Task Series 3 |  |  | Execution of Additional/Supplemental Detailed Investigations |  |  |  |  | 4 months
|  |  | Task 3.1 |  | Conduct topographical survey and existing road surveys |  |  |  |  | 3 months
|  |  | Task 3.2 |  | Conduct geological survey |  |  |  |  | 4 months
|  |  | Task 3.3 |  | Conduct material sources survey |  |  |  |  | 3 months
|  |  | Task 3.4 |  | Conduct existing utilities survey |  |  |  |  | 3 months
|  |  | Task 3.5 |  | Conduct drainage analysis |  |  |  |  | 3 months
|  | Task Series 4 |  |  | Execution of Detailed Engineering Design |  |  |  |  | 5 months
|  |  | Task 4.1 |  | Conduct highway design |  |  |  |  | 5 months
|  |  | Task 4.2 |  | Conduct bridge design |  |  |  |  | 5 months
|  |  | Task 4.3 |  | Conduct landscape design |  |  |  |  | 1 months
|  |  | Task 4.4 |  | Conduct traffic management system and facilities design |  |  |  |  | 4 months
|  |  | Task 4.5 |  | Review O&M plan |  |  |  |  | 1 months
|  |  | Task 4.6 |  | Conduct road safety audit |  |  |  |  | 1 months
|  |  | Task 4.7 |  | Study construction plan |  |  |  |  | 3 months
|  |  | Task 4.8 |  | Assist in reviewing and updating EMP |  |  |  |  | 4 months
|  |  | Task 4.9 |  | Assist in preparing existing utilities relocation plan |  |  |  |  | 3 months
| Step I-C: Preparation of Tender Documents and Project Cost Estimates | [8 empty] | 4 months
|  | Task Series 5 |  |  | Preparation of Tender Documents and Project Cost Estimates |  |  |  |  | 4 months
|  |  | Task 5.1 |  | Estimate project cost |  |  |  |  | 4 months
|  |  | Task 5.2 |  | Prepare tender documents |  |  |  |  | 3 months
| Step II: Tender Assistance Stage | [8 empty] | 14 months
|  | Task Series 6 |  |  | Assistance for Tendering Procedures and Awarding of the Contracts |  |  |  |  | 14 months
|  |  | Task 6.1 |  | Assist in tendering procedures |  |  |  |  | 14 months
|  |  | Task 6.2 |  | Assist in preparing standards forms to construction supervision |  |  |  |  | 2 months
| Technology Transfer | [8 empty] | 14 months
|  | Task Series 7 |  |  | Provision of Technical Training |  |  |  |  | 14 months
|  |  | Task 7.1 |  | Provide on-the-job training to local experts |  |  |  |  | 14 months
|  |  | Task 7.2 |  | Provide general training to local experts |  |  |  |  | 7 months
Submission Schedule of Reports and Documents
| Reports/ |  |  | Proposal |  | Inception Report |  | 10 copies | (EN:05,VN:05)
| Documents |  |  | TOR7.3.1(1) |  | Monthly Report |  | 140 copies | (EN:05,VN:05)*14 months
|  |  |  | Proposal |  | Project Completion Report |  | 10 copies | (EN:05,VN:05)
[6 empty] | Review Report1) |  | 10 copies | (EN:05,VN:05)
[6 empty] | Draft Updated EMP |  | 10 copies | (EN:05,VN:05)
[6 empty] | Draft Final Design Report |  | 20 copies | (EN:10,VN:10)
|  |  |  | TOR7.3.1(2) |  | Final Design Report |  | 20 copies | (EN:10,VN:10)
|  |  |  | Proposal |  | Draft Bill of Quantities and Cost Estimation |  | 20 copies | (EN:05,VN:05)*2 packages
|  |  |  | TOR7.3.1(3) |  | Bill of Quantities and Cost Estimation |  | 40 copies | (EN:10,VN:10)*2 packages
|  |  |  | Proposal |  | Draft P/Q Documents and Evaluation Criteria |  | 20 copies | (EN:05,VN:05)*2 packages
[6 empty] | P/Q Documents and Evaluation Criteria |  | 40 copies | (EN:10,VN:10)*2 packages
|  |  |  | Proposal |  | Draft Tender Documents and Evaluation Criteria |  | 20 copies | (EN:05,VN:05)*2 packages
|  |  |  | TOR7.3.1(4) |  | Tender Documents and Evaluation Criteria |  | 40 copies | (EN:10,VN:10)*2 packages
|  |  |  | Proposal |  | Draft P/Q Evaluation Report |  | 20 copies | (EN:05,VN:05)*2 packages
[6 empty] | Draft Technical Bid Evaluation Report |  | 20 copies | (EN:05,VN:05)*2 packages
[6 empty] | Draft Price Bid Evaluation Report |  | 20 copies | (EN:05,VN:05)*2 packages
[6 empty] | Draft Contract Documents |  | 20 copies | (EN:05,VN:05)*2 packages
[6 empty] | Standard Forms and Reporting Format (C/S) |  | 10 copies | (EN:05,VN:05)
| Technical |  |  | Proposal |  | D/D Framework2) |  | 6 copies | (EN:03,VN:03)
| Reports/ |  |  |  |  | Work Plan (4 Surveys) |  | 24 copies | (EN:03,VN:03)*4 surveys
| Discussion |  |  |  |  | Survey Report (4 Surveys) |  | 24 copies | (EN:03,VN:03)*4 surveys
| Papers3) |  |  |  |  | Drainage Plan |  | 6 copies | (EN:03,VN:03)
[6 empty] | Geometric Design Criteria |  | 6 copies | (EN:03,VN:03)
[6 empty] | Typical Cross Sections |  | 6 copies | (EN:03,VN:03)
[6 empty] | Alignment Design |  | 6 copies | (EN:03,VN:03)
[6 empty] | Interchange Plan |  | 6 copies | (EN:03,VN:03)
[6 empty] | Pavement Design |  | 6 copies | (EN:03,VN:03)
[6 empty] | Bridge Design Criteria |  | 6 copies | (EN:03,VN:03)
[6 empty] | Bridge Plan |  | 6 copies | (EN:03,VN:03)
[6 empty] | Landscape Design |  | 6 copies | (EN:03,VN:03)
[6 empty] | O&M Plan |  | 6 copies | (EN:03,VN:03)
[6 empty] | Road Safety Audit |  | 6 copies | (EN:03,VN:03)
[6 empty] | Draft Exisitng Utilities Relocation Plan |  | 6 copies | (EN:03,VN:03)
: Rainy Season (Summer Season, Monthly Rainfall > 200mm)
1) |  | Including Right-of-Way Acquisition Situation
2) |  | Including Updated Project Implementation Program, Contract Packaging, Work Schedule of Consulting Services and List of Applicable Technical Standards.
3) |  | List of Technical Reports/Discussion Papers will be updated with PMU Thang Long at the beginning of Consulting Services.
Step I: D/D Stage (7 months)
Step II: Tender Assistance Stage (14 months)