## List of Moblized Staff
28th July, 2015
Mobilization Status of Consultant Staff
ID | Position | Name | Original/ Replaced/ Nominated | Mobilization date | Plan to Mobilize | Approved by PMUTL | Remark | I | L | S
I1 | Team Leader | Ichizuru ISHIMOTO | Orginal | 2015-06-22 |  | 2015-06-22
I2 | Highway/Pavement Engineer | Naresh STHAPIT | Orginal | 2015-07-27 |  | 2015-07-24
I1 | Team Leader | Ichizuru ISHIMOTO | Orginal | 2015-06-22 |  | 2015-06-22 |  | 1
I2 | Highway/Pavement Engineer | Naresh STHAPIT | Orginal | 2015-07-27 |  | 2015-07-24 |  | 2
I3 | Bridge Engineer 1 (PC) | Tetsuya MAEDA | Orginal | 2015-07-06 |  | 2015-06-25 |  | 3
I4 | Bridge Engineer 2 (Steel) | Shunzo NAKAZAKI | Replaced | 2015-07-15 |  | 2015-07-14 |  | 4
I5 | Bridge FoundationEngineer (Rotation Pile) | Norio KOYANAGI | Orginal |  | 2015-10-15
I6 | Landscape Engineer | Yasuhiro OTA | Orginal |  | 2015-09-15
I7 | Utility Engineer | Koichi NISHIMURA | Orginal |  | 2015-09-15
I8 | Material Engineer | Toru Fujino | Replaced | 2015-07-15 |  | 2015-07-02 |  | 5
I9 | Road Safety Specialist | Maurice FredericBuvley | Nominated |  | 2015-09-15
I10 | Expressway Engineer/ O&M Engineer | Yuichi TSUJIMOTO | Orginal |  | 2015-09-15
I11 | Environmental Specialist | Norihiko INOUE | Orginal | 2015-07-31 |  | 2015-07-03
I12 | Safety & Construction Plan Engineer | Masatomo MATSUBARA | Orginal |  | 2015-10-15
I13 | Cost Estimator | Masanori NAKAGI | Orginal |  | 2015-10-15
I14 | Contract Specialist | Kazuo MAKINO | Orginal | 2015-07-15 |  | 2015-07-07 |  | 6
L1 | Deputy Team Leader | Do Hoang Anh | Replaced | 2015-07-15 |  | 2015-07-02 |  |  | 1
L2 | Highway/Pavement Engineer 1 | Nguyen Manh Chung | Orginal | 2015-07-20 |  | 2015-07-14 |  |  | 2
L3 | Highway/Pavement Engineer 2 | Nguyen Huu Hanh | Orginal | 2015-08-15 |  | 2015-07-14
L7 | Bridge Superstructure Engineer 4 (Steel) | Nguyen Hong Nhat | Orginal |  | 2015-10-15
L8 | Bridge Substructure Engineer 1 | Nguyen Duc Hung | Orginal |  | 2015-09-15
L9 | Bridge Substructure Engineer 2 | Dang Khac Nhien | Orginal |  | 2015-10-15
L10 | Bridge Substructure Engineer 3 | Hoang Nghia Trung | Orginal |  | 2015-10-15
L11 | Bridge Substructure Engineer 4 | Nguyen Thanh Son | Orginal |  | 2015-10-15
L12 | Bridge Foundation Engineer 1 | Nguyen Cong Tam | Orginal |  | 2015-10-15
L13 | Bridge Foundation Engineer 2 | Tran Truong Phi | Orginal |  | 2015-10-15
L14 | Electrical Engineer | Cu Thanh Ha | Orginal |  | 2015-10-15
L18 | Geological Engineer 2 | Nguyen Nam Duong | Nominated | 2015-08-15 |  | 2015-07-14
L19 | Material Engineer | Nguyen Van Lam | Orginal |  | 2015-08-15
L20 | Environmental Specialist | Nguyen Thu Ha | Orginal | 2015-08-03 |  | 2015-07-14
L21 | Environmental Specialist | Dao Thi Chung Thúy | Orginal | 2015-08-03 |  | 2015-07-14
L22 | Construction Planner/ Safety Engineer | Nguyen Trung Thành | Orginal |  | 2015-10-15
L23 | Cost Estimator 1 | Nguyen Thi Thu Huong | Orginal |  | 2015-11-15
L24 | Cost Estimator 2 | Nguyen Thi Hong Nga | Replaced | 2015-07-15 |  | 2015-07-14 |  |  | 3
L25 | Document Specialist | Tran Le Khanh | Replaced |  | 2015-09-15
L26 | Document Specialist 2 | Pham Quang Dau | Replaced | 2015-07-15 |  | 2015-07-14 |  |  | 4
S1 | Office Manager | Nguyen Thanh Lan | Nominated | 2015-07-15 |  | 2015-07-13 |  |  |  | 1
S2 | Accountant | Tran Huyen Trang | Replaced | 2015-07-22 |  | 2015-07-21 |  |  |  | 2
S3 | Translator 1 | Nguyen Cuong Xuan | Nominated | 2015-07-15 |  | 2015-07-13 |  |  |  | 3
S4 | Translator 2 | Doan Hong Giang | Nominated | 2015-08-01 |  | 2015-07-13
S5 | Translator 3 | Nguyen Thi Huong | Replaced | 2015-08-15 |  | 2015-07-21
S6 | Bilingual Secretary 1 | Nguyen Thi Kim Cuc | Nominated | 2015-07-15 |  | 2015-07-13 |  |  |  | 4
S7 | CAD Operator 1 | Bach Hung Phu | Nominated | 2015-07-15 |  | 2015-07-13 |  |  |  | 5
S8 | CAD Operator 2 | Nguyen Quang Dao | Nominated | 2015-08-15 |  | 2015-07-13
S9 | Bilingual Secretary 2 | Tran Minh Chau | Nominated | 2015-07-21 |  | 2015-07-13 |  |  |  | 6
S10 | CAD Operator 3 | Nguyen Huu Quang | Nominated | 2014-07-24 |  | 2015-07-23 |  |  |  | 7
S11 | CAD Operator 4 | Ngo Van Tu | Nominated | 2015-08-15 |  | 2015-07-23
S12 | CAD Operator 5 | Vu Quang Linh | Nominated | 2015-08-15 |  | 2015-07-23
S13 | CAD Operator 6 | Pham Tien Hai | Nominated | 2015-08-15 |  | 2015-07-23
S14 | Bilingual Secretary 3 | Bùi Thị Diệu Hiền | Nominated | 2015-07-15 |  | 2015-07-13 |  |  |  | 8
S15 | CAD Operator 7 | Nguyen Truong Khang | Nominated | 2015-07-15 |  | 2015-07-13 |  |  |  | 9
List of pending request
ID | Position | Name | Replaced/ Delayed | Request for replacement | Request for late mobilization | Tentative mobilization date
L4 | Bridge Superstructure Engineer 1 (PC) | Dinh Van Nghia | Replaced | 2015-07-20 |  | 2015-07-20
L5 | Bridge Superstructure Engineer 2 (PC) | Nguyen Van Thao | Replaced | 2015-07-24 |  | 2015-08-15
L6 | Bridge Superstructure Engineer 3 (Steel) | Dang Van Hieu | Replaced | 2015-07-20 |  | 2015-08-15
L15 | Utility Engineer | Ho Minh Tuan | Delayed |  | 2015-07-24 | 2015-08-17
L16 | Topographical Engineer | Dinh Viet Hung | Replaced | 2015-07-20 |  | 2015-07-21
L17 | Geological Engineer 1 | Mai Huy Dao | Replaced | 2015-07-20 |  | 2015-07-20