Work Schedule and Progress of Survey Works

Work Schedule of Survey Works

Progress of Survey Works

Submission of Work Plan for Survey Works

NK-NE-NKV JV (JV) has submitted Work Plans for following survey works as of 27th July 2015.

| Survey in TOR | Work Plan | Submission Date | Status |
| --- | --- | --- | --- |
| - Topographic Survey | Restoration Work for Primary Control Network Grade IV (GPS) and Secondary Control Point | 30th June 2015 | WA |
|  | Alignment Survey (profile, cross-section) /Existing Road Survey | 22nd July 2015 | WA |
| - Existing Road Survey |  |  |  |
| - Geological Survey and Construction Material Survey | Draft Work Plan For License Application to DOT | 27th July 2015 | WA |
|  | Work Plan for Geological Survey | Planned on 3rd August 2015 | UP |
|  | Work Plan for Construction Material Survey | Planned on 17th August 2015 | UP |
| - Existing Utilities Survey | Work Plan for Existing Utilities Survey | 22nd July 2015 | WA |

Note: Plan Survey and Hydrological Survey will re-use existing data.

WA: Waiting Approval

UP: Under Preparation

Topographic Survey

Topographic survey consists of followings three items:

        - Vertical and horizontal control network grade IV

        - Secondary Control Point and Vertical Control Network

        - Alignment Survey

Vertical and horizontal control network grade IV and Secondary Control Point and Vertical Control Network

Primary control network grade IV and secondary control points established in F/S stage were handed over from F/S consultant to JV on 26th June 2015 with the attendance of PMUTL. Minutes of on-site handover (No. HRR3/SW/TS/AM-01) was signed by representatives of all parties.

As mentioned in the minutes, following situation was found by survey points checking.

        - 1 of 3 GPS landmark has been lost

        - 6 of 27 Secondary control points have been lost

        - 4 Secondary points has been damaged

Based on the result above, restoration and checking for control network grade IV (GPS) and secondary control network and technical leveling control network have been carried out by sub-consultant of JV in July 2015. A joint site inspection was carried out by JV and sub-consultant on 24th July and 25th July 2015. JV has submitted survey report on 28th July 2015.

Alignment Survey (profile and cross-sectional survey)

JV submitted Work Plan for the survey to PMUTL on 22nd July 2015. The survey is expected to be started in the beginning of August 2015 after confirmation/approval of center line alignment of the Project road for technical design by PMUTL. The survey is expected to be completed in the end of August 2015.

Existing Road Survey

JV submitted Work Plan for the survey to PMUTL on 22nd July 2015. The survey is expected to be started and finished in late August 2015. A team for profile and cross-sectional survey will shift to the existing road survey.

Geological Survey and Construction Material Survey

Geological Survey

JV submitted a draft Work Plan for the survey to PMUTL on 22nd July 2015 in order to apply survey license to DOT. A complete Work Plan for the survey is planned to be submitted on 3rd August 2015 to PMUTL.

JV will mobilize equipment and start the survey on site after confirmation/approval of pier location, getting license of survey, approval for work plan, and notification of survey to local police. JV expects to start the survey in the end of August. The survey (boring investigation and lab test) is expected to be completed in 50 days from the commencement.

Construction Material Survey

JV is planned to submit Work Plan for the survey to PMUTL on 17th August 2015. The survey is expected to be complete in September 2015.

Existing Utilities Survey

PMUTL issued a supporting letter on 3rd July 2015 for data collection from relevant management agencies/companies. Sub-consultant of JV distributed 1/500 topographic map with the PMUTL letter to 16 agencies as below. Sub-consultant also got an answer of expected reply date from each agency however many agencies answered very late reply schedule. JV discussed this issue with PMUTL on 22nd July 2015 and PMUTL agreed to issue reminder of early submission.

Sub-consultant also has started an initial survey for plotting existing utilities on ground on 1/500 topographic map. The survey result by AutoCAD format is expected to be submitted to JV on 29th July 2015. Sub-consultant will start a detail survey for measurement of existing utilities after collection of data from management agencies and completion of the initial survey.

Outstanding Issues

It is strongly requested PMUTL to support work coordination with local authorities for confirmation of utility relocation works.

Is it necessary that proposed utility relocation plan should be reviewed and approved by Hanoi DOT or not?

We would like to receive smooth approval of Work Plan for each survey work.