## Sheet1
Consulting Services of Technical Design, Cost Estimate and Tender Assistance for
Hanoi City Ring Road No.3 Construction Project, Mai Dich - South Thang Long Section
JICA Loan Agreement No.VN 13-P2 dated December 24 2013
|  | Schedule of Document Team | [100 empty] | Schedule of Document Team | [98 empty] | Schedule of Document Team | [100 empty] | Schedule of Document Team
|  | 2015-07-01 | [15 empty] | Aug-2015 | [30 empty] | Sep-2015 | [29 empty] | Oct-2015 | [23 empty] | Oct-2015 | [6 empty] | Nov-2015 | [29 empty] | Dec-2015 | [30 empty] | Jan-2016 | [30 empty] | Feb-2016 | [28 empty] | Mar-2016 | [30 empty] | Apr-2016 | [29 empty] | May-2016 | [10 empty] | May-2016 | [19 empty] | Jun-2016 | [29 empty] | Jul-2016 | [30 empty] | Aug-2016
|  | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
|  | PQ Document | [31 empty] | MOT & JICA Approval | [27 empty] | Prequalification Period | [47 empty] | Detail Design and Drawings | [91 empty] | MOT & JICA Approval | [20 empty] | Bidding Period | [68 empty] | Techical Bid Evaluation | [10 empty] | Techical Bid Evaluation | [19 empty] | MOT & JICA Approval | [16 empty] | Price Bid Evaluation | [9 empty] | MOT & JICA Approval | [19 empty] | Contract Negotiation
A | Package-1 Mai Dich - Co Nhue Section
1 | Study of Requirement in this Project | bar: 2015-07-01 16 to 2015-07-01 18
2 | Study of Previous Projects | bar: 2015-07-01 16 to 2015-07-01 18
3 | Prequalification Documents | 2015-07-01 20: = = Drafting = =; 2015-07-01 27: Drafting
4 | Prequalification Criteria | bar: 2015-07-01 20 to 2015-07-01 25; 2015-07-01 27 to 2015-07-01 29
5 | Tender Document | 2015-07-01 20: = = Drafting = =; 2015-07-01 27: = = Drafting = =; Aug-2015 3: = = Drafting = =; Aug-2015 10: = = Drafting = =; Dec-2015 1: = Drafting =; Dec-2015 7: = = Drafting = =; Dec-2015 14: -PMUTL Review-; Dec-2015 21: = Finalization =
6 | General Terms and Conditions | bar: 2015-07-01 20 to 2015-07-01 25; 2015-07-01 27 to Aug-2015 1; Aug-2015 3 to Aug-2015 8; Aug-2015 10 to Aug-2015 15; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26
7 | Particular Conditions | bar: 2015-07-01 20 to 2015-07-01 25; 2015-07-01 27 to Aug-2015 1; Aug-2015 3 to Aug-2015 8; Aug-2015 10 to Aug-2015 15; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26
8 | Technical Specifications | Feb-2016 6: Tet Holiday
| 8-01 TS-Section 01 General | 2015-07-01 20: = = Drafting = =; Dec-2015 1: =Design Data=; Dec-2015 7: = = Drafting = =; Dec-2015 14: = = Drafting = =; Dec-2015 21: = = Drafting = =; Dec-2015 28: = Design Team =; Jan-2016 4: = Cost Team =; Jan-2016 11: = = Drafting = =; Jan-2016 18: -PMUTL Review-; Jan-2016 25: = Finalization =
| 8-02 TS-Section 02 Site Clearing | 2015-07-01 20: =; 2015-07-01 21: =; 2015-07-01 22: =; 2015-07-01 23: =; 2015-07-01 24: =; 2015-07-01 25: =; Dec-2015 1: = Collection =; Dec-2015 7: =; Dec-2015 8: =; Dec-2015 9: =; Dec-2015 10: =; Dec-2015 11: =; Dec-2015 12: =; Dec-2015 14: =; Dec-2015 15: =; Dec-2015 16: =; Dec-2015 17: =; Dec-2015 18: =; Dec-2015 19: =; Dec-2015 21: =; Dec-2015 22: =; Dec-2015 23: =; Dec-2015 24: =; Dec-2015 25: =; Dec-2015 26: =; Dec-2015 28: = = Review = =; Jan-2016 4: = = Review = =; Jan-2016 11: =; Jan-2016 12: =; Jan-2016 13: =; Jan-2016 14: =; Jan-2016 15: =; Jan-2016 16: =; Jan-2016 18: -; Jan-2016 19: -; Jan-2016 20: -; Jan-2016 21: -; Jan-2016 22: -; Jan-2016 23: -; Jan-2016 25: =; Jan-2016 26: =; Jan-2016 27: =; Jan-2016 28: =; Jan-2016 29: =; Jan-2016 30: =
8-03 TS-Section 03 Demolition | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-04 TS-Section 04 Road Earthwork | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-05 TS-Section 05 Structure Excavation | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-06 TS-Section 06 Drainage | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-07 TS-Section 07 Subgrade | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-08 TS-Section 08 Sub-base and Base Course | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-09 TS-Section 09 Pavements | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-10 TS-Section 10 Concrete Structures | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-11 TS-Section 11 Steel Structures | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-12 TS-Section 12 Miscellaneous | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-13 TS-Section 13 Ｅｌｅｃｔｒｉｃａｌ Road Facility | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
9 | Special Conditions
| 9-01 Environmental Management Plan | 2015-07-01 27: = = Drafting = =; Aug-2015 3: = = Drafting = =; Aug-2015 10: = = Drafting = =; Dec-2015 28: = = Drafting = =; Jan-2016 4: = = Drafting = =; Jan-2016 11: = = Drafting = =; Jan-2016 18: -PMUTL Review-; Jan-2016 25: = Finalization =
9-02 Environmental Monitoring Program | bar: 2015-07-01 27 to Aug-2015 1; Aug-2015 3 to Aug-2015 8; Aug-2015 10 to Aug-2015 15; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
9-03 Health and safety plan | bar: 2015-07-01 27 to Aug-2015 1; Aug-2015 3 to Aug-2015 8; Aug-2015 10 to Aug-2015 15; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
9-04 Special Specifications | bar: 2015-07-01 27 to Aug-2015 1; Aug-2015 3 to Aug-2015 8; Aug-2015 10 to Aug-2015 15; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
B | Package-2 Co Nhue - South Thang Long Section
1 | Study of Requirement in this Project | bar: 2015-07-01 16 to 2015-07-01 18
2 | Study of Previous Projects | bar: 2015-07-01 16 to 2015-07-01 18
3 | Prequalification Documents | 2015-07-01 20: = = Drafting = =; 2015-07-01 27: Drafting
4 | Prequalification Criteria | bar: 2015-07-01 20 to 2015-07-01 25; 2015-07-01 27 to 2015-07-01 29
5 | Tender Document | 2015-07-01 20: = = Drafting = =; 2015-07-01 27: = = Drafting = =; Aug-2015 3: = = Drafting = =; Aug-2015 10: = = Drafting = =; Dec-2015 1: = Drafting =; Dec-2015 7: = = Drafting = =; Dec-2015 14: -PMUTL Review-; Dec-2015 21: = Finalization =
6 | General Terms and Conditions | bar: 2015-07-01 20 to 2015-07-01 25; 2015-07-01 27 to Aug-2015 1; Aug-2015 3 to Aug-2015 8; Aug-2015 10 to Aug-2015 15; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26
7 | Particular Conditions | bar: 2015-07-01 20 to 2015-07-01 25; 2015-07-01 27 to Aug-2015 1; Aug-2015 3 to Aug-2015 8; Aug-2015 10 to Aug-2015 15; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26
8 | Technical Specifications
| 8-01 TS-Section 01 General | 2015-07-01 20: = = Drafting = =; Dec-2015 1: =Design Data=; Dec-2015 7: = = Drafting = =; Dec-2015 14: = = Drafting = =; Dec-2015 21: = = Drafting = =; Dec-2015 28: = Design Team =; Jan-2016 4: = Cost Team =; Jan-2016 11: = = Drafting = =; Jan-2016 18: -PMUTL Review-; Jan-2016 25: = Finalization =
| 8-02 TS-Section 02 Site Clearing | 2015-07-01 20: =; 2015-07-01 21: =; 2015-07-01 22: =; 2015-07-01 23: =; 2015-07-01 24: =; 2015-07-01 25: =; Dec-2015 1: = Collection =; Dec-2015 7: =; Dec-2015 8: =; Dec-2015 9: =; Dec-2015 10: =; Dec-2015 11: =; Dec-2015 12: =; Dec-2015 14: =; Dec-2015 15: =; Dec-2015 16: =; Dec-2015 17: =; Dec-2015 18: =; Dec-2015 19: =; Dec-2015 21: =; Dec-2015 22: =; Dec-2015 23: =; Dec-2015 24: =; Dec-2015 25: =; Dec-2015 26: =; Dec-2015 28: = = Review = =; Jan-2016 4: = = Review = =; Jan-2016 11: =; Jan-2016 12: =; Jan-2016 13: =; Jan-2016 14: =; Jan-2016 15: =; Jan-2016 16: =; Jan-2016 18: -; Jan-2016 19: -; Jan-2016 20: -; Jan-2016 21: -; Jan-2016 22: -; Jan-2016 23: -; Jan-2016 25: =; Jan-2016 26: =; Jan-2016 27: =; Jan-2016 28: =; Jan-2016 29: =; Jan-2016 30: =
8-03 TS-Section 03 Demolition | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-04 TS-Section 04 Road Earthwork | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-05 TS-Section 05 Structure Excavation | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-06 TS-Section 06 Drainage | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-07 TS-Section 07 Subgrade | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-08 TS-Section 08 Sub-base and Base Course | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-09 TS-Section 09 Pavements | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-10 TS-Section 10 Concrete Structures | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-11 TS-Section 11 Steel Structures | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-12 TS-Section 12 Miscellaneous | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
8-13 TS-Section 13 Ｅｌｅｃｔｒｉｃａｌ Road Facility | bar: 2015-07-01 20 to 2015-07-01 25; Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 19; Dec-2015 21 to Dec-2015 26; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
9 | Special Conditions
| 9-01 Environmental Management Plan | 2015-07-01 27: = = Drafting = =; Aug-2015 3: = = Drafting = =; Aug-2015 10: = = Drafting = =; Dec-2015 28: = = Drafting = =; Jan-2016 4: = = Drafting = =; Jan-2016 11: = = Drafting = =; Jan-2016 18: -PMUTL Review-; Jan-2016 25: = Finalization =
9-02 Environmental Monitoring Program | bar: 2015-07-01 27 to Aug-2015 1; Aug-2015 3 to Aug-2015 8; Aug-2015 10 to Aug-2015 15; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
9-03 Health and safety plan | bar: 2015-07-01 27 to Aug-2015 1; Aug-2015 3 to Aug-2015 8; Aug-2015 10 to Aug-2015 15; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
9-04 Special Specifications | bar: 2015-07-01 27 to Aug-2015 1; Aug-2015 3 to Aug-2015 8; Aug-2015 10 to Aug-2015 15; Dec-2015 28 to Jan-2016 2; Jan-2016 4 to Jan-2016 9; Jan-2016 11 to Jan-2016 16; Jan-2016 18 to Jan-2016 23; Jan-2016 25 to Jan-2016 30
C | Tender Assistance | bar: Dec-2015 1 to Dec-2015 5; Dec-2015 7 to Dec-2015 12; Dec-2015 14 to Dec-2015 15; May-2016 2 to May-2016 7; May-2016 9 to May-2016 14; May-2016 16 to May-2016 21; May-2016 23 to May-2016 28; May-2016 30 to Jun-2016 4; Jun-2016 6 to Jun-2016 11; Jun-2016 13 to Jun-2016 18; Jun-2016 20 to Jun-2016 25; Jun-2016 27 to Jun-2016 30
[140 empty] | PQ Evaluation | [151 empty] | Techical Bid Evaluation | [10 empty] | Techical Bid Evaluation | [19 empty] | Assistance for Presentation to MOT & JICA | [16 empty] | Price Bid Evaluation
List of Document to be submitted (tentative target dates）
1. Prequalification Document by July 31 2015
2. Prequalification Criteria by July 31 2015
3. Prequalification Evaluation Report by December 15 2015
4. Tender Documents by January 29 2016
5. Tender Evaluation Criteria by January 29 2016
6. Technical Bid Evaluation Report by May 15 2016
7. Price Bid Evaluation Report by June 15 2016
Advertizing for Prequalification
Advertizing for Prequalification
DesignTeam for Reference
Cost Team for Reference
DesignTeam for Reference
Cost Team for Reference
Environmental Team for Review
Environmental Team for Review
Cost Team for Review
Cost Team for Review
Design Team for Review
Design Team for Review
Target Submission for Tender Document including Detail Design
Target Submission for Tender Document including Detail Design
Target Submission for PQ Document
Target Submission for PQ Document
Target Submission Date for Technical Evaluation Report
Target Submission Date for Technical Evaluation Report
Target Submission Date for Price Bid Evaluation Report
Target Submission Date for PQ Evaluation Report
Target Submission Date for PQ Evaluation Report
Target Submission Date for Price Bid Evaluation Report
Issue of Bid Document
Issue of Bid Document
Opening of Technical Bid
Opening of Technical Bid
Opening of
Price Bid
Opening of
Price Bid