## 160615
28th July, 2015
Overall Work Schedule
Task |  |  |  |  | 2015 | [22 empty] | 2016
[5 empty] | June |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  | November |  |  |  | December |  | January |  |  | February |  |  | March |  |  | April |  | May |  | June |  |  | July
[5 empty] | Prior Period |  |  |  | 1st Month |  |  |  | 2nd |  |  |  | 3rd |  |  | 4th |  |  |  | 5th |  |  | 6th |  | 7th |  |  | 8th |  |  | 9th |  |  | 10th |  | 11th |  | 12th
Step I: Detailed Engineering Design Stage
Step I-A: Review of Preliminary Design
|  | Task Series 2 |  | Review of Preliminary Design
|  |  | Task 2.1 | Review preliminary design
1.Review Works
|  |  | Task 2.2 | Establish detailed engineering design framework
2.D/D
Framework
Step I-B: Execution of Detailed Investigation and Detailed Engineering Design
|  | Task Series 3 |  | Execution of Additional/Supplemental Detailed Investigations
|  |  | Task 3.1 | Conduct topographical survey and existing road surveys
3.Re-installation
(Control Points and Network)
[8 empty] | 4.Preparation |  |  |  | 5.Survey |  |  |  | 6.
[8 empty] | (incl. Work Plan) |  |  |  | (CL, X-sections) |  |  |  | Report
|  |  | Task 3.2 | Conduct geological survey
[8 empty] | 7.Preparation | [7 empty] | 8.Boring, | [6 empty] | 9.
[8 empty] | (incl. Work Plan) | [7 empty] | Laboratory test | [6 empty] | Report
|  |  | Task 3.3 | Conduct material sources survey
[14 empty] | 10.Preparation |  |  |  | 11.Survey, |  |  | 12.
[14 empty] | (incl. Work Plan) |  |  |  | Laboratory Test |  |  | Report
|  |  | Task 3.4 | Conduct existing utilities survey
[8 empty] | 13.Preparation |  |  |  | 14.Survey |  |  |  | 15.
[8 empty] | (incl. Work Plan) | [7 empty] | Report
|  |  | Task 3.5 | Conduct drainage analysis
[14 empty] | 16.Data |  |  |  | 17.Drainage |  |  | 18.Reporting
[14 empty] | Collection |  |  |  | Analysis
|  | Task Series 4 |  | Execution of Detailed Engineering Design
|  |  | Task 4.1 | Conduct highway design
[10 empty] | 19.Geometric |  |  |  | 21.Alignment | [6 empty] | 23.Road Structure Design, Drawings, Work Quantities | [8 empty] | Appraisal |  |  | Finalization
[10 empty] | Design Criteria |  |  |  | Design | [6 empty] | (Pavement, Retaining Wall, Drainage, Accessories) | [8 empty] | Works |  |  | Works
[10 empty] | 20.Typical |  |  |  | 22.Interchange Plan
Cross Sections
|  |  | Task 4.2 | Conduct bridge design
[10 empty] | 24.Bridge |  |  |  | 25.Bridge Planning, Preparation of D/D Works | [6 empty] | 26.Structural Calculation, Drawings, Work Quantities
[10 empty] | Design Criteria | [10 empty] | (PC Bridges)
27.Structural Calculation, Drawings, Work Quantities
(Steel Bridges)
|  |  | Task 4.3 | Conduct landscape design
28.Landscape
Design
|  |  | Task 4.4 | Conduct traffic management system and facilities design
[18 empty] | 29.Facility |  |  | 30.Facility Design
[18 empty] | Planning |  |  | (Conduit, Road Lightings)
|  |  | Task 4.5 | Review O&M plan
31.O&M Plan
(Review)
|  |  | Task 4.6 | Conduct road safety audit
32.Road
Safety Audit
|  |  | Task 4.7 | Study construction plan
[21 empty] | 33.Construction |  |  |  | 34.Temporary Facilities Design
Planning
|  |  | Task 4.8 | Assist in reviewing and updating EMP
35.EMP
(Update)
|  |  | Task 4.9 | Assist in preparing existing utilities relocation plan
36.Existing Utilities Relocation Plan
Step I-C: Preparation of Tender Documents and Project Cost Estimates
|  | Task Series 5 |  | Preparation of Tender Documents and Project Cost Estimates
|  |  | Task 5.1 | Estimate project cost
[21 empty] | 37.Construction Cost Estimate | [11 empty] | Appraisal |  |  | Finalization
[33 empty] | Works |  |  | Works
|  |  | Task 5.2 | Prepare tender documents
[10 empty] | 38. P/Q Documents | [10 empty] | 39.Tender Documents | [8 empty] | Appraisal, | [5 empty] | Revision
[30 empty] | Finalization Works | [5 empty] | Works
Step II: Tender Assistance Stage
|  | Task Series 6 |  | Assistance for Tendering Procedures and Awarding of the Contracts
|  |  | Task 6.1 | Assist in tendering procedures
[21 empty] | 40.P/Q Evaluation | [14 empty] | 41. Tender Eval. | [6 empty] | 42.Contract Doc.
[21 empty] | (Draft) | [14 empty] | (Draft) | [6 empty] | (Draft)
|  |  | Task 6.2 | Assist in preparing standards forms to construction supervision
43.Standards Forms
: Finalization of Pier Locations in "25: Bridge Planning" and Boring Survey in "8: Boring, Laboratory Test" will be commenced after confirmation of existence/non-existence of existing utlities in "14: Survey".to avoid re-survey and design works.
Inputs/Outputs between Linkages: TBD