|  | Ministry of Transport |  | Japan International Cooperation Agency |
| --- | --- | --- | --- |
|  | Project Management Unit Thang Long |  |  |

Loan No.	:	VN13-P2

Contract No. 127/HD-PUMTL

Consulting Services for Package 3

Technical Design, Cost Estimation and Tender Assistance

for

Hanoi City Ring Road No.3 Construction Project

Mai Dich – South Thang Long Section

Work Plan for Geological Survey

August 2015

| The Joint Venture of |  |
| --- | --- |
|  | NIPPON KOEI VIETNAM INTERNATIONAL CO., LTD. |

Table of Contents

1	GENERAL INFORMATION	1

1.1 Introduction	1

1.2 Legal basis	1

1.3 Definition	1

1.4 Location of the Work	2

1.5 Technical Features of the Project	2

2	GEOLOGICAL SURVEY PLAN	3

2.1 General requirements	3

2.2 Quality management	3

2.3 Reference Standard	3

2.4 Equipment and Tools	4

2.5 Work Procedure	5

2.5.1 Review Existing Information	5

2.5.2 Geological Survey Method	5

2.6 Work Organization	8

2.7 Key personnel	9

3	Details of Geological Survey	9

3.1 Other regulations	9

3.2 Laboratory	9

3.3 Traffic safety management	9

4	SURVEY SCHEDULE	10

5	WORK QUANTITIES	11

6	DOCUMENTATION AND SUBMISSION	11

6.1 Report preparation	11

6.2 Language	11

GENERAL INFORMATION

Introduction

The Project road is a part of HRR3 (Western Section) and is planned as viaduct on the median of existing Pham Van Dong Street (primary urban road).  The Project road starts at the north side of existing Mai Dich Flyover (KM0+130) and ends at the south side of existing Thang Long Bridge (KM5+493.7).

The Project site is located in Cau Giay and Tu Liem districts at west of urban area in Hanoi city.

Legal basis

Construction Low No.50/2014/QH13 dated June 18th 2014 instead of Construction Low No.16/2003/QH11 dated November 26th 2003;

Highway Transportation Law No.23/2008/QH12 dated November 13th 2008

Land Law No.45/2013/QH11 dated November 29th 2013

Environmental Protection Law No.55/2014/QH13 dated June 23th 2014

Degree No.12/2009/NĐ-CP dated February 12th 2009, issued by Government for management of construction and investment project. And Degree No.83/2009/NĐ-CP dated November 15th 2009 for supplementation and modification some provisions of Degree No. 12/2009/NĐ-CP;

Degree No.15/2013/NĐ-CP, dated February 6th 2013, issued by Government for quality management of construction work;

Terms of Reference (TOR) for consulting services of technical design for Hanoi Ring Road No.3 construction project, Mai Dich – South Thang Long section;

Contract for consulting services of technical design, cost estimation and tender assistance for Hanoi Ring Road No.3 construction project, Mai Dich – South Thang Long section, Contact No 1725/HD-PMUTL, dated June 19th 2015;

Work Plan of control network approved by the Client;

Data on control network grade IV (GPS) and secondary control point formulated for technical design.

Definition

Words and expressions in this work plan shall be referred to the followings:

”Client” means PMUTL,

”Consultant” means NK-NE-NKV JV

”Sub-Consultant” means Service Trading Technology and Construction Joint Stock Company (T&C)

”Project” means stage 1 of Ring Road No. 3 Construction Project, Mai Dich – South Thanh Long Section,

”Survey” or ”Work” means geological survey in the Project,

”Consulting Service” means package 3: consulting services of Technical Design, Cost Estimation and Tender Assistance for the Project.

Location of the Work

Beginning point is at the North of Mai Dich flyover (Mai Dich flyover on the Ring Road 3 overpass Xuan Thuy street).

Ending point is at approach of the Thang Long bridge in front of Ciputra residental area

Length: 5,5 km along the Project road

Project road alignment: Start from Mai Dich flyover and run along the median of Pham Van Dong street, overpass Hoang Quoc Viet intersection, continuously run straight and cross with the NH69 intersection, go to the North and cross with planned interchnage of West Lake – Ba Vi axis road (at the area of Hoa Binh park) and end at the approach of the Thang Long bridge.

Technical Features of the Project

The technical features of the project are shown in the table below:

Main Technical Features of the Project

| No. | Item | Main Features |  |
| --- | --- | --- | --- |
|  |  | Stage 1: Initial Stage (The Project) | Stage 2: Ultimate Stage |
| 1 | Beginning Point (BP) | KM0+130, North side of the existing Mai Dich Flyover |  |
| 2 | Ending Point (EP) | KM5+493.7, South side of the existing Thang Long Bridge |  |
| 3 | Road Length | 5.364km |  |
| 4 | Road Classification | Expressway Class A, Grade 100 |  |
| 5 | Design Speed | 100km/hr |  |
| 6 | Nos. of Lane | 4 lanes |  |
| 7 | Road Width | 24.0m |  |
| 8 | Cross Section Elements | 0.5m+2.5m+2@3.75m+0.75m+1.5m+0.75m+2@3.75m+2.5m+0.5m |  |
|  |  | - Carriageway : 4@3.75m= 15.0m |  |
|  |  | - Outer Safe Line : 2@2.50m= 5.0m |  |
|  |  | - Median : 1@1.50m= 1.5m |  |
|  |  | - Inner Safe Line : 2@0.75m= 1.5m |  |
|  |  | - Concrete Barrier : 2@0.50m= 1.0m |  |
| 9 | Interchange (IC) | 1 Interchange | 2 ICs (Half-diamond) |
|  |  | South Thang Long IC | - Hoang Quoc Viet IC |
|  |  | - IC Type: Half-diamond | - Co Nhue IC |
|  |  | - Rampway: 1 lane (Width: 7.0m (0.5m+0.5m+3.5m +2.0m+0.5m)) |  |
| 10 | Viaduct | Total Length: 4.803km |  |
|  |  | Superstructure |  |
|  |  | - Typical Type: PC Super T Girder (Span Length: 30-40m) |  |
|  |  | - At Hoang Quoc Viet/Co Khue Intersections: Steel Box Girder |  |
|  |  | (Fewness Type, Span Arrangement: 63m+78m+63m) |  |
|  |  | Substructure |  |
|  |  | - All Sections: One Column RC Pier |  |
|  |  | Foundation |  |
|  |  | - Standard Section : RC Bored Pile |  |
|  |  | - Narrow Section : Rotation Steel Pile |  |
| 11 | Pavement Structure | Ultra-thin Bonded Wearing Course, t=2cm (Urban Road: Porous Course, t=4cm) |  |
| 12 | Auxiliary Works | Retaining wall, drainage system, lighting system, plants, ditch, noise barrier and preparation works for future installation of ITS equipment. |  |
|  |  | Urban Road: Improvement of existing pavement after construction, restoration of existing drainage system and road lighting. |  |

GEOLOGICAL SURVEY PLAN

General requirements

To provide the correct data about the status and characteristics of the underlying soil strata and foundation for design alternative of sub-structure;

The tests shall be carried out in compliance with relevant Vietnamese standards or ASTM standard

Quality management

The management of quality of works carried out in accordance with decree issued by the Vietnamese government.

Team leader of Sub-consultant must fully examine the information on the work diary: date of delivery, the work of each person assigned, schedule completed, to enable effective inspection and control.

All survey work must proceed from the overall sequence to details, follows the survey process.

Survey data must be fully recorded, tidy and free from erasing and follow the prescribed form.

Personnel of Consultant are responsible for checking the measurements, calculated daily when the job ends.

Upon completion of documentation, team leaders and technicians must re-examine, compare the scene, additional shortcomings.

Supervisor of the Client and Consultant will have to comply with the requirements and contents of the Decree No.15/2013/CP dated 6/2/2013 of the Government, supervisor of the investor to make frequent monitoring survey job from start to finish the job.

Reference Standard

Proposal of Replacement Standards

| No. | Standards to be applied | Standards approved in Decision No1502/QD-BGTVT | Proposed Standards |
| --- | --- | --- | --- |
| 1 | Geodesy works in engineering - general requirements | TCXDVN309-2004 | TCVN 9398:2012 |
| 2 | Specification for measuring and analyzing GPS data | TCXDVN364-2006 | TCVN 9401:2012 |
| 3 | Construction soil site testing method SPT | TCXD226-1999 | TCVN 9351:2012 |
| 4 | Construction soil-physic-mechanical test | TCVN4195-4202-1995 | TCVN 4195-4202: 2012 |
| 5 | Construction soil exploiting packing transporting and maintaining samples | TCXD2683-1991 | TCVN 2683:1012 |

Proposal of Additional Standards

| No. | Standards to be applied | Additional Standards |
| --- | --- | --- |
| 6 | Determination of moisture in soils by means of a calcium carbide gas pressure moisture tester | AASHTO T217 (ASTM D2434) |
| 7 | Consolidated, undrained triaxial compression test on cohesive soils | AASHTO T29+A197 (ASTM D4767) |
| 8 | Standard test method for unconsolidated – undrained triaxial compression test on cohesive soils | ASTM D2850 |
| 9 | One-dimensional consolidation properties of soils | AASHTO T216 (ASTM D2435 or D4186) |
| 10 | Unconfined compressive strength of cohesive soil | AASHTO T208 (ASTM D2166) |
| 11 | Standards test method for unconfined compressive strength of intact rock core specimens | ASTM D2938 |
| 12 | Standard Practice for Rock Core Drilling and Sampling of Rock for Site Investigation | ASTM D 2113-2008 |
| 13 | Standard Practices for Preserving and Transporting Rock Core Samples | ASTM D 5079-2008 |
| 14 | Standard Test Method for Standard Penetration Test (SPT) and Split-Barrel Sampling of Soils | ASTM D 1586-1999 |
| 15 | Standard Test Methods for Laboratory Determination of Water (Moisture) Content of Soil and Rock by Mass | ASTM D 2216-2010 |
| 16 | Standard Practice for Correction of Unit Weight and Water Content for Soils Containing Oversize Particles | ASTM D 4718 |
| 17 | Standard Test Method for Density, Relative Density (Specific Gravity), and Absorption of Coarse Aggregate | ASTM C 127-2007 |
| 18 | Undisturbed sampling | ASTM D1587, D6519 |

Equipment and Tools

Machines and equipments using in the survey must ensure to implement technical requirements of the project. List of machine and equipment are in the following table:

| No. | Equipment Sub Contractor | Drilling machine & sampling equipment (set) | SPT testing equipments (set) | Total Stations (set) | Water sampling tools (set) |
| --- | --- | --- | --- | --- | --- |
|  | T&C | 16 | 16 | 03 | 16 |
| Total |  | 16 | 16 | 03 | 16 |

The quality of all equipment should be inspected carefully before mobilizing and/or commencing the work in order to avoid any unexpected risks.

List of Equipment, Tools and Machinery for each a bore hole

| No. | Name | Description | Unit | Quantity |
| --- | --- | --- | --- | --- |
| 1 | Drilling machine | XY100, China | set | 1 |
| 2 | Normal drilling bit | Dia. 130mm | set | 1 |
|  |  | Dia. 110mm | set | 1 |
|  |  | Dia. 91mm | set | 3 |
|  |  | Dia. 76mm | set | 2 |
| 3 | Drilling tube | Dia. 130mm, 1.0m/set | set | 1 |
|  |  | Dia. 110mm, 1.5m/set | set | 1 |
|  |  | Dia. 91mm, 2.0m/set | set | 1 |
|  |  | Dia. 76mm, 2.0m/set | set | 1 |
| 4 | Casing | Dia. 112mm | m | 3 |
| 5 | Drilling arms | Dia. 42mm | m | 30 |
| 6 | Undisturbed sampler | Dia. 91mm, 0.2~0.6m/set | set | 20 |
| 7 | Disturbed sampler | Dia. 91mm, 0.2~0.6m/set | set | 15 |
| 8 | SPT tube | ASTM D 1586 | set | 1 |
| 9 | SPT bit | ASTM D 1586 | set | 1 |
| 10 | Sampling tray |  | set | 5 |
| 11 | Bentonite |  | kg | 100 |
| 12 | Survey Instrument |  | set | 1 |
| 13 | Camera |  | set | 1 |

All captioned equipment is in good condition and calibrated (attached with calibration record)

Measurement equipment is followed specification on maintenance, transportation and usage.

Above stated quantity of equipments could be changed in case of being required or necessary.

Work Procedure

Review Existing Information

The road alignment shall be provided by (highway design team of) Consultant upon the Client’s approval;

Pier positions shall be provided by (bridge design team of) Consultant upon the Client’s approval.

Geological Survey Method

Positioning

This work will be implemented by topographical survey group using high accuracy electronic tachometer NIVO3M and GTS -235N (ToPcom – Japan) from planned survey control point. Coordinates of boreholes are taken according to VN2000 coordinate system.

Setup and trial

The machine and equipment drilling stands should be setup properly so that the axis of rotation meets the axis of borehole. After setting up the following item should be checked carefully:

- Error and accuracy of machine

- Lubrication of parts

- Movement status

- Status of wire at winch, pulley

- Damper status

- Technical status of engine

- Status of safety part

After checking and correcting all defects of equipment, run the Testing will be takes place.

Drilling, Sampling and Field Testing

Supplementary drilling

The drilling process, site recording, description of the stony soil and sampling will comply with the current procedures, norms as The process of boring engineering geology investigations TCVN 9437-2012, Highway investigation standard 22TCN-263- 2000 and Highway embankment on soft soil design survey standard 22TCN 262-2000 and other standards.

This work will be conducted by using rotary drilling method and using bentonite liquid for maintaining of borehole wall.

It only carries out for piers or abutments of bridges, which have no drilling in detail design stage.

Condition of finishing working with boreholes with large and medium bridge boreholes: the drilling must be carried out through the soft soil layer and drilling deeply into the bearing layer from 10m to 12m for clayey soil layers having SPT blow count of greater than 30 or sandy soil having SPT blow count of greater than 50 and into the bearing layer from 6m to 8m for gravel having SPT blow count of greater than50.

Sampling

During drilling, samples will be taken every 2m for an experiment sample..Disturbed samples and undisturbed samples will be taken by using thin-walled metal tube in conformity with AASHTO T207 for soft soil. After using, all samples should be maintained in such good manner as specified in Specification of Project so that its properties will not be changed.

See Appendix I for sampling and test location.

Standard Penetration Test (SPT)

SPT will be carried out at 2m for one turn interval or at each change of strata whichever is lesser to obtain shear strength and identify the soil’s properties following 20 TCVN 9351-2012 or ASTM-D1586. This test is done by the number of blows required to take a standard split spoon sample by 30cm, using a mass of 63.6 kg falling from a height of 76.3 cm terminals penetrate on 45 cm sum total penetrate into the soil. The static ground water level will be recorded carefully for each borehole.

Quantity and location for Test Drilling with SPT are shown in Appendix I.

Finishing and Backfilling the Drilling Hole

The drilling holes should be backfilled after completion to keep or limit changes on properties and status of soil below foundation.

Backfilling Method

Use clay or sandy clay soil for backfilling.

In case of backfilling, the diameter of soil should be around 1/2 or 1/3 of the diameter of hole..

Drop gradually such rolled soil into the holes. Do not drop tumultuously to avoid blocking holes.

Use the drilling rod to compact the soil in the hole.

Finally, each hole is marked by wooden stake for inspection later.

Daily report

During implementation Works, drilling results and daily site testing shall be reported to Consultant by site engineers with the following information:

1) Structure name			2) Bore exact position and code number

3) Reduced level of top of bore	4) Date and time of boring

5) Diameter of bore			6) Depth to which bore of each stratum

7) Type of plant used			8) Depth to base of each stratum

9) Description of stratum structure	10) Depth and results of in-situ tests

11) Static water level			12) Remarks

Storage and transportation of samples to the Laboratory

This work will be started along with drilling and sampling, and under VN standard 2638:2012

Taken samples will be temporarily preserved in the adequate conditions area of the field. The samples are orderly arranged in line and not overlapping, not impacted by driving forces. Those samples should be transported to the laboratory within 05 days.

The stored samples in the laboratory must be ensured on requirements of temperature and timing as well as preservation procedures.

Laboratory for sample testing

Number of samples and parameters must follow the terms of reference. 70% samples taken will be tested in laboratory of which 70% is undisturbed samples and 30% is disturbed samples.

After the geological survey is completed, , the Contractor must submit a fully detailed report, including all test results in order to be approved by in charge engineer;

All analyzed samples must comply with current VN standards and follow the list of technical standards below:

* Undisturbed samples :

| No | Test | Symbol | Unit | Standard reference code |
| --- | --- | --- | --- | --- |
| 1 | Grain size distribution | P | % | TCVN 4198:2012 |
| 2 | Moisture content | Wo | % | TCVN 4196:2012 |
| 3 | Liquid limit | Wch | % | TCVN 4197:2012 |
| 4 | Plastic limit | Wd | % | TCVN 4197:2012 |
| 5 | Plastic Index | Id | % | Value calculation |
| 6 | Liquidity index | Is |  | Value calculation |
| 7 | Wet density |  | g/cm3 | TCVN 4202:2012 |
| 8 | Dry density | c | g/cm3 | Value calculation |
| 9 | Specific Gravity |  | g/cm3 | TCVN 4198:2012 |
| 10 | Porosity | e |  | Value calculation |
| 11 | Void Ratio | n | % | Value calculation |
| 12 | Degree of saturation | G | % | Value calculation |
| 13 | Coef of. compress | a1.0-2.0 | cm2/KG | TCVN 4200:2012 |
| 14 | Cohesion | c | KG/cm2 | TCVN 4199:2012 |
| 15 | Angle of internal friction |  | degree | TCVN 4199:2012 |
| 16 | Unconfined compression test | qu |  | ASTM-D2216 |
| 17 | Total deformation module of soil | E1.0-2.0 | KG/cm2 | Value calculation |
| 18 | Conventional strength of soil | R0 | KG/cm2 | Value calculation |

* Disturbed samples:

| No | Test | Symbol | Unit | Standard reference code |
| --- | --- | --- | --- | --- |
| 1 | Percent passed sieve size | P | % | TCVN 4198:2012 |
| 2 | Specific Gravity |  | g/cm3 | TCVN 4198:2012 |
| 3 | Moisture content | W0 | % | TCVN 4196:2012 |
| 4 | Angle of repose Dry | c | degree | TCVN 8724:2012 |
| 5 | Angle of repose Saturated | w | degree | TCVN 8724:2012 |
| 6 | Void ratio of sand max | emax |  | TCVN 8721:2012 |
| 7 | Void ratio of sand min | emin |  | TCVN 8721:2012 |
| 8 | Conventional strength of soil | R0 | KG/cm2 | Value calculation |
| 9 | Total deformation module of soil | E0 | KG/cm2 | Value calculation |
| 10 | Average N value / 30cm | N30 | hammer | TCXD 226:1999 |

Work Organization

Including:

1 Project manager

16 Drill team: each with 4 workers and 1site engineer

2 Laboratory: each with 1 Head of the laboratory and 8 laboratory staff

3 surveyed reporter

Key personnel

| No. | Position | Name | Tasks | Remark |
| --- | --- | --- | --- | --- |
| A | Consultant |  |  |  |
| 1 | Team Leader | Ichizuru Ishimoto | Management and Guidance | Accountability for the Service |
| 2 | Deputy Team Leader | Do Hoang Anh | Management and Guidance |  |
| 3 | Material Engineer | Toru Fujino | In charge | Responsibility for the Team |
| 4 | Geological Engineer | Mai Huy Dao | In charge |  |
| B | Sub Consultant |  |  |  |
| 1 | Director | Tran Dung Thang | Engineering geological engineer |  |
| 2 | Leader of geological survey group | Le Tien Dung | Engineering geological engineer | Acting QC Team Leader |
| 3 | Vice leader of geological survey group | Nguyen The Anh | Engineering geological engineer |  |
| 4 | Leader of Laboratory Las910 | Hoang Trung Hieu | Engineering geological engineer |  |
| 5 | Vice leader of Laboratory Las910 | Pham Thi Thu Ha | Engineering geological engineer |  |
| 6 | Leader of Laboratory Las69 | Pham Tuan Anh | Engineering geological engineer |  |

- Full name of the personnel shall be informed in details upon actual deployment.

- Compliance with Decree No. 12/2009/ND-CP on management of works construction investment and technical requirements of the Project

- Detailed staffing plan is in Appendix IV.

Details of Geological Survey

Other regulations

All items of survey must be taken photo in order to store and attach in Document of geological survey report, as following:

A photograph of eachborehole must betakenwithitsattached information likeprojectname, boreholename, break ground date, a photo of SPT test,a photo of all takensamples and a photo of completingborehole time.

Laboratoryanalysis: take a photograph of openingsample and aphotograph ofstoredsampleafteranalysis.

Laboratory

Laboratory for sample testing is following 02 laboratories.

| - No | - Laboratory | - Number LAS | - Address |
| --- | --- | --- | --- |
| - 1 | - Geotecnical and Material Laboratory Department | - LAS-XD 910 | - 69/160, Nguyen Khanh Toan, Quan Hoa, Cau Giay, Ha Noi |
| - 2 | - Geotechnical &Inspection Testing Center | - LAS-XD 69 | - 237 Luong The Vinh, Trung Van, Tu Liem, Ha Noi |

Traffic safety management

The geological survey is conducted on the median strips, carriageway, and sidewalk of Pham Van Dong Street stretch from Mai Dich Bridge to Thang Long Bridge. Due to the survey is located on a road with crowded dense traffic, especially during rush hours. Thus, in construction solutions, ensuring safe construction workers and people in traffic is very practical and important.

Preparation prior to survey

Work area shall be fenced by the thin hard separator, about 70-90cm; due to crowded traffic, so drillers should be arranged neatly and reasonably.

The occupying area of driller is 3.5m in width, 7.5m in length, before putting the machine to survey position, it's necessary to put signboards, set up a temporary fence around the survey location. In addition to that, it is necessary to appoint staff for traffic guidance to ensure the safety for passing vehicles.

Safety management during survey

Before construction, machinery is assembled along sidewalks, set up the fence around the machine and signboards;

After sorting machinery stably, carrying out the preparation of work site:

- The sites of drill hole surface are arranged 4m x 10m

- Set up piles in order to protected corridor on both sides of the machine, positioned parallel to the roadway. Piles are designed 1.5m in length, the distance between the poles is 1.5-2m, connected with wire stakes are reflective rope. Each corridor is estimated at 10m.

- Traffic signal should be settled at the first pile and the last pile and necessary to appoint staff to guide and manage the traffic

- Set up warning signboards (alert direction warning signboard, narrow road sign board, construction site boards) at two sides of the construction area. Placement of billboards should be about 5m far from marker fence.

- After finishing the preparation work, it is necessary to appoint staff to guide and manage the traffic to transport the driller to the drilling position. Arranging machine floor neatly, not exceed the scope of construction. During executing the survey, the occupied area by the driller should be about 3-4m; after finished drilling date, put machine's leg (reduced to about 1 meter), supplies and piles neatly in order to return road for traffic participants.

Because of location of construction includes roadway and sidewalk so construction time should be arranged throughout the day and night:

- With line heart boreholes, because of high traffic density, conducted time should be at night from 8 pm (previous day) to 4 am (next day)

- With side walk boreholes, there is a little effect on the circulation of vehicles, so the conducted time should be during the day, starting from 7am to 6 pm.

On implementing the construction works, all drilling teams must obey all the regulations on labor safety in the construction and regulations during the construction on roads where being exploited. People on the construction site must be fully equipped with protective clothing, shoes, hard hat as prescribed.

After finished all the construction, original status of road should be returned.

Details of construction solutions can be seen in the drawing (Appendix III)

SURVEY SCHEDULE

See Appendix II.

WORK QUANTITIES

See Appendix I.

DOCUMENTATION AND SUBMISSION

Report preparation

Geological survey report must be prepared in accordance with TOR and the latest VN standards. Geological survey (10 English, 10 Vietnamese) report shall consist of:

Explanation of geological survey report;

Soil physical properties standards;

Borehole location plan;

Borehole log (by one form);

Geotechnical cross-sections (by one form);

Summary of laboratory soil test result;

Results of water tests (by one form);

Detail laboratory testing form(by one form);

Photos taken at the site;

Language

All letters submitted to the advisory report uses the English language. Final Report Deliverables will perform in both English and Vietnamese

Appendix I: Estimated quantity and boreholes location plan

Appendix II: Investigation Schedule

AppendixIII: Safety Plan

AppendixIV: Staffing Plan

AppendixV: Minutes

Refer to next page as attached

- Request of Inspection

- Checking record or equipment and labour at site

- Minutes of determination for co-ordinate and elevation

- Daily records construction and quality of works

- Minutes of completion for drilled borehole

- Minutes of taking water sample

- Minutes of backfilling for drilled borehole

- Minutes of sample transportation to LAB

- Minutes of changing for borehole position