## Appendix 1
Appendix-1 Progress Monitoring of Main Documents
No. |  | PKG | Volume |  | Report Title |  | Draft DD (Rev-0) |  |  |  |  | Draft D/D (Rev-1) | [5 empty] | Final DD (Rev-2)
[7 empty] | Ver. 0 | Ver. 1 | Ver. 2 | Ver. 3 | Ver. 4 | Comment | Meeting | Submission |  |  |  | Comment | Conclusion | Revision | Apprival
[14 empty] | Conclusion | Submit to AC | Checked by AC | Submit to PMUTL
I. Survey Report
|  | Common | I |  |  | Topographic Survey Report
1 |  |  |  | I.1 |  | General Report | 2015-10-20 |  |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-03-08 | 2016-03-08 | 2016-03-08
2 |  |  |  | I.2 |  | Topographic Survey Drawings | 2015-10-20 |  |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-03-08 | 2016-03-08 | 2016-03-08
3 |  |  |  | I.3 |  | Additional Topographic Survey Drawings | 2016-01-22 |  |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-03-07 | 2016-03-07 | 2016-03-08
4 |  |  | II |  |  | Existing Pavement Survey Report | 2015-09-04 |  |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-03-07 | 2016-03-07 | 2016-03-08
5 |  |  | III |  |  | Geological Survey Report | 2015-12-03 |  |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-03-07 | 2016-03-07 | 2016-03-08
6 |  |  | IV |  |  | Material Sources Survey Report | 2015-12-31 |  |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-03-07 | 2016-03-07 | 2016-03-08
7 |  |  | V |  |  | Existing Utilities Survey Report | 2015-09-30 |  |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-03-11 | 2016-03-11 | 2016-03-11
II. Technical Design Report
8 |  | Common | I |  |  | Design Report | 2016-01-22 |  |  |  |  | --- | --- | --- | 2016-03-01 | --- | 2016-03-01
|  | Package 1 | II |  |  | Design Drawings
9 |  | (Stage1) |  | II.1 |  | Highway Design Drawings | 2016-01-15 |  |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-02-25 | 2016-02-25 | 2016-02-25
10 |  |  |  | II.2 |  | Bridge Design Drawings | 2016-01-18 |  |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-02-29 | 2016-02-29 | 2016-02-29
11 |  |  |  | II.3 |  | Electric and Lighting Design Drawings | 2016-01-16 |  |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-02-29 | 2016-02-29 | 2016-02-29
12 |  |  |  | II.4 |  | Utilities Drawings | 2016-01-15 |  |  |  |  | 2016-01-26 | 2016-02-02 | 2016-02-03 | 2016-02-29 | 2016-02-29 | 2016-02-29
13 |  |  |  | II.5 |  | Construction Drawings | 2016-01-19 |  |  |  |  | 2016-01-26 | 2016-02-02 | 2016-02-03 | 2016-02-29 | 2016-02-29 | 2016-02-29
14 |  |  | III |  |  | Quantity Report | 2016-01-25 |  |  |  |  | --- | --- | --- | 2016-03-14 | --- | 2016-03-12
15 |  |  | IV |  |  | Cost Estimate Report | 2016-02-03 |  |  |  |  | --- | --- | --- | 2016-03-14 | 2016-03-14 | 2016-03-12
|  | Package 2 | II |  |  | Design Drawings
16 |  | (Stage1) |  | II.1 |  | Highway Design Drawings | 2016-01-15 |  |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-02-25 | 2016-02-25 | 2016-02-25
17 |  |  |  | II.2 |  | Bridge Design Drawings | 2016-01-18 |  |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-02-29 | 2016-02-29 | 2016-02-29
18 |  |  |  | II.3 |  | Electric and Lighting Design Drawings | 2016-01-16 |  |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-02-29 | 2016-02-29 | 2016-02-29
19 |  |  |  | II.4 |  | Utilities Drawings | 2016-01-15 |  |  |  |  | 2016-01-26 | 2016-02-02 | 2016-02-03 | 2016-02-29 | 2016-02-29 | 2016-02-29
20 |  |  |  | II.5 |  | Construction Drawings | 2016-01-19 |  |  |  |  | 2016-01-26 | 2016-02-02 | 2016-02-03 | 2016-02-29 | 2016-02-29 | 2016-02-29
21 |  |  | III |  |  | Quantity Report | 2016-01-25 |  |  |  |  | --- | --- | --- | 2016-03-14 | --- | 2016-03-12
22 |  |  | IV |  |  | Cost Estimate Report | 2016-02-03 |  |  |  |  | --- | --- | --- | 2016-03-14 | 2016-03-14 | 2016-03-12
|  | Stage2 | V |  |  | Design Drawings
23 |  |  |  | V.1 |  | Highway Design Drawings | 2016-01-25 |  |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-02-25 | 2016-02-25 | 2016-02-25
24 |  |  |  | V.2 |  | Bridge Design Drawings | 2016-01-25 |  |  |  |  | --- | --- | --- | 2016-02-29 | 2016-02-29 | 2016-02-29
25 |  |  |  | V.3 |  | Quantity Report | 2016-01-25 |  |  |  |  | --- | --- | --- | 2016-03-14 | --- | 2016-03-12
26 |  |  |  | V.4 |  | Cost Estimate Report | 2016-03-21 | [9 empty] | 2016-03-21
Appendices (Volume II: Technical Design Report)
|  | Common | I |  |  | Technical Standards
27 |  |  |  | I.1 |  | Updated List of Applicable Technical Standards | 2015-08-15 | 2015-09-25 |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | --- | --- | 2016-03-07
28 |  |  |  | I.2 |  | Specifications for Steel - Concrete Composite Slab | 2015-12-31 |  |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | --- | --- | ---
29 |  |  |  | I.3 |  | Specifications for Rotation Steel Pile | 2015-12-31 |  |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | --- | --- | ---
30 |  |  |  | I.4 |  | Specifications for Noise Barrier | 2016-03-17 |  |  |  |  | --- | --- | --- | --- | --- | 2016-03-17
31 |  |  | II |  |  | Drainage Analysis Report | 2015-11-04 | 2015-12-22 |  |  |  | 2016-01-26 | 2016-02-02 | 2016-02-03 | 2016-02-25 | 2016-02-25 | 2016-02-25
|  |  | III |  |  | Highway Design
32 |  |  |  | III.1 |  | Review of Horizontal Alignment | 2015-08-06 | 2015-08-18 |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-02-25 | 2016-02-25 | 2016-02-25
33 |  |  |  | III.2 |  | Pavement Design | 2015-08-17 | 2015-09-30 |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-02-25 | 2016-02-25 | 2016-02-25
34 |  |  |  | III.3 |  | Geometric Design Criteria | 2015-09-14 | 2015-10-06 |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-02-25 | 2016-02-25 | 2016-02-25
35 |  |  |  | III.4 |  | Preliminary Design of Additional Interchanges | 2015-09-30 | 2015-12-07 |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-02-25 | 2016-02-25 | 2016-02-25
36 |  |  |  | III.5 |  | Determination of Vertical Alignment (Expressway) | 2015-11-23 |  |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-02-25 | 2016-02-25 | 2016-02-25
|  |  | IV |  |  | Bridge and Structural Design
37 |  |  |  | IV.1 |  | Bridge Design Criteria | 2015-08-19 | 2015-12-31 |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-02-29 | 2016-02-29 | 2016-02-29
38 |  |  |  | IV.2 |  | Concrete Bridge Design Calculation Sheets
[6 empty] | Superstructure Part | 2016-01-12 |  |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-02-29 | 2016-02-29 | 2016-02-29
[6 empty] | Substructure and miscellaneous Part | 2016-01-18 |  |  |  |  | 2016-01-26 | 2016-02-02 | 2016-02-03 | 2016-02-29 | 2016-02-29 | 2016-02-29
39 |  |  |  | IV.3 |  | Steel Bridge Design Calculation Sheets | 2015-12-25 |  |  |  |  | 2016-01-25 | 2016-02-02 | 2016-02-03 | 2016-02-29 | 2016-02-29 | 2016-02-29
40 |  |  |  | IV.4 |  | Retaining Wall Design Claculation Sheets | [5 empty] | --- | --- | --- | 2016-02-29 | 2016-02-29 | 2016-02-29
41 |  |  | V |  |  | Electricity and Lighting Design Calculation Sheets | 2016-01-20 |  |  |  |  | 2016-01-26 | 2016-02-02 | 2016-02-03 | 2016-03-11 | 2016-03-11 | 2016-03-11
III. Environmental and Social Considerations
42 |  | Common | I |  |  | Draft Updated Environmental Management Plan | 2016-01-28 |  |  |  |  | --- | --- | --- | --- | --- | ---
43 |  |  | II |  |  | Updated Land Status Report | 2016-01-28 |  |  |  |  | --- | --- | --- | --- | --- | ---
IV. Traffic Management Plan
44 |  | Common | I |  |  | Operation and Maintenance Plan | 2015-11-02 |  |  |  |  | --- | --- | --- | --- | --- | ---
45 |  |  | II |  |  | Road Safety Audit Report | 2015-11-02 |  |  |  |  | 2016-01-26 | 2016-02-02 | 2016-02-03 | --- | --- | ---
V. Tender Documents
46 |  | Package 1 |  |  |  | Draft Pre-qualification Documents and Evaluation Criteria | 2015-07-28 | 2015-08-04 | 2015-08-18 | 2015-10-24 | 2015-11-16 | --- | --- | --- | --- | --- | ---
47 |  | Package 2 |  |  |  |  | 2015-07-28 | 2015-08-04 | 2015-08-18 | 2015-10-24 | 2015-11-16 | --- | --- | --- | --- | --- | ---
48 |  | Package 1 | Volume I |  |  | Draft Tender Documents and Evaluation Criteria | 2015-12-16 |  |  |  |  | --- | --- | --- | --- | --- | 2016-03-14
|  |  | Volume II |  |  |  | 2016-01-19 |  |  |  |  | --- | --- | --- | --- | --- | 2016-03-14
49 |  | Package 2 | [9 empty] | --- | --- | --- | --- | --- | 2016-03-14
[12 empty] | --- | --- | --- | --- | --- | 2016-03-14
VI. Tender Assistance
50 |  | Package 1 |  |  |  | Draft Pre-qualification Evaluation Report | (16/02/22) |  |  |  |  | --- | --- | --- | --- | --- | ---
51 |  | Package 2 |  |  |  |  | (16/02/22) |  |  |  |  | --- | --- | --- | --- | --- | ---
52 |  | Package 1 |  |  |  | Draft Technical Bid Evaluation Report | (16/05/31) |  |  |  |  | --- | --- | --- | --- | --- | ---
53 |  | Package 2 |  |  |  |  | (16/05/31) |  |  |  |  | --- | --- | --- | --- | --- | ---
54 |  | Package 1 |  |  |  | Draft Price Bid Evaluation Report | (16/06/30) |  |  |  |  | --- | --- | --- | --- | --- | ---
55 |  | Package 2 |  |  |  |  | (16/06/30) |  |  |  |  | --- | --- | --- | --- | --- | ---
56 |  | Package 1 |  |  |  | Draft Contract Documents | (16/07/29) |  |  |  |  | --- | --- | --- | --- | --- | ---
57 |  | Package 2 |  |  |  |  | (16/07/29) |  |  |  |  | --- | --- | --- | --- | --- | ---

## Appendix 2
Appendix 2: Revised Contents of No. 7 (Volume I: Design Report)
Project Location Map
Table of Contents
List of Figures
List of Tables
Abbreviation
Main Text
1 | General
| 1.1 | Main Documents submitted in the Services
| 1.2 | Objectives
| 1.3 | Report Structure
2 | Project Description
| 2.1 | Background
| 2.2 | Location
| 2.3 | Objectives
| 2.4 | Site Conditions
|  | 2.4.1 | Geological Features
|  | 2.4.2 | Existing Urban Road (Pham Van Dong Street)
|  | 2.4.3 | Main Cross Roads and Metro Lines
|  | 2.4.4 | Existing Utilities
| 2.5 | Implementation Plan
|  | 2.5.1 | Legal Basis
|  | 2.5.2 | Applicable Technical Standards
|  | 2.5.3 | Main Features and Facilities
|  | 2.5.4 | Operation and Maintenance
|  | 2.5.5 | Stage Construction Plan
|  | 2.5.6 | Contract Packaging
|  | 2.5.7 | Environmental and Social Considerations
|  | 2.5.8 | Project Implementation Structure
|  | 2.5.9 | Project Implementation Program
3 | Review of Preliminary Design
| 3.1 | Relevant Documents
|  | 3.1.1 | Documents Reviewed
|  | 3.1.2 | Correspondences
| 3.2 | Summary of Review Results
4 | Detailed Design of Highway
| 4.1 | General
| 4.2 | Geometric Design Standards
| 4.3 | Typical Cross Sections
| 4.4 | Designed Horizontal Alignment
| 4.5 | Designed Vertical Alignment
| 4.6 | Pavement Design
| 4.7 | Drainage Design
| 4.8 | Interchange Design
| 4.9 | Miscellaneous Design
| 4.10 | Items to be Considered during Construction
5 | Detailed Design of Bridge and Structures
| 5.1 | General
| 5.2 | Design Standards
| 5.3 | Typical Cross Sections
| 5.4 | Bridge Planning
| 5.5 | Superstructure Design
| 5.6 | Substructure Design
| 5.7 | Foundation Design
| 5.8 | Miscellaneous Design
| 5.9 | Items to be Considered during Construction
6 | Landscape Design
7 | Detailed Design of Electricity and Lighting
| 7.1 | General
| 7.2 | Design Standards
| 7.3 | Road Lighting and Illumination
|  | 7.3.1 | Design Principles
|  | 7.3.2 | Required Lighting Area and Illumination Object
|  | 7.3.3 | Lighting and Illumination Source
|  | 7.3.4 | Required Luminance and Illumination Levels
|  | 7.3.5 | Lighting Design
|  |  | (1) | Lighting Iluminance
|  |  |  | (a) | Expressway
[5 empty] | (i) | Main Line
[5 empty] | (ii) | Rampway
|  |  |  | (b) | Urban Road (Pham Van Dong Street)
|  |  |  | (c) | Illumination for Pier Column Parking Area
|  |  | (2) | Lighting Control
| 7.4 | Power Supply System
|  | 7.4.1 | Design Principles
|  | 7.4.2 | Power Receiving Points
|  | 7.4.3 | Estimated Power Demand
|  | 7.4.4 | Power Receiving System Configuration
|  | 7.4.5 | Transformer
|  | 7.4.6 | Emergency Power Supply Diesel Engine Generator
|  | 7.4.7 | Power Supply Type
|  | 7.4.8 | Power Cable
| 7.5 | Intelligent Transport System
| 7.6 | Items to be Considered during Construction
8 | Preliminary Design of Utilities Relocation
9 | Construction Planning
10 | Maintenance Plan
11 | Conclusion
Appendices
| Appendix 1 |  | Relevant Documents (TBD)
| Appendix 2 |  | Updated List of Applicable Technical Standards
| Appendix 3 |  | Technical Notes on Noise Barrier

## Ho so
Appendix 1: Revised List of Main Documents (Final Outputs)/ Submission Schedule of Draft Version
No. |  | PKG | Volume |  | Report Title
I. Survey Report
|  | Common | I |  |  | Topographic Survey Report
1 |  |  |  | I.1 |  | General Report
2 |  |  |  | I.2 |  | Topographic Survey Drawings
3 |  |  | II |  |  | Existing Pavement Survey Report
4 |  |  | III |  |  | Geological Survey Report
5 |  |  | IV |  |  | Material Sources Survey Report
6 |  |  | V |  |  | Existing Utilities Survey Report
| II. Technical Design Report | [5 empty] | PK1 | PK2 | Main report & Calculation (A4)
7 |  | Common | I |  |  | Design Report
|  | Package 1 | II |  |  | Design Drawings
8 |  |  |  | II.1 |  | Highway Design Drawings | 279 | 263
[6 empty] | Highway Design Drawings (OJ detailed cross section) | 97 | 98
9 |  |  |  | II.2 |  | Bridge and Structural Design Drawings
[6 empty] | Superstructure (Mr Hieu) | 120 | 92 | 110
[6 empty] | Steel bridge (Mr Nghia) | 133 | 129
Sub-structure and miscelenous (Britec)
10 |  |  |  | II.3 |  | Electric and Lighting Design Drawings | 88 | 81
11 |  |  |  | II.4 |  | Utilities Drawings | 83 | 89
12 |  |  |  | II.5 |  | Construction Drawings
13 |  |  | III |  |  | Quantity Report
14 |  |  | IV |  |  | Cost Estimate Report
|  | Package 2 | II |  |  | Design Drawings
15 |  |  |  | II.1 |  | Highway Design Drawings
16 |  |  |  | II.2 |  | Bridge and Structural Design Drawings
17 |  |  |  | II.3 |  | Electric and Lighting Design Drawings
18 |  |  |  | II.4 |  | Utilities Drawings
19 |  |  |  | II.5 |  | Construction Drawings
20 |  |  | III |  |  | Quantity Report
21 |  |  | IV |  |  | Cost Estimate Report
Appendices (Volume II: Technical Design Report)
|  | Common | I |  |  | Technical Standards
22 |  |  |  | I.1 |  | Updated List of Applicable Technical Standards
23 |  |  |  | I.2 |  | Specifications for Steel - Concrete Composite Slab
24 |  |  |  | I.3 |  | Specifications for Rotation Steel Pile
25 |  |  |  | I.4 |  | TBD (Noise Barrier, etc., if required)
26 |  |  | II |  |  | Drainage Analysis Report
|  |  | III |  |  | Highway Design
27 |  |  |  | III.1 |  | Review of Horizontal Alignment
28 |  |  |  | III.2 |  | Pavement Design
29 |  |  |  | III.3 |  | Geometric Design Criteria
30 |  |  |  | III.4 |  | Preliminary Design of Additional Interchanges
31 |  |  |  | III.5 |  | Determination of Vertical Alignment (Expressway)
|  |  | IV |  |  | Bridge and Structural Design
32 |  |  |  | IV.1 |  | Bridge Design Criteria
33 |  |  |  | IV.2 |  | Concrete Bridge Design Calculation Sheets
34 |  |  |  | IV.3 |  | Steel Bridge Design Calculation Sheets
35 |  |  |  | IV.4 |  | Retaining Wall Design Claculation Sheets
36 |  |  | V |  |  | Electricity and Lighting Design Calculation Sheets
III. Environmental and Social Considerations
37 |  | Common | I |  |  | Draft Updated Environmental Management Plan
38 |  |  | II |  |  | Updated Land Status Report
IV. Traffic Management Plan
39 |  | Common | I |  |  | Operation and Maintenance Plan
40 |  |  | II |  |  | Road Safety Audit Report
V. Tender Documents
41 |  | Package 1 |  |  |  | Draft Pre-qualification Documents and Evaluation Criteria
42 |  | Package 2
43 |  | Package 1 |  |  |  | Draft Tender Documents and Evaluation Criteria
44 |  | Package 2 |  |  |  | Draft Tender Documents and Evaluation Criteria
VI. Tender Assistance
45 |  | Package 1 |  |  |  | Draft Pre-qualification Evaluation Report
46 |  | Package 2
47 |  | Package 1 |  |  |  | Draft Technical Bid Evaluation Report
48 |  | Package 2
49 |  | Package 1 |  |  |  | Draft Price Bid Evaluation Report
50 |  | Package 2
51 |  | Package 1 |  |  |  | Draft Contract Documents
52 |  | Package 2
Note:
1: Updated List of Applicable Technical Standards shall also be included in Appendix of No. 7 (Volume I: General Report)
2: No. 8-21 shall be separatelly included Stage 1 and Stage 2 in one (1) volume