Appendix-2: Construction Cost Estimate

-	Section 2.1 shows comparison of estimated construction cost between JICA M/D and

D/D Cost Estimate Report Rev. 1

-	Section 2.2 shows Consultant’s Study on Construction Cost Estimate

at labor cost and construction cost of steel bridge for reference.

2.1	Estimated Construction Cost (Cost Estimate Report Revision1)

1)	General

-	Estimated Construction Cost in JICA M/D (28/06/2013) was referred

Draft Feasibility Study Report (April, 2013)

-	Estimated Construction Cost (D/D Rev. 1) was submitted to PMUTL on 12/03/2016

2)	Scope of Construction Works

Table 1: Scope of Construction Works

| Item | JICA M/D | D/D |
| --- | --- | --- |
| Project Length | 5.36 km | 5.368 km |
| Viaduct Length | 4.80 km | 4.723 km |
| Retaining Wall Length | 0.30 km | 0.645 km |
| Nos. of Pier | 117 nos. | 115 nos. |
| Others | --- | [Additional Work]: Widening of main line and construction of Off ramp at Hoang Quoc Viet Ramp |

3)	Estimated Total Construction Cost

[Main Issues in Conditions of Cost Estimate]

- Labor Cost [Section 2.2-2)]

Unit cost of labor was applied daytime rate only in accordance with Vietnamese Norm, and it is inevitable that nighttime work can’t be considered in the norm.

- Steel Bridge Construction Cost [Section 2.2-3)]

Fabrication of Steel Box Girder [Section 2.2-3)-a)]

Norm does not cover some important cost Items and determine by smaller production rate in some cost items (i.e.: cutting, assembling, welding, etc.).

Erection of Steel Box Girder [Section 2.2-3)-b)]

Crane size for girder erection in the norm is determined as 30 ton truck crane and it is too small in comparison with the construction plan in the D/D stage (160 ton).

Bolt Tightening Cost [Section 2.2-3)-c)]

Equipment cost for bolt tightening work is not enough in the norm.

Painting Cost [Section 2.2-3)-d)]

Equipment cost for painting is not enough in the norm.

Site Welding Cost [Section 2.2-3)-e)]

Norm covers by 20mm thickness of steel plate, but thickness of steel plate in the Project applies more than 20mm (maximum 50mm).

[Main Reasons of Decreasing Estimated Total Construction Cost compared with JICA M/D]

-	Labor Unit Cost	:	Decreased	[Table 3]

-	Material Unit Cost	:	Decreased (especially at steel panel and re-bar)	[Table 4]

-	Equipment Cost	:	Decreased (especially at crane and bulldozer)	[Table 5]

-	Foundation Cost	:	Decreased	[Table 6]

(decreased the nos. of rotation steel pile)

(revised over-design of bored pile)

-	Additional IC Construction	:	Increase (additional scope of works)

Followings are comparison of estimated total construction cost between JICA M/D and D/D (Rev. 1).

This cost includes additional IC construction (Widening of Main Line and Off ramp at Hoang Quoc Viet Ramp) cost in Package 1. (VND 85,207,320,000 = JPY 432,000,000) [Appendix-3]

Table 2: Comparison of Estimated Total Construction Cost (Excluding Escalation and VAT)

[VND]	[converted into JPY]

| Package | JICA M/D [A] | D/D (Rev. 1) [B] |  | Package | JICA M/D [A] | D/D (Rev. 1) [B] |
| --- | --- | --- | --- | --- | --- | --- |
| Package 1 | 1,774,785,735,691 | 1,183,683,260,522 |  | Package 1 | 8,078,061,511 | 6,001,274,131 |
| Package 2 | 1,487,320,028,913 | 971,158,692,672 |  | Package 2 | 6,769,641,224 | 4,923,774,572 |
| Total | 3,262,105,764,604 | 2,154,841,953,194 |  | Total | 14,847,702,735 | 10,925,048,703 |
| Difference | [B]-[A] ([B]-[A])/[A] | 1,107,263,811,410 |  | Difference | [B]-[A] ([B]-[A])/[A] | 3,922,654,032 |
|  |  | -33.9 % |  |  |  | -26.4 % |

Note	: in JICA M/D	1 VND = 0.00455 JPY

: in D/D (Revision1)	1 VND = 0.00507JPY

Followings are detail of unit cost (Labor Cost, Material Cost and Equipment Cost) and quantities of Bored Pile and Rotation Steel Pile.

Table 3: Comparison of Labor Unit Cost (VND)

| Labor Type | Unit | JICA M/D (Draft F/S) [A] | D/D (Rev. 1) [B] | Difference ([B]-[A])/[A] |
| --- | --- | --- | --- | --- |
| Class 2.5/7 | day | 256,562 | 164,398 | -35.9% |
| Class 3.0/7 | day | 276,483 | 177,192 |  |
| Class 3.5/7 | day | 300,073 | 192,342 |  |
| Class 3.7/7 | day | 309,510 | 198,402 |  |
| Class 4.0/7 | day | 323,664 | 207,492 |  |
| Class 4.3/7 | day | 340,334 | 218,198 |  |
| Class 4.5/7 | day | 351,448 | 225,335 |  |
| Class 5.0/7 | day | 379,232 | 243,179 |  |

Note	: [JICA M/D (Draft F/S)] apply labor cost decided by Government

- Decree No.205/2004/ND-CP on December 2004

“Government detailing a number of articles of the Labor Code regarding wage”

- Decree No.31/2012/ND-CP dated April 12, 2012

“Government providing for the common minimum wage”

- Decree No.103/2012/ND-CP dated December 04, 2012

“Government stipulating region-based minimum wage levels for laborers”

[D/D] apply labor cost decided by Hanoi People’s Committee

- Decision No.7414/QD-Committee dated December 31, 2015

“Hanoi City PC announced the market price of labor in the construction sector in Hanoi”

Table 4: Comparison of Main Material Unit Cost (VND)

| Items | Unit | JICA M/D (Draft F/S) [A] | D/D (Rev. 1) [B] |  | Difference (%) ([B]-[A])/[A] |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Cau Giay | Tu Liem | Cau Giay | Tu Liem |
| Steel Plate SM400 | kg | 15,100 | 12,500 |  | -17.2% |  |
| Steel Plate SM490Y | kg |  | 13,580 |  | -10.1% |  |
| Steel Plate SM570 | kg |  | 15,280 |  | +1.2% |  |
| Steel Plate SKK490 | ton | JPY 90,000 | JPY 134,000 |  | +48.9% |  |
| Reinforcing Bar over 18mm, CB400 | kg | 15,610 | 12,970 |  | -16.9% |  |
| Coarse Aggregate | m3 | 209,800 | 208,730 | 184,937 | -0.5% | -11.9% |
| Crashed Stone 2x4 | m3 | 187,800 | 233,604 | 214,137 | +24.4% | +14.0% |
| Sand for Concrete | m3 | 192,800 | 223,785 | 177,050 | +16.1% | -8.2% |

Table 5: Comparison of Main Equipment Unit Cost (VND)

| Equipment | Unit | JICA M/D (Draft F/S) [A] | D/D (Rev. 1) [B] | Difference (%) ([B]-[A])/[A] |
| --- | --- | --- | --- | --- |
| Crawler Crane 16T | shift | 2,315,275 | 1,557,702 | -32.7% |
| Concrete Mixer 250L | shift | 310,068 | 252,538 | -18.6% |
| Bulldozer 110cv | shift | 2,042,732 | 1,373,902 | -32.7% |
| Bentonite Mixer | shift | 284,061 | 344,725 | +21.4% |

Table 6: Comparison of Quantity of Pile

| Type | Unit | JICA M/D (Draft F/S) [A] | D/D (Rev. 1) [B] | Difference (%) ([B]-[A])/[A] |
| --- | --- | --- | --- | --- |
| Bored Pile |  |  |  |  |
| Diameter | mm | 1,500 | 1,200 | --- |
| Number of Pile | N | 669 | 795 | +18.8% |
| Total Length | m | 25,800 | 28,237 | +9.6% |
| Concrete Volume | m3 | 45,592 | 31,935 | -30.0% |
| Rotation Steel Pile |  |  |  |  |
| Diameter | mm | 1,300 | 1,200 | --- |
| Number of Pile | N | 374 | 248 | -33.7% |
| Total Length | m | 14,960 | 9,096 | -39.2% |

2.2	(Reference) Consultant’s Study on Construction Cost Estimate

-	Some cost items are missing in Norm as mentioned in Section2.1-1). However, Cost Estimate Report Rev. 1 was calculated based on this Norm in accordance with instruction from PMUTL.

-	Followings are Consultant’s study on appropriate Construction Cost at labor cost and steel bridge construction cost based on experience in other project.

1)	Summary of Construction Cost in Main Items

Table 7: Summary of Consultant’s Study Construction Cost

[VND]	[converted into JPY]

| Cost Items |  | D/D (Rev. 1) [A] | Reference Cost [B] |  | Cost Items |  | D/D (Rev. 1) [A] | Reference Cost [B] |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Labor Cost |  | 106,523,910,857 | 138,481,084,114 |  | Labor Cost |  | 540,076,228 | 702,099,096 |  |
| Steel Bridge Construction Cost |  |  |  |  | Steel Bridge Construction Cost |  |  |  |  |
|  | Fabrication Cost | 96,167,473,536 | 115,967,912,386 |  |  | Fabrication Cost | 487,569,091 | 587,957,316 |  |
|  | Erection Cost | 13,830,657,814 | 14,446,156,688 |  |  | Erection Cost | 70,121,435 | 73,242,014 |  |
|  | Bolt Tightening Cost | 2,033,345,818 | 4,066,714,652 |  |  | Bolt Tightening Cost | 10,309,063 | 20,618,243 |  |
|  | Painting Cost | 19,940,011,440 | 21,649,713,246 |  |  | Painting Cost | 101,095,858 | 109,764,046 |  |
|  | Site Welding Cost | 57,353,464 | 354,202,494 |  |  | Site Welding Cost | 290,782 | 1,795,807 |  |
| Total |  | 238,552,752,929 | 294,965,783,580 |  | Total |  | 1,209,462,457 | 1,495,476,522 |  |
| Difference |  | [B]-[A] ([B]-[A])/[A] | 56,413,030,651 |  | Difference |  | [B]-[A] ([B]-[A])/[A] |  | 286,014,065 |
|  |  |  | +23.6 % |  |  |  |  |  | +23.6 % |

Note	: in D/D (Revision1)  1 VND = 0.00507JPY

Steel Bridge Construction Cost (Fabrication Cost, Erection Cost, Bolt Tightening Cost, Painting Cost and Site Welding Cost) is estimated as two steel bridges.

Labor Cost	: refer section 2.2-2), table 9

Steel Bridge Construction Cost	: refer section 2.2-3)

Fabrication Cost	: refer section 2.2-3)-a), Table 10

Erection Cost	: refer section 2.2-3)-b), Table 11

Bolt Tightening Cost	: refer section 2.2-3)-c), Table 12

Painting Cost	: refer section 2.2-3)-d), Table 13

Site Welding Coat	: refer section 2.2-3)-e), Table 14

2)	Labor Cost

-	Unit cost of labor was applied daytime rate only in accordance with Vietnamese Norm, and it is inevitable that nighttime work can’t be considered in the norm.

-	It depend on approval from Hanoi DOT and Police, but some construction work may conduct in nighttime, so there are some difference in Cost Estimate and actual.

-	Therefore, classify a construction work into Daytime Work or Nighttime Work (Not consider all day for one construction work), and estimate labor cost roughly for reference.

-	Classification of Nighttime work:

- In case of detour road shall be narrowed during a construction work, this construction work shall be classified as Nighttime Work

- Construction area is narrow and vehicles will passes through near the area. In case of considering a fall down of rotation steel pile during a lifting, construction of rotation steel pile shall be classified as Nighttime Work

-	Labor cost for nighttime is calculated by following conditions;

- Labor will work only 8 hours per day (normal working time in Vietnam) and no overtime work, and no work in Sunday and National Holiday

- Daytime: 8:00-16:00  Nighttime: 22:00-6:00

- Labor cost for nighttime: +30% (Labor Code 10/2012/QH13)

-	Construction works in nighttime and reference construction cost estimate are assumed as following;

Table 8: Construction Works in Nighttime

|  | Construction Works in Nighttime (additional cost: VND) |  |  |
| --- | --- | --- | --- |
|  | Standard Section | Narrow Section | Steel Bridge |
| Foundation (Pile) | --- | ○ (VND 11,543,706,977) | --- |
| Substructure (Pire Head) | --- | ○ (VND 4,986,995,956) | ○ (VND 152,047,281) |
| Substructure (Others) | --- | --- | --- |
| Superstructure (Girder Erection) | --- | ○ (VND 11,879,870,960) | ○ (VND 2,325,680,906) |
| Surface (Slab, Concrete Barrier) | --- | ○ (VND 953,935,055) | ○ (VND 114,936,122) |

Table 9: Comparison of Labor Cost for Nighttime Works

[VND]	[converted into JPY]

| Item | D/D (Rev. 1) [A] | Reference Cost [B] |  | Item | D/D (Rev. 1) [A] | Reference Cost [B] |
| --- | --- | --- | --- | --- | --- | --- |
| Labor Cost | 106,523,910,857 | 138,481,084,114 |  | Labor Cost | 540,182,104 | 702,236,735 |
| Difference | [B]-[A] ([B]-[A])/[A] | 31,957,173,257 |  | Difference | [B]-[A] ([B]-[A])/[A] | 162,054,631 |
|  |  | +30 % |  |  |  | +30 % |

Note	: in D/D (Revision1)  1 VND = 0.00507JPY

This Labor Cost is summed only construction work in nighttime (not all of work)

3)	Construction Cost for Steel Bridge (sum of 2 steel bridges)

-	Construction Cost for Steel Bridge is estimated based on;

- HPC’s Decision No.7139/QD-UBND dated 27th December, 2014,

- MOC’s Decision No.1776/BDX-VP dated 16th October, 2007,

- MOT’s Decision MUC 1479/BGTVT, 1987.

-	However, some important cost items are missing in the Norm [Appendix-4]

-	Followings are reference cost of main items

a)	Fabrication Cost

-	Norm for fabrication of steel bridge is not enough at type of work and equipment

-	In American Institute of Steel Construction, steel bridge in the Project is classified as “Category 3”. In case of a factory fabricate a steel bridge of the Category 3, inspection of equipment and approval of equipment are required.

-	In Cost Estimate Report Revision 1, ratio of cost is Material : Labor : Equipment = 60:30:10. But usually, this ratio will be 40:30:30, so the cost for equipment seems too small.

-	Labor cost is different at country by country, but Material Cost and Equipment Cost may be same in any country. Therefore, increase Equipment cost to fit with usual ratio of cost as mentioned above.

Table 10: Comparison of Fabrication Cost for Steel Bridge

[VND]	[converted into JPY]

| Item | D/D (Rev. 1) [A] | Reference Cost [B] |  | Item | D/D (Rev. 1) [A] | Reference Cost [B] |
| --- | --- | --- | --- | --- | --- | --- |
| Fabrication Cost | 96,167,473,536 | 115,967,912,386 |  | Fabrication Cost | 487,569,091 | 587,957,316 |
| Difference | [B]-[A] ([B]-[A])/[A] | 19,800,438,850 |  | Difference | [B]-[A] ([B]-[A])/[A] | 100,388,225 |
|  |  | +20.6 % |  |  |  | +20.6 % |

Note	: in D/D (Revision1)  1 VND = 0.00507JPY

b)	Erection Cost

-	As shown in [Appendix-4], there is difference between Norm and Construction Plan

- Norm in Vietnam	: estimated by 30 ton truck crane

    - In Construction Plan	: planned by 160 ton truck crane

-	Crane capacity shall be decided in accordance with not only weight of segment but also the installation height of segment and working space for the crane, and actually 30 ton truck crane can’t apply in the Project.

-	In case of 160 ton truck crane is applied, work efficiency will be better than 30 ton truck crane, therefore cost increase is only 4.45%

Table 11: Comparison of Erection Cost for Steel Bridge

[VND]	[converted into JPY]

| Item | D/D (Rev. 1) [A] | Reference Cost [B] |  | Item | D/D (Rev. 1) [A] | Reference Cost [B] |
| --- | --- | --- | --- | --- | --- | --- |
| Erection Cost | 13,830,657,814 | 14,446,156,688 |  | Erection Cost | 70,121,435 | 73,242,014 |
| Difference | [B]-[A] ([B]-[A])/[A] | 615,498,874 |  | Difference | [B]-[A] ([B]-[A])/[A] | 3,120,579 |
|  |  | +4.45% |  |  |  | +4.45% |

Note	: in D/D (Revision1)  1 VND = 0.00507JPY

c)	Bolt Tightening Cost

-	Norm for High Tension Bolt is published by Hanoi People’s Committee, however the Norm is not enough at equipment and tightening procedure.

-	Vietnamese Norm shows that Labor Cost of Tightening high strength bolt is evaluated by 2 times of Tightening Normal bolt, but it shall be evaluated at least 4 times more considering the tightening procedure.

Table 12: Comparison of Bolt Tightening Cost for Steel Bridge

[VND]	[converted into JPY]

| Item | D/D (Rev. 1) [A] | Reference Cost [B] |  | Item | D/D (Rev. 1) [A] | Reference Cost [B] |
| --- | --- | --- | --- | --- | --- | --- |
| Bolt Tightening Cost | 2,033,345,818 | 4,066,714,652 |  | Bolt Tightening Cost | 10,309,063 | 20,618,243 |
| Difference | [B]-[A] ([B]-[A])/[A] | 2,033,368,834 |  | Difference | [B]-[A] ([B]-[A])/[A] | 10,309,180 |
|  |  | +100 % |  |  |  | +100 % |

Note	: in D/D (Revision1)  1 VND = 0.00507JPY

d)	Painting Cost

-	Norm for Painting is not enough at equipment cost.

-	Basically, painting shall be conducted in dry space with heater and roof, but such condition is not considered in Norm.

-	Therefore, consider as equipment cost shall be relate with painting material cost, and equipment cost is modified.

-	Cost of painting equipment will be evaluated at least same as material cost based on quantity and its quality.

Table 13: Comparison of Painting Cost for Steel Bridge

[VND]	[converted into JPY]

| Item | D/D (Rev. 1) [A] | Reference Cost [B] |  | Item | D/D (Rev. 1) [A] | Reference Cost [B] |
| --- | --- | --- | --- | --- | --- | --- |
| Painting Cost | 19,940,011,440 | 21,649,713,246 |  | Painting Cost | 101,095,858 | 109,764,046 |
| Difference | [B]-[A] ([B]-[A])/[A] | 1,709,701,806 |  | Difference | [B]-[A] ([B]-[A])/[A] | 8,668,188 |
|  |  | +8.57 % |  |  |  | +8.57 % |

Note	: in D/D (Revision1)  1 VND = 0.00507JPY

e)	Site Welding Cost

-	Norm for site wilding is considered for welding of 20mm steel plate

-	In the Project, thickness of steel plate is 50mm in some section, therefore increase welding cost based on ratio of cross section of welding area.

Table 14: Comparison of Site Welding Cost for Steel Bridge

[VND]	[converted into JPY]

| Item | D/D (Rev. 1) [A] | Reference Cost [B] |  | Item | D/D (Rev. 1) [A] | Reference Cost [B] |
| --- | --- | --- | --- | --- | --- | --- |
| Site Welding Cost | 57,353,464 | 354,202,494 |  | Site Welding Cost | 290,782 | 1,795,807 |
| Difference | [B]-[A] ([B]-[A])/[A] | 296,849,030 |  | Difference | [B]-[A] ([B]-[A])/[A] | 1,505,025 |
|  |  | +517.6 % |  |  |  | +517.6 % |

Note	: in D/D (Revision1)  1 VND = 0.00507JPY