Appendix-4: Discrepancy between Norm and Actual Work

The Difficulties of Cost Estimate has been found out in case of applying the Vietnamese norm to steel bridge. Followings are explanation of some issues in main items.

1 	Crane Capacity

Norm AG.511 shows Installation and Combination (Assembly) works, and 30 ton crane is assumed in this Norm as shown in Figure 1.

However, 30 ton crane can’t apply for erection of steel bridge in the Project because of weight ofsegment, erection height and working space.

Figure 1: Vietnamese Norm for Installation and Combination

a)	Profile of 30 ton crane (Refer from Catalogue)

-	Figure 2and Figure 3 shows size of crane, capacity table (working radius and Boom Length) and Chart Diagram (Lifting Height and Working Radius) for 30 ton crane.

-	From the capacity table, in case of boom length is 7.7m and Working Radius is within 5.0m, the crane can lift up the segment more than 20 ton.

-	From the chart diagram, lifting height is less than 8m, and distance between crane and segment can be applied from 3m (height: 8m) to 5m (height: 4m)

b)	Profile of 160 ton crane (Refer from Catalogue)

-	Figure 4 and Figure 5 shows size of crane, capacity table (working radius and Boom Length) and Chart Diagram (Lifting Height and Working Radius) for 160 ton crane.

-	From the capacity table, in case of boom length is 45.4m and Working Radius is within 20m, the crane can lift up the segment more than 20 ton.

-	From the chart diagram, lifting height is more than 40m, and distance between crane and segment can be applied from 5m (height: 50m) to 20m (height: 40m). In case of weight is lighter than segment of steel girder (ex: cross beam and other small pieces), the distance can be kept longer.

As mentioned above, crane capacity shall be determined by the construction procedure which is considered suitably about not only weight of segment but also erection height and working space.

Figure 2: Detail Size of 30 ton crane

Figure 3: Capacity Table and Chart Diagram for 30 ton crane

Figure 4: Detail Size of 160 ton crane

Figure 5: Capacity Table and Chart Diagram for 160 ton crane

2 	Tightening of High Strength Bolt

-	Tightening of high strength bolt shall be considered as most important work for erection of steel structure. So, tightening procedure shall be sufficiently controlled to keep accuracy and quality.

-	The items to be controlled are;

- Roughness of contact surface for keeping friction force

- Tensile force of bolt producing friction force against slide force induced spliced joint

-	Friction force will be guaranteed by induced tensile force of bolt and friction coefficient of contacted surface. If this condition is not enough, contact surface will be slip.

-	If co-rotation will occur, it can be considered that tensile force doesn’t satisfy required value and the bolt shall be replaced.

Figure 6: Image of Bolt Connection

| Preliminary Tightening with marking | Secondary Tightening with checking co-Rotation | Photo of Bolt Tightening Work |
| --- | --- | --- |
| Condition of Marking |  |  |

Figure 7: Marking Condition of Bolt

Figure 8: Image of Bolt Tightening Works

-	In order to install the bolt correctly, tightening procedure shall be carried out in accordance with controlled steps. So, special equipment for tightening bolts; Bolt Tensioner, Nut Runner and Torque Wrench are necessary.

-	Tightening procedure shall be carried out sequentially, Preliminary tightening, Marking, Tightening, Checking Co-rotation.

-	It seems that these actual procedure will be not evaluated on the Vietnamese Norm. Vietnamese Norm of High strength bolt and Normal bolt are shown in table 9.

-	Comparison with the above norm, only the labor price of high strength bolt will be evaluated as 2 times only of the normal bolt. However, this evaluation seem not be too enough in comparison with the procedure and equipment as mentioned before.

| 9. Erection of high strength bolt components Work items: Preparation, erection of components of steel girder and steel components by high strength bolt ensuring technical requirements. | 10. Erection of normal Bolt Work items: Preparation, erection of components of steel girder and steel components by normal bolt ensuring technical requirements. |
| --- | --- |

Figure 9: Comparison of Norm for High Strength Bolt and Normal Bolt

3	Site welding

-	This project has the site welding at the pier head as shown in below. This site welding is decided in accordance to the condition of availability of transportation dimension.

-	The site welding of box girder shall be conducted at any other equipment or temporary pieces which are different from shop welding

-	Erection pieces as strong backing plate is necessary for prevent distortion due to shrinkage of welding and also keeping gap between both welding edges

Figure 10: Pier Head of Steel Bridge in the Project

- Welding edges have been beveled and protected by anti-blast coating during fabrication

- Strong backing plate will be prepared so as high strength bolting joint, and then it shall be removed after completion welding

- Welding will be affected by wind, so scaffolding for welding shall be surrounded by sheet or other material for protecting against wind.

- In case of special welding condition of quenched and tempered material like as SM570, pre- heating procedure shall be needed same as shop welding.

- Prepared welding machine shall have enough capacity for the large sized full-penetration weld (Plate thickness of this pier head is about 50-30mm).

- Deposit (volume) of weld will be increased the 3 multiplier to in accordance with the thickness of plate (Compared to 6mm filet weld). This means welding time and material will be much increased according to thickness of plate.

|  | size GMAW SAW | 30mm: K=27.4 40mm: K=44.9 50mm: K=96.7 |
| --- | --- | --- |

Figure 11: Calculation of K for Welding

4	Installation of Bearing

-	Bearing for steel bridge will be made from not only elastomer but also casting iron or steel plate using for pot and base plate

-	Although dimension of bearing depends on its capacity of reaction, bearing weight will be more than 500kg. And this weight is unable to shift by man power only, nevertheless the Vietnamese Norm prescribe about installation of bearing without Crane work.

-	After placing bearing on the bearing seat(bearing base), the  position shall be adjusted so as error will be minimized. For this purpose, survey work shall be necessary during installation work.

Figure 12: Image of Bearing