Ministry of Physical Infrastructure and Transport, Department of Roads

Government of Nepal

Nagdhunga Tunnel Construction Project

Loan Agreement No. (NE-P10)

Contract No. DOR - NTCP -W-ICB-01

Bidding Documents

Part 2: Works Requirements

(SECTION VI)

VI-C: Special Provisions to Standard Specifications (SPSS)

VOLUME-Ⅱ: TUNNEL WORS AND FACILITIES

section vi-c: Special Provisions to the Standard Specifications (SPSS) FOR road and bridge works, ASAD, 2058 / JULY 2001

preface

The Standard Specifications for Road and Bridge Works, ASAD, 2058 / July 2001 has not hitherto referred to tunnelling work.

In order to cope with various underground geotechnical behaviours likely to be encountered during construction, the Sections in the series of 4000s systematise the requirements of the civil elements of roadway tunnel construction, inter alia, underground excavation, ground support systems, waterproofing/drainage systems and final tunnel lining.

Table of Contents

Tunnel works – Civil Elements

SECTION 4000 – general requirements	40-1

SECTION 4100 – TUNNEL PROFILE AND SUPPORT SYSTEMS	40-7

SECTION 4200 - INSTRUMENTATION AND MONITORING	40-9

SECTION 4300 - EXCAVATION	40-14

SECTION 4400 - PRE-SUPPORT	40-23

SECTION 4450 - STEEL RIB	40-26

SECTION 4500 - WIRE MESH	40-29

SECTION 4550 – SHOTCRETE	40-31

SECTION 4600 - ROCK BOLT	40-37

SECTION 4650 - WATERPROOFING	40-43

SECTION 4700 – CONCRETE LINING	40-49

SECTION 4750 – INTERIOR FINISH	40-54

SECTION 4800 - DRAINAGE SYSTEM, WALKWAY & PATH	40-58

SECTION 4850 – PORTAL WORKS	40-63

SECTION 4900 - GATES	40-67

SECTION 4000 – general requirements

4001. 	Objectives and Application

These specifications for Tunnel works - Civil Elements are prepared on a project specific basis for the use in Nagdhunga Tunnel Construction Project in the Kingdom of Nepal in mountain terrains using the New Austrian Tunnelling Method (NATM).

Tunnel features (dimensions, cross sections, shapes, orientations, support types, lining types, required construction sequences) have been determined in conformity to the following Japanese Standards taking into account of the ground conditions assumed from the findings of the ground investigations;

- Standard Specifications for Tunnelling – 2006 [Mountain Tunnels] published by Japan Society of Civil Engineers (JSCE),

- Design Standard Section 3 [Tunnel] published by Nippon Expressway Company Limited (NEXCO), and

- Technical Standard for Road Tunnel [Structure Division] published by Japan Road Association (JRA).

Notwithstanding the foregoing, other standards, where specified in these Specification Sections, shall be regarded as equally applicable under the Contract.

4002. 	Acronyms

Whenever these abbreviations are used in these Specification Sections, they represent the following:

AASHTO - American Association of State Highway and Transportation Officials

ACI - American Concrete Institute

ACGAI - American Conference of Governmental Industrial Hygienists

ASTM- American Society for Testing and Materials

AWS - American Welding Society

JHS – Japan Highway Standards

JIS – Japan Industrial Standards

JCOSHA – Japan Construction Occupational Safety and Health Association

JRA – Japan Road Association

JSCE – Japan Society of Civil Engineers

LSM – Linier Schedule Method

NATM – New Austrian Tunnelling Method

NEXCO – Nippon Expressway Company Limited

SEM – Sequential Excavation Method (aka New Austrian Tunnelling Method)

4003.	Contractor’s General Obligations

Tunnel construction is inherently a dangerous undertaking. Excavation, mucking, support installation, shotcrete application, concrete placing and all other activities are carried out in a sequential way in close quarters often with moving heavy machinery.

The Contractor is required to fulfil the obligations described in more detail below.  Payment for fulfilling these obligations is deemed included under other pay items.

Approval or consent given by the Engineer for the use of materials proposed by the Contractor shall not relieve the Contractor from any duties, obligations or responsibilities he has under the Contract.

4003.1	Safety of Personnel

Safety of personnel on the Site is the first priority above all in all construction activities. The Contractor shall vigilantly observe the requirements described hereunder. Rules and regulations currently effective under the laws of Nepal or bylaws imposed by the local authorities shall prevail in the event of disagreement.

Suitable Personal Protective Equipment (PPE) shall be provided to all persons permitted to be on site. PPE including head protection, respiratory protection, eye protection, reflective vest, etc. shall be of the type approved by the local authorities.

The Contractor shall prepare a written statement (a booklet) of safe systems of working which shall be issued to all persons at site.

4003.1.1	Safety Training

Persons when first employed on the Site shall be instructed in the hazards inherent in the Site, precautions to be taken, the form of construction, and emergency procedures and firefighting. The Contractor shall maintain a record of all persons on assignments and each person shall be required to sign such record confirming that instruction has been received.

In addition, the Contractor is required to hold a daily toolbox talk before entering into tunnels with the aim of promulgating the inherent risks related to the activities scheduled on the day. The toolbox talk shall be conducted by each ganger in charge of particular activities. The record of assignment mentioned above can be logged at the end of such toolbox meeting before starting the given assignments.

4003.1.2	Fire Prevention and firefighting Arrangements

Fire protection and proper firefighting arrangements such as fire extinguishers shall be provided on the tunnelling machines, other than machines which are too small to allow personal entry. Similar arrangement shall be provided when operations may emit potentially noxious gases or fumes in addition to ventilation arrangements stated hereinafter.

4003.2	Temporary Electrical Installations

Unless specified in the Contract, the Contractor shall be responsible for obtaining an adequate electrical supply for all his Site operations.

Installations shall comply with the current edition of the rules and regulations of the local authorities. If required by the Engineer, the Contractor shall make available a copy of all certificates prepared upon completion of electrical installations.

The Contractor shall appoint a competent person to be solely responsible for ensuring the safety of all temporary electrical installations,

4003.2.1	Ventilation during Construction

Constant supply of high quality breathable air is one of the more challenging safety aspects for tunnel workers. The Contractor shall provide a suitable ventilation system to remove dust caused by drill/blast and shotcrete as well as exhaust gases emitted from diesel engines during construction to comply with the requirements specified in Articles 86 [Ventilation] and 89 [Safety and Health] of Standard Specification for Tunnelling – 2006: Mountain Tunnels or as specified in theses specifications. The ventilation rate that is required to dilute the gas emissions from diesel engines of construction machines and dust produced during drill/blast and shotcrete application should be calculated taking account of type and numbers of equipment used inside tunnels.

For safe working of persons in the tunnels, the Contractor shall use the following limit values in calculating the total fresh air requirement at the face area;

- The minimum fresh air supply shall not be less than 3 m3/minute/person measured at the face,

- The target dust (respiratory dust) concentration should be not more than 3 mg/m3 measured at 50 m from the face,

- The minimum air velocity throughout the tunnels shall not be less than 0.3 m/second, and

- The maximum ambient temperature inside the tunnels shall be maintained below 30 degrees centigrade.

The Contractor shall, as a means of achieving the above values, determine the diameter of air piping and the capacity of fans, considering ventilation efficiency, machine efficiency and dimensions of profiles.

As drill/blast and shotcrete application take place at the face area, the Contractor will be required to provide a mobile dust collector attached extensible air duct at each tunnel face in order to achieve the limit value of the dust concentration.

For monitoring of the ventilation requirements, the Contractor shall provide necessary measuring devices to the satisfaction of the Engineer.

The Contractor shall submit a layout plan of his ventilation systems including dust collection systems along with a calculation of required fresh air supply for agreement with the Engineer before commencing tunnel excavation.

4003.2.1	Lighting during Construction

Suitable and sufficient lighting shall be provided in working places and pathways, so as to secure safe working environments. Working places such as the face need sufficient light that should exceed seventy (70) lux (1 lux = 1 lumen per square meter) in order that the work can be performed safely and efficiently.

It is also necessary to light walkway areas for the safe passage of workers and the safe operation of vehicles. It may be difficult to secure uniform light in the whole walkway areas, but the light of a minimum of ten (10) lux is necessary at the darkest site and twenty (20) lux in average is desired as recommended in Article 85 [Lighting] of Standard Specifications for Tunnelling – 2006: Mountain Tunnels.

4003.3	Security and Access Restriction

The Contractor shall be responsible for the security and tunnel entry in and around all tunnels work areas. Tunnel security and exit/entry procedures and controls shall be detailed in the Contractor’s safety plan (or health and safety plan) for the Works. The Contractor shall co-ordinate and plan tunnel security and entry with others having access to the tunnels, including all interfacing contractors, so as not to disrupt or interfere with their operations.

The Contractor shall provide and maintain fences and barricades in good conditions. Notice signs shall be displayed at intervals (as consented by the Engineer) around the Site and portal areas to warn the public of the dangers of entrance.

During the progress of the Works the Contractor shall maintain security patrols over the portal areas of the Works as may be necessary to protect the work and prevent trespassing.

4003.4	Entry/Exit Procedures

The Contractor shall establish a procedure for recording all tunnel entry and exits, preventing unauthorized tunnel entry. This procedure, as a minimum, shall incorporate name cards and entry/exit records at all tunnel portals to record the entrance and exit of all personnel.

The Contractor shall set up and operate a system whereby only those persons entitled to be on the Site and/or in the tunnels can enter the Site and/or tunnel.  The Contractor shall provide specific points of entry through a security fence or barricade. The Contractor shall provide gates and barriers at such points of entry and maintain a twenty-four-hour security guard or other security personnel as necessary to maintain security and prevent unauthorized entry

4003.5	Temporary Communication Systems

The Contractor shall provide both a complete wired and a wireless telephone communication system capable of providing clear and concise communication between all tunnel works and the tunnel portals. The communication systems shall also provide for communication between the tunnel works, Contractor’s site office, and Employer’s and Engineer’s site offices.

The Contractor shall maintain at all times both wired and wireless communication systems in full working order during construction. The communication systems and equipment shall be suitable for use in all area, providing clear and dependable communication. This shall be subject to approval by relevant authority prior to use as the case may be.

The communication systems shall incorporate underground communication stations (telephone receptacle with bell and Indication lamp) within 50-metre of any work and at 100-meter intervals along the driven tunnel. The Contractor shall provide and maintain communication systems until the completion and acceptance of all tunnel works or as otherwise required by the Engineer.

4003.6	Daily Records/Reports

Notwithstanding reports on other work activities, the Contractor shall prepare daily records and reports of all tunnel works that shall include the following information and data, or as directed by the Engineer.

duration of sequential excavation,

all personnel working in tunnel areas,

work stoppage, with reason for stopping work,

all instrument recordings with appropriate graphs,

weather conditions,

tunnel work equipment,

tunnel water inflows,

size of excavated sections,

length of advance,

station numbers,

photographs (not less than 12 Megapixels) of all tunnel faces after excavation, before support system installation,

the location and number of supports system members etc. for each round, and

reports and records required under specific specification requirements.

Unless agreed with the Engineer, the Contractors daily records/report shall be submitted to the Engineer before 10 AM on the following working day, and

The Contractor shall, as witnessed in the presence of the Engineer, record in detail geological conditions and prepare geological maps with necessary photographs attached to evaluate the suitability of excavation methods and supports. These details and maps shall serve as the basis for anticipating geological conditions ahead of the excavated tunnel face.

The Contractor shall immediately notify the Engineer in case of substantial difference between actual geological conditions and anticipated ones, or when severe changes in geological conditions are observed.

For the recording of geological data by the Engineer, the Contractor shall give all necessary assistance, and provide all workforce, facilities and equipment as may be required by the Engineer.

- 4004	Measurement and Payment

- Measurement is not performed for the Works described in this Section. The Works required under this section is a subsidiary obligation of the Contractor. Payment for such Works is indirectly included under the pay items listed in the Schedule (reference Sub-Clause 1.1.1.7 of the Conditions of Contract).

- As a general rule, the rates in the Bill of Quantities shall be deemed to include all the cost, without limiting to the following, in respect of:

- Provision of all labour, equipment and materials required for the execution and completion of the Works and remedying of any defects;

- Provision for loading, hauling and stockpiling the excavated material on approved areas or points of incorporation into Permanent Works up to a lead of 5.0 km and all lifts from the tunnel face, re-handling of materials including segregating, grading, draining and drying of materials suitable for use in the embankment construction or as backfill;

- All delays resulting from unfavourable weather conditions;

- Complying with all requirements of statutory laws and regulations relating to the works and any restrictions resulting therefrom, obtaining all necessary permits and licenses for use and transport of explosives and other materials; and

- Surveying, setting out, checking and monitoring of excavated profile, layouts and any subsequent rectification works.

SECTION 4100 – TUNNEL PROFILE AND SUPPORT SYSTEMS

4101.	General

Physical properties for a ground, typically expressed as a class of ground or rock/ground classification, shall be formulated in accordance with Standard Specifications for Tunnelling – 2006 [Mountain Tunnels] published by Japan Society of Civil Engineers based on the samples taken from upper half (above the spring line) tunnel section.

Support members are selected based on the ground classification, and the support pattern shall be determined in combination with selected support members. It will be necessary to properly modify the design by reviewing from time to time the class of ground and support pattern/combination during construction.

4102.	Ground Classification

Rock/ground classification and the corresponding support types are determined generally on the basis of the parameters prescribed in the Standard Specifications for Tunnelling – 2006 [Mountain Tunnels]. These terms of ground classifications are also applicable to the tunnel profiles and the support patterns used thereto.

Notwithstanding the above classifications, a special support pattern, Type DIII, is required particularly at the portal zones as prescribed by the Standard Specifications for Tunnelling. Physical properties of ground are described below to provide helpful guidelines for determining support patterns.

- Type CI

Rock Classification: Relatively solid, fair discontinuity orientation and stable.

The rock strength is greater than the tangential and radial stresses induced by the tunnel opening. The condition of discontinuity is fair and the yielding by the tunnelling occurs partly.

The partial rock falls along discontinuity which is easy to slide relatively occur rarely, and the displacement induced by tunnel opening would remain in the range of roughly 15 to 20 mm or may be less due to elastic deformation. The face can be self-supported.

- Type CII

Ground Classification: Relatively solid but poor discontinuity and unstable.

The rock strength is not greater than the tangential and radial stresses induced by the tunnel opening. In other words, the displacement created by the tunnel opening will tend to remain within the limit of elastic deformation.

Despite the intrinsic strength of the rock in the tunnel relatively high, rock blocks are prone to fall off along the discontinuity planes resulting in further ground slackening. The displacement induced by the tunnel opening, in case the tunnel width is less than 10m along the spring line, may verge on the elasto-plastic boundary of 30 mm when intrinsic rock strength of rock is lower than the tangential and radial stresses. However, the ground movement will normally cease when the tunnel face is advanced by a distance approximately 2 times of the tunnel width measured along the spring line. The face can be self-supported

- Type DI

Ground Classification: Weathered, not solid, very poor discontinuity and unstable.

The rock strength is comparably as low as the tangential and radial stresses induced by the underground opening; elastic deformation and plastic deformation may occur spontaneously and concurrently.

Since the discontinuity orientation is very poor, even the rock strength may be sufficient to hold the elastic deformation, loosening may continue along the discontinuities. When strength of rock is lower than the tangential and radial stresses, the deformation or settlement may verge on the range of 30 to 60 mm unless the invert ring is closed by temporary or permanent means.  Given the invert is closed in such a manner as agreed with the Engineer, deformation will normally cease, as with Types CII and CII-L, when the tunnel face is advanced by a distance approximately 2 times of the tunnel width measured along the spring line. The stand-up time of the cut face is so short that breast boards (face shotcrete) and ring cuts may be necessary following consultation with the Engineer.

- Type DIII

There is no ground classification according to the Standard Specifications for Tunnelling – 2006 [Mountain Tunnels]. Type DIII is specifically designated for application of support systems at portal areas irrespective of physical properties of the ground, such as degree of weathering, rock properties, material composition, planes of weakness (discontinuity) and etc.

Portals are frequently located in a generally weak geologic zone, where erosion develops and a complicated topography is created. Thus, tunnelling or construction of the portal is likely to cause landslides or slope failures.

Type DIII applies from the portal to the distance at which the depth of cover exceeds 2 times the diameter of the tunnel at the spring line. Actual application shall be determined with consultation with the Engineer.

4103.	Tunnel Profile and Support System

Tunnel profiles and the corresponding combination of support types will be determined generally on the basis of the parameters prescribed in the aforesaid Standard Specifications for Tunnelling. The initial support system in a mountain tunnel can be one or a combination of a number of options: rock reinforcement (rock bolts), steel ribs, shotcrete, wire mesh, pre-supports, etc. The combination of these support options including final concrete lining are shown on the Drawings although these options depend largely on the ground conditions encountered during tunnel driving.

- The Engineer shall at all times have the authority to instruct the Contractor to revise the support systems based on his observations and instrumental data.

- 4104.	Measurement and Payment

Measurement is not performed exclusively for the Works described in this Section. Works required under this section are subsidiary obligations of the Contractor.

Payment for such Works is indirectly included under other pay items of the Bill of Quantities.

SECTION 4200 - INSTRUMENTATION AND MONITORING

4201.	Objectives and Application

Instrumentation and monitoring are considered as an integral part of the NATM tunnelling for verification of the design assumptions on the interactions between the surrounding ground and the initial tunnel support systems induced during excavation process.

Works described herein are subsidiary obligations of the Contractor. Payment for such work is deemed included under other pay items. Compensation provided by the pay items included in the Schedules, defined in Sub-Clause 1.1.1.7 of the Conditions of Contract, is full payment for performing the obligations in a complete and acceptable manner. No separate payment shall be made.

4202.	Method of Monitoring

Monitoring of ground movement is the mandatory activities for which direct payment is not provided and is a subsidiary obligation of the Contractor to assure that the tunnel centre remains in the alignment.

The monitoring of the ground movement aims to detect the displacement and settlement of the initial tunnel support systems -- particularly the shotcrete lining -- and the ground surface while they are still small and to enable early support system modifications.

These monitoring are categorized under indirect payment items and shall consists of the following observations/surveys.

- Visual Examination of the Tunnel Opening and Ground Surface

- Geologic mapping of the face after each round.

Geologic mapping of the tunnel face and the round periphery is an important element for determining initial support systems.

Information typically included in these face maps include:

The station location for the cross-section; the date and time the face mapping was prepared;

The name of the individual who prepared the face map;

Classification of each type of material observed; the location of interface boundaries between these materials;

Rock jointing including orientation of principal joints and joint descriptions;

Shear zones;

Observed seepage conditions and their approximate locations on the face, walls, or roof;

Observed ground behaviour noting particularly the location of any instability or squeezing material at the face;

The location of any boulders or other obstructions; and

Any other significant observations.

In rock tunnels where the perimeter rock is left exposed, sketches presenting similar information can be prepared for the tunnel walls and roof. All mapping shall be prepared by an experienced geologist or geological engineer of the Contractor knowledgeable of tunnelling and with soil and rock classification.

Mapping of the face, walls and roof shall occur for every excavation round and formally documented and signed off by both the Contractor and the Engineer in the format acceptable to the Engineer.

Groundwater inflow, if observed.

The quantity of observed seepage shall be recorded and monitored on a daily basis for all groundwater inflow including seepages in the previous rounds as well. The method of measuring inflow quantity shall be subject to the Engineer’s approval.

Deformation of initial support systems after each round.

Ground movement along the tunnel alignment will be the primary cause of displacement or buckling of initial support systems. Amongst others, displacement, buckling and subsidence (settlement) of steel ribs, integrity of shotcrete with wire mesh/steel ribs and rock face, and potential damage to or loosening of rock bolt components, shall be visually checked by the Contractor’s geologist or the geological engineer before using the survey instruments. Information thus obtained shall be recorded and presented to the Engineer for review before next excavation.

Ground surface settlement along the tunnel centre

The Contractor is required to make close observation on potential anomalies such as surface cracking, tilting of trees, changes in stream water flow direction, displacement of the existing boulders, and other unusual phenomena. The Contractor shall record any such anomalies with each excavation cycle, and submit such records as soon as possible but well before next excavation takes place.

The Engineer may instruct the Contractor to lay surface settlement markers and/or benchmarks for observation of ground movement.

Lateral and Vertical Displacement

As for the lateral movement of the tunnel opening, distance between the shotcrete surfaces shall be measured at the points illustrated in Fig-1 for full-face excavation profile and Fig-2 for top-heading and bench excavation shown below.

Fig-1: Full-face excavation                Fig-2: Top-heading and bench excavation

Vertical displacement of the tunnel cross-section shall also be monitored by surveying level of the crown.

Lateral displacement shall be measured at the spring lines for full-face excavation sections (Fig-1), and if tunnel is excavated sequentially, i.e. top heading ahead of bench, measurement shall be taken first at 1.5 meters above the spring line (Fig-2) for every top heading round.

Once bench excavation starts after the top heading excavation, the Contractor shall measure the displacement again at 1.5 meters above the spring line (Fig-2) and at 1.0 meter below the spring line (Fig-2) after each bench excavation round.

In unstable ground, which is vulnerable to excavation-induced stress relief such as DIII Rock Classification or tunnel sections near the portals under shallow overburden -- say less than about twice the tunnel width measured along the spring line -- additional measurements shall be taken along a pair of symmetrical lines between the points connecting the crown and points at 1.5 meters above the spring line (Fig-3).

In tunnel domains where any of or a combination of (i) excavation-induced sharp unsymmetrical pressure, (ii) settlement of steel rib, or (iii) ground heaving is likely to occur, the Engineer may instruct the Contractor to take further measurements along a pair of the symmetrical lines (indicated in dashed lines in Fig.-3) that connect the point at the crown and points at 1.0 meters below the spring line.

Fig-3: Lateral Displacement Survey Points

for Top Heading & Bench Excavation

In case where the magnitude of the unsymmetrical pressure, settlement of steel ribs, or the ground heaving is considerable in the Engineer’s judgement, the Engineer may instruct the Contractor to take readings of the vertical displacement at two off-set points from the crown in addition to the settlement reading of the crown level.

The number of survey points will be determined at the Engineer’s discretion and the Contractor shall provide such survey points according to the Engineer’s instructions given orally or in writing.

Surface settlement above the centreline near the tunnel portal

Geological anomalies observed on the ground surface above tunnels, such as surface cracking, tilting of trees, changes in stream water turbidity and its flow direction, displacement of the existing boulders, and other unusual phenomena, shall be monitored and recorded in a format acceptable to the Engineer.

The Engineer may determine shorter intervals of survey points which are normally selected along the tunnel centre despite the normal intervals given in Table-1 below. Survey points may be increased on the ground surface at the Engineer's discretion in case readily noticeable movement is detected.

Table-1: Depth of Overburden and Intervals of Survey Points

| Depth of Overburden | Intervals |
| --- | --- |
| Not exceeding D | 5 m |
| Exceeding D and less than 2D | 10 m |

D: Tunnel diameter at spring line.

4203.	Monitoring Frequency and Interval of Distance

Lateral and vertical displacement of the tunnel opening shall be monitored at the frequencies indicated in Table-2, and at the intervals shown in Table-3.

Table-2: Parameters of Monitoring Frequencies

(*1): Monitoring frequency will be determined by either the distance from face or rate of movement whichever effectuate higher frequency.

Table-3: Intervals of Survey points

| Excavation Profiles | Interval of Survey points (*2) |  |  |  |
| --- | --- | --- | --- | --- |
|  | Within 50 m from Portal | 50 – 200 m from Portal | Over 200 m from Portal | Overburden not exceeding 2D |
| CI & CII | 10 m | 20 m | 30 m | 10 m |
| DI | 10 m | 20 m | 20 m | 10 m |
| DIII | 10 m | -- | -- | 10 m |

(*2): The intervals will be determined by the Engineer based on the ground conditions encountered.

4203.1	Surveying Requirements

- The Contractor shall use a total station for all surveys for accurate data collection. Thus, the Contractor shall submit to the Engineer for his approval details of the total station he proposes to use.

All survey shall be conducted and controlled by a qualified professional surveyor having a minimum 3 years tunnel survey experiences using a modern total station.

The required surveying accuracy is ± 2 mm for both lateral and vertical directions in any survey unless otherwise instructed by the Engineer.  The surveying instruments shall be packaged with the minimum reading function not more than ± 0.1 mm.

The lateral and vertical movement of the tunnel supports (and ground surface as well) shall be surveyed immediately after mucking is completed. It is recommended that the survey is conducted within 3 hours after completion of mucking. For synchronicity of the survey data between ground surface movement and the tunnel supports movement, the Contractor shall simultaneously carry out tunnel survey and ground survey unless otherwise the Engineer agrees.

No excavation will be permitted unless all required survey data is collected.

The data processing software shall be subject to the Engineer’s approval.

4203.2	Survey Reference Points

Permanent reference points shall be continuously located and installed along the tunnel route, no later than one day after installation of the tunnel support system.

The maximum spacing of the reference points shall be not more than 100 meters along straight sections of the tunnel, and no more than 50 meters along curved sections.

The installation of the reference points shall be to the satisfaction of and/or as required by the Engineer. The location of the reference points shall not conflict with other parts of the work, and

Reference points shall be rechecked and verified at one-kilometre intervals in conjunction with the completion of the tunnel support systems.

4203.3 	Longitudinal Profile Survey

The Contractor shall perform (and provide to the Engineer) longitudinal profile survey of the tunnel lining, by means of closed traverse, upon completion of the tunnel works.

4203.4	Submittal

- The Contractor shall submit for the Engineer’s approval the following information within 28 days after the date of commencement of the Works.

Format of geologic mapping, and method of measuring quantity of groundwater inflow,

Details of the total station, and

Data processing software.

Other documents (reporting formats) which should be submitted before next excavation are as follows.

A report notifying geological anomalies observed during visual inspection of tunnel supports and ground surface above the tunnel alignment.

- 4204	Measurement and Payment

- Measurement is not performed exclusively for the Works described in this Section. The Works required under this section is a subsidiary obligation of the Contractor.

- Payment for such Works is indirectly included under other pay items of the Bill of Quantities.

SECTION 4300 - EXCAVATION

4301	Description

The work consists of the excavation of tunnels to the cross-sectional dimensions along the neat line (pay line) prescribed in this Section.

Excavation shall be performed using the conventional “New Austrian Tunnelling Method (NATM)”, also referred to as the “Sequential Excavation Method (SEM)”.

4302	Material Requirements

There are no specific permanent materials required for excavating the tunnels.

4303	Construction Requirements

4303.1 	Equipment

Equipment used inside tunnel shall be electric or diesel fuel powered. No gasoline engine is permitted inside the tunnel.

4303.2 	Experienced Personnel

NATM tunnel construction requires solid and credible past tunnel construction experience and personnel skills. The skills should relate to the use of equipment and handling materials for excavation, installation of the initial tunnel supports including the steel ribs, shotcrete, pre-support measures, and rock reinforcing measures.

The Contractor shall provide experienced personnel including senior NATM superintendents with the minimum experience in NATM tunnelling as specified in the Bidding Documents. All general tunnel superintendents and tunnel gangers, except senior NATM superintendents, should also have the minimum in the NATM tunnelling experience as specified in the Bidding Documents.

To verify the individual experience, the Contractor shall submit, separate from the method statement mentioned below, curriculum vitae of all key personnel to be engaged in the tunnel construction activities.

The senior NATM superintendents shall be responsible for guiding excavation and support installation meeting the key requirements of NATM tunnelling:

Observation of the ground

Evaluation of ground behaviour as it responds to the excavation progress

Implementation of the right initial support.

The senior NATM engineer is required to supervise the excavation and installation of the initial tunnel supports, installation of any local or additional support measures and pre-support measures to suite the ground conditions.

4303.3 	Excavation Procedures

4303.3.1	Probing

Prior to drilling for blasting, the Contractor shall perform at least one probe drilling ahead of the face of the tunnels, using the drilling machine that the Contractor uses for drilling and blasting operations. Probing is intended to reduce risks and hazards associated with tunnelling ahead of the face. The length, diameter and the direction of probe hole shall be determined by the Contractor at his discretion.

Cost associated with the probing is deemed included in the unit of measurement for tunnel excavation and no additional payment shall be made.

4303.3.2	Drilling and Blasting

- The Contractor shall obtain all necessary licenses and shall provide and, where appropriate, maintain a secure explosives store in accordance with statutory requirements to the approval of the Police and the Engineer.

- Explosives shall be handled and used only by the Contractor’s duly authorised personnel. The name and qualifications of such personnel shall be submitted to the Engineer in writing in advance of any possible use of explosives.

- Blasting operations shall be carried out only under the direction of an experienced operator and explosives shall be handled only by shotfirers. The Contractor shall appoint one competent person to be responsible for the security of explosives.

- The Contractor shall adhere to the round length specified on the Drawings. Deviations from the specified round length are not allowed unless agreed with the Engineer.

- At an early stage, in advance of the proposed use of explosives, the Contractor shall notify the Engineer, third parties, statutory authorities and services which have an interest in or are likely to be affected by blasting operations, of the general nature of the operation. The Contractor shall subsequently give a minimum of 14 days' notice to the Engineer and others described above of the proposed use of explosives. With this notification the Contractor shall submit to the Engineer a detailed method statement on all aspects of the proposed use of explosives, including treatment of misfires

- Based on the specified round lengths, the Contractor shall prepare blasting plans, including drilling patterns, type of explosives, detonators with delay sequencing and amount of explosive charge, which shall be compatible with the ground conditions, size and shape of tunnel cross-section, etc., and shall minimise the loosened zone and obtain a smooth excavation face.

- Blasting shall be carried out carefully so as to avoid loosening or shattering rock beyond the required line of excavation, and all loose or shattered rock shall be removed by scaling down or other means before personnel will be permitted to restart operations after blasting.

- Notices of blasting operations shall be posted on site. Before each firing, the Contractor shall give audible warning, clear the area, and shall take positive measures to prevent personnel from entering the danger area.

- The Contractor shall monitor the results of blasting closely and where it is proper to do so, shall propose changes to his blasting operation for the agreement of the Engineer

- Under no circumstances shall any holes be charged until completion of all drilling operations at the face.

- No person shall be allowed to approach the face and no face operation shall commence until the Contractor's authorised person in charge of the operation has given permission

- As soon as practicable after blasting and without undue delay the Contractor shall erect such support as may be necessary to safeguard the excavation and personnel.

- The shot-firer must keep a record of the number of shots fired, their time of firing, type and weights of explosives used and the type and number of detonators used, together with a record of the post blast situation for each and every location. A copy of the record shall be available to the Engineer at the end of every shift on which shots are fired.

- The Contractor shall comply with the Explosives Act, 2018 (1961) along with its amendments and other prevalent laws and ordinances as stipulated in Clause 904 of the Standard Specification for Road and Bridge Works ASAD, 2058 / July 2001.

- The Employer shall provide reasonable assistance to the Contractor at the request of the Contractor for the Contractor’s application for any permits, licences or approvals required for import, delivery, storage and use of explosives and accessories.

4303.4 	Mucking and Disposal

- The Contractor is required to carefully select and arrange muck haulage operations (including muck loader) taking account of material conditions. Size and dimensions of the haulage equipment shall be such that they would not damage the installed steel ribs, shotcrete lining, and other key temporary facilities, such as ventilation, lighting, drainage, etc. Muck from the tunnels shall be removed from the tunnels and transported to the disposal areas shown on the Drawings or as directed by the Engineer. Materials encountered in tunnel excavation and determined by the Engineer as suitable for incorporating in the roadway construction shall be conserved and utilized as directed by the Engineer

The portal areas shall not be used as a temporary storage for muck from the tunnel excavation. Muck shall be directly transported to the designated disposal areas (except for materials suitable for incorporation in the roadway construction as mentioned above) and sorted out according to composition of the material, i.e. hard rock, mixture of rock and soil, muddy soil, etc.

The Contractor shall maintain the record of the number of trips that haulage car travelled so that the volume of muck removed from the tunnels is registered. No materials shall be removed from the disposal areas without prior consent of the Employer. The Contractor is held responsible for the control of the excavated materials in the disposal areas.

Excavation may encounter contaminated soils or groundwater. Such soils may require special treatment such as capping after disposal. Separate disposal area or separate lot within the disposal area will be determined by the Engineer. If such contaminated soils are found to be toxic, the Contractor shall dispose of such soils as directed by the Engineer.

4303.5 	Safety, Hygiene and Environment Protection

- The Contractor shall comply with the relevant laws and regulations including laws in relation to health and safety of all persons entitled to be on the Site, particularly in confined working areas such as the tunnels.

- The Contractor shall provide temporary facilities to reduce blasting noise to the threshold value imposed by the local authorities.

- The Contractor shall minimise physical harm caused by construction vibration that impairs the value, usefulness, or normal function of properties of the nearby residents.

- It is strongly recommended that the Contractor performs inventory surveys of the properties and maintain photo records before any blasting takes place.

The Contractor shall establish a regular air monitoring scheme through which content of oxygen and noxious gases, in particular carbon dioxide, in tunnels.

The Contractor shall assign a competent person to perform air monitoring required to determine proper ventilation and quantitative measurement of potentially hazardous gasses.

The objective of monitoring the atmosphere in a tunnel is to ensure that it is free from levels of toxicants and that it contains sufficient oxygen for persons to breath.

Routine checking/monitoring of oxygen and other noxious gases at every place where persons normally work or travel is a primary requirement in underground operations.

- Entering into tunnels shall be prohibited if the oxygen level in the air is below 18%(*a) and the carbon dioxide level exceeds 0.5% (5000ppm) (*b). - The oxygen level in the tunnel air body should be monitored at each shift before other gas samples are taken

(*a), (*b):  TLV-TWA (Threshold Limit Value - Time weighted Average) recommended by American Conference of Governmental Industrial Hygienists (ACGIH)

Unless the local authorities provide regulations related to entry to the tunnel, the following threshold points should be strictly observed until safe working condition is confirmed by the person in charge of monitoring. Checking of these gas concentrations shall be performed at every working shifts. If required under the local regulations, the Contractor shall obtain proper approvals in writing from the local authorities for the gas detectors that the Contractor intends to use. Otherwise, the Contractor shall obtain the Engineer’s agreement for the use of such gas detectors before commencing tunnel excavation.

The Contractor is responsible to disseminate the tunnel safety procedures among all persons entitled to be on the Site, including the Employer’s Personnel.

The Contractor shall construct, operate and maintain sedimentation systems complying to the environmental codes and regulations of the local authorities. The Contractor shall also observe the following requirements.

- The sedimentation system shall be provided as close to the portal area as possible with at least four settlement ponds divided by the biological filters or as recommended/instructed by the local authorities.

- All ground water emanating from tunnel excavation shall be discharged into these settlement ponds, to remove oil, sand, silt and other suspended matter.

- A neutralizing agent and a sedimentation accelerating agent, either in liquid form or in powder form, shall be added to the contaminated water before discharging into the settlement ponds. The chemicals to be used shall conform to the laws and regulation of the relevant local authorities.

- The inlet to the ponds shall be designed so that water discharged into the pond will not stir up sediment previously deposited in that pond. Provision shall be made for the ability to repair or clean the pond during the progress of the Works.

- The outflow from each settlement pond shall be so arranged as to prevent any floating oil from leaving the pond, irrespective of the volume of water entering the pond. The settlement pond shall be constructed using suitable watertight materials, and lined with PVC membrane or similar material to prevent leakage. Wire mesh fencing of 2 meters minimum height shall be installed around the perimeter of the ponds to prevent unauthorized access.

- The outflow channel from the pond shall be designed and constructed to the satisfaction of the Engineer and in such a manner that soil erosion is prevented.

- To ensure the continuing satisfactory operation of the system, the Contractor shall remove accumulations of sand, silt, oil and sludge must be removed and disposed of at the locations approved by the Engineer.

- Natural ground water and storm water from areas outside the immediate area of the Contractor' activities must be prevented from flowing into the pond. The Contractor shall ensure that any diversion berms or drain protecting ponds constructed below ground are adequately maintained.

- Temporary drains or pipelines leading from the tunnel portal to the sedimentation ponds shall be designed to adequately handle the expected maximum initial flow of tunnel. In no case shall be less than 2.5 cubic meter per minute.

- The Contractor may, upon approval by the Engineer, employ mechanical facilities to treat water, in lieu of settlement ponds at no additional cost to the Employer.

4303.7 	Changes to Excavation Method

- The Contractor may alter his excavation methods or procedures with a prior notice to the Engineer. If the method used by the Contractor renders the scheduled progress unviable, in the opinion of the Engineer, the Contractor shall submit upon the Engineer’s instruction a revised method statement noting corrective actions to be taken.

- 4303.	Submittals

- 4303.1	Method Statement

A method statement, which he intends to adopt in the tunnel construction, shall be prepared by the Contractor and submitted to the Engineer, not later than twenty-eight (28) days before commencing the first round of excavation, for his review and comments. The method statement shall include, inter alia, the following:

- Linear Scheduling Method (LSM), in other terms “Time-Distance Diagram” or “Time-Location Diagram”; a time schedule with “Time” on vertical axis and “Distance” in the horizontal axis. All tunnel activities from the portal preparation till completion of road pavement and markings including incidentals shall be shown by individual lines. The LSM shall be prepared separately from the Programme prepared in accordance with Sub-Clause 8.3 of the Conditions of Contract,

- The LSM shall be established based on the round length specified on the Drawings.

Organization Chart; it should show individual names and the line of responsibility amongst the different working shifts.

Equipment; type and capacity of excavation equipment, loading equipment, hauling equipment, drilling equipment, shotcrete machine, steel rib erector, ventilation facilities supported by calculations and other equipment as directed by the Engineer,

Temporary Facilities; ventilation, lighting, blasting noise/vibration control, water supply, drainage systems and other temporary facilities necessary for safe underground operations. Capacities of the temporary facilities shall be supported by proper calculations for the Engineer’s review and comments/agreement,

Evacuation and resuming procedures in blasting operations, including warning siren code and signal lights,

Emergency evacuation and resuming procedures to be followed in case of accidents or abnormal situations and the essential information shall be summarised in a booklet which should be distributed to all persons entitled to be on the Site,

Emergency Network; it shall show names and telephone numbers of all key personnel of the Contractor, the Engineer and public/private medical institutions in case of emergency,

The Contractor shall not make significant alteration to the method or arrangement without having such alteration previously been notified to the Engineer.

The Contractor shall also submit to the Engineer all deformation monitoring survey data on a daily basis, and other survey data including geological mapping and geological investigation surveys as soon as possible as requested by the Engineer.

4304	Method of Measurement

4304.1	Excavation Profile and Measurement

The quantities of tunnel excavation shall be measured in the unit of measurement specified in the Bill of Quantities along the centreline between the portal crowns for the main tunnel and the evacuation tunnel. Excavation below the portal crown shall be measured in the unit of measurement specified in the Bill of Quantities for payment under Section 900 - Earthworks of the Standard Specifications for Road and Bridge Works ASAD, 2058/July 2001.

Measurement of the excavation for cross passages and working adit shall be performed along the centreline at the height of the spring line.  No separate remuneration shall be made for excavation above and below the spring line of the cross passages and the working adit where it inter. The cost of excavation above and below the spring line shall be included in the unit rates for excavation.

The Contractor shall submit survey data showing the coordinates of the start points on the portal crowns for agreement with the Engineer. The Contractor shall not commence tunnel excavation unless the Engineer agrees with the survey data.

Typical tunnel excavation profile is illustrated in Figure 4300-1 as a reference only.

Figure 4300-1

In tunnel excavation using high explosives through rock, the effects of explosive action may well extend more than the tunnel diameter outside the designed finished surface; a good deal of overbreak is likely unavoidable. Overbreak will result in increased thickness of shotcrete lining and final concrete lining larger than design thickness.

Since overbreak is almost an inevitable result in rock tunnelling, the effects of overbreak in respect of payment shall be deemed taken into the rates and prices entered into the Bill of Quantities; thus, no payment will be made for overbreak beyond the pay line. Accordingly, the Contractor will be required to employ experienced, skilled and qualified blasting technicians so that overbreak can be controlled.

The costs contingent to such overbreak is deemed to have been included in the rates and prices in the Bill of Quantities based on the average thickness of overbreak shown on the Drawings

Note that removal and reinstallation/replacement of pre-supports (forepoles; length being 3.0 m or less, and fore-piles; length exceeding 3 m), steel ribs, wire mesh, rock bolts, shotcrete, and other incidental parts of these supports, as required necessarily in the course of excavation are not subject to separate payment; all of these activities are combined into the direct cost as incidentals necessary to complete a round of excavation irrespective of rock classifications encountered.

4304.2	Recesses (Niches)

Quantity of recess excavation shall not be measured for payment. Such quantity is deemed included in the measurement of linear metre of excavation in each profile.

4304.3	Partial Cut off

Steel ribs installed at the junctions with cross passages and niches shall be partially cut off and modified as indicated on the relevant Drawings.

The Contractor shall remove the steel ribs, the reinforced shotcrete protection and rock bolts to the dimensions necessary to accommodate the openings in the lining concrete.

4305	Basis of Payment

Payment for the excavation is deemed to include the payments for the Works performed under the following Sections which comprise initial support systems;

- Section 4400 – Tunnel Pre-Support,

- Section 4450 – Tunnel Steel Rib,

- Section 4500 – Wire Mesh

- Section 4550 – Shotcrete

- Section 4600 – Rock Bolt

Payment shall be made on condition that all initial support systems are installed according to the Drawings. Especially in the case of early-closer as an auxiliary construction method (see Fig-1.), the works, invert excavation, shotcrete, and backfilling, shall not be measured and paid separately, but shall be deemed included into the rates for unit prices of respective main items. However, the work contents, re-excavation, invert concrete, and backfilling, for final lining shall be deemed included into rates for unit prices of pay-items in the Section 4700 Concrete Lining (see Fig-2.).

Figure-1   Early closure (With invert shotcrete)

Figure-2 Invert lining

Related temporary facility works and operation (concrete batching plant, power supply, water supply, drainage, lighting etc.) shall not be measured and paid separately, but shall be deemed included into the rates for unit prices of respective main excavation items. In addition, all necessary works for controlling the dust, emission of gas and ventilating air flow inside tunnel shall be deemed included into this Section pay items.

Payment will be inclusive of difficulties in dealing with groundwater inflow being less than 10 litres per second at the face, and other potential difficulties attributable to the ground conditions that are obviously anticipated from the parameters indicated in the Contract Documents.

| Pay Item | Excavation Profile Type | Unit of Measurement |  |
| --- | --- | --- | --- |
| Main Tunnel |  |  |
| 4300-01 | Main Tunnel CI -- (Full-face Heading) | m |  |
| 4300-02 | Main Tunnel CI-L -- (Full-face Heading) | m |  |
| 4300-03 | Main Tunnel CII-B -- (Full-face Heading) | m |  |
| 4300-04 | Main Tunnel CII-L -- (Full-face Heading) | m |  |
| 4300-05 | Main Tunnel DI-B – (Top Heading/Bench) | m |  |
| 4300-06 | Main Tunnel DI-FB – (Top Heading/Bench) | m |  |
| 4300-07 | Main Tunnel DIII-A – (Top Heading/Bench) | m |  |
| 4300-08 | Main Tunnel DIII-UA – (Top Heading/Bench) | m |  |
| 4300-09 | Main Tunnel DIII-AF – (Top Heading/Bench/Invert) | m |  |
| 4300-10 | Main Tunnel DIII-UAF – (Top Heading/Bench/Invert) | m |  |
| Evacuation Tunnel |  |  |
| 4300-11 | Evacuation Tunnel CI-P -- (Full-face Heading) | m |  |
| 4300-12 | Evacuation Tunnel CI-PL -- (Full-face Heading) | m |  |
| 4300-13 | Evacuation Tunnel CII-P -- (Full-face Heading) | m |  |
| 4300-14 | Evacuation Tunnel CII-PL -- (Full-face Heading) | m |  |
| 4300-15 | Evacuation Tunnel DIP -- (Full-face Heading) | m |  |
| 4300-16 | Evacuation Tunnel DIIIP-A -- (Full-face Heading) | m |  |
| 4300-17 | Evacuation Tunnel DIIIP-UA -- (Full-face Heading) | m |  |
| Cross Passage |  |  |
| 4300-18 | Cross Passage CI-VP -- (Full-face Heading) | m |  |
| 4300-19 | Cross passage CI-VPL -- (Full-face Heading) | m |  |
| 4300-20 | Cross Passage CII-VP -- (Full-face Heading) | m |  |
| 4300-21 | Cross passage CII-VPL -- (Full-face Heading) | m |  |
| Working Adit |  |  |
| 4300-22 | Working Adit DIW -- (Full-face Heading / Invert) | m |  |
| 4300-23 | Working Adit DIW-F -- (Full-face Heading / Invert) | m |  |
| 4300-24 | Working Adit DIIIW-AF -- (Full-face Heading / Invert) | m |  |
| 4300-25 | Working Adit DIIIW-UAF -- (Full-face Heading / Invert) | m |  |

Note: Letters hyphenated with the profile types have no distinction between the capital letters and the small letters. Capital letters are used in the above list for convenience.

SECTION 4400 - PRE-SUPPORT

4401	Description

The work consists of tunnel pre-supports, also referred as the auxiliary method, by means of stabilizing techniques installed through and ahead of the tunnel face where and when tunnel encounters zones of badly weathered and/or broken rock.

The pre-supports involve installation of perforated steel pipes which shall be grouted with polyurethane resin as specified herein.

In these specifications, pre-supports are classified into the following types.

- Forepoles; φ21.7 mm, pipe length 3.0 m,

- Forepiles; φ76.3 mm or φ114 mm, pipe length 12.5 m, and

- Forepiles: φ76.3 mm or φ114 mm, pipe length 18.5 m.

4402	Material Requirements

4402.1	Pipes (Perforated)

- Pipes shall be round structural seamless tubing, conforming to the standards JIS G3444, STK490 or internationally recognised equivalent standards as approved by the Engineer.

Pipes may be assembled with a closed pointed end to prevent inflow of earth. Pipe lengths shall be measured from the pointed end of pipes.

In case the pipes for pre-supports are imported from outside the country, the Contractor shall submit manufactures data and/or certified mill test reports certifying the properties of the pipes to the Engineer for review and approval at least 6 months prior to intended use.

4402.2	Polyurethane Resin

- Grouting material shall be of non-toxic polyurethane resin type, which provide a forming effect in relatively shorter hardening period following mixing and injection. The polyurethane grouting resin type shall exhibit an expansion rate (forming factor) of 4 at least and the unilateral compressive strength of 5N/mm2 as the minimum requirements.

Since physical and mechanical properties of polyurethane grouting materials differ amongst the products, the Contractor shall propose the type of the polyurethane grouting material it plans to use in the project for approval of the Engineer.

The Contractor shall include in its proposal the manufactures application manual for review by the Engineer.

4402.3 	Grouting Equipment

Injection of grouting material into pipes of the pre-support shall be performed by grouting pumps as recommended by the manufacturer of the polyurethane grouting material. The Contractor shall include in his proposal the operation manual of the grouting pump he intend to use.

4403	Construction Requirements

- Method of driving perforated steel pipes shall be selected by the Contractor and all costs thereof are deemed included in the rate per unit measurement.

After the initial injection pressure reaches a certain constant pressure, injection shall continue until the pressure increase by 2.5 MPa or more, unless otherwise specifically recommended by the manufacture of the grouting material.

The Contractor shall remain vigilant during injection and report to the Engineer any anomalies he observes on the tunnel face and the surrounding ground until the scheduled quantity has been injected. The Engineer may instruct the Contractor to cease the injection before the scheduled quantity has been injected in the event of anomalies. The Contractor will be required to take countermeasures against such anomalies to the satisfaction of the Engineer.

Grouting shall be deemed complete when the scheduled quantity has been injected.

Care shall be taken to prevent contamination of environment. Preventive measures shall be taken as recommended by the manufacturer of the polyurethane grouting material.

4404	Method of Measurement

Pre-supports installed as shown on the Drawings will not be measured separately for individual payment. Payment for pre-supports is deemed included in the unit of measurement for each excavation profile described in Section 4300 [Tunnel Excavation].

In the event that supplemental pre-support is instructed by the Engineer, measurement for payment for the individual installation will be performed according to the unit of measurement derived from the breakdown of the contract rates included in Section 4300 [Tunnel Excavation].

4405	Basis of Payment

In the event that the Engineer instructs the Contractor to install supplemental pre-support, payment for accepted quantity will be made separately at the unit rates per unit of measurement derived from the cost breakdown of work items in Section 4300 [Tunnel Excavation]. Payment will be full compensation for the incidental fixing work including materials

- In any case that, according to the Engineer’s evaluation, the provided and installed forepoling and/or forepiling are defective, risky or not conforming the requirements herein specified, the material and performed works shall be rejected and respective payment shall be suspended until the defects are solved by the Contractor, and duly approved by the Engineer. In any case that the defect continues, the Contractor shall submit to the Engineer, for review and approval, a method statement to solve the situation.

| - Pay Item | Description | - Unit of Measurement |
| --- | --- | --- |
| - 4400-01 | Grouted Forepoling, L= 3 m | - No. |
| - 4400-02 | Grouted Fore-piling, L = 12.5 m | - No. |

SECTION 4450 - STEEL RIB

4450.1	Description

The work consists of fabrication and installation of structural steel ribs that form part of the tunnel support system. The structural steel ribs system shall provide an effective protection immediately after tunnel excavation.

Payment for the steel rib supports is deemed included in the payment of tunnel excavation by profile types.

4450.2	Material Requirements

Shaped steels used for the fabrication of tunnel ribs shall be new and shall conform to JIS G 3101, SS400 [Rolled Steel for General Structure] or equivalent international standards approved by the Engineer.

4450.3 	Construction Requirements

4450.3.1	Shaping, Fabrication and Assembly of Steel Rib Components

- H-beam steel ribs, tie rods and other steel components of the ribs shall be cut and shaped to the dimensions shown on the Drawings. Shaping shall be accomplished by means of full length cold bending. The application of heat for bending or shaping is not permitted. Steel ribs that are shaped by heating shall not be incorporated in the shotcrete lining.

The Contractor shall provide all necessary equipment, tools and facilities for the proper controlled bending and fabrication of steel components. Improperly fabricated steel components, including those with wrinkled or twisted steel ribs shall not be incorporated in the Works.

The Contractor shall submit to the Engineer for review and approval, at least 28 days prior to intended fabrication operations, shop drawings. Shop drawings shall take design intent and specifications prepared by the Employer and develop them to show in detail how the components will actually be manufactured, fabricated, assembled or installed. The Contractor shall not precede with steel fabrication operations until the Engineer gives approval. The Contractor shall not deviate from approved procedures without the written approval of the Engineer.

Allowable tolerances for the fabrication of steel ribs are as follows:

2 mm for cutting and assembling

10 mm for radius after cold bending

Bolts and accessories, in accordance with specified requirements, shall be used for all steel rib connections. Bolt tightening shall be done with properly calibrated wrenches, by turn-of-nut method or by use of direct tension indicators.

Welding shall not be permitted for any fabrication or assembly of steel rib components. Welding, in accordance with drawing requirements, shall only be used for securing tie rods and steel plates to H-beams. Welding, inspection, and corrective welding, shall be in accordance with the American Welding Society’s Standard Structural Welding Code AWS D1.1 (Structural Welding Guide).

The sizes, shapes and quantity of steel components shall be installed in accordance with the requirements of the Drawings, based on rock classification and support systems as determined in accordance with Section 4100. The Engineer may, based on tunnel conditions, require the Contractor to make modifications to support system by adding additional supports and/or changing support member sizes.

The Contractor shall take this into consideration when ordering and pricing his support system components so as to prevent delays due to lack of the stocked materials. Stocked, but unused materials shall not be measured for payment.

4450.3.2	Installation of Steel Ribs

- Steel ribs shall be erected to accommodate the theoretical profile, and assembled at elevations and in positions shown on the Drawings, and/or as required by the Engineer. Hard wood blocks, wood wedges or other acceptable devices may be used as temporary supports for adjustment of steel ribs so as to provide proper placement and positioning prior to and or during the instalment of tie rods. Temporary support materials shall be removed prior to the placement of shotcrete.

All steel-ribs shall be completely embedded in shotcrete with a minimum coverage as indicated on the Drawings. Shotcrete shall fill all voids in and around steel ribs so as to provide a composite steel and shotcrete mass that is appropriately secured to the tunnel face.

Allowable tolerances for steel rib installations are as follows:

Deviation at centre of crown from the theoretical centreline of the tunnel: 2 cm

Deviation at invert: 10 cm toward outside, and 0 cm towards inside

Longitudinal spacing: + 5 cm

4450.4	Method of Measurement

Steel ribs installed and modified as shown on the Drawings will not be measured separately for individual payment. Payment for steel ribs is deemed included in the unit of measurement for each excavation profile described in Section 4300 [Tunnel Excavation].

No deduction will be made for sections removed for construction of cross passages/niches and the like.

In the event that supplemental steel rib is instructed by the Engineer, measurement for payment for the individual installation will be performed according to the unit of measurement derived from the breakdown of the contract rates included in Section 4300 [Tunnel Excavation].

4450.5	Basis of Payment

In the event that the Engineer instructs the Contractor to install supplemental steel rib, payment for accepted quantity will be made separately at the unit rates per unit of measurement derived from the cost breakdown of work items in Section 4300 [Tunnel Excavation]. Payment will be full compensation for the incidental fixing work including materials

- In any case that, according to the Engineer’s evaluation, the provided and installed steel ribs are defective, risky or not conforming the requirements herein specified, the material and performed works shall be rejected and respective payment shall be suspended until the defects are solved by the Contractor, and duly approved by the Engineer. In any case that the defect continues, the Contractor shall submit to the Engineer, for review and approval, a method statement to solve the situation.

| Pay Item | Description | Unit of Measurement |
| --- | --- | --- |
| 4450-1 | Steel Rib Support, H-125 mm | m |

SECTION 4500 - WIRE MESH

4500.1	Description

The work consists of furnishing and installing wire mesh (Welded Wire Fabric) as indicated on the Drawings, and/or as directed by the Engineer.

Payment for the wire mesh is deemed included in the payment for the tunnel excavation by profile type.

4500.2	Material Requirements

Wire mesh shall conform to the requirements of JIS G3551.

Wire mesh shall be of a fagot type with a square spacing of 150-mm in each direction. The diameter of the wire shall be 5-mm in accordance with JIS G3551.

4500.3	Construction Requirements

Wire mesh shall be installed with the minimum clearance of 50-mm from the excavated surface as shown on the Drawings, accommodating the actual excavation profile, never to exceed more than 20-cm away from any part of the excavated rock face. A minimum overlap length of 20-cm shall be maintained. To prevent loosening during shotcrete application, wire mesh shall be firmly fixed to rock or other surfaces on which it is applied. The spacing of fixing points shall be not more than 50-cm in all directions unless approved or directed by the Engineer otherwise.

4500.4	Method of Measurement

Wire mesh installed and removed as shown on the Drawings will not be measured separately for individual payment. Payment for wire mesh is deemed included in the unit of measurement for each excavation profile described in Section 4300 [Tunnel Excavation].

No deduction will be made for sections removed for construction of cross passages/niches and the like.

In the event that supplemental wire mesh is instructed by the Engineer, measurement for payment for the individual installation will be performed according to the unit of measurement derived from the breakdown of the contract rates included in Section 4300 [Tunnel Excavation].

4500.5	Basis of Payment

In the event that the Engineer instructs the Contractor to install supplemental wire mesh, payment for accepted quantity will be made separately at the unit rates per unit of measurement derived from the cost breakdown of work items in Section 4300 [Tunnel Excavation]. Payment will be full compensation for the incidental fixing work including materials

- In any case that, according to the Engineer’s evaluation, the provided wire mesh is defective or not conforming the requirements herein specified, the wire mesh shall be rejected and respective payment shall be suspended until the defects are solved by the Contractor, and duly approved by the Engineer. In any case that the defect continues, the Contractor shall submit to the Engineer, for review and approval, a method statement to solve the situation.

| Pay Item | Description | Unit of Measurement |
| --- | --- | --- |
| 4500-1 | Wire Mesh, φ5-mm x 150-mm x 150-mm | m2 |

SECTION 4550 – SHOTCRETE

4550.1	Description

The work consists of furnishing, mixing and applying wet shotcrete. Reinforced shotcrete is mostly applied onto the excavated tunnel surfaces to act as initial tunnel support and primary lining.

Payment for shotcrete is deemed included in the payment for tunnel excavation according to the excavation profiles.

4550.2	Material Requirements

The Contractor shall obtain prior approval of the Engineer on the materials to be used in producing shotcrete. Key materials are discussed hereinbelow.

4550.2.1	Cement

Portland cement shall meet the requirements of Clause 614, Standard Specifications for Road and Bridge Works ASAD, 2058 / July 2001. Certificates attesting that the cement meets specification requirements shall be submitted to the Engineer for review and approval at least 28 days prior to the commencement of shotcrete operations. Portland Cement will be accepted on the basis of a manufacturer's certificate of compliance, accompanied by mill test reports that the material meets the requirements of these specifications. At the expense of the Contractor, when/if directed by the Engineer, the Contractor shall perform tests to verify the cement certification. Cement will be rejected if test results are not satisfactory

4550.2.2	Aggregates

Aggregates shall conform to Clause 2710, Standard Specifications for Road and Bridge Works ASAD, 2058 / July 2001.

The maximum aggregate size shall be 15-mm in consideration of thickness of application. The Contractor shall provide test results and necessary data, including sieve analyses, to the Engineer for review and approval at least 28 days prior to the commencement of shotcrete application.

Aggregates will be accepted on the basis of certificates of compliance and test reports that show the material meet the quality and grading requirements of these specifications

4550.2.3	Water

Water used in mixing or curing concrete shall be fresh, clean, potable, and free from injurious amounts of oil, salt, acid, alkali, organic matter, or other deleterious substances. Water used for curing shall not contain excessive impurities to discolour the shotcrete surface.

4550.2.4	Admixtures

Admixtures to be used, when required or approved, shall comply with the   sections of JIS A 6204 – Chemical Admixture for Concrete, or equivalent international standards as approved by the Engineer. Except as otherwise accepted by the Engineer, soluble admixtures shall be dissolved in water before introduction into the shotcrete mixture.

4550.2.5	Accelerators

If accelerating admixtures complying with ASTM C 1141, Standard Specification for Admixture for Shotcrete, Type II, Grade 1, are to be used, the Contractor shall establish the accelerator compatibility of the job cement and the proposed accelerators using ASTM C 266, Standard Test Method for Time of Setting of Hydraulic-cement Paste by Gilmore Needles, except as modified herein.

The powdered accelerator shall be blended with 50 grams of cement until uniform and 15 millilitres of water shall then be added. The liquid accelerator shall first be mixed with 15 millilitres of water and then added to 50 grams of cement. Three percent (3%) of the proposed accelerator by mass of cement shall be used as a starting point. Mixing shall be accomplished within 15 seconds.  The specimen shall be moulded within 1 minute of adding the mixing water.  If initial set is 2 minutes or less and a final set is 10 minutes or less, the accelerator is considered compatible.  If these values are not achieved in the first test, additional tests shall be run using 2 percent and 4 percent of accelerator. The quality and quantity of accelerating admixture used shall not decrease the Shotcrete 28-day strength.

Chemical admixtures that have been in storage at the project site for longer than 6 months shall be subject to retesting at the expense of the Contractor when/if directed by the Engineer and shall be rejected if test results are not satisfactory. Certificates attesting that the admixtures meet specification requirements shall be submitted to the Engineer for review and approval at least 28 days prior to the commencement of Shotcrete operations.

4550.2.6	Reinforcement

Welded wire fabric reinforcement (wire mesh) shall comply with the requirements of Section 4500 [Wire Mesh].

4550.3 	Construction Requirements

4550.3.1	Shotcrete mix Design Approval

The standard mix design for wet type shotcrete is as follows.

| Compressive Strength at 28days σ28 | Slump | W/C | Max. Aggregate | Unit Cement Content | Volume of Sand | Volume of Aggregates | Accelerator by Weight of Cement |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 18 N/mm2 | 10±2cm | 56% | 15mm | 360kg/m3 | 0.80m3 (675kg) | 0.47m3 | 5.5% |

Contractor shall submit the proposed shotcrete mix designs to the Engineer for initial evaluation and comment.  No sooner than 14 days after mix design submittal, the Contractor shall (after giving the Engineer at least 48 hours prior notice) prepare test panels using the proposed shotcrete mix design in the presence of the Engineer.

4550.3.2	Shotcrete Criteria for Mix Design

Mixture proportions (Mix Designs) for shotcrete shall be selected and approved on the basis of compressive strength tests of cores obtained from test panels fabricated in accordance with ASTM C 1140, Standard Practice for Preparing and Testing Specimens from Shotcrete Test Panels, and the initial and final set properties of the mix as determined in accordance with ASTM C 403/ C 403M, Standard Test Methods for Time of Setting of Concrete Mixtures by Penetration Resistance.

4550.3.3	Test Panels for Mix Design

Test panels shall be at least 762 mm by 762 mm.  Test panels shall be made using equipment, water pressure, air pressure and nozzle operator the Contractor proposes to use for the work. Four separate test panels shall be made, two shall be vertical placements (representing side placement of Shotcrete) and two shall be overhead placements. From each panel, six (6) cores shall be taken; two (2) from each panel for testing at 24 hours after placement, two (2) for each panel for testing at 7 days, and two (2) from each panel for testing at 28 days after placement in light of Article 46 [Mechanical Characteristics of Shotcrete] of the Standard Specifications for Tunnelling – 2006 [Mountain Tunnels] published by Japan Society of Civil Engineers (JSCE). Cores shall be taken perpendicular to the test panel and cured in accordance with the requirements of ASTM C 1140, until testing.

4550.3.4	Mix Design Acceptance Criteria

The compressive strength of the mix design for 24 hours shall attain 5 N/mm2 as a target strength and 18N/mm2 as the requirement at the age of 28 days as required by the Design Standard Section 3 [Tunnel] published by Nippon Expressway Company Limited (NEXCO) and Article 45 of the	Standard Specifications for Tunnelling – 2006 [Mountain Tunnels] published by Japan Society of Civil Engineers (JSCE).

4550.3.5	Revision to Approved Mix Design

Shotcrete mix designs, as approved by the Engineer, shall be based on the approvals for cement, admixtures, accelerator, water and aggregates used with an approved mix. If the Contractor, for any reason, changes any of these materials or gradation, the Contractor shall submit and obtain approval for new mix constituents and provide a new mix design for approval by the Engineer.

4550.3.6	Batching and Mixing of Shotcrete

Batching and mixing shall be accomplished in accordance with the applicable provisions of ASTM C 94/ C 94M, Standard Specification for Ready-Mixed Concrete and ACI 506-R, Guide to Shotcrete. The mixing equipment shall be capable of thoroughly mixing the specified materials in sufficient quantity to maintain continuous placing.  Ready-mix shotcrete complying with ASTM C 94 may be used.

4550.3.7	Delivery Equipment

The equipment shall be capable of delivering the premixed materials accurately, uniformly, and continuously through the delivery hose. Recommendations of the equipment manufacturer shall be followed on the type and size of nozzle to be used and on cleaning, inspection, and maintenance of the equipment.

4550.3.8	Air Supply

The Contractor shall provide a supply of clean, dry air adequate for maintaining sufficient nozzle velocity for all parts of the work and, if required, for simultaneous operation of a suitable blowpipe for clearing away rebound.

4550.3.9	Application of Shotcrete

Shotcrete shall be produced through wet-mix process using Portland cement, coarse and fine aggregates, water, and admixture mixed to provide a proper consistency to allow spraying using compressed air.

The cement, admixtures except accelerator, and water shall be thoroughly mixed in the mixing facility to obtain sufficient consistency so that freshly mixed shotcrete can be conveyed through a delivery hose to a nozzle whereby shotcrete is accelerated by means of compressed oil-free dry air.  The accelerator for the wet-mix process shall be added to the shotcrete mixture in such a way that the quantity can be properly regulated and the material uniformly dispersed throughout the shotcrete when it is applied.

Shotcrete will be applied on the tunnel crown and walls in combination of rock bolts, steel ribs, and wire mesh.

Time is of the essence for work associated with shotcrete application. Therefore. laboratory and field-testing shall commence as soon as possible after the Commencement Date in order to obtain an approved shotcrete mix before it is necessary to apply shotcrete to the permanent work.

4550.3.10	Shotcrete Nozzle Operators

The Contractor shall submit a resume for each nozzle operator certifying that each has not less than 2 years of experience for the particular type of shotcrete to be applied.  The resume shall include company name, address, and telephone number, name of supervisor, and detailed description of work performed.

Qualifications of additional nozzle operator throughout the job shall be similarly submitted for approval.

Each shotcrete crew shall demonstrate to the satisfaction of the Engineer, acceptable proficiency in the application of shotcrete of field trial quality to vertical and overhead test panels before beginning production work.

The nozzle operator and shotcrete crews shall also produce the shotcrete test panels for mix design evaluations.

- Placement Control

Thickness, method of support, air pressure, and water content of shotcrete shall be controlled to preclude sagging or sloughing off.  Shotcrete placement shall be discontinued or suitable means shall be provided to screen the nozzle stream if wind or air currents cause separation of the nozzle stream during placement.

- Placement around Corners

Horizontal and vertical corners and any area where rebound cannot escape or be blown free shall be filled first.

- Placement around Reinforcement

The nozzle shall be held at such distance and angle to place material behind reinforcement before any material is allowed to accumulate on the face of the reinforcement.  Shotcrete shall not be placed through more than one layer of reinforcing steel rods or mesh in one application unless demonstrated by preconstruction tests that steel is properly encased.

- Placement Precautions

The following precautions shall be taken during placement.

- Placement shall be stopped if drying or stiffening of the mixture takes place at any time prior to delivery to the nozzle. and

Rebound or previously expended material shall not be used in the shotcrete mixture.

- Repair of Defects and Core Holes

Defects

Defective areas larger than 150 cm2 or as otherwise identified by the Engineer shall be removed and replaced with fresh shotcrete at the cost of the Contractor.  These defects include honeycombing, lamination, dry patches, voids, or sand pockets.

Repair

All repairs shall be made as soon as practicable after the deficiency is discovered.  All unacceptable materials shall be removed and repaired by the Contractor at its cost in accordance with the method approved by the Engineer.

Core Hole

Core holes shall not be repaired with shotcrete.  Instead, they shall be filled solid with a dry-pack mixture, approved by the Engineer, after being cleaned and thoroughly dampened.

4550.3.11	Acceptance Criteria

Final acceptance of the Shotcrete will be based on compressive strength results obtained from cores of test panels and shotcrete placements.

- Compressive Strength

The average compressive strength of cores taken from the structure and test panels, representing a shift or not more than 38 m3 of shotcrete (tested at 28 days) shall be 18 N/mm2 or more, with no individual core less than 85 percent of the required minimum compressive strength.

- Test Panels taken during Actual Applications

For every shift or every 38 m3 of shotcrete placement, at least one sample panel fabricated in accordance with ASTM C 1140 shall be made. Three (3) cores at the age of 24 hours and three (3) cores at the age of 28 days.

Core testing shall be made in accordance with ASTM C42, Standard Test Method for Obtaining and Testing Drilled Cores and Sawed Beams of Concrete AASHUTO No. T24, core samples shall be taken perpendicular to test panels in accordance with requirements of ASTM C 1140.

- Rejection

Shotcrete placement found not to be in accordance with compressive strength acceptance criteria 18 N/nm2 at 28 days, or otherwise unacceptable due to cracking, lack of water-tightness, the presence of voids (emitting voided sound when knocked by hammer), or improper placement, shall not be accepted. Payment shall not be made for any unaccepted shotcrete placement.

The Engineer may direct the Contractor to remove and replace rejected shotcrete or make necessary corrections. Corrections deemed necessary (in the opinion of the Engineer) may include installation of additional shotcrete (with or without reinforcement), the placement of additional rock bolts, partial removal and replacement of shotcrete or other measures.

All corrective work and associated costs incurred by the Contractor for accomplishing corrective work or removing and replacing unaccepted shotcrete shall be made good at the cost of the Contractor.

4550.4	Method of Measurement

Shotcrete applied and removed as shown on the Drawings will not be measured separately for individual payment. Payment for accepted shotcrete is deemed included in the unit of measurement for each excavation profile described in Section 4300 [Tunnel Excavation].

No deduction will be made for sections removed for construction of cross passages/niches and the like.

SECTION 4600 - ROCK BOLT

4601	Descriptions

This work consists of furnishing and installation of grouted rock bolts as rock reinforcement in the tunnel opening.

Rock bolts referred to in this Specification Section are fully grouted over the whole length and principally installed untensioned at the arch section, sides or face of a tunnel, locally or systematically, during excavation. Together with shotcrete they provide a bearing force by the formation of a rock-arch and become a part of tunnel support system.

4602	Material Requirements

4602.1	Grouted Rock Bolts

Rock bolts shall be fabricated from steel bars for concrete reinforcement as specified on the Drawings. The rock bolts shall be marked with the ultimate (fracture) load. The outer end of anchor rod shall be threaded counter-clockwise along a length of at least a 150-mm. Threaded end of rock bolts shall be coated with grease and packed with PVC cloth or other materials for protection from damage.

The Contractor shall submit manufactures data certifying the properties and strength of rock bolts to the Engineer for review and approval at least 28 days prior to intended use.

The projected end of anchor and sharp edges of the washers and bearing plates shall be covered with cement mortar or other materials acceptable to the Engineer. The main purpose of covering is to protect the waterproofing sheet from potential damage.

The physical properties of the rock bolt shall satisfy the minimum requirements of Standard Specifications for Tunnelling – 2006 Mountain Tunnels published by Japan Society of Civil Engineers as listed below.

| Classification | CODE | Nominal Diameter (mm) | Physical property (threaded part) |  |  | Physical property (raw material) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Cross area (mm2) | Yield load (kN) | Fracture load (kN) | Cross area (mm2) | Yield load (kN) | Fracture load (kN) |
| >117.7kN | SD345 | D25 | 353.0 | 121.8 | 173.0 | 507.0 | 174.9 | 248.4 |
| >176.5kN | STD510 (FE500) | TD24 (D32) | 353 | 180.0 | 243.6 | 446.0 | 227.5 | 307.7 |

4602.2	Bearing Plates, Washer, and Nuts

All nuts and washers shall conform to rolled steel for general structure, Grade D SS400 manufactured according to JIS 3101, and be of the sizes and dimensions shown on the Drawings or as indicated in the Bills of Quantities.

The Contractor shall submit manufactures data certifying the properties and strength of all nuts, washers and bearing plates to the Engineer for review and approval at least 28 days prior to intended use.

4602.3	Cement Mortar

Cement mortar for grouting of rock bolts shall be approximately one-part cement and one-part sand mixed with sufficient water to provide a consistency that shall enable grouting upward into vertical holes. The water cement ratio of the mortar shall be between 0.35 and 0.45. The compressive strength for 5-cm cube specimens at 1-day shall be not less than 10-N/mm2 when tested in accordance with ASTM C579 Standard Test Methods for Compressive Strength of Chemical-Resistant Mortars, Grout, and Monolithic Surfacing and Polymer Concrete. The 28-day compressive strength of the cement mortar shall be at least 24N/mm2.

The Contractor may use commercially produced and packaged cement mortars, provided they meet the compressive strength requirements of these specifications.  Mixing and application of commercially produced cement mortars shall be in accordance with manufacturer’s instructions and recommendations. The Contractor shall provide manufactures information and data (with mixing and application information) to the Engineer for review and approval at least 28 days prior to the intended use.

Prior to the use of any cement mortar mix and/or a commercially produced mortar product, the Contractor shall provide a sample mix in the presence of a representative of the Engineer. After obtaining the approval of the Engineer, the Contractor shall not deviate from his mix design without the consent of the Engineer. The Engineer may at any time direct the Contractor to provide and test any number of cement mortar cubes. The Contractor, at no additional cost, shall accomplish such testing.

Sand used with cement mortar mixes shall be natural or manufactured sand conforming to the requirements of ASTM C 144 Standard Specification for Aggregate for Masonry Mortar, and having the following gradation;

| Sieve Size | Finer – % by weight (Natural Sand) | Finer – % by weight (Manufactured Sand) |
| --- | --- | --- |
| No.4 (4.75 mm) | 100 | 100 |
| No.8 (2.36 mm) | 95 to 100 | 95 to 100 |
| No.16 (1.18 mm) | 70 to 100 | 70 to 100 |
| No. 30 (600 μm) | 40 to 75 | 40 to 75 |
| No. 50 (300 μm) | 10 to 35 | 20 to 40 |
| No.100 (150 μm) | 2 to 15 | 10 to 25 |
| No. 200 (75 μm) | - | 0 to 10 |

The Contractor shall provide test results and necessary data, including sieve analyses, to the Engineer for review and approval at least 28 days prior to the commencement of bolt grouting operations. Aggregates will be accepted on the basis of certificates of compliance and test reports that show the material meets the quality and grading requirements of these specifications.

Cement used for cement mortar mixtures shall be Type I, II, or V Portland Cement conforming to the requirements of ASTM C 150 Standard Specification for Portland Cement. Certificates attesting that the cement meets specification requirements shall be submitted to the Engineer for review and approval at least 28 days prior to the commencement of bolt grouting operations. Portland Cement will be accepted on the basis of a manufacturer's certificate of compliance, accompanied by mill test reports that the material meets the requirements of these specifications. At the expense of the Contractor, when/if directed by the Engineer, the Contractor shall perform tests to verify the cement certification. Cement shall be rejected if test results are not satisfactory.

Water used for cement mortar mixtures shall be fresh, clean, potable, and free of injurious amounts of oil, acid, salt, or alkali.

The Contractor may at his discretion, use a set-accelerating admixture which shall have a chloride content not exceeding 1% by weight and meet the requirements of ASTM C 494 Standard Specification for Chemical Admixture for Concrete, Type C or E.  Chemical admixtures that have been in storage at the project site for longer than 6 months shall be subject to retesting at the expense of the Contractor when/if directed by the Engineer and shall be rejected if test results are not satisfactory. Certificates attesting that the admixtures meet specification requirements shall be submitted to the Engineer for review and approval at least 28 days prior to the commencement of bolt grouting operations.

4603	Construction Requirements

4603.1	Installation of Rock Bolts

- Cement mortar grouting of drill holes shall proceed continuously from the end of the drill hole to the mouth, until the whole length of hole is completely filled.

Soon after filling the drill hole with grout, rock bolt shall be inserted.

The diameter of drill holes shall be at least 1.5 time of the rock bolt diameter, but not more than 2 times.

All drill holes shall be completely cleaned of dust, sludge and debris before installation of grout.

4603.2	Improper Advancement of Rock Bolts

In cases where a rock bolt cannot be advanced to the required depth, due to a collapse of the borehole wall, failure of the rock bolt or other physical difficulties that may, in the opinion of the Engineer, cause the bolt to be unable to provide the necessary strength, installation shall be discontinued and the Contractor shall either enlarge the hole, re-grout and reinstall, or provide an alternative anchor bolt by drilling a new hole nearby the failed rock bolt as directed by the Engineer.

The failed rock bolt shall be retracted and the hole shall be re-grouted to fill the gap. If the failed rock bolt cannot be retracted, the failed rock bolt shall be cut flush with the borehole mouth and covered the cut edge with cement mortar. No additional payment will be made for unsuccessful rock bolt installation.

4603.3	Drilling for Rock Bolts

Bore holes shall be drilled to a depth of 300mm beyond the specified length of rock bolts and normal to the rock surface or within the maximum crossed axes angle of 15 degrees formed by the washer plate and the tendon.

Deviation from these requirements will not be acceptable unless the Engineer has agreed to such deviations otherwise.

4603.4	Cutting off and Final Rock Bolt Preparation

After it has been confirmed, that no additional tunnel deformations are recorded and the Contractor has been advised by the Engineer to proceed, the Contractor shall provide final rock bolt preparation. Final rock bolt preparation shall consist of cutting off the excessive rock bolt length flush with tightening nuts and covering the rock bolt, nut and washer and rock bolt plate with cement mortar the mix proportion of which is acceptable to the Engineer.

4603.5	Pullout Test and Quality Control

Testing Procedures

The tunnels have been designed partly based on Standard Specifications for Tunnelling - 2006 Mountain Tunnels published by Japan Society of Civil Engineers.

The frequency of the pullout tests shall be conducted every 20 m in the initial stage of the excavation, then every 50 m: about 3 bolts per section respectively (one in the crown, arch and side wall).  Rock bolts will be judged to be adequate, if it exhibits about 80% of the required pullout strength; required pullout strength is set to 117.7kN(SD345),176.5kN(STD510) thus, rock bolts will be tested to confirm the design pullout strength of 95k(SD345),145kN(STD510) at the age of 3 days. In general, the pullout strength is set to the yield strength of the threaded portion of rock bolts.

The Engineer may designate bolts for testing and witness all tests. The Contractor shall record all tests in a format acceptable to the Engineer. Test records shall provide for signature by the Engineer and the Contractor of all witnessed tests and clearly indicates all bolts that are accepted by the Engineer based on tests conducted. The Contractor shall provide copies of all signed test records to the Engineer daily.

The Engineer may adjust the frequency and number of rock bolt pullout tests, to assure the quality of rock bolt installation. The Contractor at no additional cost shall accomplish verification testing as required by the Engineer.

Rock Bolt Testing Equipment

All equipment for testing of rock bolts shall be provided by the Contractor and be available so that testing can be accomplished at any time at the discretion of the Engineer.

The rock bolts can be pulled using a torque wrench or a hydraulic jack, as approved by the Engineer, capable of applying load up to the pullout load (95kN,145kN) of the tested bolt (threaded portion). The testing equipment shall be calibrated every three months unless otherwise approved by the Engineer. The Contractor shall provide the operating manuals of the torque wrench and/or the hydraulic jack, as the case may be, including the most recent calibration results to the Engineer for information and approval prior to the commencement of any rock bolt installation.

Evaluation Criteria

Efficiency of grouted rock bolts will be evaluated by pullout testing as described herein before. Tested bolts will be deemed acceptable if they withstand the pulling load of 50% of the accepted yield strength of 95kN(145kN). Thus, a rock bolt is considered adequate if it exhibits 50kN(70kN) of the yield strength.

4603.5	Submittals

In accordance with requirements of this Specification Section, the Contractor shall provide the following information to the Engineer for his approval not later than 28 days before the intended commencement.

- Certificates of rock bolts, bearing Plates, washers, and anchor nuts.

Detail description of stressing methods, equipment to be used and its calibrations

Cement mortar

- Mix design including water cement ratio, compressive strength and sand gradation and data.

Corporate information if the Contractor proposes to use a commercially produced mortar grout, including product technical brochure and test certificates.

Certificates of cement such as mill certificates.

Certificates attesting that the admixtures meet specification requirements.

A complete list of equipment he intends to use for rock bolt installation and testing, noting   intended applications of all equipment, for review and comment by the Engineer.

Cement mortar test results,

4604	Method of Measurement

Rock bolts installed and removed as shown on the Drawings will not be measured separately for individual payment. Payment for rock bolts is deemed included in the unit of measurement for each excavation profile described in Section 4300 [Tunnel Excavation].

No deduction will be made for sections removed for construction of cross passages/niches and the like.

In the event that supplemental rock bolt is instructed by the Engineer, measurement for payment for the individual installation will be performed according to the unit of measurement derived from the breakdown of the contract rates included in Section 4300 [Tunnel Excavation].

4605	Basis of Payment

In the event that the Engineer instructs the Contractor to install supplemental rock bolt, payment for accepted quantity will be made separately at the unit rates per unit of measurement derived from the cost breakdown of work items in Section 4300 [Tunnel Excavation]. Payment will be full compensation for the incidental fixing work including materials

- The required strength of the rock bolts at the thread portion is approximately 95kN and 145kN. If testing of a group of rock bolts (with a representative number of tests) indicates bolts to be below the required strength, the works shall be rejected and respective payment shall be suspended until the failed bolts are replaced and re-installed, and results of re-testing are approved by the Engineer. In any case that the defect continues, the Contractor shall submit to the Engineer, for approval, a method statement to solve the situation.

- Bolt tests showing less than 50kN(or70kN)– no payment shall be made for the number of bolts in the group equivalent to the percentage represented by the number of bolts tested in the grouping.

- (ⅱ)　Bolt tests showing more than 50kN(or70kN)  but less than 95kN(or145kN) – payment shall be made at 50% of the unit rate for the number of bolts in the group equivalent to the percentage represented by the number of tests in this grouping.

| Pay Items | Descriptions | Units |
| --- | --- | --- |
| 4600-01 | Rock Bolts 2.0 m long | Nos. |
| 4600-02 | Rock Bolts 3.0m long | Nos. |
| 4600-03 | Rock Bolts 4.0m long | Nos. |

SECTION 4650 - WATERPROOFING

4650.1	Description

The work consists of installation of drained waterproofing system prior to placing the lining concrete. The tunnel waterproofing system is required to prevent groundwater inflow into tunnels.

The waterproofing system, installed between the shotcrete and concrete lining, is comprised of two layers; the non-woven geotextile outer layer and the waterproofing membrane inner layer.

4650.2 	Material Requirements

The material of the waterproofing membrane shall be Ethylene Vinyl Acetate (EVA) conforming to the requirements noted in Table 4650-1. Alternative international equivalent standards to the standards listed in Table 4650-1 may be acceptable with the approval of the Engineer.

The non-woven geotextile is a backup material for the waterproofing membrane and it shall be made of polyester and conform to the requirements of Table 4650-2. Alternative international equivalent standards to the standards listed in Table 4650-2 may be acceptable with the approval of the Engineer.

4650.2.1	Requirements for Waterproofing Membrane

- The membrane length in each roll of material shall be supplied to coincide with placement along the peripheral length of the tunnel without longitudinal joints. Longitudinal joint shall only be permitted as indicated on the Drawings.

Material Requirements and test standards as shown on Table 4650-1.

- Table 4650-1 – Requirements and Test Standards for EVA Waterproofing Membrane

| Properties | Specified Value | Standards (See Note 2) |
| --- | --- | --- |
| - Specific gravity | 0.95±0.05 | JIS K 6773 |
| Hardness (scale: Shore A) | 98 max. | JIS K 6773 |
| Variance of Thickness | Average thickness at 5 points in traverse direction shall be more than the designated thickness, and minimum thickness is more than 95% of the designated thickness. | JIS A 6008 |
| Min. Thickness | 0.8 mm | JIS A 6008 |
| Min. Tensile Strength | 16 N/mm2at 200C | JIS K 6773 |
| Elongation | 600% at 200C | JIS K 6773 |
| Min. Tear Strength | 500 N/cm | JIS K 6252 |
| Flexibility | Viable at -300C | JIS K 6773 |
| Weight Change (Alkali Resistance) | Within ± 1% | JIS K 6773 |
| Min. Seam Strength | 20% | JHS 706 or ASTM D6392 |

Notes:	1.	Seam Strength is defined as the strength at welded seam to the tensile strength.

- 2.	 For JIS standards, approved equivalent ASTM can be adopted. JHS 706 is a test method for

- strength of welded seams established by Nippon Expressway Company Limited (NEXCO).

4650.2.2	Requirements for Non-Woven Geotextile

The non-woven geotextile is a backup material for the waterproofing membrane and it shall be made of polyester and conform to the requirements of Table 4650-2.

Table 4650-2

Requirement and Test Standards for Non-Woven Geotextile Protective Fleece for EVA Waterproofing Membrane

| Properties |  | Unit | Specified Value | Test Standards (See Note) |
| --- | --- | --- | --- | --- |
| - Unit Weight |  | g/m2 | 300 min | JIS L 1096 |
| - Thickness at 19.6 x 10-4 N/mm2 load (20 g/cm2) |  | mm | 3.0 min | JIS L 1096 |
| - Tensile Strength | Vertical | N/50 mm (kgf/5cm) | 196 min (20 min) | JIS L 1096 |
|  | Horizontal |  | 49 min (5 min) |  |
| - Elongation | Vertical | % | 20 min | JIS L 1096 |
|  | Horizontal |  | 50 min |  |
| - Tear Propagation Strength | Vertical | N (kgf) | 49 min (5 min) | JIS L 1096 |
|  | Horizontal |  | 49 min (5 min) |  |

Notes:	1.	For JIS standards, approved equivalent ASTM can be adopted

4650.2.3	Transportation, Storage and Testing of Materials

- Transportation

- All materials shall be of originally packaged at the manufacturing plant. Packaging shall be sufficient to protect materials from damage, deterioration and exposure during shipping and storage. To prevent ultra-violet exposure during transportation and storage all non-woven geotextile materials shall be packaged with a black covering.

The outer face of all material packing shall clearly describe material and note the size or quantity of material, the manufacturer's name, material type number, lot number and manufacturing date.

- Storage

- All material shall be stored in the dry and well-ventilated warehouse in accordance with manufacture requirements.

Material temporarily stored outdoors shall be properly covered for protection against exposure and deterioration. No damaged material shall be used. All damaged materials shall be removed from the site at the expense the Contractor.

- Testing of Materials

Materials shall be supplied with certified test results for each lot from the manufacturer. Testing of material lots shall be accomplished and certified by an independent laboratory. All materials transported to the site shall be verified to be applicable to a certified and tested lot. Only materials from lots with acceptable test results shall be used. Copies of all certified tests for each lot of material shall be submitted to the Engineer prior to use of material.

4650.3	Construction Requirements

4650.3.1	General Requirements

- The surface to receive the Waterproofing membrane shall be clean and free of loose and foreign material.  All protruding objects such as nails, rock bolts, pipes, fittings and reinforcing steel shall be ground smooth, so as not to penetrate any layer of the membrane system. Shotcrete surfaces shall be checked and approved prior to membrane placement. The Contractor shall employ a manufacturer’s representative to inspect and approve the preparation of shotcrete surface for waterproofing membrane placement.

All membrane layers shall be installed and constructed in conformity to approved shop drawings and manufacturer’s requirements and recommendations.

The Contractor shall employ a manufacturer’s representative to supervise the placement of the membrane system. All work shall be executed by skilled labour under the guidance and supervision of a manufacturer’s representative.

The waterproofing shall be installed as specified and shown on the Drawings, or as appropriate, to accurately fit within the dimensions shown on the Drawings, or as approved by the Engineer.  Additionally, the waterproofing membrane together with geotextile, applied uniformly and continuously from the shotcrete wall, shall be extended to cover the entire Mole Drainage pipe and surrounding filter material, as detailed on the Drawings, and shall be subject to approval by the Engineer.  If necessitated, any joining between the membrane covering the shotcrete wall and the membrane extended over and under the mole drainage pipe, shall be heat welded watertight in accordance with methods and specification described herein.  Such welding connection shall be subject to all relevant bonding tests herein, and shall be subject to approval by the Engineer.

4650.3.2	Installation of Non-Woven Geotextile

- Non-woven geotextile shall be fastened onto the shotcrete face using “waterproofing disks” supplied by the membrane manufacturer. The spacing between disks shall not be more than 60 cm, and not be less than 4 disks per square meters.

The overlapping length of non-woven geotextile shall be not less than10 cm.  Longitudinal joints shall be installed with no more than two loops.

To avoid damage to the material, the non-woven geotextile shall be installed as close to shotcrete surface as possible, without an excessive pulling force.

4650.3.3	Installation of Waterproofing Membrane

- The waterproofing membrane shall be fixed on tunnel waterproofing disks installed with the geotextile by means of heat welding.

Joints shall be installed by means of heat welding in accordance with the manufacturer’s requirements and recommendations. Overlapping lengths of the waterproofing membrane shall be at least 8 cm. They shall be joined with double seams using an approved heat welding method.

The waterproofing membrane shall be installed with no longitudinal joints along its peripheral length.

In locations where heat welded double seams cannot be made, such as at intersection points, where pipes or other objects are required to pass through the membrane, at niches and inverts, the Contractor shall submit applicable details and requirements with his shop drawings for approval of the Engineer. Jointing using melted connection procedures other than double seam procedures shall also be in accordance with manufacturer’s recommendations and requirements and be approved by the Engineer.

All double seam waterproofing membrane joints shall be air pressures tested to assure proper bonding. Air pressure test and requirements shall be in accordance with the manufacturer’s requirements. All non-double seam waterproofing membrane joints shall be subject to vacuum bell testing in accordance with the manufacturer’s requirements. At least 28 days prior to commencing with the installation of waterproofing membrane, the Contractor shall submit testing procedures to the Engineer for approval. The Contractor shall be responsible for providing all equipment and materials necessary for proper joint testing as recommended by the manufacturer. The Contractor shall advise the Engineer prior to testing of joints. A manufacturer’s representative shall supervise all joint testing. All joints that fail to meet the requirements of the joint test shall be resealed and tested.

During the installation of the membrane lining, sample joint test specimens shall be made for every 1000 linear meters of double seam joint installed and for every 500 linear meters of non-double seam joints installed. An independent laboratory, approved by the Engineer, shall test all specimens. Testing and sample preparation shall be in accordance with the requirements of JIS, ASTM or internationally recognised standards approved by the Engineer for the EVA membrane as shown in the above Tables 4650-1. The Contractor shall be responsible for testing and test reporting costs including sample preparation, and transportation.

Damages to the membrane, including penetrations, rips and/or tires, shall be properly repaired. Repairs shall include proper placement (in accordance with recommended manufacture procedures) of a membrane section overlapping at least 15 cm around the circumference of the section to be repaired. All repair areas shall be vacuum bell tested tin accordance with requirements and procedures recommended by the manufacturer. The Contractor shall submit repair-testing procedures to the Engineer for approval. The Contractor shall be responsible for providing all equipment and materials necessary for proper repair testing as recommended by the manufacturer. The Contractor shall advise the Engineer prior to testing of repairs. A manufacturer’s representative shall supervise all repair testing. All repairs that fail to meet the requirements of repair test shall be reinstalled and retested.

During construction, except for its own weight, the membrane shall not be subject to external forces.

4650.3.4	Field Tests for Hermeticity of Joints and Repairs

- Air pressure test

Using equipment and procedures, as required by the manufacturer, compressed air to a pre-determined pressure (1.0 to 2.0 kg/cm2or as recommended by the manufacturer) is applied to joints. The pressure is maintained for a period of time (approximately 5 minutes – as recommended by the manufacturer).  Acceptance of the joint is based on an allowable excepted pressure drop (as recommended by the manufacturer) over the period of time the pressure is maintained on the joint.

Vacuum Bell Test

Using equipment and procedures recommended by the manufacturer, a vacuum test cup is used to draw air out of the test section with a pre-determined pressure (0.2 - 0.5 kg/cm2 or as recommended by the manufacturer).  Observance of a pressure needle indicator on the testing device indicates acceptance or rejection of the joint.

Note: The above field testing procedures are incorporated in the manufacture's specifications to provide the Contractor with a general understanding of the field-testing required. Testing equipment, testing procedures and acceptance criteria for all field testing shall be verified with the waterproofing manufacturer and accomplished in accordance with the manufacturer's recommendations and requirements, as approved by the Engineer.

4650.3.5	Submittals

The Contractor shall submit Three (3) copies of following documentation and data to the Engineer for approval at least Six (6) months before scheduled commencement of the installation, considering the time required for manufacturing and delivery to the Site.

- Shop Drawings

The Contractor shall submit shop drawings for non-woven geotextile and waterproofing membrane showing the procedures how they should be fabricated, assembled and installed at the Site. The following information shall be included in the submission, but they may be presented as installation manual/procedures.

- General installation procedures and requirements,

Overlapping requirements and treatment,

Portal installations,

Repair methods and procedures,

Anchoring systems, devices and procedures,

Treatment for membrane penetrations including construction requirements and procedures for steel bar supports, rock bolts, projecting articles, and pipes penetrations, and any other drawings and information necessary for and to fully describe the complete installation of the waterproofing system.

- Manufacturer’s Data

The Contractor shall submit manufacturer’s data and information which shall include, but not limited to:

- Original product catalogues noting material type and related technical data and information,

Test reports of material properties and seam strength shall be issued and signed by an independent testing laboratory. Reports shall be certified by the testing agency with notice that tests were conducted on representative samples of the manufacturer’s product,

Construction and installation procedures and requirements including procedures for installation of membrane joints and membrane repairs,

Testing requirements and procedures for material joints and repairs,

A copy of the agreement (excluding financial terms) between the Contractor and supplier detailing material supplies, shipping agreement, technical support and assistance, warrantees and validity of agreement (the valid period thereof shall not be shorter than the construction period of the work), and

Manufacturer’s performance certification with past performance records on highway tunnels with placement area greater than 30,000 square meters.

- Specimen/Samples

The Contractor shall submit samples of the following:

- Non-woven geotextile: (one-piece) 1m x1m,

Water-proofing membrane: (one-piece) 1m x 1m,

Anchors and fixing blocks: one set,

Sample of welded joint: one-piece 1 meter long, and

Assembled sample: one whole set.

4650.4 	Method of Measurement

Waterproofing system, geotextile and membrane combined, will be not measured separately for individual payment. The waterproofing system will be considered as integral part of concrete lining. Payment for waterproofing installed as shown on the Drawings is deemed included in the unit of measurement for concrete lining described in Section 4700 [Concrete Lining].

4650.5	Basis of Payment

- Payment for waterproofing is included as an integral part of the concrete lining. Costs of labour, materials, loss from overlapping, equipment, scaffolding, testing, inspection, technical guidance, power, storage, transportation, treatment of placing face anchor and fixing blocks and any other costs related for the Works described in this section shall be included in the concrete lining work.

- Unaccepted waterproofing sections shall be entirely removed and replaced, including all required testing. Replacements shall not be measured for payment.

SECTION 4700 – CONCRETE LINING

4700.1	Description

The work consists of cast-in-place concrete lining which is cast against the waterproofing systems installed on top of shotcrete lining. Cast-in-place concrete lining will be used as final lining and therefore the undecorated surface (mainly arch section) shall be finished with the required accuracies as specified herein.

For payment purposes, the concrete lining and the waterproofing systems are combined as a single pay item for which payment is made after completion of concrete lining.

4700.2 	Material Requirements

Materials used in cast-in-place concrete shall conform to the requirements specified under Section 2000 of the Standard Specifications for Road and Bridge Works ASAD, 2058 / July 2001 or equivalent international standards approved by the Engineer.

Steel reinforcing bars shall conform to the requirement specified in Clause 620 of the Standard Specifications for Road and Bridge Works ASAD, 2058 / July 2001 or equivalent international standards approved by the Engineer.

4700.3	Construction Requirements

4700.3.1	Concrete mix Design Approval

The standard mix design for wet type concrete is as follows.

| Compressive Strength at 28days σ28 | Slump | W/C | Max. Aggregate | Unit Cement Content | fiber-mixing ratio | application |
| --- | --- | --- | --- | --- | --- | --- |
| 18 N/mm2 | 15±2.5cm | 60% | 40mm | 270kg/m3 | - | CⅠ、CⅡ、DⅠ |
| 18 N/mm2 | 15±2.5cm | 60% | 40mm | 340kg/m3 | 0.3(vol%） | DⅢ |

Contractor shall submit the proposed concrete mix designs to the Engineer for initial evaluation and comment.  No sooner than 14 days after mix design submittal, the Contractor shall (after giving the Engineer at least 48 hours prior notice) prepare test panels using the proposed concrete mix design in the presence of the Engineer.

4700.3.2	Formwork

- Formwork shall be of a mobile carriage type equipped with external form vibrators and windows on the shell for inspection and for ensuring sufficient consolidation of concrete. The Contractor shall submit design calculations and shop drawings of formwork to the Engineer for his approval.

Design calculations and shop drawings shall clearly indicate materials and their grades according to the accepted standards, and they be delivered to the Engineer at least 28 days before starting fabrication.

The external vibrators shall be electrically driven type with sufficient vibration effect to achieve sufficient consolidation of fresh concrete. No fuel combustible vibrator will be permitted inside tunnel.

The travelling devices, hydraulic jacks, external vibrators, and other outfitting shall be easily replaceable and must also be available for replacement.  The Contractor shall have sufficient spares in hand for emergency replacement.

Before erecting formwork, damages to the waterproofing membrane shall be repaired in a manner acceptable to the Engineer.

The Contractor shall notify the Engineer before batching begins for placement of concrete. Placement shall not begin until all preparations are complete.

The Engineer will have the authority to stop or delay concrete placement if (in the opinion of the Engineer) formwork arrangement and concrete production are not adequate or are not properly prepared. The Contractor shall be responsible for all costs and time necessary to make good as required by the Engineer.

Forms shall be constantly monitored and their position adjusted as necessary during concrete placements.

4700.3.2	Concrete Placing

- Concrete shall be placed with concrete pumps or other acceptable means approved by the Engineer. The concrete shall be supplied to the concrete pump continuously. Stand-by-concrete placing equipment, including concrete pumps shall be provided for each pour to ensure smooth and uninterrupted placement in case of equipment breakdown.

When pumping is completed, concrete remaining in the pipeline shall be ejected without contamination of concrete in place.  After each operation, equipment shall be thoroughly cleaned, and flushing water shall be wasted outside of the forms.  Grout used to lubricate the pumping equipment at the beginning of the placement shall not be incorporated into the placement.

Depositing of the concrete shall be so regulated that it may be effectively consolidated in horizontal layers 500 mm or less in thickness with a minimum of lateral movement.  The amount deposited in each location shall be that which can be readily and thoroughly consolidated.  Sufficient placing capacity shall be provided so that concrete placement can be kept plastic and free of cold joints while concrete is being placed.  Concrete shall be placed by methods that will prevent segregation and/or loss of ingredients.

The maximum fall height shall not exceed 1.5 meter. If the free-falling height of the concrete exceeds 1.5 meters, flumes, tremies or the like acceptable to the Engineer shall be used to avoid the segregation of concrete constituents

The maximum rising speed of the concrete shall not exceed 2.0 m/h.  Concrete shall be placed alternately between the sidewalls to maintain balance of the pressure.

The maximum thickness of a concrete layer shall not exceed 0.5 meter per lift.

4700.3.3	Compaction of Freshly Place Concrete

- Freshly placed concrete shall be consolidated by external formwork vibrators supplemented by poker vibrators approved by the Engineer. The vibration shall be sufficient to remove all undesirable air voids from the concrete, including the air voids trapped against forms and construction joints.

The Contractor shall avoid excessive use of vibrators. Excessive vibration will cause segregation and excessive bleeding.

Poker vibrators should be used to penetrate into the previous layer to uniformly blend the previous concrete layer with the freshly poured concrete.

4700.3.4	Finishing Tolerances

- Unless the Engineer instructs otherwise, formwork shall be provided to achieve the tolerance prescribed in this Section, which is a surface finish category with smooth and of uniform texture and appearance. For this class, the formwork lining shall leave no stain on the concrete and shall be so joined and fixed to its backing that it imparts no blemishes. It shall be of the same type and obtained from only one source throughout any one structure. The Contractor shall make good any imperfections in the finish. Internal ties and embedded metal parts shall not be used. Materials used shall be subject to the Engineer's approval.

In all cases the Contractor shall maintain the tunnel centre line within a tolerance of 5-mm throughout the tunnel length. This target tolerance is achievable since the inner dimensions of the tunnel is designed with a maximum 50-mm of allowance to the minimum clearance limit of the tunnel.

Notwithstanding the maximum allowance of 50-mm to the minimum clearance limit, the maximum deviation of finished concrete surface shall not exceed 20-mm inward at any point. In general, outward deviation will not be acceptable as outward deviations reduces the thickness of concrete lining.

The gap between the previous concrete lining and the freshly placed concrete shall not exceed 5-mm. Gaps thus formed shall be scabbled and smoothened as approved by the Engineer. The Contractor shall submit to the Engineer for approval a proposed method for making such gaps smooth.

4700.3.5	Formwork Removal

- It is recommended from the empirical knowledge that tunnel formwork may be removed about 12 hours after concrete placing with the Engineer's approval. Approval of the Engineer to remove forms does not in any way relieve the Contractor of its obligation to delay the removal of forms and shoring until the concrete has attained sufficient strength to support its own weight.  The Contractor shall demonstrate that the concrete at 12-hour age has attained sufficient compressive strength.

The formwork shall be removed slowly with due care, as the sudden removal of the formwork gives an uneven shock load on partly hardened concrete.

4700.3.6	Curing and Protection of Concrete

- Cast-in-place concrete shall be continuously cured immediately after stripping by keeping the concrete moist or by applying an approved curing compound (membrane). Curing compound, if approved by the Engineer, can only be applied if the concrete is the finished exposed surface.

All materials and equipment needed for adequate curing and protection shall be available and at the placement site prior to the start of concrete placement.  Concrete shall be continuously cured for at least 7 days for concrete mixed with ordinary Portland cement. If high-early-strength Portland cement is used, the curing period may be reduced to about 3 to 4 days with prior approval of the Engineer.

No fire or excessive heat including welding shall be permitted near or in direct contact with concrete or concrete embedment at any time.

Where wooden form sheathing is left in place during curing, the sheathing shall be kept wet at all times.

Where steel forms are left in place during curing, the forms shall be carefully broken loose from the hardened concrete and curing water continuously applied into the void so as to continuously saturate the entire concrete surface.

Horizontal surfaces may be moist cured by ponding, by covering with a minimum uniform thickness of 50 mm of continuously saturated sand, or by covering with saturated non-staining burlap or cotton mats.

Horizontal construction joints may be allowed to dry for 12 hours immediately prior to placing the next lift.

4700.3.7	Shop Drawings

Apart from the shop drawings prepared prior to formwork fabrication mentioned under Clause 4700.3.1 hereof, the Contractor shall submit tunnel lining shop drawings for review and approval by the Engineer no later than fifty-eight (58) days prior to the start of tunnel lining work. Shop drawings shall note the Contractor’s proposed sequence of lining construction, joint details, all imbedded items and incorporate details and requirements for reinforcing.

4700.4	Method of Measurement

Concrete lining shall be measured in linear meter of completed sections including the secondary lining of the portal canopy sections. Measurement shall be taken along the centre line of the tunnels, based on neat lines and thickness as shown on the Drawings.

No deduction will be made for sections removed for construction of cross passages/niches and the like.

4700.5	Basis of Payment

The accepted quantities will be paid at the contract price per unit of measurement.

Payment shall be full compensation for the work prescribed in this Specification Section. Unaccepted concrete-lining sections shall be entirely removed and replaced at the cost of the Contractor.

The works, excavation, invert concrete, and backfilling, for final lining shall not be measured and paid separately, but shall be deemed included into rates for unit prices of pay-items in this Section.

| Pay Item | Concrete Lining Profile Type | Unit of Measurement |  |
| --- | --- | --- | --- |
| Main Tunnel |  |  |
| 4700-01 | Main Tunnel CI | m |  |
| 4700-02 | Main Tunnel CI-L | m |  |
| 4700-03 | Main Tunnel CII-B | m |  |
| 4700-04 | Main Tunnel CII-L | m |  |
| 4700-05 | Main Tunnel DI-B & BF | m |  |
| 4700-06 | Main Tunnel DIII-A & UA | m |  |
| 4700-07 | Main Tunnel DIII-AF & UAH | m |  |
| Evacuation Tunnel |  |  |
| 4700-08 | Evacuation Tunnel DIIIP-A & UA | m |  |
| Cross Passage |  |  |
| 4700-09 | Cross Passage CI-VP | m |  |
| 4700-10 | Cross Passage CII-VP | m |  |
| Working Adit |  |  |
| 4700-11 | Working Adit DIIIW-AF & UAF | m |  |

SECTION 4750 – INTERIOR FINISH

4750.1	Description

The work consists of interior finish by intumescent paint coating on the walls of the main tunnel throughout the entire length as shown on the Drawings.

Painting of concrete tunnel require better visibility and higher reflective values, enabling the vehicle drivers to travel inside the tunnel with less stress. Furthermore, painting work of higher quality will allow the tunnel monitoring system (Closed Circuit Television; CCTV) to capture undistorted images.

4750.2	Material Requirements

4750.2.1	Paint

- Colour Elements

“x” value and “y” value of the colour element shall be 0.3345 and 0.3478 respectively based on the CIE 1931 x-y chromaticity diagram, or compatible colour elements as approved by the Engineer.

The Contractor shall submit the colour samples to the Engineer for his approval before placing order.

Fire Resistivity

The Contractor is required to propose water-based or solvent-based intumescent paint(s) together with the compatible primers he intend to use for the interior finish of the main tunnel. His proposal shall accompany third party verifications of the test results of ISO 5660-1.

When testing a product according to the current version of ISO 5660, average values of 3 samples shall be taken and the results should satisfy the following requirements;

- Total Heat Release is less than 8MJ/m2,

- Heat Release Rate does not exceed 200kW/m2 in 10 second, and

- No penetration either in the form of cracks or holes.

The proposed intumescent paint shall obtain approval of the Engineer before placing order.

Adhesion Strength

Adhesion strength of intumescent paints shall be tested in accordance with JIS 5600-566 (cross cut method) which is similar to ISO 4624 (pull-off test for adhesion). The minimum adhesion strength shall be not less than 1 N/mm2. If the recommended dry film thickness exceeds 250 μm, the adhesion strength shall be tested in accordance with JIS 5400-8-5.

The Contractor shall submit third party verifications of test results for evaluation and approval by the Engineer.

Scratch Hardness

The proposed intumescent paint shall have the minimum scratch hardness (pencil method) of H3 according to JIS 5600-5-4 Testing Methods for Paint – Part 5 Mechanical Property of film – Section 4: Scratch Hardness (Pencil Method).

The Contractor shall submit third party verifications of test results for evaluation and approval by the Engineer.

Reflection Rate

Initial reflection rate of finished paint surface shall be not less than 60% as tested in accordance with JIS 5600-7-7.

The Contractor shall submit third party verifications of test results for evaluation and approval by the Engineer.

4750.3	Construction Requirements

4750.3.1	Surface Preparation

The surfaces of concrete lining shall be prepared in accordance with the coating manufacture requirements and as follows.

- The concrete surface shall be free from cement laitance, oil grease and loose particles,

If a curing compound was previously applied to the concrete surface it shall be completely removed prior to the coating application, and

Surface irregularities such as air pockets and other surface depressions exceeding 5-mm from surrounding area shall be filled using two components of coating mixed with ordinary Portland cement in a ratio of 1:1, or in accordance with the paint manufactures recommendation or as directed by the Engineer.

4750.3.2	Coating Application

Unless otherwise recommended by the paint manufacturer, two coats of paint shall be applied following recommended primer application. Prior to application in the tunnel, the Contractor shall demonstrate in an open field the painting procedures.

Following permission of the Engineer, painting work may be proceeded in the manner recommended by the paint manufacture using recommended tools (rollers, brushes or other method).

Stains beyond the scheduled paint area or drips on the concrete floor shall be removed in accordance with the manufacturer’s recommendations and to the satisfaction of the Engineer.

4750.3.3	Thickness of Coating

Thickness of dry film shall be not less than the minimum thickness recommended by the paint manufacturer.

- Dry film thickness shall be measured in accordance with ASTM D 1005 – Method A or other internationally recognised standards approved by the Engineer.

The Contractor’s laboratory shall be equipped with necessary equipment which, as required and witnessed by the Engineer shall be checked for calibration.

Additional coatings shall be applied to surfaces where testing indicates there is less than the minimum specified dry-film thickness.

4750.3.4	Protection and Safety Precautions

The Contractor shall vigilantly observe the following safety precautions, failing which the Engineer may suspend the operation until the situations are improved as required.

- Adjacent materials and equipment shall be protected against damage from spillage, dripping, and spatter of coating materials.  Building materials and equipment shall be left clean and with all damaged surfaces corrected.

Forced ventilation for interior spaces shall be provided during application and drying of coatings to prevent the buildup of toxic or explosive concentrations of solvent vapors.

Fire extinguishers of the required quantity and correct type shall be provided to combat flammable liquid fires.

Rags used to wipe up coating materials, solvents, and thinners shall be disposed of by drenching them with water and putting them in a covered metal container.

4750.3.5	Clean-up

- At the end of each working day, discarded paint materials, rubbish, dirty rags, and other similar trash shall be removed from the project.

At the completion of the work, paint spots shall be removed from finish surfaces and the project left in a clean condition.

4750.3.6	Submittals

Manufacturer's Catalogue Data product information shall be submitted to the Engineer for review and approval at least 58 days prior to the Contractor’s intended start of coating work.

Data and information shall include but not be limited to the following:

- detailed analysis of the coating material, with constituents measured as percentages of the total weight of coating and verification of compliance with specification requirements,

- safety data sheets detailing safety precautions, and procedures for handling, applying and storing the coating materials,

- instructions including details of thinning, mixing, handling, and application

- manufacturer's standard color charts and color chips showing manufacturer's recommended finish color in accordance with specification requirements,

- detailed mixing, thinning and application instructions,

- minimum and maximum application temperature,

- curing and drying times between coats,

- detailed application instructions and

- surface preparation requirements.

4750.4	Method of Measurement

The accepted quantity of interior finish shall be measured in the unit of measurement specified in the Bill of Quantities. Defects of the paint shall be removed in a manner recommended by the paint manufacturer and made good for payment to the satisfaction of the Engineer.

4750.5	Basis of Payment

The accepted quantities will be paid at the contract price per unit of measurement. Payment will be full compensation for the work prescribed in this section.

| Pay Item | Description | Unit |
| --- | --- | --- |
| 4750-01 | Tunnel Interior Finish (Painting) | m2 |

SECTION 4800 - DRAINAGE SYSTEM, WALKWAY & PATH

4800.1	Description

The work consists of tunnel Drainage System, Emergency Walkway and Inspection Path. The drainage system is part of the drained waterproofing system to receive inflow of groundwater sealed and collected by the waterproofing systems.

4800.2	Material Requirements

4800.2.1	Drain Pipes

- Unless otherwise specifically indicated in the Drawings, tunnel drain pipes, joints and fittings shall be polyethylene pipes conforming to the requirements of JIS K 6761 or equivalent international standards.

All drain pipes, except short piece of transverse drain to be embedded in the concrete lining, shall be perforated as shown on the Drawings. The perforation shall be approximately 150-mm centre-to-centre along rows, and each row shall be arranged in a staggered pattern so that all perforations lie at the midpoint between perforations in adjacent rows.

Hole size of perforation shall be: 10-mm for centre drain (φ350-mm) and 5-mm for transverse drain (φ150-mm). unless indicated on the Drawings.  Deviation in hole size may be permitted with the Engineer's approval. These requirements do not apply if permeable drainage pipes are used as approved by the Engineer.

The spigot or tongue end of the pipe shall not be perforated for a length equal to the depth of the socket, and perforations shall continue at uniform spacing over the entire length of the pipe.

Detail of sidewall drain outlet connection to the transverse drain varies from one manufacturer to the others. The Contractor shall submit to the Engineer for his approval catalogue or shop drawings and installation manual for the connection he proposes to adopt. Proposal shall be delivered to the Engineer not later than 28 days before the intended date of commencement of relevant work.

4800.2.2	Filter Aggregate/Backfilling Sand

Filter aggregate to be used in the drainage system or shall be single-sized aggregate consisting of 20/40-mm coarse aggregate unless other sizes are shown on the Drawings or as approved by the Engineer.

4800.2.3	Lean Concrete Bedding

Lean concrete bedding provided for drain pipes, side ditches and structures shall conform to the classes or grades as indicated on the Drawings.

4800.2.4	Concrete for Ancillary Structures

Materials used for concrete shall conform to the requirements heretofore specified under Clause 4700.2 of Section 4700. Concrete for ancillary structures such as, Side Ditch, Kerb, Emergency Walkway and Inspection Path shall conform to the size, dimensions and classes or grades as specified on the Drawings.

4800.2.5	Handrails for Emergency Walkway

Handrails (beams, brackets and sockets) shown on the Drawings shall conform to JIS G 3444 (STK 41) or equivalent standards as approved by the Engineer.

Handrails including brackets, sockets, posts and base plates shall be hot dip galvanized to JIS H8641 [Hot Dip Galvanized Coating] according to the thickness of steel, unless approved by the Engineer otherwise. Coating thickness will be tested according to JIS H 0401 [Testing Method for Hot Dip Galvanized Coating].

4800.3	Construction Requirements

4800.3.1	Delivery and Storage of Materials

Materials delivered to site shall be inspected for damage, unloaded, and stored with minimum handling.  Materials shall not be stored directly on the ground.

Plastic pipes for drainage shall be stored to avoid exposure to direct rays of the sun and weather effects. They shall be installed within 6 months from the date of manufacture unless otherwise approved by the Engineer.

Handrails shall be delivered to the Site in crates and stored under shade to avoid direct weather effects. Defective handrails shall be replaced at no additional cost to the Employer.

4800.3.2	Installation

- Pipe Laying

Each pipe shall be carefully inspected before it is laid.  Any defective or damaged pipe shall be rejected.  Plain section of pipe shall be laid on the bedding so that water collected will run on smooth surface of the pipes. No pipe shall be laid when the trench conditions are unsuitable for such work.  Water shall be removed from trenches by sump pumping or other approved methods.  The pipe shall be laid to the grades and alignment as indicated.  The pipe shall be bedded to the established grade line. Pipes of either the bell-and-spigot type or the tongue-and-groove type shall be laid with the bell or groove ends upstream. All pipes in place shall be approved before covering up with the filter aggregates.

- Placing Filer Aggregate and Lean Concrete Bedding

- Centre Drain Pipe: The lean concrete bedding shall be placed to the thickness indicated on the Drawings. Centre drain pipe may be laid 24 hours after the lean concrete bedding is placed. Filter aggregate may be placed after the piping has been properly placed on the bedding and been inspected and approved by the Engineer. Filter aggregate shall be loosely deposited first up to top of the pipe and moderately compact both side of the pipe. Fill the rest of the trench with the filter aggregate and compact steadily to the satisfaction of the Engineer.

Transverse Drain Pipe: Filter aggregate shall be placed and compacted to the bottom level of transverse drain pipe. Lay the transverse pipe and connect to the junction socket provided at the sidewall drain pipes. Thereafter follow the procedure set out for the centre drain pipe.

- Tests of Drainage Pipes

Strength tests for pipes shall conform to field service test requirements of the ASTM F 1248 el Standard Test Method for Determination of Environmental Stress Crack Resistance (ESCR) of Polyethylene Pipe, if required in the opinion of the Engineer. Such tests shall be carried out at no additional cost to the Employer and the Engineer. The Contractor shall demonstrate that the pipes delivered to the Site meet the requirements of this Specification Section.

- Handrails

Handrails shall be installed along the edge of the Emergency Walkway as shown on the Drawings and within a tolerance of ±5-mm measured with a 3-m straight edge laid on the top of the handrail in vertical directions. For horizontal directions, the deviations shall be within a tolerance of±10-mm measured with a 3-m straight edge. Method for adjusting excessive deviations shall be subject to the Engineer’s approval.

4800.3.3	Submittals

Certifications from the manufacturers attesting that material meet specification requirements shall be submitted to the Engineer for approval no later than 28 days prior to the intended commencement of each work. Certificates are required for all drain pipe, handrails, gratings and other materials as requested by the Engineer.

4800.4	Method of Measurement

4800.4.1	Drainage Pipes

Accepted quantity of the tunnel drainage system will be measured from one end to the other end along the centre drain of the main tunnel. The transverse drains, joints, all filter aggregates, foundation concrete and all other incidentals necessary to complete the drainage system are deemed included in the length of the centre drain, without any deduction for the dimensions of connecting structures. Connecting structures are deemed included in the unit of measurement. No separate measurement will be performed for the connecting structures.

4800.4.2	Side Ditch

Accepted quantity of the side ditches will be measured along both side ditches in the unit of measurement listed in the Bill of Quantities. All connecting structures and incidental fittings of the connecting structures, which are reasonably estimated from the Drawings, are deemed included in the unit of measurement. No separate measurement will be performed for individual payment.

4800.4.3	Inspection Path, Emergency Walkway and Handrails

Accepted quantity of the Inspection Path and the Emergency Walkway will be measured in the unit of measurement listed in the Bill of Quantities.

The Emergency Walkway including steps and the handrails shall be measured in linear meter as all-in-one complete element irrespective of opening for steps.

Kerbs (curbs) installed along the Inspection Path shall be deemed included in the unit of measurement for the Inspection Path.

4800.5	Basis of Payment

The accepted quantity will be paid at the contract price per unit of measurements shown below and as indicated in the Bill of Quantities.

Payment will be full compensation for the materials and all work described in this section, such as excavation, lean concrete fittings, filter aggregates and other incidentals to complete the Works.

4800-01　Drainage system for Main tunnel

4800-02　Drainage system for Evacuation tunnel

4800-03　 Side Ditches

4800-04   Inspection Path with Kerbs

4800-05    Emergency Walkway with

Handrails and Steps

| Pay Items | Descriptions | Unit of Measurement |
| --- | --- | --- |
| 4800-01 | Drainage System for Main Tunnel as all-in-one complete element | m |
| 4800-02 | Drainage System for Evacuation Tunnel as all-in-one complete element | m |
| 4800-03 | Side Ditches with Connecting Structures | m |
| 4800-04 | Inspection Path with Kerbs | m |
| 4800-05 | Emergency Walkway with Handrails and Steps | m |

SECTION 4850 – PORTAL WORKS

4850.1	Description

The work consists of tunnel portal preparation, which include, without limiting to, clearing, grubbing, excavation, slope protective measures, door of reducing a noise in blasting, pre-support at the portal face, erection of shotcrete canopies, concrete retaining walls, backfilling and drainage networks to the lines, levels, grades, dimensions and cross-sections shown on the Drawings or established by the Engineer.

Portal works will include both surface and subsurface activities. Requirements for surface activities, such as will be discussed in the respective Sections/Clauses of the Standard Specifications for Road and Bridge Works ASAD, 2058 / July 2001 or in the modifications introduced in the Special Provisions. Thus, payment for the Works performed in the subsurface activities are dealt with under those Sections/Clauses.

4850.2	Material Requirements

Particulars of the materials used under this Section are identical to the requirements of materials discussed heretofore in these tunnel specifications.

The Contractor is required to refer to the respective Sections/Clauses of these tunnel specifications for detail requirements.

Corrugated metal sheet used as the outer shell of the steel rib (main frame of the shotcrete canopy) shall conform to JIS G 3352, having the metal thickness of 1.2mm. Alternative metal sheet, if the Contractor wishes to use, shall be of equivalent quality as approved by the Engineer.

4850.3	Construction Requirements

4850.3.1	General

- Operation Procedure

  - Removal of topsoil and subsequent excavation shall commence from the upper surface and progress carefully in incremental steps, lest the stability of the existing slopes above the portal areas should be disturbed.

(ii)	Excavation shall cease when it reaches the formation level (subgrade surface level). If unsuitable material, rock fragments, or boulders are found at the formation level, they shall be removed as directed by the Engineer and cave-ins, holes, or depressions formed below the formation level after removal shall be backfilled with suitable material compacted in layer in accordance with the provisions of Clause 906 of the Standard Specifications for Road and Bridge Works or any modifications introduced in the special provisions.

(iii)	The Contractor shall not start the first round of tunnel excavation until the shotcrete canopy is provided in its full length.

(v)	Backfilling of the cut-and-cover section (shotcrete canopy section) may start after the canopy has gained the desired compressive strength which shall be agreed with the Engineer.

(vi)	Materials for backfilling may be taken from the stockpiles at the designated areas or material excavated from within the Site as proposed by the Contractor and approved by the Engineer. Maximum size allowed shall not exceed 70 mm (1/3 of the compacted thickness of a layer).

(vii)	Backfill materials shall be cement treated soil with cement content of 4 to 8 % by weight. When cement is uniformly blended and mixed with soil within 2 % above the optimum moisture content and compacted to 95% of the maximum density, it shall yield the compressive strength of at least 1 N/mm2 (10 kgf/cm2) at the age of 28 days. Compressive strength testing shall be performed in accordance with ASTM D 1633 Standard Test Methods for Compressive Strength of Molded Soil-Cement Cylinders.

(viii)	Blending, mixing, spreading and compaction of soil cement will not be permitted in wet condition. If the time between blending and compaction exceed 2 hours, such materials shall not be incorporated into the Permanent Works. Unused materials shall be disposed of with no additional cost to the Employer.

(ix)	If the time compacting adjacent partial width exceed 30 minutes, or when trying into the previous work, the Contractor shall provide a construction joint according to the Engineer’s direction.

(x)	The Contractor is required to determine and report to the Engineer the in-place density and moisture content according to AASHTO T 3310 or other test procedures approved by the Engineer.

(xi)	Where use of heavy rollers is not practical, the Contractor shall use approved light weight mechanical or vibratory compacting equipment. Soil cement layers within 1 m of the canopy shall be compacted using light weight compacting equipment approved by the Engineer.

(xii)	The thickness of each layer shall not exceed 20-cm before compaction, if a light weight compacting equipment is used. Notwithstanding, a thick layer may be acceptable to the Engineer, provided the Contractor can demonstrate that that a thicker layer can be compacted to 95% of the maximum density.

(xiii)	Backfill materials shall be placed evenly in layers on both sides of the arch so that the side pressure on the canopy walls will be balanced.

(xiv)	Movement or deformation of the canopy shall be made good by the Contractor with no additional cost to the Employer.

Method of Operation

The Contractor shall submit to the Engineer for his review and comment a method statement for the construction, including type of equipment, procedures to achieve required quality, and sequence of operations which the Contractor intend to adopt, and other essential information.

Method of backfilling operations may be presented separately from that of excavation. As for backfilling, the Contractor shall demonstrate, either by mould specimen compressive testing or trial compaction tests as acceptable to the Engineer, at least 28 days before intended commencement of backfilling operation for different cement contents, e.g. 4%, 6%, and 8% by weight.

No placement of soil cement shall commence in the Permanent Works without the authorisation of the Engineer.

4850.3.2	Submittals

No later than 28 days prior to the intended commencement of work for portal construction the Contractor shall submit to the Engineer for his approval the survey data, profile drawings, the method of construction. Failure to provide such detail information will be considered a default of the Contractor and thereby rendering the Engineer to instruct to suspend that part of the Works in accordance with Sub-Clause 8.8 of the Conditions of Contract.

4850.3.3	Slope Protection Measures

The Contractor shall perform the excavation with full care, and ensure that the cut slope remains stable during and after the excavation until the portal canopies are backfilled to the lines, grades, and dimensions shown on the Drawings or as directed by the Engineer.

4850.2.4	Dewatering

All excavation shall be maintained free of water and the Contractor shall provide all necessary materials, equipment and labour for de-watering (pumping), diverting water-ways and the construction of temporary drains, cut-off walls and cofferdams as occasion may demand. Standby pumps shall be maintained in the vicinity of the workplace in good working order at all times to ensure no interruption in the continuity of de-watering procedures.

4850.4	Method of Measurement

4850.4.1	Surface Work

Quantity of clearing, grubbing, felling of trees, slope excavation and protective measures, concrete headwalls and retaining walls (wing walls) and all incidental works will be measured according to the unit of measurement specified in the Bill of Quantities. and paid according to the relevant items under the Standard Specification for Road and Bridge Works, ASAD, 2058 / July 2001 or modifications introduced in the Special Provisions.

4850.4.2	Portal Face and Canopy Works

- Pre-supports installed at the portal faces as shown on the Drawings and shotcrete applied at the portal face will not be measured separately for individual payment. Payment for the pre-supports installation and application/removal of the shotcrete protection is deemed included as the integral part of the portal construction and is therefore deemed included in the unit of measurement of the portal canopy.

Shotcrete applied inside the portal canopies as shown on the Drawings will not be measured separately for individual payment. Payment for shotcrete applied inside the portal canopies is deemed included as the integral part of portal construction and is therefore deemed included in the unit of measurement of the portal canopy.

Steel rib and the corrugated metal sheet installed as the main frame of the portal canopies will not be measured separately for individual payment. Payment for the steel ribs and corrugated metal sheets is deemed included in the unit of measurement for construction of the portal canopies.

Backfilling performed in the periphery of the portal canopies as shown on the Drawings will not be measured separately for individual payment. Payment for backfilling is deemed included in the unit of measurement for construction of the portal canopies.

Payment for soundproof door against tunnel blasting is deemed included in the unit of measurement for construction of the portal canopies.

4850.5	Basis of Payment

Accepted quantities of clearing, grubbing, felling of trees, slope excavation and protective measures, concrete headwalls and retaining walls (wing walls) and all incidental works will be paid separately according to the relevant items under the Standard Specification for Road and Bridge Works, ASAD, 2058 / July 2001 or modifications introduced in the Special Provisions.

Accepted quantities of portal canopy will be paid according to the unit of measurement specified below and as listed in the Bill of Quantities.

No separate remuneration will be paid for demolition of shotcrete protection at the portal face. The cost is deemed included in the tunnel excavation.

Payment will be full compensation for the materials, labour, equipment and any other incidentals necessary to complete the portal canopies.

| Pay Items | Descriptions | Unit of Measurement |
| --- | --- | --- |
| 4850-01 | Erection of Portal Canopy – Main Tunnel | m |
| 4850-02 | Erection of Portal Canopy – Working Adit | m |
| 4850-03 | Erection of Portal Canopy – Evacuation Tunnel | m |

SECTION 4900 - GATES

4900.1	Description

The work consists of furnishing and installation of the entrance gate for the evacuation tunnel and the gate connecting the main tunnel with the evacuation tunnel as shown in the Drawings.

4900.2	Material Requirements

4900.2.1   Type and Functional configuration

- The types of doors are as shown below:

| Type | Description |
| --- | --- |
| Gate for cross passage | Consists of a door for person and emergency car (between Main Tunnel and Evacuation Tunnel) |
| Gate for entrance of evacuation tunnel | Consists of a door for person and roadway |

Functional configuration

The material shall be equivalent to SUS 304.

When the door opens, put the display signal to the management site such as the facility control room.

4900.2.2 Structure

- Door for people

Make it easy for people to pass (W 1350 mm × H 2000 mm).

It shall be robust even when the static pressure difference between the front and back of the door is 760 Pa.

It shall have a mechanism that automatically starts closing even if it stops at any position within an arbitrary set time after opening.

Door for emergency car

Make it easy for emergency car  to pass (W 2900 mm × H 3200mm).

It shall be robust even when the static pressure difference between the front and back of the door is 760 Pa.

4900.3	Construction Requirements

4900.3.1	Inspection contents

- Wind resistance test

Confirm that the door will not be damaged when a static pressure difference of 760 Pa door is generated. (Reference JIS A1515 Wind resistance test method of fittings 6 test)

Door operation force inspection

With door for emergency car, the inspection is carried out with a push-pull gauge in a state of no static pressure difference between the front and back of the door. With door for people, in accordance with "JIS A 1519 Testing method of opening and closing force of fittings", at the time of pressurization of 290 Pa, from the fully closed state to the initial 10 cm which requires the most operation force is released with the push-pull gauge Measure the operating force of 98N or less.

4900.4	Method of Measurement

The accepted quantity of gates shall be measured in the unit of measurement specified in the Bill of Quantities. Defects of the gates shall be repaired in a manner recommended by the manufacturer and made good for payment to the satisfaction of the Engineer.

4900.5	Basis of Payment

The accepted quantities will be paid at the contract price per unit of measurement. Payment will be full compensation for the work prescribed in this section.

| Pay Item | Description | Unit |
| --- | --- | --- |
| 4900-01 | Gate for cross passage | nos |
| 4900-02 | Gate for west entrance of evacuation tunnel | nos |
| 4900-03 | Gate for east entrance of evacuation tunnel | nos |